## pmo
Phase-I (Define PMO)
Assessment Phase
Develop Project Charter for PMO setup
Stakeholder Identification
Design Survey
Conduct assessment
Prepare assessment report
Share assessment report with stakeholders
Define Phase
Set PMO Success Criteria
Develop Project Plan for PMO setup
Develop RACI Matrix & Project Org Chart
Interviews to understand requirement and pain areas
Define the scope of PMO
Project Risk Planning Phase
Project Risk & Issue management workshop
Identify intial risk & Develop Risk response plan
Define risk dashboard
Process Design Phase
Identify KPI/ metrices and calculation
Map pain areas to PMI processes
Define processes
Design templates/forms/checklist as per the process requirement
Process Validation & Verification Phase
Review processes & related artifacts with relevant stakeholders
Incorporate feedback
Phase-II (Automate PMO Processes)
System Design Phase
Identify automation requirment
Hardware/software procurement/installation/configuration
Sharepoint/EPM customization
Automate the work flows
Develop Customzied Reports
Design KPI & Dashboards
System Validation & Verification Phase
System testing
Incorporate feedback
User Acceptance Testing (UAT) Phase
User Acceptance Testing
Incorporate feedback
PMO Training & Documentation
PMI Training & Certificaiton
Design training modules for various roles
PMO Role Based Training
System Go Live
Deploy to Production
Hand-holding
Phase-III (Manage PMO)
Running PMO & Audits
Prepare project plan & WBS
Review/publish Plans, monitor actual status, manage project websites
Periodic reporting to stakeholders
Conduct Audit for each project/program/function
Prepare and compile audit report
Share audit report
Reassessment
Reassess the organization
Prepare assessment report
Share organizational maturity with senior management

## pmo-deliverables
Assessment Phase
· Understand business as is,
· Identify stakeholders,
· Project Management Skills available within the organization
Define Phase
· Baseline List of success criteria & measurement,
· Baselined PMO Setup Plan,
· PMO Business Case,
· Baselined Functional & Non-Functional Requirements,
· Baselined customization requirements,
· List of processes required
Project Risk Planning Phase
· Risk identification & Risk response plan workshop,
· Document initial risk & risk response plan
Process Design Phase
· Identify KPI & Metrics required by management to management the project,
· Mapping of business processes with PMI processes,
· Defined & Documented Listed Processes,
· Templates/Forms/Checklist/Guidelines with respect to processes
Process Validation & Verification Phase
· Reviewed & Baselined Processes & KPI,
· Process Mapping
System Design Phase
· Procure Hardware-Software and Network,
· Installed-Typical ready to use EPM,
· Customize EPM as per process requirement & dashboards required
System Validation & Verification Phase
· Project team verifies whether EPM implemented processes are working as defined
User Acceptance Testing (UAT) Phase
· Customer verifies EPM implemented processes are working as defined
PMO Training & Documentation
· Reviewed & Approved Training Material,
· Training to Project Administrator, Project Managers, Team Members
System Go Live
· Move EPM into Production

## pmo-case
CMMI
Prioritization & Organizational focus | Planning & Process Baselining | Performance Monitoring | Capacity Assessment
Scoping | Defining | Institutionalizing | Validating
Proposal | Process Training | End user training | ROI Analysis
Process Diagnosis | Process Definition | Process Rollout | SCAMPI Assessment
Process/Gap Analysis | Process Refinement | Process Implementation | Improvement Planning
| Process Interfacing | Implementation Assessment
What is unique in consulting?
Approach of De-Mystification
Solution Oriented Approach
Building Strength into processes
Teaming up
The effect of missing element
PMO Experience
Many activities PMO establishment like
Wrote many detail PMO proposal
Educating and discussing with prospects on possibility and potential of PMO
Maintaining project management website
PMP simulation website
50+ pmp, CAPM, schedule, cost, risk management trainings for project managers of 500+ professionals from various Indian & foreign MNCs
Conducted 1000+ hours training on project management
EPM implementation which helps in defining and implementing one of the aspect of PMO
Implementing full-fledged PMO
Companies | Work done
Aurovision | Full PMO implementation & automation
Sutherland | Proposal
Alcatel | EPM Implementation
Karnataka Police | Sharepoint EPM
Aforeserve | EPM Proposal
Gammon | PMO Proposal
Titan
Unitech-Wipro | EPM Implementation
Vedanta | PMO Proposal
What is there in Project Mgmt Consulting
Setting up project office: Define Process, Methodology, Lifecycle, Maturity Assessment, Best Practices
PMO: Mission, Vision & Scope of PMO & its alignment with organizational mission vision
Understanding current projects, project managment framework and infrastructre available
Assessing current project managment maturity level
Determining the training needs, process needs, tool need at high level & getting consent from stakeholders
Setting planning and governance setup
Setup architecture of knowledgement
Conducting periodic lessons learned session
Conducting periodic audits
Conduct trainings
Mentor & coach in planning, issue managment
Developing quality managment framework (templates, forms, checklist, quality metrices & thresholds)
Developing enterprise risk managment framework

## Verticle-Customers
Verticle | Organizaton Name
Architecture | Venire
Arms Manufacturing | Colt
Audit | KPMG
Banking & Finance | American Express
Banking & Finance | Citigroup
Banking & Finance | Fidelity
Banking & Finance | HDFC
Banking & Finance | Merill Lynch
Chemical | Deptt. Of Fertilizers
Chemical | IFFCO
Construction | Alpha G Corp
Construction | Ansal API
Construction | Ansal Housing
Construction | Ansal Housing
Construction | CPWD
Construction | Domex
Construction | Essel Group
Construction | Gammon
Construction | GMR DIAL
Construction | HBH
Construction | HP Housing And Urban Development
Construction | Jaypee
Construction | JLLM
Construction | Lanco
Construction | MPWSRP
Construction | Navayuga
Construction | NBCC
Construction | NHAI
Construction | Punjab Roads & Bridges DB
Construction | PWD
Construction | Raheja Builders
Construction | Satellier
Construction | Scott Wilson
Construction | SMEC
Construction | Unitech
Construction | UPID
Construction | UPRRDA
Construction | Venire
Electronics | Samsung
FMCG | Dabur
FMCG | ITC
FMCG | PepsiCo
Government | ADB
Government | BEL
Government | Chandigarh
Government | CSIR
Government | Delhi Tourism
Government | DIT
Government | EPIL
Government | FICCI
Government | FRI
Government | Govt of Bihar
Government | HUDCO
Government | IAF
Government | J&K
Government | Ministry of Earth Sciences
Government | MIT
Government | MRVC
Government | Navy
Government | NCRB
Government | NICSI
Government | NVS
Government | Panchyati Raj Deptt
Government | PGCIL
Government | Power
Government | Punjab Road & Bridge
Government | Railway
Government | Rajasthan
Government | Rajasthan rajya vidyut
Government | RDSO
Government | RUIDP
Government | STPI-CHiPS
Government | STPI-Dehradun
Government | UAA
Government | UNDP
Government | Uttar Pradesh
Government | Uttaranchal
Government | Uttaranchal Jal Sansthan
Government | WHO
Government-Electronics | LRDE
Govt-IT | IT
Govt-IT | ITD
Govt-IT | NIC
Healthcare & Pharma | Biocon
Healthcare & Pharma | CliniRX
Healthcare & Pharma | EPOS
Healthcare & Pharma | Fortis Healthcare
Healthcare & Pharma | Jagsonpal
Healthcare & Pharma | Jubilant
Healthcare & Pharma | Orchid
Healthcare & Pharma | Panacea Biotec
Healthcare & Pharma | Ranbaxy
Healthcare & Pharma | Ryhdburg
Healthcare & Pharma | Torrent
Healthcare & Pharma | United Health Group
Healthcare & Pharma | Wockhardt
Hotels | Plantation Club
Insurance | Apollo DKV
Insurance | Birla Sun Life
Insurance | Max
Insurance | Max New York Life
Investment | Indiabulls
IT | Accenture
IT | AG Technologies - PMP Proposal
IT | Bharti Telesoft
IT | BrickRed
IT | Citixsys
IT | Contakt Tech
IT | CSC
IT | Eclipsys India
IT | Equant
IT | EXL Services
IT | Fiserv
IT | FTIL
IT | Genband
IT | Hewitt
IT | Honeywell
IT | IBM
IT | IDS Infotech
IT | Infosys
IT | Ishir
IT | Kring Technologies
IT | Mind Share
IT | Net Soultions
IT | Network Solutions
IT | NIC
IT | Nucleus Software
IT | Omine Solutions
IT | Orange FT
IT | Quark
IT | RateGain IT Sloution
IT | Reliance ADA
IT | Remail Softech
IT | S T Microelectronics
IT | Second Foundation
IT | Sify
IT | System Plus
IT | Team Computers
IT | Thales
IT | Thomson Digital
IT | Trinity BPM
IT | UPTEC
IT | Winshuttle
IT | Wipro
Manufacturer | Titan
Manufacturing | Aditya Birla Group
Manufacturing | Asahi Glass
Manufacturing | DE Office
Manufacturing | Ercom Engg
Manufacturing | Godfrey Philips
Manufacturing | Hero Honda
Manufacturing | Hi Tech Gears
Manufacturing | Jindal Poly Films
Manufacturing | Kodak
Manufacturing | Maruti
Manufacturing | Micromatic Grinding
Manufacturing | Moser Baer
Manufacturing | Omya
Manufacturing | Rockwell Automation
Manufacturing | Schenck Rotec
Manufacturing | Secure Meter
Manufacturing | SKH Metals
Manufacturing | Stone India
Manufacturing | Subros
Manufacturing | Taikisha Engg
Manufacturing | TMTL
Manufacturing | Valvoline
Manufacturing | Vertical specific contents
Minining | Vedanta
Misc | Acme
Misc | Macmet
Oil, Gas & Petroleum | HPCL
Oil, Gas & Petroleum | OIL
Oil, Gas & Petroleum | ONGC
Partners | Amar Consulting
Partners | Aptech_Shimla
Partners | Asset Infotech
Police | Karnataka Police
Power | Areva
Power | BHEL
Power | HVPN
Power | MMTC
Power | MSEB
Power | NASL
Power | NHPC
Power | NJPC_Shimla
Power | NTPC
Power | Power Grid
Power | Power Mail Merge
Power | PTCUL
Power | SEB
Power | Siemens
Power | Tata Power
Power | THDC
Power | UPCL
Power | UPPCL
Powergrid | EPM tender
Powergrid | Trng
R & D | Grail
Retail | Benetton
Retail | Hypercity
Retial | Aforeserve
Services | Bharti Learning Systems
Services | CPA Global
Services | PWC
Services | VLCC
SEZs | Reliance
Steel | Arcelor
Steel | Jindal
Steel | Jindal Stainless
Steel | Jindal Steel & Power
Steel | Pentair Waters
Steel | SAIL
Steel | Steelÿ & Mines Department_files
Steel | Tata
Steel | Usha Martin
Telecom | ACL Wireless
Telecom | Acme
Telecom | Aircel
Telecom | Airtel
Telecom | Alcatel
Telecom | Alcatel-Lucent
Telecom | Aricent
Telecom | BSNL
Telecom | By Cell
Telecom | Colt
Telecom | Comverse
Telecom | Datacom Solutions
Telecom | Huawei
Telecom | Indus Towers
Telecom | Infratel
Telecom | MTNL
Telecom | MTS
Telecom | Nokia Siemens Networks
Telecom | Reliance Communications
Telecom | Shyam Telelink
Telecom | Spanco Telesystems
Telecom | Spice
Telecom | Tata Communications
Telecom | Tata Teleservices
Telecom | TCIL
Telecom | TelExcell
Telecom | Telsima
Telecom | Transcend
Telecom | Uninor
Telecom | Unitech Wireless
Transportation & Shipping | Gujarat Pipavav
Transportation & Shipping | Port of Pipavav
Visa Processing | VSF Global

## PMP-Roadmap
S.No. | Milestones/Phases | Description | Duration | Consultant Involvment | Why
1 | Discuss organizational business objectives & goal | Meet with PMO head & CTO | 2 hours | 100% | ~ PMO cannot play key role without knowing Business goal and aligning resources, skills, processes, metrics with those. It will remain support function without vision ~ As per survey there are only 50% chances of surving PMO after longer than 3 years. One of the key reason is not aligned to business goals. In short run also these PMO struggle to survive
2 | Establish PMO objective and goals | Meet with PMO head & CTO | 2 hours | 100%
3 | Align Business goals with PMO objectives | Meet with PMO head & PMO staff | 2 hours | 100%
4 | Develop charter for PMO | ~Document PMO objectives, milestones, budget ~Assign Champion for this project | 1 Day | 100% | ~ Document and sign off of project (Implement PMO) objective helps sponsor in knowing the purpose, high level budget, key milestones, high level risks, stakeholder identification and involving those
5 | PMO- Project signoff | ~Take approval in terms of finance, time require of project managers & time frame | 1 Day | 0%
6 | Project Management Maturity assessment | ~Develop a PMM questionnaire ~Get response from project managers ~Evaluate response ~Prepare a final assessment report and recommondation on process improvement | 4 Days | 50% | ~ Knowing PMM maturity of organization will help consultant and management in planning the strategy for around weak processes and exploit strong processes
7 | Define the project management maturity goals | ~Meet with PMO head & PMO staff | 1 Day | 100% | ~ Identify which process/skill need to be focussed/improved and why
8 | Conduct Project Management concept training | ~Conduct a 4 days PMP workshop for project Managers/ Functional managers | 4 Days | 100% | ~ Institutionlize the international PM terminology, concept and understand their values ~ Without this it will impossible to fully involve project managers in the PMO journey
9 | Conduct Software size estimation effort estimation workshop | ~2 Days workshop on software sizing- FPA ~Finalize template for FPA and Scheduling | 2 days | 100% | ~ Organization should standarize software sizing concepts across the org ~ PM should learn how to use scheduling tool effectively rather as an excel sheet ~ Organization should institutionalize scheduling best practices across org ~ Organization should standardize software sizing and scheduling templates ~ Communication of metrices and estimation across the organization and with management will be effective
10 | Conduct schedule using MSP workshop | ~2 Days workshop on project scheduling using MSP ~Discuss scheduling best practices | 2 days | 100% | ~ Use MSP for project resource, schedule estimate, work planning ~ Use MSP for project tracking and status updating ~ Use MSP for generating reports, charts, view and filtering ~ Develop confidence of using MSP
11 | Size the completed projects | ~Complete the software sizing of completed projects ~Benchmark productivity ~Benchmark size of product components | 4 Days | 25% | ~ This will help in benchmarking the productivity technologywise ~ Project Manager will be able to apply FPA concepts learned to the completed projects & learn further ~ Org will know how many function point delivered till now, every month and set the future goal/ know the capacity ~ Org will know the size of components and it can help them in presales FP estimation
12 | Evaluate existing PMIS | ~Discuss various PMIS today at org level & project level & their purpose | 1 Day | 100% | ~ Identify the various tool, templates, PM softwares each project team is using & why ~ Should that tool/software be institutionlize? ~ What other team members have used in their previous companies / any other suggested tool team feel is good
13 | Inventory of ongoing projects | ~Understand #, type of projects, team size, project challenges, miliestones, technology, risks, delivery status, variances, commitment to customer, # of defects, # of test cases, CSR # ~Which projects are important, ~What is their overall success, ~Why those projects should continue, ~What are lessons from those ~Project lifecycle ~Customer commitments | 1 Day | 100% | ~ Stratigize specific need of running project ~ Understand issues/risk and plan to address those ~ Develop comprehensive project plan for running projects ~ Review the resource utilization of resource on running projects ~ Ensure that projects are reporting in the agreed format ~ To plan the audit
14 | Inventory of completed projects (2 years) | ~Understand #, type of projects, team size, project challenges, miliestones, technology, risks, delivery status, variances, lessons learned, application size, project manager, CSR, # of defects, # of test cases, # Complains | 4 Days | 25% | Knowing OPA. Moving ahead with due respect to organization culture, strengthes & weaknesses. ~ Bench marking of productivity, utilization ~ Typical risks faced by the team and how they encountered those ~ What were major challenges with particular type of technology, business vertical, customer, team
15 | Identify processes already in place & their relevancy. | Discuss with Project team & ~know the process defined at org level and their maturity/ relevancy ~Know the processes team is following and value add these processes are doing to organization | 2 days | 100% | So that PMO does not endup creating those process ~ Which are not of much value ~ Which are already strong in some projects ~ Idetify involement of those PM who are applying best practices
16 | List down organizational resources | ~Finalize the resource attribute ~Identify various type of resources available ~Human resource with their experience, skills, # of years in org, projects worked on, project working on, team name etc | 2 Days | 25% | ~ Knowing the resources which PMO need to manage (skills, machines, sitting capacity, software component developed) and managing their utilization from central place will help in optimum utilization of resources
17 | Set up PMO reporting structure | ~Establish reporting hierarchy ~Change org strcture, if needed | 7 days | 20% | ~ Who reports to whom ~ Roles & responsibilites of team members ~ KRA of team members/PM ~ Reporting relationship between portfolio, programs, projects
18 | Conduct a Risk management workshop | ~ Know the meaning of Assumptions,Constraints, Dependency wrt to project ~ Identify ACD in each project ~ Prepare list of risk for each project ~ Prepare organization risk database ~ Priorization of risk based on the impact on project objectives ~ Prepare contingency and mitigation plan for Risk ~ How to determine the contingency reserve ~ Develop risk management plan for each risk | 1 Day | 100% | ~ Without knowing the risks or without planning those risks project team will endup exercising wrong options at the time of event ~ Without RMP PM waste their time in workaround/stop gap arrangements and complete project plan goes for toss
19 | Access the risks and resources required for important projects. | ~ Access risks in projects ~ Assign risk managers ~ Access risk mitigation and contingency plan ~ Convey & convince PM that overall risk rating is good for the project and them. It is not about rating them as good/bad PM | 3 Days | 50% | ~ Ensure practical risk management plans are place in every project ~ Time risk audits are conducted
20 | Define/refine processes & identify automation need | Document the new processes Update existing processes Document automation need | 15 Days | 25% | ~Without knowing automation need a wrong EPM tool can be selected or wrongly configured
21 | Implement Project Server | ~ Implement project server as per the process need ~ Recommend what feature is possible and what not possible using EPM | 15 Days | 25% | ~ PMO, PM & Project Team will save lots of time in data collection, collaboration, searching, report preparation, sharing reports etc
22 | EPM Pilot Run | Pilot Run | 7 Days | 25% | ~ Address the configuration hiccups ~ EPM tool Training
23 | Projects are managed using PMO | ~Project Planning ~Monitor & control ~Collaboration ~Document management ~Project reporting etc using the EPM Server | Continuous | 0%
24 | Conduct routinely audits | ~Define Audit scope ~Define Audit template ~Conduct Audit ~Prepare Audit reports ~Share Audit reports Conduct 4-5 audit cycles | 5 | 100% | ~Ensure PMO is meeting the defined goals or not ~Cause of variation ~Suggestive corrective and preventive actions ~ Share best practices
25 | Continuous improvement and move to new maturity levels
Note on D6: Offsite
Note on D21: Depends upon number of projects under PMO

## Sheet2
A | Understanding PMO Vision |  | % Cons. Inv. | 2 Days
1 | Discuss organizational business objectives & goal | 2 hours | 100% | 0.3
2 | Establish PMO objective and goals | 2 hours | 100% | 0.3
3 | Align Business goals with PMO objectives | 2 hours | 100% | 0.3
4 | Develop charter for PMO | 1 Day | 100% | 1
5 | PMO- Project signoff | 1 Day | 0% | 0
B | PM Comptency Training |  |  | 9.5 Days
6a | Conduct PM Skill Gap Analysis | 1 Day | 50% | 0.5
6 | Conduct Project Management concept training (including earn value management) | 4 Days | 100% | 4
7 | Conduct Software size estimation effort estimation workshop | 2 days | 100% | 2
8 | Conduct schedule using MSP workshop | 2 days | 100% | 2
9 | Conduct a Risk management workshop | 1 Day | 100% | 1
C | Understanding As is |  |  | 11 Days
10 | Size the completed projects | 4 Days | 25% | 1
11 | Access the risks and resources required for important projects. | 3 Days | 50% | 1.5
12 | Evaluate existing PMIS | 1 Day | 100% | 1
13 | Inventory of ongoing projects | 1 Day | 100% | 1
14 | Inventory of completed projects (2 years) | 4 Days | 25% | 1
15 | Project Management Maturity assessment | 4 Days | 50% | 2
16 | Define the project management maturity goals | 1 Day | 100% | 1
17 | Identify processes already in place & their relevancy. | 2 days | 100% | 2
18 | List down organizational resources | 2 Days | 25% | 0.5
D | Develop PMO Processes, Structure |  |  | 21 days
19 | Set up PMO reporting structure | 7 days | 20% | 1.4
20 | Define & Review processes & supporting strctures | 10 Days | 100% | 10
21 | Train relevant stakeholders on the developed process | 4 Days | 100% | 4
22 | Audit projects as per the agreed processes | 2 days | 100% | 2
23 | Define/refine processes & identify automation need | 15 Days | 25% | 3.75
E | Implement Project Management Tools |  |  | 6 Days
24 | Implement Project Server | 15 Days | 25% | 3.75
25 | EPM Pilot Run | 7 Days | 25% | 1.75
F | Manage Projects using PMO |  |  | 5 Days
26 | Projects are managed using PMO | Cont.. | 0%
27 | Conduct routinely audits | 5 Days | 100% | 5
28 | Continuous improvement and move to new maturity levels

## Sheet3
Recruitment and selection
Training and certification
Appraisal and promotion
Providing resources to projects
Time recording
Career planning
Personnel administration
External vendor management
Counseling and mentoring
Risk and issue management
Impact and change management
Communication
Project auditing
Focus on major or special projects
Adopting external standards like ISO, CMMI, OPM3
Developing project charter
Setting project management methodologies
Providing templates
Providing project management tools
Providing repositories
Collection of initiatives
Project evaluation
Project prioritization
Project planning and scheduling
Project approval and funding
Project monitoring and controlling
Project portfolio management