## Sheet1
Project Name | Department | Location | District | Project Manager | Sponsor | Start Date | Finish Date | Duration | BAC (Cr) | Actual Cost | EV | CV% | PV | SV% | SPI | CPI | EAC | VAC
Construction of Base Hospital | Health | Pithoragarh | Pithoragarh | Ram | Rajiv | 2011-06-01 | 2012-09-26 | 483 | 9 | 7 | 4 | -80% | 18 | 9 | 0.22 | 0.57 | 16 | -77.78% | 483
Upgradation and strengthening of Naini Saini Air strip | Aviation | Pithoragarh | Pithoragarh | Abdul | Ranjan | 2011-06-02 | 2013-12-16 | 928 | 94 | 46 | 11 | -320% | 97 | 94 | 0.11 | 0.24 | 392 | -317% | 928
Resident Commissioner's office Building | PWD | New Delhi | New Delhi | Mohan | Venkat | 2011-06-03 | 2013-09-04 | 824 | 8 | 2 | 5 | 60% | 9 | 8 | 0.56 | 2.5 | 3 | 62.5% | 824
Girls Hostel and Type-II Qtrs. | Education | IHM | Dehradun | Rangaswami | Seetaram | 2011-06-04 | 2012-09-15 | 469 | 8 | 7 | 1 | -600% | 16 | 8 | 0.06 | 0.14 | 57 | -612.5% | 469
Construction of Degree College Thalisain | Education | Thalisain | Pauri | Kadir | Rajiv | 2011-06-05 | 2012-02-18 | 258 | 1 | 1 | 1 | 0% | 4 | 1 | 0.25 | 1 | 1 | 0% | 258
Construction of Annexy Building at Vidhan Sabha | Assembly | Dehradun | Dehradun | Gulab | Ranjan | 2011-06-06 | 2013-10-25 | 872 | 9 | 4 | 4 | 0% | 10 | 9 | 0.4 | 1 | 9 | 0% | 872
State Information Commission Building | Information | Dehradun | Dehradun | Kavita | Venkat | 2011-06-07 | 2012-10-14 | 495 | 49 | 38 | 41 | 10% | 94 | 49 | 0.44 | 1.08 | 45 | 8.163% | 495
Construction of Juvenile/Minor Jail at Sitargang | Police | Sitargang | US Nagar | George | Seetaram | 2011-06-08 | 2011-11-10 | 155 | 84 | 23 | 75 | 70% | 516 | 84 | 0.15 | 3.26 | 26 | 69.05% | 155
Expansion of Rajkiya Ayurvedic Chikitsalaya | Health | Dehradun | Dehradun | Jim | Rajiv | 2011-06-09 | 2012-01-15 | 220 | 63 | 2 | 32 | 90% | 272 | 63 | 0.12 | 16 | 4 | 93.65% | 220
Administrative Building of Directorate Higher Education | Education | Haldwani | Haldwani | Krishna | Ranjan | 2011-06-10 | 2014-04-23 | 1048 | 49 | 48 | 48 | 0% | 44 | 44 | 1.09 | 1 | 49 | 0% | 950
Construction of Degree College | Education | Rikhanikhal | Pauri | Ram | Venkat | 2011-06-11 | 2013-04-23 | 682 | 16 | 14 | 9 | -60% | 22 | 16 | 0.41 | 0.64 | 25 | -56.25% | 682
Construction of Administrative and Academic Building for UOU | Education | Haldwani | Haldwani | Abdul | Seetaram | 2011-06-12 | 2013-12-03 | 905 | 92 | 31 | 79 | 60% | 96 | 92 | 0.82 | 2.55 | 36 | 60.87% | 905
Construction of Auditorium at Govt. Degree College Augustyamuni | Education | Rudraprayag | Rudraprayag | Mohan | Rajiv | 2011-06-13 | 2013-01-16 | 583 | 39 | 23 | 34 | 30% | 63 | 39 | 0.54 | 1.48 | 26 | 33.33% | 583
Construction of Food Craft Institute | Food | Almora | Almora | Rangaswami | Ranjan | 2011-06-14 | 2015-02-07 | 1334 | 63 | 15 | 16 | 10% | 45 | 45 | 0.36 | 1.07 | 59 | 6.349% | 946
Renovation work of Semant Institute of Technology College | Education | Pithoragarh | Pithoragarh | Kadir | Venkat | 2011-06-15 | 2014-06-11 | 1092 | 8 | 1 | 2 | 50% | 7 | 7 | 0.29 | 2 | 4 | 50% | 945
Construction of Research Centre at Central Hope Town | Health | Selaqui | Dehradun | Gulab | Seetaram | 2011-06-16 | 2012-08-16 | 427 | 45 | 21 | 10 | -110% | 99 | 45 | 0.1 | 0.48 | 94 | -108.9% | 427
Construction of Distt. Jail | Police | Champawat | Champawat | Kavita | Rajiv | 2011-06-17 | 2016-09-19 | 1921 | 50 | 25 | 26 | 0% | 25 | 25 | 1.04 | 1.04 | 48 | 4% | 943
Construction of Women jail | Police | Sitargang | Sitargang | George | Ranjan | 2011-06-18 | 2015-04-24 | 1406 | 10 | 2 | 6 | 70% | 7 | 7 | 0.86 | 3 | 3 | 70% | 942
Construction of Grain Store, Sitarganj Jail | Police | Sitargang | Sitargang | Jim | Venkat | 2011-06-19 | 2011-11-15 | 149 | 96 | 73 | 51 | -40% | 606 | 96 | 0.08 | 0.7 | 137 | -42.71% | 149
Construction of Govt. Degree College, Sitarganj | Education | Sitargang | Sitargang | Krishna | Seetaram | 2011-06-20 | 2012-12-04 | 533 | 31 | 26 | 29 | 10% | 55 | 31 | 0.53 | 1.12 | 28 | 9.677% | 533
Construction of Science building at Govt. Degree College | Education | Bazpur | Bazpur | Rangaswami | Rajiv | 2011-06-21 | 2012-01-02 | 195 | 54 | 30 | 7 | -330% | 260 | 54 | 0.03 | 0.23 | 235 | -335.2% | 195
Uttarakhand University of Horticulture and Forestry | Forest | Bharsar | Bharsar | Kadir | Ranjan | 2011-06-22 | 2012-11-30 | 527 | 21 | 5 | 8 | 40% | 37 | 21 | 0.22 | 1.6 | 13 | 38.1% | 527
Construction of IHM | Health | Ramngar | Ramngar | Ram | Venkat | 2011-06-23 | 2013-04-22 | 669 | 72 | 27 | 63 | 60% | 101 | 72 | 0.62 | 2.33 | 31 | 56.94% | 669
Formulas:
Finish Date = [Start Date]+ROUND(RAND()*2000,0)

## Sheet2
Project Name | Department | Location | District | Project Manager | Sponsor | Start Date | Finish Date | Duration | BAC (Cr) | Actual Cost | EV | CV% | PV | SV% | SPI | CPI | EAC | VAC
Construction of Base Hospital | Health | Pithoragarh | Pithoragarh | Ram | Rajiv | 2011-06-01 | 2012-04-13 | 317 | 26 | 18 | 6 | -200% | 79 | 26 | 0.08 | 0.33 | 79 | -203.8% | 317
Upgradation and strengthening of Naini Saini Air strip | Aviation | Pithoragarh | Pithoragarh | Abdul | Ranjan | 2011-06-02 | 2014-08-08 | 1163 | 87 | 0 | 41 | 100% | 72 | 72 | 0.57 | #DIV/0! | #DIV/0! | #DIV/0! | 958
Resident Commissioner's office Building | PWD | New Delhi | New Delhi | Mohan | Venkat | 2011-06-03 | 2014-08-27 | 1181 | 24 | 7 | 6 | -20% | 19 | 19 | 0.32 | 0.86 | 28 | -16.67% | 957
Girls Hostel and Type-II Qtrs. | Education | IHM | Dehradun | Rangaswami | Seetaram | 2011-06-04 | 2013-08-31 | 819 | 6 | 4 | 2 | -100% | 7 | 6 | 0.29 | 0.5 | 12 | -100% | 819
Construction of Degree College Thalisain | Education | Thalisain | Pauri | Kadir | Rajiv | 2011-06-05 | 2013-08-25 | 812 | 72 | 45 | 0 | #DIV/0! | 85 | 72 | 0 | 0 | #DIV/0! | #DIV/0! | 812
Construction of Annexy Building at Vidhan Sabha | Assembly | Dehradun | Dehradun | Gulab | Ranjan | 2011-06-06 | 2011-06-18 | 12 | 73 | 61 | 7 | -770% | 5804 | 73 | 0 | 0.11 | 664 | -809.6% | 12
State Information Commission Building | Information | Dehradun | Dehradun | Kavita | Venkat | 2011-06-07 | 2016-04-05 | 1764 | 73 | 29 | 43 | 30% | 39 | 39 | 1.1 | 1.48 | 49 | 32.88% | 953
Construction of Juvenile/Minor Jail at Sitargang | Police | Sitargang | US Nagar | George | Seetaram | 2011-06-08 | 2014-06-06 | 1094 | 27 | 4 | 6 | 30% | 23 | 23 | 0.26 | 1.5 | 18 | 33.33% | 952
Expansion of Rajkiya Ayurvedic Chikitsalaya | Health | Dehradun | Dehradun | Jim | Rajiv | 2011-06-09 | 2015-01-14 | 1315 | 99 | 91 | 18 | -410% | 72 | 72 | 0.25 | 0.2 | 495 | -400% | 951
Administrative Building of Directorate Higher Education | Education | Haldwani | Haldwani | Krishna | Ranjan | 2011-06-10 | 2015-06-17 | 1468 | 23 | 5 | 17 | 70% | 15 | 15 | 1.13 | 3.4 | 7 | 69.57% | 950
Construction of Degree College | Education | Rikhanikhal | Pauri | Ram | Venkat | 2011-06-11 | 2014-01-16 | 950 | 55 | 9 | 1 | -800% | 55 | 55 | 0.02 | 0.11 | 500 | -809.1% | 949
Construction of Administrative and Academic Building for UOU | Education | Haldwani | Haldwani | Abdul | Seetaram | 2011-06-12 | 2012-12-07 | 544 | 65 | 18 | 53 | 70% | 113 | 65 | 0.47 | 2.94 | 22 | 66.15% | 544
Construction of Auditorium at Govt. Degree College Augustyamuni | Education | Rudraprayag | Rudraprayag | Mohan | Rajiv | 2011-06-13 | 2013-11-27 | 898 | 82 | 44 | 29 | -50% | 86 | 82 | 0.34 | 0.66 | 124 | -51.22% | 898
Construction of Food Craft Institute | Food | Almora | Almora | Rangaswami | Ranjan | 2011-06-14 | 2012-10-06 | 480 | 12 | 12 | 3 | -300% | 24 | 12 | 0.13 | 0.25 | 48 | -300% | 480
Renovation work of Semant Institute of Technology College | Education | Pithoragarh | Pithoragarh | Kadir | Venkat | 2011-06-15 | 2015-03-07 | 1361 | 34 | 18 | 31 | 40% | 24 | 24 | 1.29 | 1.72 | 20 | 41.18% | 945
Construction of Research Centre at Central Hope Town | Health | Selaqui | Dehradun | Gulab | Seetaram | 2011-06-16 | 2012-11-11 | 514 | 52 | 7 | 18 | 60% | 96 | 52 | 0.19 | 2.57 | 20 | 61.54% | 514
Construction of Distt. Jail | Police | Champawat | Champawat | Kavita | Rajiv | 2011-06-17 | 2012-09-09 | 450 | 19 | 11 | 6 | -80% | 40 | 19 | 0.15 | 0.55 | 35 | -84.21% | 450
Construction of Women jail | Police | Sitargang | Sitargang | George | Ranjan | 2011-06-18 | 2013-11-08 | 874 | 33 | 9 | 22 | 60% | 36 | 33 | 0.61 | 2.44 | 14 | 57.58% | 874
Construction of Grain Store, Sitarganj Jail | Police | Sitargang | Sitargang | Jim | Venkat | 2011-06-19 | 2012-02-07 | 233 | 77 | 5 | 34 | 90% | 311 | 77 | 0.11 | 6.8 | 11 | 85.71% | 233
Construction of Govt. Degree College, Sitarganj | Education | Sitargang | Sitargang | Krishna | Seetaram | 2011-06-20 | 2013-05-26 | 706 | 49 | 7 | 11 | 40% | 65 | 49 | 0.17 | 1.57 | 31 | 36.73% | 706
Construction of Science building at Govt. Degree College | Education | Bazpur | Bazpur | Rangaswami | Rajiv | 2011-06-21 | 2015-10-24 | 1586 | 24 | 7 | 1 | -600% | 14 | 14 | 0.07 | 0.14 | 171 | -612.5% | 939
Uttarakhand University of Horticulture and Forestry | Forest | Bharsar | Bharsar | Kadir | Ranjan | 2011-06-22 | 2012-06-25 | 369 | 88 | 86 | 44 | -100% | 224 | 88 | 0.2 | 0.51 | 173 | -96.59% | 369
Construction of IHM | Health | Ramngar | Ramngar | Ram | Venkat | 2011-06-23 | 2015-02-15 | 1333 | 87 | 0 | 31 | 100% | 61 | 61 | 0.51 | #DIV/0! | #DIV/0! | #DIV/0! | 937

## Sheet3
Row Labels | Average of SPI | Average of CPI
Assembly | 0 | 0.11
Construction of Annexy Building at Vidhan Sabha | 0 | 0.11
Aviation | 0.57 | #DIV/0!
Upgradation and strengthening of Naini Saini Air strip | 0.57 | #DIV/0!
Education | 0.42 | 1.2267
Administrative Building of Directorate Higher Education | 1.13 | 3.4
Construction of Administrative and Academic Building for UOU | 0.47 | 2.94
Construction of Auditorium at Govt. Degree College Augustyamuni | 0.34 | 0.66
Construction of Degree College | 0.02 | 0.11
Construction of Degree College Thalisain | 0 | 0
Construction of Govt. Degree College, Sitarganj | 0.17 | 1.57
Construction of Science building at Govt. Degree College | 0.07 | 0.14
Girls Hostel and Type-II Qtrs. | 0.29 | 0.5
Renovation work of Semant Institute of Technology College | 1.29 | 1.72
Food | 0.13 | 0.25
Construction of Food Craft Institute | 0.13 | 0.25
Forest | 0.2 | 0.51
Uttarakhand University of Horticulture and Forestry | 0.2 | 0.51
Health | 0.2575 | #DIV/0!
Construction of Base Hospital | 0.08 | 0.33
Construction of IHM | 0.51 | #DIV/0!
Construction of Research Centre at Central Hope Town | 0.19 | 2.57
Expansion of Rajkiya Ayurvedic Chikitsalaya | 0.25 | 0.2
Information | 1.1 | 1.48
State Information Commission Building | 1.1 | 1.48
Police | 0.2825 | 2.8225
Construction of Distt. Jail | 0.15 | 0.55
Construction of Grain Store, Sitarganj Jail | 0.11 | 6.8
Construction of Juvenile/Minor Jail at Sitargang | 0.26 | 1.5
Construction of Women jail | 0.61 | 2.44
PWD | 0.32 | 0.86
Resident Commissioner's office Building | 0.32 | 0.86
Grand Total | 0.35913 | #DIV/0!