## Prj. Initiation
Resource collection | Project Initiation | Resource | Amount
Project Initiation
| Statutory Approal-Phase1 | Statutory | 102200
|  | Hazop Study | 60000
| Statutory Approal-Phase2 | Statutory | 102200
|  | Hazop Study | 60000
Civil Vendor Finalization
Shutdown planning for hook up
|  | TOTAL | 324400
| Reconciliation | Amount Allocated | Amount to be allocated | Total | Actual | Diff.
| Project Initiation | 0 | 324400 | 324400 | 324400 | 0
| Primary Brine | 20388740.5 | 7990893 | 28379633.5 | 28379633.6159 | -0.11586
| Electrical | 70872944 | 14191276 | 85064220 | 85064220 | -3.4273e-07
| Utilities | 8676451 | 5637448 | 14313899 | 14313898.9786 | 0.02139
| Hypo | 8171674 | 3413310 | 11584984 | 11584984.2834 | -0.28342
| Dry Cl2 handling | 9926307 | 3930113 | 13856420 | 13856420.2089 | -0.20891
| Cl2 - H2 handling | 30270548 | 9224973 | 39495521 | 39495521.0554 | -0.055437
| Cell House | 180265470.6667 | 20477055 | 200742525.6667 | 200742525.9086 | -0.24189
| Secondary brine | 13628074 | 3978756 | 17606830 | 17606830.1159 | -0.11586
| Commissioning | 0 | 0 | 0 | 0 | 0
| Instrumentation | 7130676 | 18221130 | 25351806 | 25351806 | 0
| Total | 349330885.1667 | 87389354 | 436720239.1667 | 436720240.1667 | -1
|  | Total Allocation to be made |  | 436720236
|  | Difference |  | 3.1667

## Py Brine
Resource collection | 01-Py-Brine | Resource | Amount
1. CIVIL and Erection
Saturator
Civil Foundation for Saturator | a) Dismantling, excvation, PCC, Reinforcement work | Civil Foundation for Saturator | 537558
Civil Foundation for Saturator | c) Foundation | Civil Foundation for Saturator | 537558
| Positioning of saturator | Order amendment for MSRL saturator | 310000
|  | Saturator | 4892138
Internals for saturator- 1 lot | receipt of internals | Internals for saturator- 1 lot | 2760674
fixing of internals in saturator
| piping works | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
extension of ramp
e) Filling and Leak Testing
Clear Brine Tank & Pumps
Civil Foundation for Clear Brine tank | Completion of civil foundation and curing works | Civil Foundation for Clear Brine tank | 530089
Shifting of tank
Inspection charges for Rubber lined tanks, Clear Brine tank- 1 No - T 118 A | Erection of new tank | Inspection charges for Rubber lined tanks | 17500
|  | Clear Brine tank- 1 No - T 118 A | 1185821
| Pumps receipt | Clear Brine pump-- 2 Nos - | 579400.6667
|  | Motor- For Clear Brine pump - 2 nos | 251780
|  | SS centrifugal pump for NAOH dosing | 95860
|  | SS centrifugal pump for Soda ash dosing- 2 Nos | 95860
|  | Acidic Effluent pump- 1 No | 71100
|  | Vertical pit pump- 2 No - | 63140
Clear Brine pump-- 2 Nos - | pumps assembling and testing | Clear Brine pump-- 2 Nos - | 579400.6667
Clear Brine pump-- 2 Nos - | Pumps erection | Clear Brine pump-- 2 Nos - | 579400.6667
| piping work | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
UF Feed Tank & pump
Civil Foundation for UF feed tank | Completion of civil foundation and curing works | Civil Foundation for UF feed tank | 458693
Finalising of contractor
Shifting of tank
UF feed tank- 1 No - T 108 A, Inspection charges for Rubber lined tanks | Erection of new tank | UF feed tank- 1 No - T 108 A | 1435820
|  | Inspection charges for Rubber lined tanks | 17500
Tank commissioning
UF feed pump- 120 M3/hr - 1 No -, Motor- For UF feed pump - 1 no | Pumps receipt | UF feed pump- 120 M3/hr - 1 No - | 434550.5
|  | Motor- For UF feed pump - 1 no | 87473
Removal of old UF feed tank
Completion of civil foundation and curing works
UF feed pump- 120 M3/hr - 1 No - | pumps assembling and testing | UF feed pump- 120 M3/hr - 1 No - | 434551
Pumps erection
| piping work | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
Filter Press
Filter Press- 1 No - F 116 | Receipt of new filter press | Filter Press- 1 No - F 116 | 1799551
Removal of Existing filter press-B & its accesroies, pipings
Building Structure of Ion exchange column pipes and valves | Structure correction to suit the new filter press | Building Structure of Ion exchange column pipes and valves | 516000
Erection of new filter press & its accessories
| slurry Pump & wash water pump foundation & positioning | Slurry pump (20 m3/hr)- 1 No - | 276067
|  | Wash water pump | 65550
| Piping work | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
Idle run
5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments
BOQ Receipt from Consultants
Erection contract Finalization - Mech
Mobilization of erection material
Pipe rack and supports
| Process Piping | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
| Utility Piping | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Fabrication and Erection of CS & SS Pipelines | 866662
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Erection of CS pipes and SS pipes | 326166.6667
|  | SS pipes and fittings | 96975
|  | CS HDGI Fasteners | 28214
Erection of cable tray ( Electrical and Instrument )
Laying of cables (Electrical and Instrument)
Erection of instruments , Testing
Erection of MCC and Motors
Installation of Light fittings with LDB
|  | TOTAL | 28379633.6159

## Electrical
Resource Collection | 10-Electricals | Resource | Amount
1.1 Electrical
New Rectifier (ABB)
New Transformer(ABB)
HT PANEL 22 KV 1600 AMPS, 31.5 KA
Siemens Make Motors - 18 Nos
Siemens Make Motors - 5 Nos
HT Cables
| LT cables | LT Cables | 8767882
Copper Bus Bars and Flexibles and accessories-Cell House
Copper Bus Bars and Flexibles and accessories- Rectifier
UPS 2 * 20 kVA | 2 x 20 kVA UPS | UPS 2 * 20 kVA | 869101
PCC & MCC Panels
DG Set 1010 KVA with accessories
Fabrication and supply MS Insert Plates - 221 Nos
| Cable Trays | FRP Cable Tray | 1058259
Supply of Bus duct for DG set
UPS for ABB rectifier system 2 x 5 kVA | UPS for ABB (2*5 KVA) rectifier system | UPS for ABB rectifier system 2 x 5 kVA | 299439
Supply of MCCB 4 pole 250 amps for CPU transformer isolation at new RT room | Supply of MCCB 4 pole, 250 amps for CPU transformer isolation at new RT room | Supply of MCCB 4 pole 250 amps for CPU transformer isolation at new RT room | 34760
Supply of bus duct for auxiliary transformer
Supply of Local Control push button station | FRP Local Control Station | Supply of Local Control push button station | 138034
2 Tender Documents / BOQ
Elec
BOQ receipt for cable rack
3 Contractor Finalization
HT Panel Erection Contractor Finalization
| Elec - Erection contractor (M/s Sudhan Powertech) | Erection of Electrical Equipments | 3703585
|  | Electrical erection | 14942.5287
Elec- Copper Bus Bar
Rectifier erection contractor finalization
Transformer erection contractor finalization
Cable rack erection contractor finalization
4 Erection of Electrical Equipments
Rectifier
Rectifier 23 kA 690 Volts | New Rectifier civil | Rectifier 23 kA 690 Volts | 628722.5
New Rectifier positioning
Transformer
Rectifier Transformer 23kA 690 Volts | New Transformer Civil | Rectifier Transformer 23kA 690 Volts | 628722.5
New Transformer positioning
New 22KV HT Panel Erection
Contractor finalization for erection
| Procurement of materials (Channels & Angle) | Erection of HT Panel | 2857
|  | MS Stesl items for HT Panel | 10033
|  | Electrical erection | 14942.5287
| Fabrication of base frame | Erection of HT Panel | 2857
|  | Electrical erection | 14942.5287
| Erection of base frame and grouting | Erection of HT Panel | 2857
|  | Electrical erection | 14942.5287
HT Panel for 22 kV Substation, Erection of HT Panel | Receipt of HT panel | HT Panel for 22 kV Substation | 3578652
|  | Erection of HT Panel | 2857
| Unloading, leading and positioning of panels in HT room | Erection of HT Panel | 2857
|  | Electrical erection | 14942.5287
| Interconnection between panels, Tightness checking | Erection of HT Panel | 2857
|  | Electrical erection | 14942.5287
| Formation of earth pits and HT panel earthing | Erection of HT Panel | 2857
|  | Electrical erection | 14942.5287
| Fixing of supports for Cable Trays | Electrical erection | 14942.5287
| Erection of cable trays for Top entry | Electrical erection | 14942.5287
Dispatch signoff for HT Cable, Approval
| Receipt of HT cable | HT Cables - 1235 Mtrs | 170170.5556
| Laying of HT cables for incomer - 3 Runs | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Laying of HT cable O/G 2 - New RT | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Laying of HT cables for O/G 1- Old HT I/C, | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Laying of HT cables for OG 3 - New Aux Transformer | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Termination of HT cables in I/C | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Termination of HT cables of O/G 2 - New RT | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Termination of HT cables of O/G 1 - Old HT I/C | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Termination of HT cables of O/G 3 - New Aux. Transformer | Electrical erection | 14942.5287
|  | HT Cables - 1235 Mtrs | 170170.5556
| Submission of Drawing, work completion report to CEA for Inspection | Statutory | 102200
| CEA Inspection | Statutory | 102200
Completion of compliance and submission
Obtaining Safety certifcate and approval for operation
| PED Approval | Statutory | 102200
Precommissioning Tests by Supplier
Termination of HT cables in 22KV yard I/C and Energizing the HT panel and put into service
Erection of Rectifier Transformer, Rectifier unit and accessories
Service indent for Rectifier erection
Approval & Contractor finalization for erection
Rectifier 23 kA 690 Volts | Receipt of Rectifier after clearance | Rectifier 23 kA 690 Volts | 21900901
Unloading of Rectifier | Unloading, leading and positioning of Rectifier cubicle in New RT room | Unloading of Rectifier | 22500
Unloading of Rectifier, Foundation Bolt for Rectifier | Fabrication of J bolt, fixing and grouting in rectifier bed. | Unloading of Rectifier | 22500
|  | Foundation Bolt for Rectifier | 18266
Service indent for Transformer erection
Approval & Contractor finalization for erection
Rectifier Transformer 23kA 690 Volts | Receipt of Transformer after clearance | Rectifier Transformer 23kA 690 Volts | 16870788
Erection of transformer, MS insert plates | Fixing of Rails in the Transformer bed | Erection of transformer | 83333
|  | MS insert plates | 113827
Erection of transformer | Unloading, leading and positioning of Rectifier transformer in New RT room | Erection of transformer | 83333
Erection of transformer | Erection of Oil heat exchanger, piping connection, Oil conservator, HT panel Adaptor box | Erection of transformer | 83333
Oil Filtration for Transformer
Positioning Rectifier in Rectifier bed and alignment with Transformer
| Fixing of copper flexible connecting between Rectifier cubicle and Transformer. | Electrical erection | 14942.5287
Construction of Transformer oil Soak pit
Drain line pipe connecting to Soak pit
Construction of waste oil collection pit and interconnecting with pipe line.
New Trench connectivity with the existing trench
| Fabrication of base frame for erection of Rectifier panel, Polarization panel, AC DC Panel, UPS | Electrical erection | 14942.5287
| Fabrication and Connecting Raw water, DM water Inlet, out let pipe line with Rectifier and Transformer. | Electrical erection | 14942.5287
Rectifier control room aluminum partition work etc | Aluminium and Glass partition construction and provision of Air conditioning. | Rectifier control room aluminum partition work etc | 410000
| Fabrication of Cable tray supports, laying of cable trays in the new trenches provided in RT room | Electrical erection | 14942.5287
| Laying of Power, Control, communication cable between RCP, PCP, RT, Rectifier cubicle, Polarization Transformer, AC DC panel, Cooling cubicle | Electrical erection | 14942.5287
| Laying of GI earth flats and connecting with Transformer, RT cubicle, Control panel & AC DC panels. | Electrical erection | 14942.5287
| Glanding, Termination and loop check of all power, control and communication cables | Electrical erection | 14942.5287
| Temporary arrangement for charging ACDB | Electrical erection | 14942.5287
| Laying of Incomer Power cable from MCC 3 to AC DC Panel and Termination | Electrical erection | 14942.5287
Testing of Transformer , Rectifier cubicle
Energising the panels, Checking of controls and interlocks
Copper bus bar, Flexibles for Inside Rectifier room & Cell house
Finalization Erection contractor
Copper Busbar & Accs at cell house side | Receipt of material inside cell house | Copper Busbar & Accs at cell house side | 5299195
Copper Busbar & Accs at rectifier side | Receipt of material inside rectifier room | Copper Busbar & Accs at rectifier side | 3415018
Civil - opening for interconnection between cell house and rectifier room
Erection of Hallmar CT
Providing Supports for DC isolators and erection
Supports erection for Copper bus bar both on rectifier room and cell house
Erection of Copper bus bar and flexibles inside Cell house
Erection of Copper bus bar and flexibles inside Rectifier room
Erection of cable tray and support
Mobilization of electrical erection contractor
Receipt of LT cables
Receipt of Cable trays
| Fabrication of cable tray supports in the pipe rack | Electrical erection | 14942.5287
| Laying of cable trays and connecting with supports | Electrical erection | 14942.5287
Laying LT cable
| From LT PCC to Aux PCC | Electrical erection | 14942.5287
Cable trench formation from LT PCC existing trench
Finalising contractor for Cable rack fabrication and erection
Electrical Miscellanous Civil Jobs | Civil Foundation for cable rack | Electrical Miscellanous Civil Jobs | 321117
| Cable rack Fabrication and erection | Electrical erection | 14942.5287
| Fabrication of tray supports | Electrical erection | 14942.5287
| erection of Cable trays | Electrical erection | 14942.5287
| From LT PCC to DG Aux PCC | Electrical erection | 14942.5287
| From LT PCC to MCC 1 | Electrical erection | 14942.5287
| From LT PCC to MCC 4A | Electrical erection | 14942.5287
| From LT PCC to MCC 6 | Electrical erection | 14942.5287
| From DG Aux PCC to MCC 3A | Electrical erection | 14942.5287
| From DG Aux PCC to existing 380KVA PCC | Electrical erection | 14942.5287
Auxilliary Transformer
Electrical Miscellanous Civil Jobs, Eletrical civil foundation | Civil foundation for Aux Transformer
|  | Electrical Miscellanous Civil Jobs | 321117
|  | Eletrical civil foundation | 273975
Electrical Miscellanous Civil Jobs, Eletrical civil foundation | Curing of Foundation
|  | Electrical Miscellanous Civil Jobs | 321117
|  | Eletrical civil foundation | 273975
Electrical Miscellanous Civil Jobs | Neutral & Body earth pits formation for Transformer | Electrical Miscellanous Civil Jobs | 321117
| Installation of Aux. Transformer | Aux transformer - 4 MVA | 307437
| Laying and connecting earth flats from earth pits to Transformer | Electrical erection | 14942.5287
Bus duct for LT PCC 2
Measurement with Transformer & LT PCC drg.
Floating enquiry, Receiving offers, Technical sign off, negotiation, Finalization of vendor, Approval and ordering
| Receipt of bus duct at site after clearance | Sandwich Bus duct for 4 MVA Transformer | 613500
| Erection of bus duct, supports, connecting with PCC 2 | Electrical erection | 14942.5287
|  | Sandwich Bus duct for 4 MVA Transformer | 613500
Erection of LT PCC, Aux PCC
Main PCC - HT room, Aux PCC - HT room | Recipt of LT PCC Panel | Main PCC - HT room | 3900731
|  | Aux PCC - HT room | 698348
| Fabrication of Base frame for LT PCC, Aux PCC | Electrical erection | 14942.5287
| Fixing of frames and erection of LT PCC - Partial | Electrical erection | 14942.5287
| Erection of LT PCC - Partial | Electrical erection | 14942.5287
| Removal of power and control cables from the outgoing feeders in existing old PCC and tagging. | Electrical erection | 14942.5287
| Removal of old panels in existing PCC | Electrical erection | 14942.5287
| Fixing of frames and erection of LT PCC | Electrical erection | 14942.5287
| Interconnecting old and new PCC bus bars | Electrical erection | 14942.5287
| Panel earthing connections | Electrical erection | 14942.5287
| Power and control cable termination to new PCC | Electrical erection | 14942.5287
| Power and control check, interlock checking in new PCC | Electrical erection | 14942.5287
| Shifting of old battery charger panel, spare VCB, to other location and lining up. | Electrical erection | 14942.5287
| Fixing of frames and erection of LT Aux PCC | Electrical erection | 14942.5287
| Panel earthing connections | Electrical erection | 14942.5287
| Power and control cable termination to new Aux PCC | Electrical erection | 14942.5287
Erection of MCC 1
Shifting of lab from Brine plant to other location
Electrical Miscellanous Civil Jobs | Civil work - Removal of wall, excavation for cable trenches, Fixing of insert plate, provision for panel erection | Electrical Miscellanous Civil Jobs | 321117
MCC -1 - Brine plant | Dispatch clearance and receipt of MCC 1 | MCC -1 - Brine plant | 582809
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 1 | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Removal of all power and control cables from existing MCC 1 and tagging | Electrical erection | 14942.5287
| Rerouting of Power and control cables and termination in the new mcc on respective feeders | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
Erection of MCC 3A
Electrical Miscellanous Civil Jobs | Civil - Extension of DG room towards toilet | Electrical Miscellanous Civil Jobs | 321117
Electrical Miscellanous Civil Jobs | Excavation for cable trenches, Fixing of insert plate, provision for panel erection | Electrical Miscellanous Civil Jobs | 321117
MCC - 3A - DG extension room | Dispatch clearance and receipt of MCC 3A | MCC - 3A - DG extension room | 593034
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 3A | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Laying of power and control cables from MCC3A to respective motors | Electrical erection | 14942.5287
| Power & control cables and termination in the new mcc on respective feeders and motors | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
Erection of MCC 3
MCC- 3 - DG room | Dispatch clearance and receipt of MCC 3 | MCC- 3 - DG room | 725955
Removal of all power and control cables from existing MCC 3 and tagging
Removal of old MCC3 from its position
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 3 | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Power & control cables and termination in the new mcc on respective feeders and motors | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
Erection of MCC 4
Removal of all power and control cables from existing MCC 4 partially and tagging
MCC - 4 - Boiler House | Removal of old MCC4 partial from its position | MCC - 4 - Boiler House | 531685
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 4 | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Power & control cables and termination in the new mcc on respective feeders and motors | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
Erection of MCC 6
Electrical Miscellanous Civil Jobs | Civil - Removal of wall, cupboards, Extension of MCC area by 2.5mtrs in Mechanical shed by Frame work, chequered plate and provision for cabling | Electrical Miscellanous Civil Jobs | 321117
Electrical Miscellanous Civil Jobs | Civil work readiness | Electrical Miscellanous Civil Jobs | 321117
MCC - 6 - Mechanical Work shop | Dispatch clearance and receipt of MCC 6 | MCC - 6 - Mechanical Work shop | 961124
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 6 | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Laying of power and control cables from MCC6 to respective motors | Electrical erection | 14942.5287
| Power & control cables termination in the new mcc on respective feeders and motors | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
Erection of MCC 10
MCC - 10 - Boiler House | Dispatch clearance and receipt of MCC 10 | MCC - 10 - Boiler House | 449888
Removal of all power and control cables from existing MCC 10 and tagging
Removal of old MCC 10 from its position
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 10 | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Power & control cables and termination in the new mcc on respective feeders and motors | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
Erection of MCC 12
MCC-12 - Brine Plant | Dispatch clearance and receipt of MCC 12 | MCC-12 - Brine Plant | 449888
| Base frame fabrication | Electrical erection | 14942.5287
| Fixing of base frame and erection of MCC 12 | Electrical erection | 14942.5287
| Busbar tightness checking, control check | Electrical erection | 14942.5287
| Laying of power and control cables from MCC 12 to respective motors | Electrical erection | 14942.5287
| Power & control cables and termination in the new mcc on respective feeders and motors | Electrical erection | 14942.5287
Individual motors trial for direction check, equipment confirmation.
2*20 KVA UPS commissioning
Existing Hypo UPS to be Shifted
| Incoming Power Cable Laying And Termination | Electrical erection | 14942.5287
Power up and Commisioning
|  | TOTAL | 85064220
Reconciliation
|  | Project Initiation | 0
|  | Primary Brine | 28379633.6159
|  | Electrical | 85064220
|  | Utilities | 14313898.9786
|  | Hypo | 11584984.2834
|  | Dry Cl2 handling | 13856420.2089
|  | Cl2 - H2 handling | 39495521.0554
|  | Cell House | 200742525.9086
|  | Secondary brine | 17606830.1159
|  | Commissioning | 0
|  | Instrumentation | 25351806
|  | Total | 436395840.1667
|  | New WBS | 87389355
|  | Total Allocation made | 523785195.1667
|  | Total allocation to be made | 436720236
|  | Excess / ( Shortage allocation ) | 87064959.1667

## Utilities
Resource Group | 07-Utilities | Resource | Amount
3. Civil and Erection
3.3 Chiller
Foundation for Chiller 210 TR & N2 Generator Unit | Excavation | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Delay in Construction
Foundation for Chiller 210 TR & N2 Generator Unit | RR masnory work | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | Earth filling & soil consolidation | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | PCC | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | RCC | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | PCC and RCC flooring | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
3.4 Erection of Chiller
Air cooled chiller- 1 No | a) Positioing of Chiller | Air cooled chiller- 1 No | 3676405
b)Erection of chiller
3.4 Erection of Chilled water storage tank
Contract Finalization
modification of proposed chilled water tank
Positioing of Chilled water tank
4.1 Chilled water pumps
Receipt of Chilled Water Pumps
| Piping | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
|  | Centrifugal Pump Cap: 20 M3/HR - 2 Nos for DM water | 202440
Erection Contract Mobilization
Pipe Rack Extension In Chilled Water Area
Laying Of Chilled Water Pipe Lines for Chiller
Pipe Rack Extension In drying Tower Area
Main Pipe Rack Extension
Pipe Rack Extension In Hypo Area
Prefabricaton of Chilled Water inlet and Outlet Pipings
Laying of Chilled Water Pipe Lines
Fabrication of Pipe Lines
Pressure Testing
Insulation
Removal of Old chilled water pump-A
Civil bed modification
Chilled water circulation pumps 250 M3/hr 40M Head - 2 nos | Positioning of new pump-A | Chilled water circulation pumps 250 M3/hr 40M Head - 2 nos | 304000
Hook up With Existing System
Removal of Old chilled water pump-B
Civil bed modification
Chilled water circulation pumps 250 M3/hr 40M Head - 2 nos | d) Positioning of new pump - B | Chilled water circulation pumps 250 M3/hr 40M Head - 2 nos | 304000
| Piping | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Strainers- 1 lot - Metallic | 68972
|  | CS HDGI Fasteners | 28214
|  | PVC + FRP fittings | 1099000
|  | PVC braided hoses and Hose clamps | 51000
|  | Insulation - Hot and Cold | 3067000
Hook up With Existing System
Trail run of Chiller
N2 Unit
Foundation for Chiller 210 TR & N2 Generator Unit | Dismantling | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | Excavation | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | PCC | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | RCC | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Foundation for Chiller 210 TR & N2 Generator Unit | PCC and RCC flooring | Foundation for Chiller 210 TR & N2 Generator Unit | 60317.0909
Nitrogen generation unit with nitrogen receiver- 20 NM3/hr- 1 lot | Receipt of N2 Unit | Nitrogen generation unit with nitrogen receiver- 20 NM3/hr- 1 lot | 2249438
Positioning of N2 unit
| Piping | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | CS HDGI Fasteners | 28214
a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines )
4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
a) Pipe rack and supports
c) Utility Piping
flushing & leak checking
Insulation
Erection of cable tray ( Electrical and Instrument )
Laying of cables (Electrical and Instrument)
Erection of instruments , Testing
Erection of MCC and Motors
MCC-6
Installation of Light fittings with LDB
|  | TOTAL | 14313898.9786

## Hypo
Resource Group | 06-Hypo | Resource | Amount
Civil and Erection
3.1 Guard tower circulation System
Receipt of Hypo Plant Pipes and Fittings
Receipt of Guard Tower Pump
Foundation for Hypo Plant equipments | Excavation | Foundation for Hypo Plant equipments | 50500
Foundation for Hypo Plant equipments | PCC | Foundation for Hypo Plant equipments | 50500
Foundation for Hypo Plant equipments | RCC | Foundation for Hypo Plant equipments | 50500
Foundation for Hypo Plant equipments | b)Civil Bed construction | Foundation for Hypo Plant equipments | 50500
Guard tower hypo cooler -1 No, Guard tower pump - 1 No, Motor for Guard tower circulation pump - 1 no | c) Positioning of new guard circulation pumps and Heat Exchanger | Guard tower hypo cooler -1 No | 124587
|  | Guard tower pump - 1 No | 511236
|  | Motor for Guard tower circulation pump - 1 no | 24292
| Piping | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Hypo plant | 240551
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
|  | PVC/FRP Pipes and Fittings | 289347.4
|  | 300 NB FRPFalnged Elbow | 14672
Provision of 6" nozzle in Guard Tower circulation tank
chilled Water inlet and Outlet Pipe laying
Hypo Pump suction and Delivery Line Laying
Hook Up with Existing System
3.1 Hypo circulation System
Receipt of Hypo Circulation Pumps
Erection Contract Mobilization
Provision of 6" nozzle in hypo circulation tank
| Piping | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Hypo plant | 240551
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
|  | PVC/FRP Pipes and Fittings | 289347.4
Prefabrication of Hypo Pumps Suction and Delivery Lines
Prefabrication of Chilled Water Pipe Lines To PHE
Removal of Old pump-A
Foundation for Hypo Plant equipments | Civil bed modification | Foundation for Hypo Plant equipments | 50500
Hypo Circulation Pump - 2 Nos, Motor for Hypo circulation pump - 2 nos | Positioning of new pump-A | Hypo Circulation Pump - 2 Nos | 511236
|  | Motor for Hypo circulation pump - 2 nos | 27953
chilled Water inlet and Outlet Pipe laying
Hypo Pump suction and Delivery Line Laying
Hypo Cooler - 1 No | Removal of Old PHE | Hypo Cooler - 1 No | 124587
Positioning Of New PHE
Hook Up with Existing System
Removal of Old pump-B
Foundation for Hypo Plant equipments | Civil bed modification | Foundation for Hypo Plant equipments | 50500
Hypo Circulation Pump - 2 Nos, Motor for Hypo circulation pump - 2 nos | Positioning of new pump - B | Hypo Circulation Pump - 2 Nos | 511236
|  | Motor for Hypo circulation pump - 2 nos | 27953
| Piping and Instrumentation | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Hypo plant | 240551
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
Hook up with Existing System
4.1 Hypo Blowers
Civil Bed new Blower A
Receipt of Hypo Blowers
Dismantling
Excavation
PCC
RCC Level 1
RCC Level 2
Erection of VFD for new blower - A
Hypo Blowers - 2 Nos | Positioning of new blower-A | Hypo Blowers - 2 Nos | 1047784
Prefabrication of Hypo Blower Suction and Delivery Lines
Laying of PreFabricated Hypo Blower Lines
Hook Up with Existing System
Erection of VFD for new blower - B
Removal of Old blower-B
Foundation for Hypo Plant equipments | Civil bed modification | Foundation for Hypo Plant equipments | 50500
Hypo Blowers - 2 Nos | d) Positioning of new blower - B | Hypo Blowers - 2 Nos | 1047784
| Piping and Instrumentation | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Hypo plant | 240551
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
|  | PVC/FRP Pipes and Fittings | 289347.4
Hook UP with Existing System
3.2 Acidic Wash Tower system
Acidic Wash Tower - 1 No, Inspection charges for FRP tanks | Receipt of Acidic wash tower | Acidic Wash Tower - 1 No | 140693
|  | Inspection charges for FRP tanks | 24791
a) Removal of Old acidic wash tower circulation pumps and tower
Foundation for Hypo Plant equipments | Civil Bed Modification for Acidic Wash Tower and Circulation Pumps | Foundation for Hypo Plant equipments | 50500
Acidic water circulation pump - 2 Nos | c) Positioning of acidic wash tower and Circulation pumps | Acidic water circulation pump - 2 Nos | 83250
Prefabricaton of Acidic Wash Tower And Circulation Pumps Lines
| Piping and Instrumentation | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Hypo plant | 240551
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
|  | PVC/FRP Pipes and Fittings | 289347.4
Hook up with Existing System
3.3 Caustic Over Head Tank
Mobilization of Erection Material
| Erection of structures | Fabricaiton and erection of over head Tank Structure | 90800
|  | Painting | 511200
Fabricaiton and erection of over head Tank Structure | welding of structures | Fabricaiton and erection of over head Tank Structure | 90800
Fabricaiton and erection of over head Tank Structure | Erection and welding of handrails | Fabricaiton and erection of over head Tank Structure | 90800
| painting of structures | Fabricaiton and erection of over head Tank Structure | 90800
|  | Painting | 511200
Caustic OHT - 1 No, Inspection charges for FRP tanks | Receipt of OHT | Caustic OHT - 1 No | 493139
|  | Inspection charges for FRP tanks | 24791
Erection of OHT
Cleaning & Leak Testing
| Piping and Instrumentation | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Hypo plant | 240551
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS HDGI Fasteners | 28214
|  | PVC/FRP Pipes and Fittings | 289347.4
Commissioning of Caustic OHT
|  | TOTAL | 11584984.2834

## Dry Cl2 handling
Resource Group | 05-Dry-Cl2-Handling | Resource | Amount
3. Civil and Erection
3.1 Drying tower system
Cl2 drying Tower - 1 No | Receipt of equipments | Cl2 drying Tower - 1 No | 1047727
plant shut down & process clearance
dismanlting of existing drying tower connections and opening
removal of packings
removal of existing drying tower
positioning & supporting of new drying tower
Filling of packings
98% Sulphuric Acid Dosing Pumps - 2 Nos, 78% sulphuric Acid circulation pumps - 2 Nos | Recepit of pumps | 98% Sulphuric Acid Dosing Pumps - 2 Nos | 86808
|  | 78% sulphuric Acid circulation pumps - 2 Nos | 570000
Removal of old pumps
Dry chlorine equipment civil foundation work | Civil bed modification | Dry chlorine equipment civil foundation work | 303000
Position and hookup of pumps
| pipings | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Alloy 20 Ball Valves Size: 2550100 NB (VB07) | 327191
|  | Bellow Seal Globe Valves | 77401
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | Globe Control Valves 2" | 96112
leaktest
commissioning
3.2 Chlorine compressor system
| Receipt of Chlorine compressor | Spares for Chlorine compressor for Upgradation | 503158
a) Removal of Old Chlorine compressor
Chlorine compressor | b) Positioning of new chlorine compressor | Chlorine compressor | 1814888
Chlorine compressor | c) Positioning of suction knock out drum, acid separator and Heat exchanger | Chlorine compressor | 1814888
d) idle run test
b) Hook up with Existing set up (Process and utilities)
4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
a) Pipe rack and supports
| b) Process Piping | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
| c) Utility Piping | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Fabrication and Erection of CS & SS Pipelines & Erection of Metallic Pipelines | 866662
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Erection of CS pipes and SS pipes | 326166.6667
|  | SS pipes and fittings | 96975
|  | CS HDGI Fasteners | 28214
Erection of cable tray ( Electrical and Instrument )
Laying of cables (Electrical and Instrument)
Erection of instruments , Testing
Erection of MCC and Motors
MCC-6
|  | TOTAL | 13856420.2089

## Cl2 - H2 handling
Resource Collection | 04-Cl2-H2-Handling | Resource | Amount
3. Civil and Erection
3.1 Structurals Civil foundation
Cl2/H2 handling section Building foundation | a) Dismantling | Cl2/H2 handling section Building foundation | 309188
Cl2/H2 handling section Building foundation | b) Excavation | Cl2/H2 handling section Building foundation | 309188
Cl2/H2 handling section Building foundation | c) PCC | Cl2/H2 handling section Building foundation | 309188
Cl2/H2 handling section Building foundation | d) Footing and column construction | Cl2/H2 handling section Building foundation | 309188
3.2 Equipments civil foundation
Civil Equipment Foundation at Hydrogen and Chlorine Sections | a) Dismantling | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
Civil Equipment Foundation at Hydrogen and Chlorine Sections | b) Exacavation | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
Civil Equipment Foundation at Hydrogen and Chlorine Sections | c) PCC | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
Civil Equipment Foundation at Hydrogen and Chlorine Sections | d) Civil bed construction | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
Civil Equipment Foundation at Hydrogen and Chlorine Sections | e) Soil consolidation | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
Civil Equipment Foundation at Hydrogen and Chlorine Sections | f) PCC and RCC flooring | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
Civil Equipment Foundation at Hydrogen and Chlorine Sections | g) Plastering of flooring | Civil Equipment Foundation at Hydrogen and Chlorine Sections | 170298
3.3 Erection of equipments and Structurals
a) Erection of Structurals
| Column Erection | Structural for Cl2 / H2 washing section | 322787
|  | Foundation bolts for Cl2 & H2 Section | 37265
|  | Structure for chlorine and hydrogen | 75090.9091
|  | Painting | 511200
| Tie beam erection - 3.65 m level | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Tie beam erection - 6.4 m level | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Tie beam erection - 9.5 m level | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Tie beam erection - 13 m level | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Cross member erection - 3.65 m | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Cross member erection -6.4 m | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Cross member erection - 9.5 | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Cross member erection- 13 m | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| staircase erection | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| Handrail erection | Structural for Cl2 / H2 washing section | 322787
|  | Structure for chlorine and hydrogen | 75090.9091
| FRP Grating Fixing | FRP gratings for Cl2/ H2 structure+Hpo plant | 914427
|  | FRP Gratings Mesh Size: 28x28x30mm | 1891573
b) Positioing of Equipment and pumps
Cl2 gas mist eliminator - Housing- 1 No, Cl2 Mist Eliminator candle, H2 gas mist eliminator Housing - 1 No, H2 gas mist eliminator candle - 2 Nos | Cl2 / H2 gas mist eliminator | Cl2 gas mist eliminator - Housing- 1 No | 474427
|  | Cl2 Mist Eliminator candle | 512361
|  | H2 gas mist eliminator Housing - 1 No | 678617
|  | H2 gas mist eliminator candle - 2 Nos | 203370
| H2 buffer vessel , SP-401 , E-402, T-403, E-501, T-401 | Brine Dechlorination Tower - T401- 1 No | 2249438
|  | Hydrogen buffer vessel - 1 No | 310823
|  | Sodium Sulphite OHT- 1 No - T 403 | 156336
|  | Dechlorination Tower Condensate Separator - SP 401- 1 No | 95090
|  | Remi Make Agitator | 49181
| T-501, T-502 , T-601 , T-602 , T-402 | Sodium sulphite preparation tank - T 402- 1 No | 200000
|  | Cl2 wash tower 1 - 1 No | 1382568.5
|  | Cl2 wash tower 2 - 1 No | 1382568.5
|  | Hydrogen wash tower-1 - 1No | 730659
|  | Hydrogen wash tower-2 - 1 No | 532913
|  | Chlorine wash tower 1 packing support- 1 No | 281691
|  | Chlorine wash tower 2 packing support-1 No | 281691
|  | Inspection charges for Hydrogen wash tower 1&2 | 70000
|  | Hydrogen condensate seal pot - 3 nos | 68225
| Heat Exchangers | Dechlorination Tower Vapor Condenser - 1 No | 213303
|  | Instrument Cooler - 1 No | 23596
|  | PHE for Cl2 wash tower - 1 - 1 No | 126472
|  | PHE for Cl2 wash tower - 2 - 1 No | 101933
|  | Hydrogen wash tower-1 cooler -1 No | 72674
|  | Hydrogen wash tower-2 cooler - 1 No | 58517
|  | 78% sulphuric Acid cooler E-504 | 266158
|  | DB heat exchanger- 1No - | 168004
|  | NaOH product cooler- 1 No - | 547415
|  | Chlorine Recuperator - 1 No | 2811798
| Pumps | Dechlorination Tower Pumps - 2 Nos | 1022472
|  | Sodium Sulphite Pumps - 2 Nos | 142200
|  | Cl2 wash tower 1 circulation Pumps - 2 Nos | 869101
|  | Cl2 wash tower 2 circulation Pumps - 2 Nos | 869101
|  | Hydrogen wash tower-1 Pumps - 2 No | 109390
|  | Hydrogen wash tower-2 Pumps - 2 No | 109390
|  | Motor for Chlorine wash tower pump - 1 - 2 nos | 26518
|  | Motor for Chlorine wash tower pump - 2 - 2 nos | 26518
|  | Motor for Dechlorination tower pump - 2 nos | 48583
Air Blower - 2 No | Blower | Air Blower - 2 No | 483629
3.4 Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
Pipe rack - Supply and Erection | a) Pipe rack and supports | Pipe rack - Supply and Erection | 3540321
| b) Process Piping | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Sight glass- 1lot | 64438.5
|  | Static Mixers- 1lot | 216750
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | Insert pipes - 1 lot | 26000
|  | Base plate and foundation bolt | 25000
| c) Utility Piping | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Fabrication and Erection of CS & SS Pipelines Erection of Metallic Pipelines | 866662
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Erection of CS pipes and SS pipes | 326166.6667
|  | SS pipes and fittings | 96975
|  | CS HDGI Fasteners | 28214
|  | Base plate and foundation bolt | 25000
d) Erection of cable tray ( Electrical and Instrument )
e) Laying of Electrical cables and Instrument cables
Schaefer's DIaphragm PG Air Blower B-401 A Discharge, Schaefer's DIaphragm PG Air Blower B-401 B Discharge, Diaph.Seal PG P-401 A Pump Discharge, Diaph.Seal PG P-401 B Pump Discharge, Diaph.Seal PG P-402 A Pump Discharge, Diaph.Seal PG P-402 B Pump Discharge, Rotameter Air Blower B-401 A/B Comm.Disch., Rotameter 18% Caustic From B/L, Rotameter Brine O/L Cooler E-401, Std.Bimetallic Temp. gauge Vapour Condenser E-402 inlet gas, Std.Bimetallic Temp. gauge Vapour Condenser E-402 Cooling Water Return, Temp. Trans. Condensate Separator SP-401 inlet gas, RTD Element Condensate Separator SP-401 inlet gas, Temp. Trans.Dechlorination Tank D-401, RTD Element Dechlorination Tank D-401, Remote Seal Trans. Dechlorination Tank D-401, Diaphragm Control valve Dechlorination Tank D-401, pH Transmitter Brine Outlet E-401, ORP Transmitter Brine Outlet E-401, Globe Control Valve Brine Outlet E-401, Magflow Trans. Return Brine to Saturator, Magflow Trans. Sodium Sulphate from T-403, Flanged Mounted Trans.Sodium Sulphite Filter Tank T-402, Flanged Mounted Trans.Sodium Sulphite Over Head Tank T-403, Ball Control Valve Sodium Sulphate from T-403, Ball Control Valve From T 403 Tank, Temp. Trans. Chlorine Gas from Cell House to Chlorine Recuperator, RTD Element Chlorine Gas from Cell House to Chlorine Recuperator, Std.Bimetallic Temp. gauge Polished Brine O/L Recuparator, Std.Bimetallic Temp. gauge Polished Brine I/L Recuperator, Std.Bimetallic Temp. gauge Cooling water Return, Std.Bimetallic Temp. gauge Cooler E-502 to Chlorine Wash Tower-I, Std.Bimetallic Temp. gauge Chlorine Wash Tower-II, Std.Bimetallic Temp. gauge Chilled water Return, Std.Bimetallic Temp. gaugeCooler E-503 to Chlorine Wash Tower-II, Diaph.Seal PG Clorine Gas from Cell House, Diaph.Seal PG Clorine Recuperator to Chlorine Wash Tower-I, Standard PG Cooling Water Supply, Diaph.Seal PG Chlorine Wash Tower-I to Chlorine Wash Tower-II, Diaph.Seal PG P-501 A Pump Discharge, Diaph.Seal PG P-501 B Pump Discharge, Diaph.Seal PG Mist Eliminator Inlet, Diaph.Seal PG P-502 A Pump Discharge, Diaph.Seal PG P-502 B Pump Discharge, Standard PG Chilled Water Supply, Temp. Trans.Chlorine Wash Tower-I to Chlorine Wash Tower-II, RTD Element Chlorine Wash Tower-I to Chlorine Wash Tower-II, Temp. Trans.Clorine Recuperator to Chlorine Wash Tower-I, RTD Element Clorine Recuperator to Chlorine Wash Tower-I, Temp. Trans. Chlorine Wash Tower-I, RTD Element Chlorine Wash Tower-I, Temp. Trans. Chlorine Wash Tower-II to Mist Eliminator, RTD Element Chlorine Wash Tower-II to Mist Eliminator, Temp. Trans. Chlorine Wash Tower-II Cooler Outlet, RTD Element Chlorine Wash Tower-II Cooler Outlet, Butterfly Control valve Wet Cl2 Gas Header, Butterfly Control valve Wet Cl2 Gas Header, Rotameter Process Water to T-502, Rotameter Process Water to T-501, Remote Seal Trans. Chlorine Wash Tower-I T-501, Globe Control valve Chlorine Wash Tower-I T-501, Magflow Trans. Cooler E-502 Outlet, Magflow Trans. Cooler E-503 Outlet, Globe Control Valve Chlorine Wash Tower-II Cooler Outlet, Magnetic Chlorine Wash Tower-II, Std.Bimetallic Temp. gauge Hydrogen Gas from Header, Std.Bimetallic Temp. gauge Hydrogen Gas Wash Tower-I to Hydrogen Gas Wash Tower-II, Std.Bimetallic Temp. gauge Cooling water Return, Std.Bimetallic Temp. gauge Cooler E-601 Water Outlet, Std.Bimetallic Temp. gauge Hydrogen Gas Wash Tower-II, Std.Bimetallic Temp. gaugeChilled water Return, Std.Bimetallic Temp. gaugeHydrogen Wash Tower-II Cooler Outlet, Standard PG Cooling Water Supply, Diaph.Seal PG Hydrogen Gas Wash Tower-I to Hydrogen Gas Wash Tower-II, Diaph.Seal PG Hydrogen Gas from Header, Diaph.Seal PG P-601 A Pump Discharge, Diaph.Seal PG P-601 B Pump Discharge, Diaph.Seal PG P-602 A Pump Discharge, Diaph.Seal PG P-602 B Pump Discharge, Standard PG Hydrogen Gas Wash Tower-II to Mist Eliminator, Temp. Trans. Hydrogen Gas Wash Tower-I, RTD Element Hydrogen Gas Wash Tower-I, Temp. Trans. Hydrogen Gas Wash Tower-II to Mist Eliminator, RTD Element Hydrogen Gas Wash Tower-II to Mist Eliminator, Temp. Trans.FA-601 Flame Arrestor, RTD Element FA-601 Flame Arrestor, RTD Element Hydrogen Gas to Hydrogen Gas Wash Tower-I, Globe Control valve Diffl Pressure between N2 & Cl2 O/L Electrolyser, Globe Control valve Diffl Pressure between N2 & Cl2 O/L Electrolyser, On-Off Valve Nitrogen To FA-601, Butterfly Control Valve Hydrogen Gas To Hydrogen Holder, Standard Pr.Trans.Hydrogen Gas To Hydrogen Holder, Remote Seal Trans. Hydrogen Gas Wash Tower-I T-601, Globe Control Valve Hydrogen Gas Wash Tower-I T-601, Rotameter P-601 A/B Pump Comm.Disch., Rotameter DM Water to T-602, Rotameter P-602 A/B Pump Comm.Disch., Rotameter DM Water to T-602 gas outlet line, MagneticHydrogen Gas Wash Tower-II T-602 | f) Erection of instruments | Schaefer's DIaphragm PG Air Blower B-401 A Discharge | 2430
|  | Schaefer's DIaphragm PG Air Blower B-401 B Discharge | 2430
|  | Diaph.Seal PG P-401 A Pump Discharge | 3439
|  | Diaph.Seal PG P-401 B Pump Discharge | 3439
|  | Diaph.Seal PG P-402 A Pump Discharge | 2834
|  | Diaph.Seal PG P-402 B Pump Discharge | 2834
|  | Rotameter Air Blower B-401 A/B Comm.Disch. | 59111
|  | Rotameter 18% Caustic From B/L | 8916
|  | Rotameter Brine O/L Cooler E-401 | 26584
|  | Std.Bimetallic Temp. gauge Vapour Condenser E-402 inlet gas | 30207
|  | Std.Bimetallic Temp. gauge Vapour Condenser E-402 Cooling Water Return | 2739
|  | Temp. Trans. Condensate Separator SP-401 inlet gas | 13292
|  | RTD Element Condensate Separator SP-401 inlet gas | 26934
|  | Temp. Trans.Dechlorination Tank D-401 | 13292
|  | RTD Element Dechlorination Tank D-401 | 29652
|  | Remote Seal Trans. Dechlorination Tank D-401 | 101467
|  | Diaphragm Control valve Dechlorination Tank D-401 | 103781
|  | pH Transmitter Brine Outlet E-401 | 58690
|  | ORP Transmitter Brine Outlet E-401 | 54191
|  | Globe Control Valve Brine Outlet E-401 | 54354
|  | Magflow Trans. Return Brine to Saturator | 82104
|  | Magflow Trans. Sodium Sulphate from T-403 | 58817
|  | Flanged Mounted Trans.Sodium Sulphite Filter Tank T-402 | 34764
|  | Flanged Mounted Trans.Sodium Sulphite Over Head Tank T-403 | 34764
|  | Ball Control Valve Sodium Sulphate from T-403 | 79600
|  | Ball Control Valve From T 403 Tank | 79600
|  | Temp. Trans. Chlorine Gas from Cell House to Chlorine Recuperator | 13292
|  | RTD Element Chlorine Gas from Cell House to Chlorine Recuperator | 29652
|  | Std.Bimetallic Temp. gauge Polished Brine O/L Recuparator | 7143
|  | Std.Bimetallic Temp. gauge Polished Brine I/L Recuperator | 7143
|  | Std.Bimetallic Temp. gauge Cooling water Return | 2784
|  | Std.Bimetallic Temp. gauge Cooler E-502 to Chlorine Wash Tower-I | 26625
|  | Std.Bimetallic Temp. gauge Chlorine Wash Tower-II | 33677
|  | Std.Bimetallic Temp. gauge Chilled water Return | 2739
|  | Std.Bimetallic Temp. gaugeCooler E-503 to Chlorine Wash Tower-II | 26624
|  | Diaph.Seal PG Clorine Gas from Cell House | 4248
|  | Diaph.Seal PG Clorine Recuperator to Chlorine Wash Tower-I | 4248
|  | Standard PG Cooling Water Supply | 450
|  | Diaph.Seal PG Chlorine Wash Tower-I to Chlorine Wash Tower-II | 4248
|  | Diaph.Seal PG P-501 A Pump Discharge | 3439
|  | Diaph.Seal PG P-501 B Pump Discharge | 3439
|  | Diaph.Seal PG Mist Eliminator Inlet | 4248
|  | Diaph.Seal PG P-502 A Pump Discharge | 3439
|  | Diaph.Seal PG P-502 B Pump Discharge | 3439
|  | Standard PG Chilled Water Supply | 450
|  | Temp. Trans.Chlorine Wash Tower-I to Chlorine Wash Tower-II | 13292
|  | RTD Element Chlorine Wash Tower-I to Chlorine Wash Tower-II | 28610
|  | Temp. Trans.Clorine Recuperator to Chlorine Wash Tower-I | 13292
|  | RTD Element Clorine Recuperator to Chlorine Wash Tower-I | 29629
|  | Temp. Trans. Chlorine Wash Tower-I | 13292
|  | RTD Element Chlorine Wash Tower-I | 29629
|  | Temp. Trans. Chlorine Wash Tower-II to Mist Eliminator | 13292
|  | RTD Element Chlorine Wash Tower-II to Mist Eliminator | 28610
|  | Temp. Trans. Chlorine Wash Tower-II Cooler Outlet | 13292
|  | RTD Element Chlorine Wash Tower-II Cooler Outlet | 24540
|  | Butterfly Control valve Wet Cl2 Gas Header | 145717
|  | Butterfly Control valve Wet Cl2 Gas Header | 118413
|  | Rotameter Process Water to T-502 | 8916
|  | Rotameter Process Water to T-501 | 8916
|  | Remote Seal Trans. Chlorine Wash Tower-I T-501 | 91511
|  | Globe Control valve Chlorine Wash Tower-I T-501 | 111526
|  | Magflow Trans. Cooler E-502 Outlet | 82105
|  | Magflow Trans. Cooler E-503 Outlet | 82105
|  | Globe Control Valve Chlorine Wash Tower-II Cooler Outlet | 57034
|  | Magnetic Chlorine Wash Tower-II | 29299
|  | Std.Bimetallic Temp. gauge Hydrogen Gas from Header | 3008
|  | Std.Bimetallic Temp. gauge Hydrogen Gas Wash Tower-I to Hydrogen Gas Wash Tower-II | 3008
|  | Std.Bimetallic Temp. gauge Cooling water Return | 2784
|  | Std.Bimetallic Temp. gauge Cooler E-601 Water Outlet | 2739
|  | Std.Bimetallic Temp. gauge Hydrogen Gas Wash Tower-II | 3074
|  | Std.Bimetallic Temp. gaugeChilled water Return | 2739
|  | Std.Bimetallic Temp. gaugeHydrogen Wash Tower-II Cooler Outlet | 2739
|  | Standard PG Cooling Water Supply | 450
|  | Diaph.Seal PG Hydrogen Gas Wash Tower-I to Hydrogen Gas Wash Tower-II | 2430
|  | Diaph.Seal PG Hydrogen Gas from Header | 2430
|  | Diaph.Seal PG P-601 A Pump Discharge | 450
|  | Diaph.Seal PG P-601 B Pump Discharge | 450
|  | Diaph.Seal PG P-602 A Pump Discharge | 450
|  | Diaph.Seal PG P-602 B Pump Discharge | 450
|  | Standard PG Hydrogen Gas Wash Tower-II to Mist Eliminator | 2430
|  | Temp. Trans. Hydrogen Gas Wash Tower-I | 13292
|  | RTD Element Hydrogen Gas Wash Tower-I | 4140
|  | Temp. Trans. Hydrogen Gas Wash Tower-II to Mist Eliminator | 13292
|  | RTD Element Hydrogen Gas Wash Tower-II to Mist Eliminator | 3966
|  | Temp. Trans.FA-601 Flame Arrestor | 13292
|  | RTD Element FA-601 Flame Arrestor | 4036
|  | RTD Element Hydrogen Gas to Hydrogen Gas Wash Tower-I | 4036
|  | Globe Control valve Diffl Pressure between N2 & Cl2 O/L Electrolyser | 105734
|  | Globe Control valve Diffl Pressure between N2 & Cl2 O/L Electrolyser | 97800
|  | On-Off Valve Nitrogen To FA-601 | 33010
|  | Butterfly Control Valve Hydrogen Gas To Hydrogen Holder | 80903
|  | Standard Pr.Trans.Hydrogen Gas To Hydrogen Holder | 36809
|  | Remote Seal Trans. Hydrogen Gas Wash Tower-I T-601 | 57258
|  | Globe Control Valve Hydrogen Gas Wash Tower-I T-601 | 56206
|  | Rotameter P-601 A/B Pump Comm.Disch. | 25112
|  | Rotameter DM Water to T-602 | 8916
|  | Rotameter P-602 A/B Pump Comm.Disch. | 25112
|  | Rotameter DM Water to T-602 gas outlet line | 8916
|  | MagneticHydrogen Gas Wash Tower-II T-602 | 11809
Erection of MCC and Motors
MCC-6
MCC-3
MCC-3A
h) Installation of Light fittings with LDB
4. Pre-commissioning
b) Hook up with Existing set up (Process and utilities)
c) Trial run of Equipments
d) Brine filling and circulation
5. Commissioning of plant
|  | TOTAL | 39495521.0554

## Cell House
Resource Collection | 03-Cell-House | Resource | Amount
4. CIVIL and Erection
Electrolyzer area
Electrolyzers footings | Dismantling | Electrolyzers footings | 205754.2857
Electrolyzers footings | Excavation | Electrolyzers footings | 205754.2857
Electrolyzers footings | PCC | Electrolyzers footings | 205754.2857
Electrolyzers footings | Column and footing | Electrolyzers footings | 205754.2857
Electrolyzers footings | Soil consolidation | Electrolyzers footings | 205754.2857
Electrolyzers footings | PCC and RCC of flooring | Electrolyzers footings | 205754.2857
Electrolyzers footings | Plastering of flooring | Electrolyzers footings | 205754.2857
MS Steel Items of cell house platform | Mobilization of erection material | MS Steel Items of cell house platform | 322206
MS Steel Items of cell house platform | Pipe rack erection at inside cell house | MS Steel Items of cell house platform | 322206
| Erection of cell platform | MS Steel Items of cell house platform | 322206
|  | FRP gratings for cell house & IEC | 586899
|  | MS Structures | 91066
|  | Painting | 511200
Erection of Bus Bar at rectifier room and Cell house | Bus bar column level checking | Erection of Bus Bar at rectifier room and Cell house | 127750
Erection of Bus Bar at rectifier room and Cell house | Insulator erection | Erection of Bus Bar at rectifier room and Cell house | 127750
Erection of Bus Bar at rectifier room and Cell house | Erection of busbar at cell house side | Erection of Bus Bar at rectifier room and Cell house | 127750
Erection of Bus Bar at rectifier room and Cell house | Erection of busbar at rectifier side | Erection of Bus Bar at rectifier room and Cell house | 127750
Electrolyser assembly | Electrolyzer column level checking | Electrolyser assembly | 126667
Electrolyser assembly | Insulator erection for busbar | Electrolyser assembly | 126667
| Cell Workshop Material | Electrolyser erection material | 510000
Electrolyzers(Imported)- 1 lot | Positioning of cell frame | Electrolyzers(Imported)- 1 lot | 11813086.75
Electrolyzers(Imported)- 1 lot | Alignment of cell frame | Electrolyzers(Imported)- 1 lot | 11813086.75
| Electrolyzer piping | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Static Mixers- 1lot | 216750
|  | Titanium pipes and fittings | 4788339
|  | CS PFA Lined Valves & PP Ball Valves | 64951
|  | CS & SS Ball Valves | 7259
|  | SS Fasteners | 299313
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | SS pipes and fittings - Addl items | 1366000
Electrolyzers(Imported)- 1 lot | Shifting of elements from salt godowon to cell house | Electrolyzers(Imported)- 1 lot | 11813086.75
Electrolyzers(Imported)- 1 lot, Electrolyser assembly | Element inspection | Electrolyzers(Imported)- 1 lot | 11813086.75
|  | Electrolyser assembly | 126667
Electrolyzers(Imported)- 1 lot, Electrolyser assembly | Gasket cleaning & attaching | Electrolyzers(Imported)- 1 lot | 11813086.75
|  | Electrolyser assembly | 126667
Electrolyzers(Imported)- 1 lot | Outlet Manifold preparation | Electrolyzers(Imported)- 1 lot | 11813086.75
Electrolyzers(Imported)- 1 lot | Inlet Manifold preparation | Electrolyzers(Imported)- 1 lot | 11813086.75
Electrolyzers(Imported)- 1 lot | Tie rod & spring washer preparation | Electrolyzers(Imported)- 1 lot | 11813086.75
Pre-assembly training
Pre-disassmbly training
Electrolyser assembly | Clean up cell room | Electrolyser assembly | 126667
Electrolyzers(Imported)- 1 lot, Electrolyser assembly | Membrane soaking | Electrolyzers(Imported)- 1 lot | 11813086.75
|  | Electrolyser assembly | 126667
Electrolyzers(Imported)- 1 lot, Electrolyser assembly | Gasket greasing | Electrolyzers(Imported)- 1 lot | 11813086.75
|  | Electrolyser assembly | 126667
Electrolyzers(Imported)- 1 lot, Electrolyser assembly | Electr-R-201 assembly & pin hole test | Electrolyzers(Imported)- 1 lot | 11813086.75
|  | Electrolyser assembly | 126667
Electrolyzers(Imported)- 1 lot, Electrolyser assembly | Electr R-202 assembly & pin hole test | Electrolyzers(Imported)- 1 lot | 11813086.75
|  | Electrolyser assembly | 126667
Cable connection for voltage monitoring system
Platform removal
Electrolyser filling
Bus bar connection
Tie rod refastening
Anolyte Pit Extension-1
Pipe Rack Strengthning
New Pit Extension
Pit Extension | Excavation | Pit Extension | 206388.8235
Breaking Of Wall Between Anolyte and Catholyte Tank
Pit Extension | PCC | Pit Extension | 206388.8235
Pit Extension | RCC | Pit Extension | 206388.8235
Pit Extension | Concreting up to raft level | Pit Extension | 206388.8235
Pit Extension | Pump Civil bed construction | Pit Extension | 206388.8235
Pit Extension | Wall construction | Pit Extension | 206388.8235
Pit Extension | Curing | Pit Extension | 206388.8235
Phase-1 shutdown
Process dept activities before work
Shut down
Clearance activities
Caustic/ H2 seperator stream
Dismantling of Inlet & outlet pipe connection
Shifting of Caustic H2 seperator
shifting of pumps & suction discharge line hook up
hook up of cell overflow to caustic seperator line
hookup of caustic seperator outlet gas line
Inst & Elec Dept activities
Process dept activities after work
leak checking
start up
Phase-2 shutdown
Process dept activities before work
Shut down
Clearance activities
Mechanical dept activities after clearance
DB-Cl2 seperator stream
Dismantling of Inlet & outlet pipe connection
Shifting of DB-Cl2 seperator
shifting of pumps & suction discharge line hook up
hook up of cell overflow to DB Cl2 line
hookup of DB-Cl2 seperator outlet gas line
Inst & Elec Dept activities
Process dept activities after work
leak checking
start up
Anolyte Pit Extension-2
Breaking of wall between old & new pit
Pit Extension | Dismantling of old catholyte tank area | Pit Extension | 206388.8235
Pit Extension | RCC work | Pit Extension | 206388.8235
Pit Extension | Civil bed construction | Pit Extension | 206388.8235
Pit Extension | Dismantling of old anolyte tank area | Pit Extension | 206388.8235
Pit Extension | RCC Work at Anolyte Area | Pit Extension | 206388.8235
Pit Extension | tank Civil bed construction | Pit Extension | 206388.8235
Pit Extension | Demolition of existing wall towards western side | Pit Extension | 206388.8235
Pit Extension | Excavation | Pit Extension | 206388.8235
Pit Extension | RCC work | Pit Extension | 206388.8235
Pit Extension | Pump Civil bed construction | Pit Extension | 206388.8235
Anolyte / Catholyte circulation tank / Pump.
Catholyte circulation tank- 1 No | Position of new catholyte tank | Catholyte circulation tank- 1 No | 817978
Anolyte Circulation Tank- 1 No | Position of new anolyte tank | Anolyte Circulation Tank- 1 No | 6850562
Catholyte circulation pumps- 2 Nos - | Position of new catholyte pumps | Catholyte circulation pumps- 2 Nos - | 1741951
Anolyte Circulation pumps- 2 Nos - | Position of new anolyte pumps | Anolyte Circulation pumps- 2 Nos - | 951921
Erection of cable tray ( Electrical and Instrument )
Motor for Anolyte circulation pump - 2 nos, Motor for catholyte circulation pump - 2 nos | Erection of motors | Motor for Anolyte circulation pump - 2 nos | 55905
|  | Motor for catholyte circulation pump - 2 nos | 111359
| Piping erection | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Strainers - 1 lot - Non Metallic | 28438
|  | Expansion Bellow - 1 lot | 58424
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | Additional valves | 501000
Cleaning and Flushing of tanks and pipe lines
Instrument erection
Anolyte drain tank / individual Catholyte circulation tank and pump
Removal of old anolyte & catholyte Tank
Removal of old anolyte & catholyte Pumps
Anolye Drain tank- 1 No, Anolyte Drain pump- 1 No -, Drain anolyte transfer pump- 1 No -, Inspection charges for FRP tanks | Positioning of Anolyte drain tank with pumps | Anolye Drain tank- 1 No | 713277
|  | Anolyte Drain pump- 1 No - | 412823
|  | Drain anolyte transfer pump- 1 No - | 427393
|  | Inspection charges for FRP tanks | 24791
Individual catholyte tank- 1 No, Catholyte circulation pumps- 2 Nos -, Inspection charges for FRP tanks | Positioning of Individual catholyte tank with pumps | Individual catholyte tank- 1 No | 817978
|  | Catholyte circulation pumps- 2 Nos - | 870975.6667
|  | Inspection charges for FRP tanks | 24791
Motor for Individual catholyte circulation pump - 1 no | Erection of motor and cables | Motor for Individual catholyte circulation pump - 1 no | 45389
| Pipe line laying and erection | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | SS pipes and fittings | 96975
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
Instrument erection
Process line Hook up
Utility line hook up
Cleaning and Flushing of tanks and pipe lines
Hydrogen Handling system
Removal of Existing H2 Handling system - H2 vent stack, H2 blower, H2 wash tower & pumps
Modification of Civil Bed - Cl2 seal pot
Construction of civil bed for H2 vent stack
E 201 and E 203 Bed construction
Civil pedestal construction for pipe rack & Pipes supports
H2 vent gas stack- 1 No -, Flame arrestor - 1 No | Hydrogen gas vent stack positioning | H2 vent gas stack- 1 No - | 306742
|  | Flame arrestor - 1 No | 225839
Chlorine gas pressure seal pot- 1 No | Chlorine seal pot positioning | Chlorine gas pressure seal pot- 1 No | 372895
Catholyte Heat exchanger-1 No -, Individual catholyte heat exchanger- 1 No - | E 201 and E 203 Positioning | Catholyte Heat exchanger-1 No - | 500224
|  | Individual catholyte heat exchanger- 1 No - | 407730
Pipe rack erection
| Pipe line laying and erection | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Steam Traps- 1 lot | 97135
|  | Sight glass- 1lot | 64438.5
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Piston Valves | 488921
|  | PP Ball Valves - 27 Nos | 16848
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | Raschig ring for H2 vent stack | 2000
Instrument erection
Process line Hook up
Utility line hook up
Cleaning and Flushing of tanks and pipe lines
Cell House Pipe rack
Removal of Cl2 wash tower & Pumps., Cl2 Blowers & Recuperator
Civil Foundation for pipe rack
Civil bed construction for SC-2001
Sample cooler- 1 No - | SC-2001 positioning | Sample cooler- 1 No - | 25483
Pipe rack erection
| Pipe line laying | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Dil. HCl transfer pumps- 2 Nos | 83250
Instrument erection
Process line Hook up
Utility line hook up
Cleaning and Flushing of tanks and pipe lines
P-I OHT area
Mobilization of Erection Material
Structural building for head tanks CDU etc. | Arrival of contractor and start of the work | Structural building for head tanks CDU etc. | 139606
Structural building for head tanks CDU etc. | Fabrication of structures | Structural building for head tanks CDU etc. | 139606
| Erection of coulmns | Structural building for head tanks CDU etc. | 139606
|  | Head tank structure | 954000
|  | Painting | 511200
Structural building for head tanks CDU etc. | welding of structures | Structural building for head tanks CDU etc. | 139606
Structural building for head tanks CDU etc. | Erection and welding of handrails | Structural building for head tanks CDU etc. | 139606
Structural building for head tanks CDU etc. | painting of structures | Structural building for head tanks CDU etc. | 139606
Structural building for head tanks CDU etc. | Closure of the welding work | Structural building for head tanks CDU etc. | 139606
Catholyte head tank- 1 No, Inspection charges for FRP tanks | Catholyte OHT receipt | Catholyte head tank- 1 No | 601213
|  | Inspection charges for FRP tanks | 24791
Pure Brine head tank - 1 No, Inspection charges for FRP tanks | Pure brine OHT receipt | Pure Brine head tank - 1 No | 1467451
|  | Inspection charges for FRP tanks | 24791
Chlorate destruction tank receipt
Erection of Cathoylte OHT
Erection of pure brine OHT
Erection of Chlorate destruction tank
Arrival of piping contractor
| piping erection | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
| finish of piping | Fasteners | 29900
5. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
Erection contract Finalization
Mobilization of erection material
Pipe rack and supports fabrication and erection
| Process Piping- Inside cell house | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | Base plate and foundation bolt | 25000
| Process Piping - Outside cell house | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Base plate and foundation bolt | 25000
| Utility Piping - Inside cell house | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Fabrication and Erection of CS & SS Pipelines & Erection of Metallic Pipelines | 866662
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Erection of CS pipes and SS pipes | 326166.6667
|  | SS pipes and fittings | 96975
|  | CS HDGI Fasteners | 28214
|  | Ball Gate Globe & Check valves | 41458.2353
|  | CS Fittings | 81585
|  | CS Seamless and ERW Pipes | 384692.8
|  | Metallic Pipe & Valve supports | 194677.8
|  | CS pipes and fittings | 147200
|  | Gaskets | 102200
|  | Fasteners | 29900
|  | Base plate and foundation bolt | 25000
| Utility Piping - Outside Cell House | FRP pipes and fittings - CPP - cell house and Cl2/H2 handling - supply and Erection | 839114
|  | Fabrication and Erection of CS & SS Pipelines & Erection of Metallic Pipelines | 866662
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Erection of CS pipes and SS pipes | 326166.6667
|  | SS pipes and fittings | 96975
|  | CS HDGI Fasteners | 28214
|  | Base plate and foundation bolt | 25000
Erection of cable tray ( Electrical and Instrument )
Laying of cables (Electrical and Instrument)
Erection of instruments , Testing
|  | TOTAL | 200742525.9086

## Sc. Brine
Resource Collection | 02-Sec-Brine-Plant | Resource | Amount
4. CIVIL and Erection
4.1 Polished Brine storage tank and pumps
a) Removal of Old Polished Brine tank
b) Excavation
c) Foundation
Polished Brine tank- 1 No - T 105 A, Inspection charges for Rubber lined tanks | d) Positioning of Brine Storage tank | Polished Brine tank- 1 No - T 105 A | 1875473
|  | Inspection charges for Rubber lined tanks | 17500
e) Filling and Leak Testing
Removal of Old Polished Brine pump-A
| Civil bed modification | Primary and secondary Brine pumps foundation | 262000
| d) Positioning of new pump-A | Polished Brine pumps- 90 M3/hr- 2 Nos - | 545318
|  | Motor- For Polished Brine pump - 2 nos | 67979
|  | Ball Gate Globe & Check valves | 41458.2353
Piping
Commissioning
Removal of Old Polished Brine pump-B
| Civil bed modification | Primary and secondary Brine pumps foundation | 262000
Polished Brine pumps- 90 M3/hr- 2 Nos -, Motor- For Polished Brine pump - 2 nos | d) Positioning of new pump - B | Polished Brine pumps- 90 M3/hr- 2 Nos - | 545318
|  | Motor- For Polished Brine pump - 2 nos | 67979
| Piping | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
Polished Brine pumps- 90 M3/hr- 2 Nos - | Commissioning | Polished Brine pumps- 90 M3/hr- 2 Nos - | 545318
4.3Pure Brine Tank and Pumps
a)Removal of old Pure brine tank
b)Old Bed Dismantling
c)Excavation
d)Bed Construction
Curing
Pure Brine tank- 1 No - 06TU008 A, Inspection charges for Rubber lined tanks | e) Receipt , Positioning & commissioning | Pure Brine tank- 1 No - 06TU008 A | 1058235
|  | Inspection charges for Rubber lined tanks | 17500
Removal of Old Pure Brine pump-A
| Civil bed modification | Primary and secondary Brine pumps foundation | 262000
Pure Brine pump- 90 M3/hr- 2 No -, Motor- For Pure Brine Pump - 2 nos | d) Positioning of new pump-A | Pure Brine pump- 90 M3/hr- 2 No - | 528277
|  | Motor- For Pure Brine Pump - 2 nos | 36473
Piping
Commissioning
Removal of Old Pure Brine pump-B
| Civil bed modification | Primary and secondary Brine pumps foundation | 262000
Pure Brine pump- 90 M3/hr- 2 No -, Motor- For Pure Brine Pump - 2 nos | d) Positioning of new pump - B | Pure Brine pump- 90 M3/hr- 2 No - | 528277
|  | Motor- For Pure Brine Pump - 2 nos | 36473
| Piping | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
Pure Brine pump- 90 M3/hr- 2 No - | Commissioning | Pure Brine pump- 90 M3/hr- 2 No - | 528277
4.2 IEC
a)Dismantling
b)Excavation
c)Footings and column construction
Ion Exchange column- 1 No, Building Structure of Ion exchange column pipes and valves | d)Positioning of Ion exchange column | Ion Exchange column- 1 No | 1026179
|  | Building Structure of Ion exchange column pipes and valves | 516000
f) Ion exchange column strainer erection
g)filling of Ion exchange column with resin
i) Leak testing of resins
| e)Internal Piping | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Sight glass for IEC | 35129
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
|  | Diaphargm Valves - IEC - 3 Nos | 56424
|  | CPVC Socket type ball valve for IEC | 2025
|  | CPVC pipes and fittings for IEC | 50495
|  | CPVC/FRP Pipes and Fittings | 665505
Control valve receipts & positioning
Loop & regeneration Checking
Commissioning
5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments
Erection contract Finalization
Mobilization of erection material
Pipe rack and supports
| Process Piping | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | Ball Gate Globe & Check valves | 41458.2353
|  | PPHCPVC & UPVC Valves | 83603.7727
|  | PTFE Lined Valves - 132 Nos | 103999.8182
|  | CS+PFA Lined Valves (Alternate to PVDF) | 47401.2273
|  | Ball Gate Globe & Check valves | 41458.2353
|  | Rubber Lined Check Valves - 28 Nos | 18312
|  | Diaphargm Valves - 187 Nos | 112316
| Utility Piping | FRP pipes and fittings - Modern - Brine plant - Supply and Erection | 875973
|  | Fabrication and Erection of CS & SS Pipelines & Erection of Metallic Pipelines | 866662
|  | Valve supports and Pipe supports - Supply and Erection | 205976
|  | PVC pipes and fittings for Chilled water Utilities | 287064
|  | Erection of CS pipes and SS pipes | 326166.6667
|  | SS pipes and fittings | 96975
|  | CS HDGI Fasteners | 28214
|  | TOTAL | 17606830.1159

## Commissioning
Commissioning
Primary-Brine
6. Pre-commissioning
5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments
Cleaning and Flushing ( Tanks, equipment and Pipe lines )
Hook up with Existing set up (Process and utilities)
Trial run of equipment
Brine filling and circulation
7. Commissioning of plant
Secondary-Briner
6. Pre-commissioning
5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments
Cleaning and Flushing ( Tanks, equipment and Pipe lines )
Hook up with Existing set up (Process and utilities)
Trial run of equipment
Brine filling and circulation
7. Commissioning of plant
Cell-House
7. Pre-commissioning
5. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines )
b) Hook up with Existing set up (Process and utilities)
c) Trial run of Equipments
d) Brine filling and circulation
8. Commissioning of plant
Cl2-H2
4. Pre-commissioning
3.4 Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines )
b) Hook up with Existing set up (Process and utilities)
c) Trial run of Equipments
d) Brine filling and circulation
5. Commissioning of plant
Dry Cl2
5. Precommissioning
4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
b) Hook up with Existing set up (Process and utilities)
c) Trial run of Equipments
6. Commissioning of plant
Hypo
5. Precommissioning
4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines )
b) Hook up with Existing set up (Process and utilities)
c) Trial run of Equipments
6. Commissioning of plant
Utilities
5. Precommissioning
4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines )
b) Hook up with Existing set up (Process and utilities)
c) Trial run of Equipments
6. Commissioning of plant

## Insrtm.
Resource Collection | 09-Instrumentation | Resource | Amount
DCS
| DCS Room Civil Work Completion | AC for DCS room | 100000
DCS Supply & erection, DCS Panel Room Modification, FalseFloor, Erection of False Floor | Positioning of DCS Panels in room | DCS Supply & erection | 1039139
|  | DCS Panel Room Modification | 551855
|  | FalseFloor | 142987
|  | Erection of False Floor | 0
DCS Supply & erection | Moving DCS consoles to CR & removing existing consoles | DCS Supply & erection | 1039139
DCS Supply & erection | Power up of Existing DCS Consoles | DCS Supply & erection | 1039139
DCS Supply & erection | Power up of new DCS Consoles | DCS Supply & erection | 1039139
DCS Supply & erection | Power up of new DCS panels | DCS Supply & erection | 1039139
| Commissioning of New DCS | DCS Supply & erection | 1039139
|  | Analog Input module | 193248
2.Instruments Cabling & Termination- Main cable
Mobillisation of site by Erection Contractor
Fabrication of tray support for main cables
| Erection of Main cable trays | Erection of cable tray and instruments | 1726055.5
Fabrication and Erection of JB support
| Receipt of I & C cables at site | Instrumentation Cables | 639290.5
| Laying & dressing of Main cables from JB to CR | Instrumentation Cables | 639290.5
| Cable Glanding & Termination of Main cables | Instrumentation Cables | 639290.5
| Loop check from JB end to DCS | Instrumentation Cables | 639290.5
3. Field Inst erection
Fabrication of stancheon for remote mounted instruments
Erection of stancheons at required place
Branch cable tray fabrication, erection
Branch cable laying & Termination at JB end
Receipt of all control valves, flowmeters, RTD, TG & PG
| Installation of all field Instruments | erection of Instruments | 201000
|  | Erection of cable tray and instruments | 1726055.5
|  | Lined ON/OFF Diaphragm Type Valve - 10 Nos & Buterfly valve - 1 No | 991568
|  | Magflow Trans.-Pump P-107 A & B Comm.Discharge | 97032
|  | Standard Pr.Trans. F-116 Inlet | 40899
|  | Flanged Mounted Trans.Clear Brine Tank T-118A | 57258
|  | Flanged Mounted Trans. UF Feed Tank T-108A | 57258
|  | Magflow Trans. Pump P-108 A & B Comm.Discharge | 97032
|  | Ultrasonic Type Trans.Filtrate PIT | 36809
|  | Vortex flow Trans. DM Water to T-404 | 76685
|  | Magflow Trans.32% HCL Acid to T-404 | 59713
|  | Globe Control Valve DM Water to T-404 | 54354
|  | Diaphragm Control Valve32% HCL Acid to T-404 | 41461
|  | Flanged Mounted Trans. Tank 06TU008 A | 57258
|  | Magflow Trans. 06TU008 A Inlet | 97032
|  | Magnetic Flow Meter Tag No: FT-1401 | 73618
|  | Hart Communicator | 235169
|  | ASCO MAKE 3/2 WAY DIRECT OPERATED SOLENOID VALVE: NORMALLY CLOSED MODEL: WPB 320 A 202 | 35429
|  | pH Transmitter Static Mixer SM-1401 Outlet | 58690
|  | Diaphragm Control Valve 20% HCL to SM-1401 | 41461
|  | Flanged Mounted Trans.Polished Brine Tank T-105A | 57258
|  | Ball Control Valve Polished Brine Tank T-105A Inlet | 73618
|  | pH Transmitter Polished Brine Tank T-105A Inlet | 58690
|  | Diaph.Seal PG P-118 A Pump Discharge | 3439
|  | Diaph.Seal PG P-118 B Pump Discharge | 3439
|  | Diaph.Seal PG P-108 B Pump Discharge | 3439
|  | Diaph.Seal PG P-116 A Pump Discharge | 3439
|  | Diaph.Seal PG P-116 B Pump Discharge | 3439
|  | Diaph.Seal PG P-117 A Pump Discharge | 2833
|  | Diaph.Seal PG P-117 B Pump Discharge | 2833
|  | Diaph.Seal PG P-403 A Pump Discharge | 2834
|  | Diaph.Seal PG P-403 B Pump Discharge | 2834
|  | Diaph.Seal PG P-008 A Pump Discharge | 3439
|  | Diaph.Seal PG P-008 B Pump Discharge | 3439
|  | Diaph.Seal PG P-105 A Pump Discharge | 3439
|  | Diaph.Seal PG P-105 B Pump Discharge | 3439
|  | Electrolyser Cell Voltage acquisition system | 1326657
|  | Flanged Leve Trans. Brine Head Tank V-205 | 48056
|  | Tubular Brine Head Tank V-205 | 40095
|  | Magflow Trans. Super Purified Brine to Electrolyzer-1 | 82104
|  | Magflow Trans. Super Purified Brine to Electrolyzer-2 | 82104
|  | Butterfly Control Valve Super Purified Brine to Electrolyzer-1 | 117451
|  | Butterfly Control Valve Super Purified Brine to Electrolyzer-2 | 117451
|  | Magflow Trans.NaOH to Electrolyzer-1 | 44784
|  | Magflow Trans.NaOH to Electrolyzer-2 | 44784
|  | Butterfly Control Valve NaOH to Electrolyzer-1 | 117451
|  | Butterfly Control Valve NaOH to Electrolyzer-2 | 117451
|  | Diaph.Seal PG Cl2 / Brine separator Electrolyzer -1 Outlet | 3843
|  | Diaph.Seal PG Cl2 / Brine separator Electrolyzer -2 Outlet | 3843
|  | Diaph.Seal PG H2 / NaOH separator Electrolyzer-1 Outlet | 3843
|  | Diaph.Seal PG H2 / NaOH separator Electrolyzer-2 Outlet | 3843
|  | Cell Voltage Trans. ELECTROLYZER R-201 | 0
|  | Cell Voltage Trans. ELECTROLYZER R-202 | 0
|  | Remote Seal Level Trans. Anolyte Drain Tank V-203 | 91511
|  | Tubular Anolyte Drain Tank V-203 | 40095
|  | Diaph.Seal PG P-203 Pump Discharge | 3843
|  | Diaph.Seal PG P-205 Pump Discharge | 2389
|  | Standard Pr.Trans. Wet Cl2 Gas Header | 47033
|  | Diaph.Seal PG Cl2 Gas Header | 3843
|  | Rotameter Industrial Water to T-205 | 8915
|  | Standard Pr.Trans. Wet H2 Gas Header | 34252
|  | Schaefer's Diphragm Gauge T-206 Inlet | 1016
|  | Tubular T-206 | 30175
|  | Rotameter N2 gas to T-206 | 8916
|  | Vortex flow Trans. DM water to Recycle Caustic | 76685
|  | Globe Control Valve DM water to Recycle Caustic | 183922
|  | Flanged Leve Trans.Caustic Head Tank V-206 | 38854
|  | Tubular V-206 | 34241
|  | Flange Mounted Trans.Individual Catholyte Tank V-204 | 38854
|  | Butterfly Control Valve.Individual Catholyte Tank V-204 | 113689
|  | Tubular V-204 | 40095
|  | Diaph.Seal PG P-204 Pump Discharge | 2389
|  | Std.Bimetallic Temp. gauge NaOH E-203 Inlet | 5835
|  | Std.Bimetallic Temp. gauge NaOH E-203 Outlet | 5835
|  | Std.Bimetallic Temp. gaugeCooling Water E-203 Inlet | 2701
|  | Bimetallic Temp. gauge Cooling Water E-201 Inlet | 2701
|  | RTD Element Recycle NaOH E-203 Outlet | 25874
|  | Temp. Trans. Recycle NaOH E-203 Outlet | 13292
|  | Globe Control Valve. Recycle NaOH E-203 Outlet | 67074
|  | Magflow Trans. Depleted Brine Recycle to Electrolyzer | 70731
|  | Butterfly Control Valve Depleted Brine Recycle to Electrolyzer | 64789
|  | RTD Element Off Spec. NaOH to V-204 | 25874
|  | Temp. Trans. Off Spec. NaOH to V-204 | 13292
|  | Density Transmitter NaOH in V-204 | 444775
|  | Vortex flow Trans. DM water to Recycle Caustic | 76685
|  | Globe Control Valve DM water to Recycle NaOH | 151991
|  | Rotameter N2 Gas to V-204 | 8915
|  | Remote Seal Trans. Catholyte Circulation Tank V-202 | 63393
|  | Butterfly Control Valve Catholyte Circulation Tank V-202 | 113689
|  | Tubular V-202 | 40095
|  | Rotameter N2 Gas to V-202 | 8916
|  | Diaph.Seal PG P-202 A Pump Discharge | 3843
|  | Diaph.Seal PG P-202 B Pump Discharge | 3843
|  | Density Transmitter 32% NaOH in V-202 | 444775
|  | Mass Flow Trans.32% Product NaOH | 843539
|  | Density Transmitter32% Product NaOH | 0
|  | Temp. Transmitter32% Product NaOH | 0
|  | Bimetallic Temp. gauge NaOH E-201 Inlet | 5836
|  | Bimetallic Temp. gauge NaOH E-201 Outlet | 5836
|  | Temp. Trans. NaOH E-203 Outlet | 13292
|  | RTD Element NaOH E-203 Outlet | 25874
|  | Globe Control Valve NaOH E-203 Outlet | 97646
|  | Globe Control Valve NaOH E-203 Outlet | 184045
|  | Remote Seal Trans. Anolyte Tank V-201 | 91510
|  | Tubular V-201 | 40095
|  | Butterfly Control Valve Anolyte Tank V-201 | 126663
|  | Diaph.Seal PG P-201 A Pump Discharge | 3843
|  | Diaph.Seal PG P-201 B Pump Discharge | 3843
|  | pH Transmitter Depleted Brine in V-201 | 58690
|  | Rotameter Depleted Brine at Analyer AE-2001 O/L | 26584
|  | Temp. Trans.NaOH Outlet Elect. R-201 | 13292
|  | RTD Element NaOH Outlet Elect. R-201 | 25874
|  | Temp. Trans. NaOH Outlet Elect. R-202 | 13292
|  | RTD Element NaOH Outlet Elect. R-202 | 25874
|  | Magflow Trans. HCL to Depleted Brine | 59712
|  | Globe Control Valve HCL to Depleted Brine | 147778
|  | Magflow Trans. Depleted Brine to E-161 | 59713
|  | Diaphragam Control Valve Depleted Brine to E-161 | 64789
|  | Bimetallic Depleted Brine E-161 Outlet | 5835
|  | Rotameter Plant Air | 10143
|  | Std.Bimetallic Temp. gauge Low Pr. Steam E-161 Inlet | 2590
|  | RTD Element Depleted Brine E-161 Outlet | 25874
|  | Temp. Trans. Depleted Brine E-161 Outlet | 13292
|  | Globe Control Valve Depleted Brine E-161 Outlet | 70448
|  | Std. Gauge with Syphon Low Pr. Steam to E-161 Inlet | 1016
|  | Remote Seal D.P. Trans. Chlorate Decomposition Tank V-161 | 91511
|  | RTD Element Depleted Brine V-161 | 32527
|  | Temp. Trans.Depleted Brine V-161 | 13292
|  | Magflow Trans. HCL to V-161 | 59713
|  | Globe Control Valve HCL to V-161 | 147778
|  | Bimetallic Depleted Brine E-161 Inlet | 5835
|  | Globe Control Valve Nitrogen To Cl2 Gas Heade | 148228
|  | Globe Control Valve Nitrogen To N2 Gas Header | 148228
|  | Rotameter TransmitterN2 Gas to Cl2 Gas Header | 50613
|  | Diaph.Seal PG Cl2 Gas Header | 3843
|  | Diaph.Seal PG H2 Gas Header | 1016
|  | Std. Gauge with Syphon Low Pressure Steam E-201 Inlet | 1016
|  | Std. Gauge with Syphon Steam E-203 Inlet | 1016
|  | Standard PG Pressure Gauge for N2 Gas | 1016
|  | Bourden sending Pressure Gauge for N2 Gas line | 1016
|  | Rotameter Transmitter N2 Gas to H2 Gas Header | 50613
|  | Rotameter DM Water to Electrolyzer | 61512
|  | Rotameter Recyc. NaOH to Electrolyzer | 26583
|  | Standard Pr.Trans. Cooling Water To Rectifier Transformer | 16459
|  | Standard PG Cooling water Supply | 450
|  | Std.Bimetallic Temp. gauge32% NaOH To E-204 NaOH Cooler | 2739
|  | Std.Bimetallic Temp. gauge Cooling water Return | 2850
|  | Std.Bimetallic Temp. gauge Cooling water Supply | 2850
|  | Std.Bimetallic Temp. gauge E-204 NaOH Cooler to 32% NaOH Storage | 2739
|  | 2051lwaapfd31aas1mtdrQr Level Transmitter | 91511
|  | Rotameter Depleted Brine to Electrolyser | 30911
|  | Rotameter Depleted Brine | 30911
|  | Rotameter DM Water to Cell Feed Brine Line | 61511
|  | Rotameter DM Water to Cell Feed Brine Line | 61511
|  | Diaph.Seal PGChlorine Gas from F-501 To T-503 | 4247
|  | Diaph.Seal PG 21 PU-001-A Pump Discharge | 3439
|  | Diaph.Seal PG 21 PU-001-B Pump Discharge | 3439
|  | Std.Bimetallic Temp. gauge Dry Chlorine Gas To Compressor K-501A | 2963
|  | Std.Bimetallic Temp. gauge H2SO4 To T-503 | 7561
|  | Thermowell H2SO4 Circulation Pump 21 PU-001-A & B Comm. Discharge | 6628
|  | Magflow Trans. H2SO4 To T-503 | 82105
|  | Temp. Trans.H2SO4 To T-503 | 13292
|  | RTD Element H2SO4 To T-503 | 26914
|  | Globe Control Valve Wet Chlorine Gas To HCl Plant | 193073
|  | Standard Pr.Trans.Wet Chlorine Gas To HCl Plant | 42944
|  | On-Off Valve Dry Chlorine Gas To HCl Plant | 209347
|  | Diaph.Seal PG P-703 Pump Discharge | 3439
|  | Diaph.Seal PG P-701 A/B Pump Comm.Discharge | 3439
|  | Std.Bimetallic Temp. gauge Sodium Hypo Chlorite Solution To T-702 | 2784
|  | Std.Bimetallic Temp. gauge Chilled water return from E-701 A | 2739
|  | Std.Bimetallic Temp. gauge Chilled water return from E-701 B | 2739
|  | On-Off Valve Circulation Tank B T-705 Outlet | 113990
|  | On-Off Valve Circulation Tank A T-704 Outlet | 113990
|  | Magflow Trans. Sodium Hypo Chlorite Solution To T-702 | 82105
|  | Magflow Trans. Sodium Hypo Chlorite Solution To T-703 | 82105
|  | Flanged Mounted Trans.Caustic Overhead Tank V-701 | 48056
|  | Pressure Reducing valves | 23327
|  | Pressure Safety Valve | 64645
|  | Chilled water Magnetic flowmeter | 173820
|  | Standard PG Process water to Cell House | 450
|  | Standard PG DM water Supply | 450
|  | Low Pressure Switch DM water Supply | 2193
|  | pH TransmitterPump Seal Water Return | 58690
|  | Standard Pr.Trans. LP Steam to Plant | 16460
|  | Globe Control Valve LP Steam to Plant | 63352
|  | Std. Gauge with Syphon LP Steam to Plant | 1057
|  | Standard PG P-802 A Pump Discharge | 450
|  | Standard PG P-802 B Pump Discharge | 450
|  | Standard PG P-802 C Pump Discharge | 450
|  | Standard PG Instrument Air To Plant Air | 450
|  | Standard PG Instrument Air To CEC Cell House | 450
|  | Standard PG To Nitrogen PSA Unit | 450
|  | Standard PG To FA-601 | 450
|  | Flanged Mounted Trans.Chilled Water Tank T-801 | 34764
|  | RTD Element Chilled Water Tank T-801 | 4140
|  | Temp. Trans.Chilled Water Tank T-801 | 13292
|  | RTD Element Cooling Water return To New Dry Cooling Tower | 4036
|  | Temp. Trans.Cooling Water return To New Dry Cooling Tower | 13292
|  | RTD Element P-802 A/B/C Pump Comm. Discharge | 4036
|  | Temp. Trans.P-802 A/B/C Pump Comm. Discharge | 13292
|  | Globe Control Valve Cooling Water To Rectifier Transformer | 54272
|  | Low Pressure Switch Chiller Unit U-801 Outlet | 2193
|  | Low Pressure Switch P-802 A/B/C Pump Comm. Discharge | 2499
|  | Std.Bimetallic Temp. gauge Cooling Water return To New Dry Cooling Tower | 3007
|  | Std.Bimetallic Temp. gauge P-802 A/B/C Pump Comm. Discharge | 3007
|  | Standard PG P-801 A Pump Discharge | 450
|  | Standard PG P-801 B Pump Discharge | 450
|  | Honeywell Make Temperature Transmitter | 36359
Glanding &Termination branch cables of all field Instruments at Inst end
Loop Check & Calibration
Loop check of all instruments from field Inst end
Calibration of all field Instruments
Calibration /Stroke check of all Control valves & On/Off valves from DCS
Pre-commissioning
Tripchecks, Graphics modification , IEC sequence check etc
|  | TOTAL | 25351806

## OLD
# | Final Res Name | Final Cost |  | Task Name | Formual Res Name | Formla Cost | Task Name | Cost
1 |  |  |  | Plan1-Upgradation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
2 |  |  |  | Project Intiation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
3 |  |  | 1 | Statutory Approal-Phase1 | '[Resource Assignment-WIP.xlsx]Resource'!$B1 | '[Resource Assignment-WIP.xlsx]Resource'!$G1
4 |  |  |  | Statutory Approal-Phase2 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
5 |  |  |  | Civil Vendor Finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
6 |  |  |  | Shutdown planning for hook up | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
7 |  |  |  | 01-Py-Brine | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
8 |  |  |  | 1. CIVIL and Erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
9 |  |  |  | Saturator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
10 |  |  |  | a) Dismantling, excvation, PCC, Reinforcement work | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
11 |  |  |  | c) Foundation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
12 |  |  |  | d)Receipt of Saturator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
13 |  |  |  | Positioning of saturator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
14 |  |  |  | receipt of internals | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
15 |  |  |  | fixing of internals in saturator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
16 |  |  |  | piping works | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
17 |  |  |  | extension of ramp | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
18 |  |  |  | e) Filling and Leak Testing | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
19 |  |  |  | Clear Brine Tank & Pumps | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
20 |  |  |  | Completion of civil foundation and curing works | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
21 |  |  |  | Shifting of tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
22 |  |  |  | Erection of new tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
23 |  |  |  | Pumps receipt | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
24 |  |  |  | pumps assembling and testing | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
25 |  |  |  | Pumps erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
26 |  |  |  | piping work | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
27 |  |  |  | UF Feed Tank & pump | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
28 |  |  |  | Completion of civil foundation and curing works | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
29 |  |  |  | Finalising of contractor | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
30 |  |  |  | Shifting of tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
31 |  |  |  | Erection of new tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
32 |  |  |  | Tank commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
33 |  |  |  | Pumps receipt | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
34 |  |  |  | Removal of old UF feed tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
35 |  |  |  | Completion of civil foundation and curing works | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
36 |  |  |  | pumps assembling and testing | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
37 |  |  |  | Pumps erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
38 |  |  |  | piping work | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
39 |  |  |  | Filter Press | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
40 |  |  |  | Receipt of new filter press | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
41 |  |  |  | Removal of Existing filter press-B & its accesroies, pipings | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
42 |  |  |  | Structure correction to suit the new filter press | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
43 |  |  |  | Erection of new filter press & its accessories | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
44 |  |  |  | slurry Pump & wash water pump foundation & positioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
45 |  |  |  | Piping work | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
46 |  |  |  | Idle run | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
47 |  |  |  | 5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
48 |  |  |  | BOQ Receipt from Consultants | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
49 |  |  |  | Erection contract Finalization - Mech | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
50 |  |  |  | Mobilization of erection material | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
51 |  |  |  | Pipe rack and supports | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
52 |  |  |  | Process Piping | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
53 |  |  |  | Utility Piping | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
54 |  |  |  | Erection of cable tray ( Electrical and Instrument ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
55 |  |  |  | Laying of cables (Electrical and Instrument) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
56 |  |  |  | Erection of instruments , Testing | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
57 |  |  |  | Erection of MCC and Motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
58 |  |  |  | Installation of Light fittings with LDB | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
59 |  |  |  | 11-Procurement | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
60 |  |  |  | 1.1 Mechanical / Process | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
61 |  |  |  | Electrolyzer- cell frames (CEC) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
62 |  |  |  | Contract Signing | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
63 |  |  |  | Membrane (CEC) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
64 |  |  |  | Polished Brine Tank MOC: MSRL | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
65 |  |  |  | Hydrogen Buffer Vessel: MOC MS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
66 |  |  |  | Pure Brine Tank, MOC: MSRL | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
67 |  |  |  | Hydrogen Mist Eliminator Candle SS 316 -2 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
68 |  |  |  | Chlorine Mist Eliminator Candle Titanium - 2 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
69 |  |  |  | MSRL UF Feed Tank - 1 No | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
70 |  |  |  | PP Ball Valves - 27 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
71 |  |  |  | Nemo Make Slurry Pump - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
72 |  |  |  | Static Mixer -4 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
73 |  |  |  | First Lot FRP pipes & fittings received from M/s CPP | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
74 |  |  |  | Housing for Chlorine Mist Eliminator MOC: FRP | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
75 |  |  |  | First Lot of PVC + FRP, CPVC + FRP pipes & fittings received from modern | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
76 |  |  |  | Second Lot of PVC + FRP, CPVC + FRP pipes & fittings received from modern | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
77 |  |  |  | Clear Brine Tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
78 |  |  |  | Ion Exchange Column | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
79 |  |  |  | Chlorine Recuperator MOC: Titanium | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
80 |  |  |  | Centrifugal Pumps 25 M3- 4 Nos, 50 M3 - 3 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
81 |  |  |  | Chlorine Wash Tower CPVC 1 & 2 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
82 |  |  |  | Plate Heat Exchangers - 14 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
83 |  |  |  | Brine Dechlorination Tower | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
84 |  |  |  | Gould's Make Centrifugal Pump 20 M3, 18 M3, 2 M3, 2.5 M3 & 10 M3 - 2 Nos each | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
85 |  |  |  | Dechlorination Air Blower | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
86 |  |  |  | Chlorine compressor System | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
87 |  |  |  | Centrifugal Pump without Motor Cap: 40 M3/Hr | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
88 |  |  |  | Centrifugal Pump CAP: 80M3/Hr - 2 Nos & 40 M3/Hr - 1 No., HEAD: 40M, MOC-Ni , SERVICE- 32% | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
89 |  |  |  | Centrifugal Pumps, Cap: 60 M3/Hr - 2 Nos, 3 M3/Hr - 1 No & 25 M3/Hr - 1 No, MOC: Titanium | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
90 |  |  |  | Hydrogen Wash Tower No:T-601 & T-602 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
91 |  |  |  | MSRL Saturator - 1 No | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
92 |  |  |  | Centrifugal Pump Capacity: 10 MT/Hr, MOC: PVDF | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
93 |  |  |  | Centrifugal Pumps 120 M3 - 3 NOS, 90 M3 - 4 NOS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
94 |  |  |  | Centrifugal Pump with Motor PP, Capa: 15 M3 & 2 Md/Hr - 2 Nos each | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
95 |  |  |  | FRP Tanks - CPE | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
96 |  |  |  | Catholyte circulation Tank (V-202) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
97 |  |  |  | Anolyte Drain Tank (V-203) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
98 |  |  |  | Catholyte Circulation Tank (V-204) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
99 |  |  |  | Brine Head Tank (V-205) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
100 |  |  |  | Catholyte Head Tank (V-206) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
101 |  |  |  | Chlorine Gas Pressure Seal (T-205) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
102 |  |  |  | 20% Caustic Overhead Tank (V-701) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
103 |  |  |  | De-Chlorination Tower Condensate Separator (SP-401) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
104 |  |  |  | Sodium Sulphate Overhead Tank (T-403) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
105 |  |  |  | Acid Wash Tower (T-701) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
106 |  |  |  | Chlorine Drying Tower (T-503) - 1 No. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
107 |  |  |  | Chlorate Decomposition Tank -1 NO & Anolyte Circulation Tank - 1 No | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
108 |  |  |  | Antico Make Filtrate Pumps MOC: PP | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
109 |  |  |  | Centrifugal Hypo Blower with Motor | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
110 |  |  |  | Hydrogen Gas Vent MOC: SA 36 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
111 |  |  |  | Rotor, Wear Casting and cone fitted with orifice plates - 1 No each | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
112 |  |  |  | Flame Arrestor Size: 10" | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
113 |  |  |  | Steam Traps | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
114 |  |  |  | Prominent Meta Diaphragm Motorized Metering Pump | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
115 |  |  |  | PTFE Lined Valves - 132 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
116 |  |  |  | Full window and Double Window Type Sight Glasses (11 Nos) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
117 |  |  |  | Rubber Lined Check Valves - 28 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
118 |  |  |  | Piston Valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
119 |  |  |  | Titanium Internals - Saturator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
120 |  |  |  | Hydraulic Filter Press Size: 1200 x 1200mm | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
121 |  |  |  | Titanium Pipes and Fittings | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
122 |  |  |  | Packing Supports Titanium for Chlorine Wash Tower - 2 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
123 |  |  |  | Y Type Strainer & Basket Type Strainer - 3 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
124 |  |  |  | Diaphragm Valves - 126 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
125 |  |  |  | Diaphragm Valves - 61 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
126 |  |  |  | Housing for Hydrogen Gas Mist Eliminators | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
127 |  |  |  | Remi Make Agitator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
128 |  |  |  | Na2SO3 Transfer Pumps | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
129 |  |  |  | PTFE Lined Bellows Size: 100 NB, 80 NB & 40 NB | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
130 |  |  |  | MSRL Sodium Sulphite preparation tank | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
131 |  |  |  | Ball, Gate Globe & Check valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
132 |  |  |  | PPH,CPVC & UPVC Valves - George | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
133 |  |  |  | Non Metallic Strainers | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
134 |  |  |  | Alloy 20 Ball Valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
135 |  |  |  | CS+PFA Lined Diaphragm Valves + Ball Check valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
136 |  |  |  | CI Plug Valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
137 |  |  |  | Screw Chiller 210 TR | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
138 |  |  |  | Nitrogen Generator of 99.999% purity | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
139 |  |  |  | Wash Water Pump (10 m3/hr) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
140 |  |  |  | FRP trough for clarifier | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
141 |  |  |  | Raschig ring for H2 vent stack | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
142 |  |  |  | Hydrogen condensate seal pot - 3 nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
143 |  |  |  | Sight glass for IEC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
144 |  |  |  | Diaphragm Valves - IEC - 3 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
145 |  |  |  | CPVC Socket type ball valve for IEC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
146 |  |  |  | CS pipes and fittings | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
147 |  |  |  | SS pipes and fittings | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
148 |  |  |  | CPVC pipes and fittings for IEC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
149 |  |  |  | PVC + FRP pipes and fittings - Utilities | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
150 |  |  |  | FRP Pipes & Fittings- Hypo Plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
151 |  |  |  | PVC braided hoses and Hose clamps | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
152 |  |  |  | Insulation - Hot and Cold | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
153 |  |  |  | Painting | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
154 |  |  |  | Chilled Water Pump : 2 nos. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
155 |  |  |  | SS Ball valves (additional) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
156 |  |  |  | Valve supports & pipe supports | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
157 |  |  |  | H2 linking WO Engineering | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
158 |  |  |  | Hazop Study- WO - Risk Chem | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
159 |  |  |  | Gaskets | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
160 |  |  |  | SS Fasteners | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
161 |  |  |  | Insert Pipes | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
162 |  |  |  | 1.2 Electrical | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
163 |  |  |  | New Rectifier (ABB) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
164 |  |  |  | New Transformer(ABB) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
165 |  |  |  | HT PANEL 22 KV 1600 AMPS, 31.5 KA | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
166 |  |  |  | Siemens Make Motors - 18 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
167 |  |  |  | Siemens Make Motors - 5 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
168 |  |  |  | HT Cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
169 |  |  |  | LT cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
170 |  |  |  | Copper Bus Bars and Flexibles and accessories-Cell House | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
171 |  |  |  | Copper Bus Bars and Flexibles and accessories- Rectifier | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
172 |  |  |  | 2 x 20 kVA UPS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
173 |  |  |  | PCC & MCC Panels | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
174 |  |  |  | DG Set 1010 KVA with accessories | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
175 |  |  |  | Fabrication and supply MS Insert Plates - 221 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
176 |  |  |  | Cable Trays | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
177 |  |  |  | Supply of Bus duct for DG set | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
178 |  |  |  | UPS for ABB (2*5 KVA) rectifier system | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
179 |  |  |  | Supply of MCCB 4 pole, 250 amps for CPU transformer isolation at new RT room | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
180 |  |  |  | Supply of bus duct for auxiliary transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
181 |  |  |  | FRP Local Control Station | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
182 |  |  |  | 1.3 Instrument | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
183 |  |  |  | Pressure, Level, Temperature and Ultrasonic Transmitters (49 nos.) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
184 |  |  |  | MAGNETIC FLOW METERS & VORTEX FLOW METER | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
185 |  |  |  | PH/ORP TRANSMITTERS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
186 |  |  |  | Mass Flow Meters - 1 No and Density Meters - 2 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
187 |  |  |  | Control Valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
188 |  |  |  | DCS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
189 |  |  |  | Control Valves for outside cell house | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
190 |  |  |  | On/OFF Control Valves | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
191 |  |  |  | Additional IO Module, Termination Board and Cable | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
192 |  |  |  | Magnetic Flow Meter FT1401 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
193 |  |  |  | Pressure switches Model No: WP/A-2 - 2 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
194 |  |  |  | Electrolyzer Cell Voltage Acquisition system | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
195 |  |  |  | Magnetic Level Indicator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
196 |  |  |  | Temperature Elements - 16 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
197 |  |  |  | Pressure Gauges - 55 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
198 |  |  |  | Temperature Gauges - 37 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
199 |  |  |  | Hart Communicator Emerson Make | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
200 |  |  |  | Unlined Butterfly Valve 8" x 150 mm | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
201 |  |  |  | Rotameter Transmitters = 2 Nos, Metal Tuber Transmitters - 21 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
202 |  |  |  | PFA lined Ball Valves - 2 Nos and Unlined Ball type control Valves - 1 No | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
203 |  |  |  | Solenoid Valve | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
204 |  |  |  | On/OFF Control Valves for IEC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
205 |  |  |  | Inst and Control Cable | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
206 |  |  |  | Cable Trays & Cabling | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
207 |  |  |  | Chilled water Magnetic flow meter | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
208 |  |  |  | U tube manometer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
209 |  |  |  | RTD | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
210 |  |  |  | Thermowell | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
211 |  |  |  | Temperature transmitter 2 Nos. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
212 |  |  |  | Pressure Switch | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
213 |  |  |  | PSV 9001, PSV 2014 and PSV 2015 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
214 |  |  |  | PCV 2014 and PCV 2015 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
215 |  |  |  | 1.4 Tender Documents / BOQ | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
216 |  |  |  | Mech | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
217 |  |  |  | Elec | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
218 |  |  |  | Inst | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
219 |  |  |  | BOQ for calrifier,Cell House & RT | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
220 |  |  |  | BOQ for Civil - Anolyte Pit | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
221 |  |  |  | BOQ for Civil - OHT Building extension | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
222 |  |  |  | BOQ for Civil - Cl2/H2 building section | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
223 |  |  |  | BOQ-Hypo OHT Structure | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
224 |  |  |  | BOQ for DCS room Modification | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
225 |  |  |  | 1.5 Contractor Finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
226 |  |  |  | Civil (Clarifier, Cell house & RT) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
227 |  |  |  | Mech - Equipment Erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
228 |  |  |  | Mech- Piping Erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
229 |  |  |  | CPP | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
230 |  |  |  | Modern | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
231 |  |  |  | Prateeesh | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
232 |  |  |  | Elec - Erection contractor (M/s Sudhan Powertech) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
233 |  |  |  | Elec- Copper Bus Bar | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
234 |  |  |  | Inst - Erection Contractor (M/s Chalcedony) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
235 |  |  |  | Civil- Anolyte Pit | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
236 |  |  |  | Civil - Cl2/H2 building section | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
237 |  |  |  | Civil - Chiller, N2 Unit | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
238 |  |  |  | Civil - Auxiliary transformer etc | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
239 |  |  |  | Civil-CBT, UF & Saturator | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
240 |  |  |  | Civil Contractor Finalization For IEC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
241 |  |  |  | Civil DCS Room Modification | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
242 |  |  |  | civil Vendor Finalization for MCC 1 and MCC 6 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
243 |  |  |  | Civil- Related to Electrical Work | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
244 |  |  |  | Civil- DG shed extension | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
245 |  |  |  | Civil- Pump Foundation work & Miscellaneous work | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
246 |  |  |  | 1.6 Structural Fabrication contractor finalization / completion | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
247 |  |  |  | OHT Structural Modification-( All materials received at site). | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
248 |  |  |  | Cl2 / H2 washing section Strcture | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
249 |  |  |  | Cell House Platform & Pipe Rack Inside Cell house | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
250 |  |  |  | Filter Press Structure | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
251 |  |  |  | Pipe Rack Strengthning - Sept-27 work order issued, work completion 8 weeks | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
252 |  |  |  | Pipe rack extension at chiller area contractor finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
253 |  |  |  | Pipe rack strenghning of Cl2/H2 area | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
254 |  |  |  | Pipe rack strenghning at cell house area | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
255 |  |  |  | Pipe rack extension at chiller area | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
256 |  |  |  | Hypo OHT fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
257 |  |  |  | 10-Electricals | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
258 |  |  |  | 1.1 Electrical | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
259 |  |  |  | New Rectifier (ABB) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
260 |  |  |  | New Transformer(ABB) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
261 |  |  |  | HT PANEL 22 KV 1600 AMPS, 31.5 KA | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
262 |  |  |  | Siemens Make Motors - 18 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
263 |  |  |  | Siemens Make Motors - 5 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
264 |  |  |  | HT Cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
265 |  |  |  | LT cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
266 |  |  |  | Copper Bus Bars and Flexibles and accessories-Cell House | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
267 |  |  |  | Copper Bus Bars and Flexibles and accessories- Rectifier | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
268 | UPS 2 * 20 kVA | 869101 | 331 | 2 x 20 kVA UPS | '[Resource Assignment-WIP.xlsx]Resource'!$B331 | '[Resource Assignment-WIP.xlsx]Resource'!$G331 | UPS 2 * 20 kVA | 869101
269 |  |  |  | PCC & MCC Panels | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
270 |  |  |  | DG Set 1010 KVA with accessories | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
271 |  |  |  | Fabrication and supply MS Insert Plates - 221 Nos | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
272 |  |  |  | Cable Trays | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
273 |  |  |  | Supply of Bus duct for DG set | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
274 | UPS for ABB rectifier system 2 x 5 kVA | 299439 | 333 | UPS for ABB (2*5 KVA) rectifier system | '[Resource Assignment-WIP.xlsx]Resource'!$B333 | '[Resource Assignment-WIP.xlsx]Resource'!$G333 | UPS for ABB rectifier system 2 x 5 kVA | 299439
275 | Supply of MCCB 4 pole 250 amps for CPU transformer isolation at new RT room | 34760 | 334 | Supply of MCCB 4 pole, 250 amps for CPU transformer isolation at new RT room | '[Resource Assignment-WIP.xlsx]Resource'!$B334 | '[Resource Assignment-WIP.xlsx]Resource'!$G334 | Supply of MCCB 4 pole 250 amps for CPU transformer isolation at new RT room | 34760
276 |  |  |  | Supply of bus duct for auxiliary transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
277 | Supply of Local Control push button station | 138034 | 113 | FRP Local Control Station | '[Resource Assignment-WIP.xlsx]Resource'!$B113 | '[Resource Assignment-WIP.xlsx]Resource'!$G113 | Supply of Local Control push button station | 138034
278 |  |  |  | 2 Tender Documents / BOQ | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
279 |  |  |  | Elec | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
280 |  |  |  | BOQ receipt for cable rack | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
281 |  |  |  | 3 Contractor Finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
282 |  |  |  | HT Panel Erection Contractor Finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
283 | Erection of Electrical Equipments | 3703585 | 114 | Elec - Erection contractor (M/s Sudhan Powertech) | '[Resource Assignment-WIP.xlsx]Resource'!$B114 | '[Resource Assignment-WIP.xlsx]Resource'!$G114 | Erection of Electrical Equipments | 3703585
284 |  |  |  | Elec- Copper Bus Bar | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
285 |  |  |  | Rectifier erection contractor finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
286 |  |  |  | Transformer erection contractor finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
287 |  |  |  | Cable rack erection contractor finalization | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
288 |  |  |  | 4 Erection of Electrical Equipments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
289 |  |  |  | Rectifier | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
290 | Rectifier 23 kA 690 Volts | 628722.5 | 68 | New Rectifier civil | '[Resource Assignment-WIP.xlsx]Resource'!$B68 | '[Resource Assignment-WIP.xlsx]Resource'!$G68 | Rectifier 23 kA 690 Volts | 628722.5
291 |  |  |  | New Rectifier positioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
292 |  |  |  | Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
293 |  |  |  | New Transformer Civil | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
294 |  |  |  | New Transformer positioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
295 |  |  |  | New 22KV HT Panel Erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
296 |  |  |  | Contractor finalization for erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
297 | Erection of HT Panel | 2857.1429 | 117 | Procurement of materials (Channels & Angle) | '[Resource Assignment-WIP.xlsx]Resource'!$B117 | '[Resource Assignment-WIP.xlsx]Resource'!$G117 | Erection of HT Panel | 2857.1429
298 | Erection of HT Panel | 2857.1429 | 118 | Fabrication of base frame | '[Resource Assignment-WIP.xlsx]Resource'!$B118 | '[Resource Assignment-WIP.xlsx]Resource'!$G118 | Erection of HT Panel | 2857.1429
299 | Erection of HT Panel | 2857.1429 | 119 | Erection of base frame and grouting | '[Resource Assignment-WIP.xlsx]Resource'!$B119 | '[Resource Assignment-WIP.xlsx]Resource'!$G119 | Erection of HT Panel | 2857.1429
300 | Erection of HT Panel, HT Panel for 22 kV Substation | 2857.1429 | 120 | Receipt of HT panel | '[Resource Assignment-WIP.xlsx]Resource'!$B120 | '[Resource Assignment-WIP.xlsx]Resource'!$G120 | Erection of HT Panel | 2857.1429
301 |  | 3578652 | 322 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B322 | '[Resource Assignment-WIP.xlsx]Resource'!$G322 | HT Panel for 22 kV Substation | 3578652
302 | Erection of HT Panel | 2857.1429 | 121 | Unloading, leading and positioning of panels in HT room | '[Resource Assignment-WIP.xlsx]Resource'!$B121 | '[Resource Assignment-WIP.xlsx]Resource'!$G121 | Erection of HT Panel | 2857.1429
303 | Erection of HT Panel | 2857.1429 | 122 | Interconnection between panels, Tightness checking | '[Resource Assignment-WIP.xlsx]Resource'!$B122 | '[Resource Assignment-WIP.xlsx]Resource'!$G122 | Erection of HT Panel | 2857.1429
304 | Erection of HT Panel | 2857.1429 | 123 | Formation of earth pits and HT panel earthing | '[Resource Assignment-WIP.xlsx]Resource'!$B123 | '[Resource Assignment-WIP.xlsx]Resource'!$G123 | Erection of HT Panel | 2857.1429
305 |  |  |  | Fixing of supports for Cable Trays | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
306 |  |  |  | Erection of cable trays for Top entry | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
307 |  |  |  | Dispatch signoff for HT Cable, Approval | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
308 |  |  |  | Receipt of HT cable | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
309 |  |  |  | Laying of HT cables for incomer - 3 Runs | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
310 |  |  |  | Laying of HT cable O/G 2 - New RT | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
311 |  |  |  | Laying of HT cables for O/G 1- Old HT I/C, | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
312 |  |  |  | Laying of HT cables for OG 3 - New Aux Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
313 |  |  |  | Termination of HT cables in I/C | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
314 |  |  |  | Termination of HT cables of O/G 2 - New RT | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
315 |  |  |  | Termination of HT cables of O/G 1 - Old HT I/C | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
316 |  |  |  | Termination of HT cables of O/G 3 - New Aux. Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
317 |  |  |  | Submission of Drawing, work completion report to CEA for Inspection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
318 |  |  |  | CEA Inspection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
319 |  |  |  | Completion of compliance and submission | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
320 |  |  |  | Obtaining Safety certifcate and approval for operation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
321 |  |  |  | PED Approval | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
322 |  |  |  | Precommissioning Tests by Supplier | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
323 |  |  |  | Termination of HT cables in 22KV yard I/C and Energizing the HT panel and put into service | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
324 |  |  |  | Erection of Rectifier Transformer, Rectifier unit and accessories | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
325 |  |  |  | Service indent for Rectifier erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
326 |  |  |  | Approval & Contractor finalization for erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
327 | Rectifier 23 kA 690 Volts | 21900901 | 319 | Receipt of Rectifier after clearance | '[Resource Assignment-WIP.xlsx]Resource'!$B319 | '[Resource Assignment-WIP.xlsx]Resource'!$G319 | Rectifier 23 kA 690 Volts | 21900901
328 | Unloading of Rectifier | 22500 | 115 | Unloading, leading and positioning of Rectifier cubicle in New RT room | '[Resource Assignment-WIP.xlsx]Resource'!$B115 | '[Resource Assignment-WIP.xlsx]Resource'!$G115 | Unloading of Rectifier | 22500
329 | Unloading of Rectifier | 22500 | 116 | Fabrication of J bolt, fixing and grouting in rectifier bed. | '[Resource Assignment-WIP.xlsx]Resource'!$B116 | '[Resource Assignment-WIP.xlsx]Resource'!$G116 | Unloading of Rectifier | 22500
330 |  |  |  | Service indent for Transformer erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
331 |  |  |  | Approval & Contractor finalization for erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
332 | Rectifier Transformer 23kA 690 Volts | 16870788 | 320 | Receipt of Transformer after clearance | '[Resource Assignment-WIP.xlsx]Resource'!$B320 | '[Resource Assignment-WIP.xlsx]Resource'!$G320 | Rectifier Transformer 23kA 690 Volts | 16870788
333 | Erection of transformer | 83333.3333 | 124 | Fixing of Rails in the Transformer bed | '[Resource Assignment-WIP.xlsx]Resource'!$B124 | '[Resource Assignment-WIP.xlsx]Resource'!$G124 | Erection of transformer | 83333.3333
334 | Erection of transformer | 83333.3333 | 125 | Unloading, leading and positioning of Rectifier transformer in New RT room | '[Resource Assignment-WIP.xlsx]Resource'!$B125 | '[Resource Assignment-WIP.xlsx]Resource'!$G125 | Erection of transformer | 83333.3333
335 | Erection of transformer | 83333.3333 | 126 | Erection of Oil heat exchanger, piping connection, Oil conservator, HT panel Adaptor box | '[Resource Assignment-WIP.xlsx]Resource'!$B126 | '[Resource Assignment-WIP.xlsx]Resource'!$G126 | Erection of transformer | 83333.3333
336 |  |  |  | Oil Filtration for Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
337 |  |  |  | Positioning Rectifier in Rectifier bed and alignment with Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
338 |  |  |  | Fixing of copper flexible connecting between Rectifier cubicle and Transformer. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
339 |  |  |  | Drain line pipe connecting to Soak pit | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
340 |  |  |  | Construction of waste oil collection pit and interconnecting with pipe line. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
341 |  |  |  | New Trench connectivity with the existing trench | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
342 |  |  |  | Fabrication of base frame for erection of Rectifier panel, Polarization panel, AC DC Panel, UPS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
343 |  |  |  | Fabrication and Connecting Raw water, DM water Inlet, out let pipe line with Rectifier and Transformer. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
344 |  |  |  | Aluminium and Glass partition construction and provision of Air conditioning. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
345 |  |  |  | Fabrication of Cable tray supports, laying of cable trays in the new trenches provided in RT room | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
346 |  |  |  | Laying of Power, Control, communication cable between RCP, PCP, RT, Rectifier cubicle, Polarization Transformer, AC DC panel, Cooling cubicle | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
347 |  |  |  | Laying of GI earth flats and connecting with Transformer, RT cubicle, Control panel & AC DC panels. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
348 |  |  |  | Glanding, Termination and loop check of all power, control and communication cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
349 |  |  |  | Temporary arrangement for charging ACDB | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
350 |  |  |  | Laying of Incomer Power cable from MCC 3 to AC DC Panel and Termination | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
351 |  |  |  | Testing of Transformer , Rectifier cubicle | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
352 |  |  |  | Energising the panels, Checking of controls and interlocks | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
353 |  |  |  | Copper bus bar, Flexibles for Inside Rectifier room & Cell house | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
354 |  |  |  | Finalization Erection contractor | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
355 | Copper Busbar & Accs at cell house side | 5299195 | 324 | Receipt of material inside cell house | '[Resource Assignment-WIP.xlsx]Resource'!$B324 | '[Resource Assignment-WIP.xlsx]Resource'!$G324 | Copper Busbar & Accs at cell house side | 5299195
356 | Copper Busbar & Accs at rectifier side | 3415018 | 332 | Receipt of material inside rectifier room | '[Resource Assignment-WIP.xlsx]Resource'!$B332 | '[Resource Assignment-WIP.xlsx]Resource'!$G332 | Copper Busbar & Accs at rectifier side | 3415018
357 |  |  |  | Civil - opening for interconnection between cell house and rectifier room | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
358 |  |  |  | Erection of Hallmar CT | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
359 |  |  |  | Providing Supports for DC isolators and erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
360 |  |  |  | Supports erection for Copper bus bar both on rectifier room and cell house | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
361 |  |  |  | Erection of Copper bus bar and flexibles inside Cell house | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
362 |  |  |  | Erection of Copper bus bar and flexibles inside Rectifier room | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
363 |  |  |  | Approval & Contractor finalization for electrical equipments erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
364 |  |  |  | Receipt of LT cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
365 |  |  |  | Receipt of Cable trays | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
366 |  |  |  | Fabrication of cable tray supports in the pipe rack | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
367 |  |  |  | Laying of cable trays and connecting with supports | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
368 |  |  |  | Laying LT cable | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
369 |  |  |  | From LT PCC to Aux PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
370 |  |  |  | Cable trench formation from LT PCC existing trench | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
371 |  |  |  | Finalising contractor for Cable rack fabrication and erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
372 | Electrical Miscellanous Civil Jobs | 321116.6667 | 168 | Civil Foundation for cable rack | '[Resource Assignment-WIP.xlsx]Resource'!$B168 | '[Resource Assignment-WIP.xlsx]Resource'!$G168 | Electrical Miscellanous Civil Jobs | 321116.6667
373 |  |  |  | Cable rack Fabrication and erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
374 |  |  |  | Fabrication of tray supports | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
375 |  |  |  | erection of Cable trays | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
376 |  |  |  | From LT PCC to DG Aux PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
377 |  |  |  | From LT PCC to MCC 1 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
378 |  |  |  | From LT PCC to MCC 4A | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
379 |  |  |  | From LT PCC to MCC 6 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
380 |  |  |  | From DG Aux PCC to MCC 3A | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
381 |  |  |  | From DG Aux PCC to existing 380KVA PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
382 |  |  |  | Auxilliary Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
383 | Civil work in 4000 KVA Auxilliary Transformer, Electrical Miscellanous Civil Jobs, Eletrical civil foundation | 150097.5 | 135 | Civil foundation for Aux Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B135 | '[Resource Assignment-WIP.xlsx]Resource'!$G135 | Civil work in 4000 KVA Auxilliary Transformer | 150097.5
384 |  | 321116.6667 | 169 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B169 | '[Resource Assignment-WIP.xlsx]Resource'!$G169 | Electrical Miscellanous Civil Jobs | 321116.6667
385 |  | 273975 | 187 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B187 | '[Resource Assignment-WIP.xlsx]Resource'!$G187 | Eletrical civil foundation | 273975
386 | Civil work in 4000 KVA Auxilliary Transformer, Eletrical civil foundation, Electrical Miscellanous Civil Jobs | 150097.5 | 136 | Curing of Foundation | '[Resource Assignment-WIP.xlsx]Resource'!$B136 | '[Resource Assignment-WIP.xlsx]Resource'!$G136 | Civil work in 4000 KVA Auxilliary Transformer | 150097.5
387 |  | 321116.6667 | 170 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B170 | '[Resource Assignment-WIP.xlsx]Resource'!$G170 | Electrical Miscellanous Civil Jobs | 321116.6667
388 |  | 273975 | 188 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B188 | '[Resource Assignment-WIP.xlsx]Resource'!$G188 | Eletrical civil foundation | 273975
389 | Electrical Miscellanous Civil Jobs | 321116.6667 | 171 | Neutral & Body earth pits formation for Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B171 | '[Resource Assignment-WIP.xlsx]Resource'!$G171 | Electrical Miscellanous Civil Jobs | 321116.6667
390 |  |  |  | Installation of Aux. Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
391 |  |  |  | Laying and connecting earth flats from earth pits to Transformer | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
392 |  |  |  | Bus duct for LT PCC 2 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
393 |  |  |  | Measurement with Transformer & LT PCC drg. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
394 |  |  |  | Floating enquiry, Receiving offers, Technical sign off, negotiation, Finalization of vendor, Approval and ordering | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
395 |  |  |  | Receipt of bus duct at site after clearance | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
396 |  |  |  | Erection of bus duct, supports, connecting with PCC 2 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
397 |  |  |  | Erection of LT PCC, Aux PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
398 | Main PCC - HT room | 3900731 | 703 | Recipt of LT PCC Panel | '[Resource Assignment-WIP.xlsx]Resource'!$B703 | '[Resource Assignment-WIP.xlsx]Resource'!$G703 | Main PCC - HT room | 3900731
399 | Aux PCC - HT room | 698348 | 704 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B704 | '[Resource Assignment-WIP.xlsx]Resource'!$G704 | Aux PCC - HT room | 698348
400 |  |  |  | Fabrication of Base frame for LT PCC, Aux PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
401 |  |  |  | Fixing of frames and erection of LT PCC - Partial | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
402 |  |  |  | Erection of LT PCC - Partial | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
403 |  |  |  | Removal of power and control cables from the outgoing feeders in existing old PCC and tagging. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
404 |  |  |  | Removal of old panels in existing PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
405 |  |  |  | Fixing of frames and erection of LT PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
406 |  |  |  | Interconnecting old and new PCC bus bars | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
407 |  |  |  | Panel earthing connections | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
408 |  |  |  | Power and control cable termination to new PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
409 |  |  |  | Power and control check, interlock checking in new PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
410 |  |  |  | Shifting of old battery charger panel, spare VCB, to other location and lining up. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
411 |  |  |  | Fixing of frames and erection of LT Aux PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
412 |  |  |  | Panel earthing connections | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
413 |  |  |  | Power and control cable termination to new Aux PCC | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
414 |  |  |  | Erection of MCC 1 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
415 |  |  |  | Shifting of lab from Brine plant to other location | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
416 | Electrical Miscellanous Civil Jobs | 321116.6667 | 172 | Civil work - Removal of wall, excavation for cable trenches, Fixing of insert plate, provision for panel erection | '[Resource Assignment-WIP.xlsx]Resource'!$B172 | '[Resource Assignment-WIP.xlsx]Resource'!$G172 | Electrical Miscellanous Civil Jobs | 321116.6667
417 | MCC -1 - Brine plant | 582809 | 706 | Dispatch clearance and receipt of MCC 1 | '[Resource Assignment-WIP.xlsx]Resource'!$B706 | '[Resource Assignment-WIP.xlsx]Resource'!$G706 | MCC -1 - Brine plant | 582809
418 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
419 |  |  |  | Fixing of base frame and erection of MCC 1 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
420 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
421 |  |  |  | Removal of all power and control cables from existing MCC 1 and tagging | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
422 |  |  |  | Rerouting of Power and control cables and termination in the new mcc on respective feeders | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
423 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
424 |  |  |  | Erection of MCC 3A | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
425 | Electrical Miscellanous Civil Jobs | 321116.6667 | 173 | Civil - Extension of DG room towards toilet | '[Resource Assignment-WIP.xlsx]Resource'!$B173 | '[Resource Assignment-WIP.xlsx]Resource'!$G173 | Electrical Miscellanous Civil Jobs | 321116.6667
426 | Electrical Miscellanous Civil Jobs | 321116.6667 | 174 | Excavation for cable trenches, Fixing of insert plate, provision for panel erection | '[Resource Assignment-WIP.xlsx]Resource'!$B174 | '[Resource Assignment-WIP.xlsx]Resource'!$G174 | Electrical Miscellanous Civil Jobs | 321116.6667
427 | MCC - 3A - DG extension room | 593034 | 708 | Dispatch clearance and receipt of MCC 3A | '[Resource Assignment-WIP.xlsx]Resource'!$B708 | '[Resource Assignment-WIP.xlsx]Resource'!$G708 | MCC - 3A - DG extension room | 593034
428 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
429 |  |  |  | Fixing of base frame and erection of MCC 3A | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
430 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
431 |  |  |  | Laying of power and control cables from MCC3A to respective motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
432 |  |  |  | Power & control cables and termination in the new mcc on respective feeders and motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
433 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
434 |  |  |  | Erection of MCC 3 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
435 | MCC- 3 - DG room | 725955 | 707 | Dispatch clearance and receipt of MCC 3 | '[Resource Assignment-WIP.xlsx]Resource'!$B707 | '[Resource Assignment-WIP.xlsx]Resource'!$G707 | MCC- 3 - DG room | 725955
436 |  |  |  | Removal of all power and control cables from existing MCC 3 and tagging | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
437 |  |  |  | Removal of old MCC3 from its position | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
438 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
439 |  |  |  | Fixing of base frame and erection of MCC 3 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
440 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
441 |  |  |  | Power & control cables and termination in the new mcc on respective feeders and motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
442 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
443 |  |  |  | Erection of MCC 4 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
444 |  |  |  | Removal of all power and control cables from existing MCC 4 partially and tagging | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
445 | MCC - 4 - Boiler House | 531685 | 709 | Removal of old MCC4 partial from its position | '[Resource Assignment-WIP.xlsx]Resource'!$B709 | '[Resource Assignment-WIP.xlsx]Resource'!$G709 | MCC - 4 - Boiler House | 531685
446 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
447 |  |  |  | Fixing of base frame and erection of MCC 4 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
448 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
449 |  |  |  | Power & control cables and termination in the new mcc on respective feeders and motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
450 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
451 |  |  |  | Erection of MCC 6 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
452 | Electrical Miscellanous Civil Jobs | 321116.6667 | 175 | Civil - Removal of wall, cupboards, Extension of MCC area by 2.5mtrs in Mechanical shed by Frame work, chequered plate and provision for cabling | '[Resource Assignment-WIP.xlsx]Resource'!$B175 | '[Resource Assignment-WIP.xlsx]Resource'!$G175 | Electrical Miscellanous Civil Jobs | 321116.6667
453 | Electrical Miscellanous Civil Jobs | 321116.6667 | 176 | Civil work readiness | '[Resource Assignment-WIP.xlsx]Resource'!$B176 | '[Resource Assignment-WIP.xlsx]Resource'!$G176 | Electrical Miscellanous Civil Jobs | 321116.6667
454 | MCC - 6 - Mechanical Work shop | 961124 | 710 | Dispatch clearance and receipt of MCC 6 | '[Resource Assignment-WIP.xlsx]Resource'!$B710 | '[Resource Assignment-WIP.xlsx]Resource'!$G710 | MCC - 6 - Mechanical Work shop | 961124
455 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
456 |  |  |  | Fixing of base frame and erection of MCC 6 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
457 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
458 |  |  |  | Laying of power and control cables from MCC6 to respective motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
459 |  |  |  | Power & control cables termination in the new mcc on respective feeders and motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
460 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
461 |  |  |  | Erection of MCC 10 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
462 | MCC - 10 - Boiler House | 449888 | 711 | Dispatch clearance and receipt of MCC 10 | '[Resource Assignment-WIP.xlsx]Resource'!$B711 | '[Resource Assignment-WIP.xlsx]Resource'!$G711 | MCC - 10 - Boiler House | 449888
463 |  |  |  | Removal of all power and control cables from existing MCC 10 and tagging | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
464 |  |  |  | Removal of old MCC 10 from its position | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
465 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
466 |  |  |  | Fixing of base frame and erection of MCC 10 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
467 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
468 |  |  |  | Power & control cables and termination in the new mcc on respective feeders and motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
469 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
470 |  |  |  | Erection of MCC 12 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
471 | MCC-12 - Brine Plant | 449888 | 712 | Dispatch clearance and receipt of MCC 12 | '[Resource Assignment-WIP.xlsx]Resource'!$B712 | '[Resource Assignment-WIP.xlsx]Resource'!$G712 | MCC-12 - Brine Plant | 449888
472 |  |  |  | Base frame fabrication | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
473 |  |  |  | Fixing of base frame and erection of MCC 12 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
474 |  |  |  | Busbar tightness checking, control check | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
475 |  |  |  | Laying of power and control cables from MCC 12 to respective motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
476 |  |  |  | Power & control cables and termination in the new mcc on respective feeders and motors | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
477 |  |  |  | Individual motors trial for direction check, equipment confirmation. | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
478 |  |  |  | 2*20 KVA UPS commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
479 |  |  |  | Existing Hypo UPS to be Shifted | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
480 |  |  |  | Incoming Power Cable Laying And Termination | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
481 |  |  |  | Power up and Commisioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
482 |  |  |  | 09-Instrumentation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
483 |  |  |  | DCS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
484 |  |  |  | DCS Room Civil Work Completion | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
485 | DCS Supply & erection, DCS Panel Room Modification, FalseFloor, Erection of False Floor | 1039138.6667 | 130 | Positioning of DCS Panels in room | '[Resource Assignment-WIP.xlsx]Resource'!$B130 | '[Resource Assignment-WIP.xlsx]Resource'!$G130 | DCS Supply & erection | 1039138.6667
486 |  | 551855 | 70 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B70 | '[Resource Assignment-WIP.xlsx]Resource'!$G70 | DCS Panel Room Modification | 551855
487 |  | 142987 | 71 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B71 | '[Resource Assignment-WIP.xlsx]Resource'!$G71 | FalseFloor | 142987
488 |  | 0 | 72 |  | '[Resource Assignment-WIP.xlsx]Resource'!$B72 | '[Resource Assignment-WIP.xlsx]Resource'!$G72 | Erection of False Floor | 0
489 | DCS Supply & erection | 1039138.6667 | 127 | Moving DCS consoles to CR & removing existing consoles | '[Resource Assignment-WIP.xlsx]Resource'!$B127 | '[Resource Assignment-WIP.xlsx]Resource'!$G127 | DCS Supply & erection | 1039138.6667
490 | DCS Supply & erection | 1039138.6667 | 131 | Power up of Existing DCS Consoles | '[Resource Assignment-WIP.xlsx]Resource'!$B131 | '[Resource Assignment-WIP.xlsx]Resource'!$G131 | DCS Supply & erection | 1039138.6667
491 |  |  |  | Power up of new DCS Consoles | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
492 | DCS Supply & erection | 1039138.6667 | 132 | Power up of new DCS panels | '[Resource Assignment-WIP.xlsx]Resource'!$B132 | '[Resource Assignment-WIP.xlsx]Resource'!$G132 | DCS Supply & erection | 1039138.6667
493 | DCS Supply & erection | 1039138.6667 | 129 | Commissioning of New DCS | '[Resource Assignment-WIP.xlsx]Resource'!$B129 | '[Resource Assignment-WIP.xlsx]Resource'!$G129 | DCS Supply & erection | 1039138.6667
494 |  |  |  | 2.Instruments Cabling & Termination- Main cable | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
495 |  |  |  | Mobillisation of site by Erection Contractor | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
496 |  |  |  | Fabrication of tray support for main cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
497 |  |  |  | Erection of Main cable trays | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
498 |  |  |  | Fabrication and Erection of JB support | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
499 |  |  |  | Receipt of I & C cables at site | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
500 |  |  |  | Laying & dressing of Main cables from JB to CR | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
501 |  |  |  | Cable Glanding & Termination of Main cables | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
502 |  |  |  | Loop check from JB end to DCS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
503 |  |  |  | 3. Field Inst erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
504 |  |  |  | Fabrication of stancheon for remote mounted instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
505 |  |  |  | Erection of stancheons at required place | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
506 |  |  |  | Branch cable tray fabrication, erection | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
507 |  |  |  | Branch cable laying & Termination at JB end | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
508 |  |  |  | Receipt of all control valves, flowmeters, RTD, TG & PG | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
509 |  |  |  | Installation of all field Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
510 |  |  |  | Glanding &Termination branch cables of all field Instruments at Inst end | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
511 |  |  |  | Loop Check & Calibration | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
512 |  |  |  | Loop check of all instruments from field Inst end | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
513 |  |  |  | Calibration of all field Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
514 |  |  |  | Calibration /Stroke check of all Control valves & On/Off valves from DCS | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
515 |  |  |  | Pre-commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
516 |  |  |  | Tripchecks, Graphics modification , IEC sequence check etc | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
517 |  |  |  | Commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
518 |  |  |  | Primary-Brine | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
519 |  |  |  | 6. Pre-commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
520 |  |  |  | 5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
521 |  |  |  | Cleaning and Flushing ( Tanks, equipment and Pipe lines ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
522 |  |  |  | Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
523 |  |  |  | Trial run of equipment | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
524 |  |  |  | Brine filling and circulation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
525 |  |  |  | 7. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
526 |  |  |  | Secondary-Briner | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
527 |  |  |  | 6. Pre-commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
528 |  |  |  | 5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
529 |  |  |  | Cleaning and Flushing ( Tanks, equipment and Pipe lines ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
530 |  |  |  | Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
531 |  |  |  | Trial run of equipment | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
532 |  |  |  | Brine filling and circulation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
533 |  |  |  | 7. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
534 |  |  |  | Cell-House | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
535 |  |  |  | 7. Pre-commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
536 |  |  |  | 5. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
537 |  |  |  | a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
538 |  |  |  | b) Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
539 |  |  |  | c) Trial run of Equipments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
540 |  |  |  | d) Brine filling and circulation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
541 |  |  |  | 8. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
542 |  |  |  | Cl2-H2 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
543 |  |  |  | 4. Pre-commissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
544 |  |  |  | 3.4 Erection of structurals, pipes, fittings, Electrical Equipments and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
545 |  |  |  | a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
546 |  |  |  | b) Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
547 |  |  |  | c) Trial run of Equipments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
548 |  |  |  | d) Brine filling and circulation | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
549 |  |  |  | 5. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
550 |  |  |  | Dry Cl2 | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
551 |  |  |  | 5. Precommissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
552 |  |  |  | 4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
553 |  |  |  | b) Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
554 |  |  |  | c) Trial run of Equipments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
555 |  |  |  | 6. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
556 |  |  |  | Hypo | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
557 |  |  |  | 5. Precommissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
558 |  |  |  | 4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
559 |  |  |  | a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
560 |  |  |  | b) Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
561 |  |  |  | c) Trial run of Equipments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
562 |  |  |  | 6. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
563 |  |  |  | Utilities | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
564 |  |  |  | 5. Precommissioning | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
565 |  |  |  | 4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
566 |  |  |  | a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines ) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
567 |  |  |  | b) Hook up with Existing set up (Process and utilities) | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
568 |  |  |  | c) Trial run of Equipments | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
569 |  |  |  | 6. Commissioning of plant | '[Resource Assignment-WIP.xlsx]Resource'!$B | '[Resource Assignment-WIP.xlsx]Resource'!$G
573 |  |  |  | 02-Sec-Brine-Plant
574 |  |  |  | 4. CIVIL and Erection
575 |  |  |  | 4.1 Polished Brine storage tank and pumps
576 |  |  |  | a) Removal of Old Polished Brine tank
577 |  |  |  | b) Excavation
578 |  |  |  | c) Foundation
579 |  |  |  | d) Positioning of Brine Storage tank
580 |  |  |  | e) Filling and Leak Testing
581 |  |  |  | Removal of Old Polished Brine pump-A
582 |  |  |  | Civil bed modification
583 |  |  |  | d) Positioning of new pump-A
584 |  |  |  | Piping
585 |  |  |  | Commissioning
586 |  |  |  | Removal of Old Polished Brine pump-B
587 |  |  |  | Civil bed modification
588 |  |  |  | d) Positioning of new pump - B
589 |  |  |  | Piping
590 |  |  |  | Commissioning
591 |  |  |  | 4.3Pure Brine Tank and Pumps
592 |  |  |  | a)Removal of old Pure brine tank
593 |  |  |  | b)Old Bed Dismantling
594 |  |  |  | c)Excavation
595 |  |  |  | d)Bed Construction
596 |  |  |  | Curing
597 |  |  |  | e) Receipt , Positioning & commissioning
598 |  |  |  | Removal of Old Pure Brine pump-A
599 |  |  |  | Civil bed modification
600 |  |  |  | d) Positioning of new pump-A
601 |  |  |  | Piping
602 |  |  |  | Commissioning
603 |  |  |  | Removal of Old Pure Brine pump-B
604 |  |  |  | Civil bed modification
605 |  |  |  | d) Positioning of new pump - B
606 |  |  |  | Piping
607 |  |  |  | Commissioning
608 |  |  |  | 4.2 IEC
609 |  |  |  | a)Dismantling
610 |  |  |  | b)Excavation
611 |  |  |  | c)Footings and column construction
612 |  |  |  | d)Positioning of Ion exchange column
613 |  |  |  | f) Ion exchange column strainer erection
614 |  |  |  | g)filling of Ion exchange column with resin
615 |  |  |  | i) Leak testing of resins
616 |  |  |  | e)Internal Piping
617 |  |  |  | Control valve receipts & positioning
618 |  |  |  | Loop & regeneration Checking
619 |  |  |  | Commissioning
620 |  |  |  | 5. Erection of structurals, pipes, fittings, Electrical equipment and Instruments
621 |  |  |  | Erection contract Finalization
622 |  |  |  | Mobilization of erection material
623 |  |  |  | Pipe rack and supports
624 |  |  |  | Process Piping
625 |  |  |  | Utility Piping
630 |  |  |  | 03-Cell-House
631 |  |  |  | 4. CIVIL and Erection
632 |  |  |  | Electrolyzer area
633 |  |  |  | Dismantling
634 |  |  |  | Excavation
635 |  |  |  | PCC
636 |  |  |  | Column and footing
637 |  |  |  | Soil consolidation
638 |  |  |  | PCC and RCC of flooring
639 |  |  |  | Plastering of flooring
640 |  |  |  | Mobilization of erection material
641 |  |  |  | Pipe rack erection at inside cell house
642 |  |  |  | Erection of cell platform
643 |  |  |  | Bus bar column level checking
644 |  |  |  | Insulator erection
645 |  |  |  | Erection of busbar at cell house side
646 |  |  |  | Erection of busbar at rectifier side
647 |  |  |  | Electrolyzer column level checking
648 |  |  |  | Insulator erection for busbar
649 |  |  |  | Cell Workshop Material
650 |  |  |  | Positioning of cell frame
651 |  |  |  | Alignment of cell frame
652 |  |  |  | Electrolyzer piping
653 |  |  |  | Shifting of elements from salt godowon to cell house
654 |  |  |  | Element inspection
655 |  |  |  | Gasket cleaning & attaching
656 |  |  |  | Outlet Manifold preparation
657 |  |  |  | Inlet Manifold preparation
658 |  |  |  | Tie rod & spring washer preparation
659 |  |  |  | Pre-assembly training
660 |  |  |  | Pre-disassmbly training
661 |  |  |  | Clean up cell room
662 |  |  |  | Membrane soaking
663 |  |  |  | Gasket greasing
664 |  |  |  | Electr-R-201 assembly & pin hole test
665 |  |  |  | Electr R-202 assembly & pin hole test
666 |  |  |  | Cable connection for voltage monitoring system
667 |  |  |  | Platform removal
668 |  |  |  | Electrolyser filling
669 |  |  |  | Bus bar connection
670 |  |  |  | Tie rod refastening
671 |  |  |  | Anolyte Pit Extension-1
672 |  |  |  | Pipe Rack Strengthning
673 |  |  |  | New Pit Extension
674 |  |  |  | Excavation
675 |  |  |  | PCC
676 |  |  |  | RCC
677 |  |  |  | Concreting up to raft level
678 |  |  |  | Pump Civil bed construction
679 |  |  |  | Wall construction
680 |  |  |  | Curing
681 |  |  |  | Phase-1 shutdown
682 |  |  |  | Process dept activities before work
683 |  |  |  | Shut down
684 |  |  |  | Clearance activities
685 |  |  |  | Caustic/ H2 seperator stream
686 |  |  |  | Dismantling of Inlet & outlet pipe connection
687 |  |  |  | Shifting of Caustic H2 seperator
688 |  |  |  | shifting of pumps & suction discharge line hook up
689 |  |  |  | hook up of cell overflow to caustic seperator line
690 |  |  |  | hookup of caustic seperator outlet gas line
691 |  |  |  | Inst & Elec Dept activities
692 |  |  |  | Process dept activities after work
693 |  |  |  | leak checking
694 |  |  |  | start up
695 |  |  |  | Phase-2 shutdown
696 |  |  |  | Process dept activities before work
697 |  |  |  | Shut down
698 |  |  |  | Clearance activities
699 |  |  |  | Mechanical dept activities after clearance
700 |  |  |  | DB-Cl2 seperator stream
701 |  |  |  | Dismantling of Inlet & outlet pipe connection
702 |  |  |  | Shifting of DB-Cl2 seperator
703 |  |  |  | shifting of pumps & suction discharge line hook up
704 |  |  |  | hook up of cell overflow to DB Cl2 line
705 |  |  |  | hookup of DB-Cl2 seperator outlet gas line
706 |  |  |  | Inst & Elec Dept activities
707 |  |  |  | Process dept activities after work
708 |  |  |  | leak checking
709 |  |  |  | start up
710 |  |  |  | Anolyte Pit Extension-2
711 |  |  |  | Breaking of wall between old & new pit
712 |  |  |  | Dismantling of old catholyte tank area
713 |  |  |  | RCC work
714 |  |  |  | Civil bed construction
715 |  |  |  | Dismantling of old anolyte tank area
716 |  |  |  | RCC Work at Anolyte Area
717 |  |  |  | tank Civil bed construction
718 |  |  |  | Demolition of existing wall towards western side
719 |  |  |  | Excavation
720 |  |  |  | RCC work
721 |  |  |  | Pump Civil bed construction
722 |  |  |  | Anolyte / Catholyte circulation tank / Pump.
723 |  |  |  | Position of new catholyte tank
724 |  |  |  | Position of new anolyte tank
725 |  |  |  | Position of new catholyte pumps
726 |  |  |  | Position of new anolyte pumps
727 |  |  |  | Erection of cable tray ( Electrical and Instrument )
728 |  |  |  | Erection of motors
729 |  |  |  | Piping erection
730 |  |  |  | Cleaning and Flushing of tanks and pipe lines
731 |  |  |  | Instrument erection
732 |  |  |  | Anolyte drai tank / individual Catholyte circulation tank and pump
733 |  |  |  | Removal of old anolyte & catholyte Tank
734 |  |  |  | Removal of old anolyte & catholyte Pumps
735 |  |  |  | Positioning of Anolyte drain tank with pumps
736 |  |  |  | Positioning of Individual catholyte tank with pumps
737 |  |  |  | Erection of motor and cables
738 |  |  |  | Pipe line laying and erection
739 |  |  |  | Instrument erection
740 |  |  |  | Process line Hook up
741 |  |  |  | Utility line hook up
742 |  |  |  | Cleaning and Flushing of tanks and pipe lines
743 |  |  |  | Hydrogen Handling system
744 |  |  |  | Removal of Existing H2 Handling system - H2 vent stack, H2 blower, H2 wash tower & pumps
745 |  |  |  | Modification of Civil Bed - Cl2 seal pot
746 |  |  |  | Construction of civil bed for H2 vent stack
747 |  |  |  | E 201 and E 203 Bed construction
748 |  |  |  | Civil pedestal construction for pipe rack & Pipes supports
749 |  |  |  | Hydrogen gas vent stack positioning
750 |  |  |  | Chlorine seal pot positioning
751 |  |  |  | E 201 and E 203 Positioning
752 |  |  |  | Pipe rack erection
753 |  |  |  | Pipe line laying and erection
754 |  |  |  | Instrument erection
755 |  |  |  | Process line Hook up
756 |  |  |  | Utility line hook up
757 |  |  |  | Cleaning and Flushing of tanks and pipe lines
758 |  |  |  | Cell House Pipe rack
759 |  |  |  | Removal of Cl2 wash tower & Pumps., Cl2 Blowers & Recuperator
760 |  |  |  | Civil Foundation for pipe rack
761 |  |  |  | Civil bed construction for SC-2001
762 |  |  |  | SC-2001 positioning
763 |  |  |  | Pipe rack erection
764 |  |  |  | Pipe line laying
765 |  |  |  | Instrument erection
766 |  |  |  | Process line Hook up
767 |  |  |  | Utility line hook up
768 |  |  |  | Cleaning and Flushing of tanks and pipe lines
769 |  |  |  | P-I OHT area
770 |  |  |  | Arrival of contractor and start of the work
771 |  |  |  | Fabrication of structures
772 |  |  |  | Erection of coulmns
773 |  |  |  | welding of structures
774 |  |  |  | Erection and welding of handrails
775 |  |  |  | painting of structures
776 |  |  |  | Closure of the welding work
777 |  |  |  | Catholyte OHT receipt
778 |  |  |  | Pure brine OHT receipt
779 |  |  |  | Chlorate destruction tank receipt
780 |  |  |  | Erection of Cathoylte OHT
781 |  |  |  | Erection of pure brine OHT
782 |  |  |  | Erection of Chlorate destruction tank
783 |  |  |  | Arrival of piping contractor
784 |  |  |  | piping erection
785 |  |  |  | finish of piping
786 |  |  |  | 5. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
787 |  |  |  | Erection contract Finalization
788 |  |  |  | Mobilization of erection material
789 |  |  |  | Pipe rack and supports fabrication and erection
790 |  |  |  | Process Piping- Inside cell house
791 |  |  |  | Process Piping - Outside cell house
792 |  |  |  | Utility Piping - Inside cell house
793 |  |  |  | Utility Piping - Outside Cell House
794 |  |  |  | Erection of cable tray ( Electrical and Instrument )
795 |  |  |  | Laying of cables (Electrical and Instrument)
796 |  |  |  | Erection of instruments , Testing
805 |  |  |  | 04-Cl2-H2-Handling
806 |  |  |  | 3. Civil and Erection
807 |  |  |  | 3.1 Structurals Civil foundation
808 |  |  |  | a) Dismantling
809 |  |  |  | b) Excavation
810 |  |  |  | c) PCC
811 |  |  |  | d) Footing and column construction
812 |  |  |  | 3.2 Equipments civil foundation
813 |  |  |  | a) Dismantling
814 |  |  |  | b) Exacavation
815 |  |  |  | c) PCC
816 |  |  |  | d) Civil bed construction
817 |  |  |  | e) Soil consolidation
818 |  |  |  | f) PCC and RCC flooring
819 |  |  |  | g) Plastering of flooring
820 |  |  |  | 3.3 Erection of equipments and Structurals
821 |  |  |  | a) Erection of Structurals
822 |  |  |  | Column Erection
823 |  |  |  | Tie beam erection - 3.65 m level
824 |  |  |  | Tie beam erection - 6.4 m level
825 |  |  |  | Tie beam erection - 9.5 m level
826 |  |  |  | Tie beam erection - 13 m level
827 |  |  |  | Cross member erection - 3.65 m
828 |  |  |  | Cross member erection -6.4 m
829 |  |  |  | Cross member erection - 9.5
830 |  |  |  | Cross member erection- 13 m
831 |  |  |  | staircase erection
832 |  |  |  | Handrail erection
833 |  |  |  | b) Positioing of Equipment and pumps
834 |  |  |  | Cl2 / H2 gas mist eliminator
835 |  |  |  | H2 buffer vessel , SP-401 , E-402, T-403, E-501, T-401
836 |  |  |  | T-501, T-502 , T-601 , T-602 , T-402
837 |  |  |  | Heat Exchangers
838 |  |  |  | Pumps
839 |  |  |  | Blower
840 |  |  |  | 3.4 Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
841 |  |  |  | a) Pipe rack and supports
842 |  |  |  | b) Process Piping
843 |  |  |  | c) Utility Piping
844 |  |  |  | d) Erection of cable tray ( Electrical and Instrument )
845 |  |  |  | e) Laying of Electrical cables and Instrument cables
846 |  |  |  | f) Erection of instruments
847 |  |  |  | Erection of MCC and Motors
848 |  |  |  | MCC-6
849 |  |  |  | MCC-3
850 |  |  |  | MCC-3A
851 |  |  |  | h) Installation of Light fittings with LDB
852 |  |  |  | 4. Pre-commissioning
853 |  |  |  | b) Hook up with Existing set up (Process and utilities)
854 |  |  |  | c) Trial run of Equipments
855 |  |  |  | d) Brine filling and circulation
856 |  |  |  | 5. Commissioning of plant
865 |  |  |  | 05-Dry-Cl2-Handling
866 |  |  |  | 3. Civil and Erection
867 |  |  |  | 3.1 Drying tower system
868 |  |  |  | Receipt of equipments
869 |  |  |  | plant shut down & process clearance
870 |  |  |  | dismanlting of existing drying tower connections and opening
871 |  |  |  | removal of packings
872 |  |  |  | removal of existing drying tower
873 |  |  |  | positioning & supporting of new drying tower
874 |  |  |  | Filling of packings
875 |  |  |  | Recepit of pumps
876 |  |  |  | Removal of old pumps
877 |  |  |  | Civil bed modification
878 |  |  |  | Position and hookup of pumps
879 |  |  |  | pipings
880 |  |  |  | leaktest
881 |  |  |  | commissioning
882 |  |  |  | 3.2 Chlorine compressor system
883 |  |  |  | a) Removal of Old Chlorine compressor
884 |  |  |  | b) Positioning of new chlorine compressor
885 |  |  |  | c) Positioning of suction knock out drum, acid separator and Heat exchanger
886 |  |  |  | d) idle run test
887 |  |  |  | b) Hook up with Existing set up (Process and utilities)
888 |  |  |  | 4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
889 |  |  |  | a) Pipe rack and supports
890 |  |  |  | b) Process Piping
891 |  |  |  | c) Utility Piping
892 |  |  |  | Erection of cable tray ( Electrical and Instrument )
893 |  |  |  | Laying of cables (Electrical and Instrument)
894 |  |  |  | Erection of instruments , Testing
895 |  |  |  | Erection of MCC and Motors
896 |  |  |  | MCC-6
905 |  |  |  | 06-Hypo
906 |  |  |  | Civil and Erection
907 |  |  |  | 3.1 Guard tower circulation System
908 |  |  |  | Excavation
909 |  |  |  | PCC
910 |  |  |  | RCC
911 |  |  |  | b)Civil Bed construction
912 |  |  |  | c) Positioning of new guard circulation pumps and Heat Exchanger
913 |  |  |  | Piping
914 |  |  |  | Provision of 6" nozzle in Guard Tower circulation tank
915 |  |  |  | chilled Water inlet and Outlet Pipe laying
916 |  |  |  | Hypo Pump suction and Delivery Line Laying
917 |  |  |  | Hook Up with Existing System
918 |  |  |  | 3.1 Hypo circulation System
919 |  |  |  | Provision of 6" nozzle in hypo circulation tank
920 |  |  |  | Piping
921 |  |  |  | Prefabrication of Hypo Pumps Suction and Delivery Lines
922 |  |  |  | Prefabrication of Chilled Water Pipe Lines To PHE
923 |  |  |  | Removal of Old pump-A
924 |  |  |  | Civil bed modification
925 |  |  |  | Positioning of new pump-A
926 |  |  |  | chilled Water inlet and Outlet Pipe laying
927 |  |  |  | Hypo Pump suction and Delivery Line Laying
928 |  |  |  | Removal of Old PHE
929 |  |  |  | Positioning Of New PHE
930 |  |  |  | Hook Up with Existing System
931 |  |  |  | Removal of Old pump-B
932 |  |  |  | Civil bed modification
933 |  |  |  | Positioning of new pump - B
934 |  |  |  | Piping and Instrumentation
935 |  |  |  | Hook up with Existing System
936 |  |  |  | 4.1 Hypo Blowers
937 |  |  |  | Civil Bed new Blower A
938 |  |  |  | Dismantling
939 |  |  |  | Excavation
940 |  |  |  | PCC
941 |  |  |  | RCC Level 1
942 |  |  |  | RCC Level 2
943 |  |  |  | Erection of VFD for new blower - A
944 |  |  |  | Positioning of new blower-A
945 |  |  |  | Prefabrication of Hypo Blower Suction and Delivery Lines
946 |  |  |  | Laying of PreFabricated Hypo Blower Lines
947 |  |  |  | Hook Up with Existing System
948 |  |  |  | Erection of VFD for new blower - B
949 |  |  |  | Removal of Old blower-B
950 |  |  |  | Civil bed modification
951 |  |  |  | d) Positioning of new blower - B
952 |  |  |  | Piping and Instrumentation
953 |  |  |  | Hook UP with Existing System
954 |  |  |  | 3.2 Acidic Wash Tower system
955 |  |  |  | Receipt of Acidic wash tower
956 |  |  |  | a) Removal of Old acidic wash tower circulation pumps and tower
957 |  |  |  | Civil Bed Modification for Acidic Wash Tower and Circulation Pumps
958 |  |  |  | c) Positioning of acidic wash tower and Circulation pumps
959 |  |  |  | Prefabricaton of Acidic Wash Tower And Circulation Pumps Lines
960 |  |  |  | Piping and Instrumentation
961 |  |  |  | Hook up with Existing System
962 |  |  |  | 3.3 Caustic Over Head Tank
963 |  |  |  | Arrival of contractor and start of the work
964 |  |  |  | Erection of structures
965 |  |  |  | welding of structures
966 |  |  |  | Erection and welding of handrails
967 |  |  |  | painting of structures
968 |  |  |  | Receipt of OHT
969 |  |  |  | Erection of OHT
970 |  |  |  | Cleaning & Leak Testing
971 |  |  |  | Piping and Instrumentation
972 |  |  |  | Commissioning of Caustic OHT
975 |  |  |  | 07-Utilities
976 |  |  |  | 3. Civil and Erection
977 |  |  |  | 3.3 Chiller
978 |  |  |  | Excavation
979 |  |  |  | Delay in Construction
980 |  |  |  | RR masnory work
981 |  |  |  | Earth filling & soil consolidation
982 |  |  |  | PCC
983 |  |  |  | RCC
984 |  |  |  | PCC and RCC flooring
985 |  |  |  | 3.4 Erection of Chiller
986 |  |  |  | a) Positioing of Chiller
987 |  |  |  | b)Erection of chiller
988 |  |  |  | 3.4 Erection of Chilled water storage tank
989 |  |  |  | Contract Finalization
990 |  |  |  | modification of proposed chilled water tank
991 |  |  |  | Positioing of Chilled water tank
992 |  |  |  | 4.1 Chilled water pumps
993 |  |  |  | Receipt of Chilled Water Pumps
994 |  |  |  | Piping
995 |  |  |  | Pipe Rack Extension In Chilled Water Area
996 |  |  |  | Laying Of Chilled Water Pipe Lines for Chiller
997 |  |  |  | Pipe Rack Extension In drying Tower Area
998 |  |  |  | Main Pipe Rack Extension
999 |  |  |  | Pipe Rack Extension In Hypo Area
1000 |  |  |  | Prefabricaton of Chilled Water inlet and Outlet Pipings
1001 |  |  |  | Laying of Chilled Water Pipe Lines
1002 |  |  |  | Fabrication of Pipe Lines
1003 |  |  |  | Pressure Testing
1004 |  |  |  | Insulation
1005 |  |  |  | Removal of Old chilled water pump-A
1006 |  |  |  | Civil bed modification
1007 |  |  |  | Positioning of new pump-A
1008 |  |  |  | Hook up With Existing System
1009 |  |  |  | Removal of Old chilled water pump-B
1010 |  |  |  | Civil bed modification
1011 |  |  |  | d) Positioning of new pump - B
1012 |  |  |  | Piping
1013 |  |  |  | Hook up With Existing System
1014 |  |  |  | N2 Unit
1015 |  |  |  | Dismantling
1016 |  |  |  | Excavation
1017 |  |  |  | PCC
1018 |  |  |  | RCC
1019 |  |  |  | PCC and RCC flooring
1020 |  |  |  | Receipt of N2 Unit
1021 |  |  |  | Positioning of N2 unit
1022 |  |  |  | Piping
1023 |  |  |  | a) Cleaning and Flushing ( Tanks, Equipments and Pipe lines )
1024 |  |  |  | 4. Erection of structurals, pipes, fittings, Electrical Equipments and Instruments
1025 |  |  |  | a) Pipe rack and supports
1026 |  |  |  | c) Utility Piping
1027 |  |  |  | flushing & leak checking
1028 |  |  |  | Insulation
1029 |  |  |  | Erection of cable tray ( Electrical and Instrument )
1030 |  |  |  | Laying of cables (Electrical and Instrument)
1031 |  |  |  | Erection of instruments , Testing
1032 |  |  |  | Erection of MCC and Motors
1033 |  |  |  | MCC-6
1034 |  |  |  | Installation of Light fittings with LDB