## Training Plan
Phase | Activity | Duration | Start Date | End Date
1 | Functional Training - Finance Essentials & Trade | 4 days | 2015-03-17 | 2015-03-20
2 | ISKCON to work on the Action Items and any pending decisions to be taken | 6 days | 2015-03-23 | 2015-03-28
3 | Technical Setup & Key User Training | 3 days | 2015-03-30 | 2015-04-01
4 | ISKCON users to pass entries and record scenarios which need to be addressed | 12 days | 2015-04-02 | 2015-04-17
5 | Functional / Technical Training | 3 days | 2015-04-20 | 2015-04-22
Deliverables
Phase | Deliverable | Who | Target Date | Delivered On
1 | Training to the core team on the NAV features (essentials) | Venugopal | 2015-03-20
1 | List of all features & reports in NAV | JNVD | 2015-03-20 | 2015-03-20
1 | List of Scenarios Discussed and the Solutions Proposed | Core Team | 2015-03-23
1 | List of Customization Required for Mandatory Features Expected | Core Team | 2015-03-23
2 | Master Data required for the administrative setup activities | Core Team
2 | Consolidated list of user stories for all trusts (GST, SST, TSG, TSF, ISK) | Core Team
2 | Check with Microsoft for getting 3 developer licenses (free of cost?) | SMVD
2 | Identify reporting requirements & map to the standard report features in NAV | Core Team
2 | Explore all features in detail | Core Team
2 | Complete the lab work connected to the different modules | Core Team
2 | Setup a system for query resolution during lab exercises | JNVD
3 | Setup the training environment with actual data | Srinivas
3 | Training to all key users on the respective modules | Core Team
3

## Training Sessions
S. No | Date | Start Time | End Time | Topic | Who
1 | 2015-03-17 | 10:30 | 13:30 | Overview of MS Dynamics NAV | Venugopal
|  |  |  | Finalizing the Training Methodology | Hari Prasad
2 | 2015-03-17 | 14:30 | 16:00 | Road map, methodology and team structure | JNVD
|  |  |  | Discuss the plan for next 3 days (feature mapping) | Hari Prasad
3 | 2015-03-17 | 10:00 | 18:00 | Finance Essentials | Venugopal
4 | 2015-03-18 | 10:00 | 18:00 | Trading and Manufacturing / Fixed Assets Overview | Venugopal
5 | 2015-03-19 | 10:00 | 18:00 | Finance Essentials | Venugopal
6 | 2015-03-20 | 10:00 | 13:00 | Finance Essentials | Venugopal
7 | 2015-03-20 | 14:00 | 18:00 | Trading | Venugopal

## Training Attendees
Trainee | Trust / Org | Department | Role | Mobile Number | e-Mail ID | Session 1 | Session 2 | Session 3 | Session 4 | Session 5 | Session 6 | Session 7
Shrihari C Vaidyakar | ISKCON | Accounts & Finance | Core Team |  | shrihari.cv@hkm-group.org | ü | û | ü | ü | ü | ü | ü
Shyama Vallabha Dasa | ISKCON | Accounts & Finance | Core Team |  | smvd@hkm-group.org | ü | û | ü | û | ü | ü | û
Yuvaraj A | ISKCON | Accounts & Finance | Core Team | 9342928017 | yuvaraj.a@hkm-group.org | ü | û | ü | ü | ü | ü | ü
Ganesh M S | TSF-GIFT | Business Analyst | Core Team | 8884949238 | ganesh.mavathur@hkm-group.org | ü | û | ü | ü | û | û | ü
Ayyappa Dasika | ISKCON | Information Technology | Core Team |  | ayyappa.dasika@hkm-group.org | ü | û | û | û | û | û | û
Janaki Vallabha Dasa | ISKCON | Information Technology | Core Team | 9342671724 | jnvd@hkm-group.org | ü | ü | ü | û | ü | ü | ü
Hari Prasad | VEDAVIT | PM Consultant | Core Team |  |  | ü | ü | ü | ü | ü | ü | ü
Nanjunda Swamy | TSF-GIFT | Purchase | Core Team | 9035792038 | nanjunda.swami@hkm-group.org | ü | û | ü | ü | û | û | ü
Raghavendra Rao Y | TSF-FOOD | Sales | Core Team | 9019420027 | raghavendra.rao@hkm-group.org | ü | û | û | ü | û | û | ü
Rashmi N | TSF-FOOD | Stores / Production | Core Team | 9663512164 | rashmi.n@hkm-group.org | ü | û | û | ü | û | û | ü
Basavaraj Basappa Doddamani | ISKCON | Accounts & Finance | Key User | 9481184494 | basavaraj.d@hkm-group.org | ü | û | û | û | ü | ü | û
Krishna G | TSF-GIFT | Sales | Key User |  |  | û | û | û | ü | û | û | û
Santosh P | TSF-FOOD | Sales | Key User |  |  | û | û | û | ü | û | û | û
Srinivas | VARNAAZ | Technical Training | Trainer |  |  | ü | ü | ü | û | ü | ü | ü
Venugopal | VARNAAZ | Functional Training | Trainer |  |  | ü | û | û | ü | ü | ü | ü
Pavan | VARNAAZ | Functional Training | Trainer |  |  | û | û | û | û | û | û | û

## Topics Covered
S. No. | Course | Module | Topics Covered | Phase | Day | Status | Date
617 | Finance Essentials | Chart of Accounts | Chart of Accounts Overview | 1 | Day 01 | Completed
618 | Finance Essentials | Chart of Accounts | G/L Account Card | 1 | Day 01 | Completed
607 | Finance Essentials | Finance Management Setup | General Ledger Setup | 1 | Day 01 | Completed
608 | Finance Essentials | Finance Management Setup | Accounting Periods | 1 | Day 01 | Completed
2000 | Fixed Assets | Fixed Assets Setup | Fixed Assets Overview | 1 | Day 02 | Completed
1413 | Trade | Analysis and Reporting | Sales and Purchase Budgets | 1 | Day 02 | Completed
1397 | Trade | Assembly Management | Reservations and Item Tracking | 1 | Day 02 | Completed
1316 | Trade | Customer Service Features | Item Substitutions | 1 | Day 02 | Completed
1317 | Trade | Customer Service Features | Item Cross References | 1 | Day 02 | Completed
1355 | Trade | Item Charges | Sales Item Charges | 1 | Day 02 | Completed
1329 | Trade | Purchase Order Management | Manage Purchase Transactions | 1 | Day 02 | Completed
1330 | Trade | Purchase Order Management | Purchase Prices and Discounts | 1 | Day 02 | Completed
1331 | Trade | Purchase Order Management | Purchase Prices | 1 | Day 02 | Completed
1332 | Trade | Purchase Order Management | Invoice and Line Discounts | 1 | Day 02 | Completed
1345 | Trade | Requisition Management | Requisition Management Setup | 1 | Day 02 | Completed
1346 | Trade | Requisition Management | Requisition Worksheet | 1 | Day 02 | Completed
1386 | Trade | Returns Managements | Manage Customer Returns | 1 | Day 02 | Completed
1286 | Trade | Sales Order Management | Set Up Sales Order Management | 1 | Day 02 | Completed
1287 | Trade | Sales Order Management | Manage Sales Transactions | 1 | Day 02 | Completed
1288 | Trade | Sales Order Management | Item Reservation | 1 | Day 02 | Completed
1289 | Trade | Sales Order Management | Posting Orders | 1 | Day 02 | Completed
1304 | Trade | Sales Prices and Discounts | Sales Prices | 1 | Day 02 | Completed
1305 | Trade | Sales Prices and Discounts | Maintain Sales Prices | 1 | Day 02 | Completed
1306 | Trade | Sales Prices and Discounts | Sales Line Discounts | 1 | Day 02 | Completed
1307 | Trade | Sales Prices and Discounts | Invoice Discounts | 1 | Day 02 | Completed
870 | Finance Advance | Budgets | Creating Budgets | 1 | Day 03 | Completed
871 | Finance Advance | Budgets | Copying Budgets | 1 | Day 03 | Completed
872 | Finance Advance | Budgets | Exporting and Importing Budgets | 1 | Day 03 | Completed
850 | Finance Advance | Multicurrency | Currency Card and Exchange Rates | 1 | Day 03 | Completed
851 | Finance Advance | Multicurrency | Set Up Multicurrency for Customers, Vendors, and Bank Accounts | 1 | Day 03 | Completed
642 | Finance Essentials | Cash Management - Receivables and Payables | Bank Account Overview | 1 | Day 03 | Completed
643 | Finance Essentials | Cash Management - Receivables and Payables | Customer Overview | 1 | Day 03 | Completed
644 | Finance Essentials | Cash Management - Receivables and Payables | Vendor Overview | 1 | Day 03 | Completed
645 | Finance Essentials | Cash Management - Receivables and Payables | Cash Receipt Journal and Payment Journal Overview | 1 | Day 03 | Completed
646 | Finance Essentials | Cash Management - Receivables and Payables | Suggest Vendor Payments | 1 | Day 03 | Completed
647 | Finance Essentials | Cash Management - Receivables and Payables | Print and Post Payables Checks | 1 | Day 03 | Completed
648 | Finance Essentials | Cash Management - Receivables and Payables | Voiding Checks | 1 | Day 03 | Completed
649 | Finance Essentials | Cash Management - Receivables and Payables | Applying Payments | 1 | Day 03 | Completed
650 | Finance Essentials | Cash Management - Receivables and Payables | Unapply Customer and Vendor Ledger Entries | 1 | Day 03 | Completed
651 | Finance Essentials | Cash Management - Receivables and Payables | Reversal of Posted Journals | 1 | Day 03 | Completed
675 | Finance Essentials | Cash Management - Reconciliation | Bank Reconciliation | 1 | Day 03 | Completed
676 | Finance Essentials | Cash Management - Reconciliation | Complete a Bank Reconciliation | 1 | Day 03 | Completed
619 | Finance Essentials | Chart of Accounts | G/L Account Card Ribbon | 1 | Day 03 | Completed
628 | Finance Essentials | General Journals | Creating and Posting Journal Entries | 1 | Day 03 | Completed
629 | Finance Essentials | General Journals | Standard Journals | 1 | Day 03 | Completed
630 | Finance Essentials | General Journals | Recurring Journals | 1 | Day 03 | Completed
631 | Finance Essentials | General Journals | Processing Recurring Journals | 1 | Day 03 | Completed
682 | Finance Essentials | Receivables and Paybales Management | Set Up Payment Discounts | 1 | Day 03 | Completed
683 | Finance Essentials | Receivables and Paybales Management | Process Payment Discounts | 1 | Day 03 | Completed
684 | Finance Essentials | Receivables and Paybales Management | Set Up and Process Payment Tolerances | 1 | Day 03 | Parked
685 | Finance Essentials | Receivables and Paybales Management | Review the Posted Payment Discount Tolerance and the Payment Tolerance Entries | 1 | Day 03 | Parked
686 | Finance Essentials | Receivables and Paybales Management | Review Customer and Vendor Statistics | 1 | Day 03 | Completed
769 | Finance Essentials | Year End Procedures | Closing a Fiscal Year | 1 | Day 03 | Completed
2001 | Finance Advance | Cost Accounting | Cost Accounting Overview | 1 | Day 04 | Completed
852 | Finance Advance | Multicurrency | Process Documents and Journals | 1 | Day 04 | Completed
853 | Finance Advance | Multicurrency | Adjust Exchange Rates Batch Job for Customers, Vendors, and Bank Accounts | 1 | Day 04 | Completed
854 | Finance Advance | Multicurrency | Reporting Currency | 1 | Day 04 | Completed
855 | Finance Advance | Multicurrency | View the Exchange Rate Adjustment Register | 1 | Day 04 | Completed
856 | Finance Advance | Multicurrency | Summary of Currency Exchange Rates | 1 | Day 04 | Completed
737 | Finance Essentials | Prepayments | Setting Up Prepayments | 1 | Day 04 | Completed
738 | Finance Essentials | Prepayments | Set Up Prepayment Percentages for Customers and Vendors | 1 | Day 04 | Completed
739 | Finance Essentials | Prepayments | Set Up Prepayment % for Customer-Item & Vendor-Item Combinations | 1 | Day 04 | Completed
740 | Finance Essentials | Prepayments | Set Up Prepayments Verification | 1 | Day 04 | Completed
741 | Finance Essentials | Prepayments | Prepayments Processing Flows | 1 | Day 04 | Completed
742 | Finance Essentials | Prepayments | Prepayment Sales and Purchase Orders Overview | 1 | Day 04 | Completed
743 | Finance Essentials | Prepayments | Process Prepayment Sales and Purchase Orders | 1 | Day 04 | Completed
744 | Finance Essentials | Prepayments | Prepayment Sales and Purchase Invoices | 1 | Day 04 | Completed
745 | Finance Essentials | Prepayments | Prepayment Purchase Order Process | 1 | Day 04 | Completed
699 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Reminder Terms | 1 | Day 04 | Completed
700 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Number Series for Reminders and Issue Reminders | 1 | Day 04 | Completed
701 | Finance Essentials | Receivables and Paybales Management | Create and Issue Reminders | 1 | Day 04 | Completed
702 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Finance Charge Terms | 1 | Day 04 | Completed
703 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Number Series for Finance Charge Terms | 1 | Day 04 | Completed
704 | Finance Essentials | Receivables and Paybales Management | Create and Issue Finance Charge Memos | 1 | Day 04 | Completed
705 | Finance Essentials | Receivables and Paybales Management | Calculate Interest on Reminders | 1 | Day 04 | Completed
1411 | Trade | Analysis and Reporting | Analysis Views and Reports | 1 | Day 04 | Completed
1412 | Trade | Analysis and Reporting | Analysis by Dimensions | 1 | Day 04 | Completed
1395 | Trade | Assembly Management | Assembly Items and Assembly Bill of Materials | 1 | Day 04 | Completed
1396 | Trade | Assembly Management | Assemble to Order | 1 | Day 04 | Completed
1398 | Trade | Assembly Management | Selling ATO Items and Inventory Items Together | 1 | Day 04 | Completed
1399 | Trade | Assembly Management | Assemble-to-Order Shipments | 1 | Day 04 | Completed
1318 | Trade | Customer Service Features | Set Up and Create Nonstock Items | 1 | Day 04 | Completed
1319 | Trade | Customer Service Features | Sell Nonstock Items | 1 | Day 04 | Completed
1354 | Trade | Item Charges | Purchase Item Charges | 1 | Day 04 | Completed
1356 | Trade | Item Charges | Purchase and Sales Allowances | 1 | Day 04 | Completed
1328 | Trade | Purchase Order Management | Purchase Order Management Setup | 1 | Day 04 | Completed
1333 | Trade | Purchase Order Management | Vendor Prepayments | 1 | Day 04 | Completed
1347 | Trade | Requisition Management | Additional Worksheet Features | 1 | Day 04 | Completed
1385 | Trade | Returns Managements | Returns Management Setup | 1 | Day 04 | Completed
1387 | Trade | Returns Managements | Manage Returns to Vendors | 1 | Day 04 | Completed
1290 | Trade | Sales Order Management | Drop Shipments | 1 | Day 04 | Completed
1291 | Trade | Sales Order Management | Customer Prepayments | 1 | Day 04 | Completed
2009 | Indian Localization | Excise | Overview of Excise |  | NA
2010 | Indian Localization | Excise | Basic Setup |  | NA
2011 | Indian Localization | Excise | Excise Calculation in Purchase order or Purchase Return order for CENVAT Items |  | NA
2012 | Indian Localization | Excise | Excise Calculation in case of Capital Goods |  | NA
2013 | Indian Localization | Excise | Excise calculation in case of Imported goods in Purchase Invoice and Return Order |  | NA
2014 | Indian Localization | Excise | Excise Refund and Excise loading on Inventory |  | NA
2015 | Indian Localization | Excise | Output entries for finished goods |  | NA
2016 | Indian Localization | Excise | Excise calculation in Sales order or Sales invoice |  | NA
2017 | Indian Localization | Excise | Supplementary Invoice |  | NA
2018 | Indian Localization | Excise | Sales Cancellation |  | NA
2019 | Indian Localization | Excise | Excise Calculation in Case of Sale of Capital Goods |  | NA
2020 | Indian Localization | Excise | Excise Calculation in free sample given to Customer |  | NA
2021 | Indian Localization | Excise | Sale of Goods which are Returned |  | NA
2022 | Indian Localization | Excise | Depositing of PLA amount and creating of excise charge liability using the Tax Journal |  | NA
2023 | Indian Localization | Excise | Direct debit to PLA/RG in Sales Invoice |  | NA
2024 | Indian Localization | Excise | Excise Calculation in case Goods removed as such |  | NA
2025 | Indian Localization | Excise | Excise Calculation in Sales Invoice as per MRP Provision of the Excise Act |  | NA
2026 | Indian Localization | Excise | Transfer of Intermediate Goods from one Location to another Location |  | NA
2027 | Indian Localization | Excise | Transfer of Raw material from one Location to another Location |  | NA
2028 | Indian Localization | Excise | Calculation of Excise duty in case of Captive Consumption |  | NA
2029 | Indian Localization | Excise | Purchase Invoice with Service Tax Credit taken on Input service |  | NA
2030 | Indian Localization | Excise | Service tax Credit utilized for Excise payment |  | NA
2031 | Indian Localization | Excise | Excise Payment |  | NA
2032 | Indian Localization | Excise | Update ER 1 PLA Payments Type |  | NA
2033 | Indian Localization | Excise | Excise calculation in Purchase order or Purchase Return order for CENVAT Items in case of Trading |  | NA
2034 | Indian Localization | Excise | Excise calculation in Sales order or Sales Return order for CENVAT Items in case of Trading |  | NA
2035 | Indian Localization | Excise | Transfer of Goods from Trading location to Manufacturing Location |  | NA
2036 | Indian Localization | Excise | Transfer of goods from manufacturing location to trading location |  | NA
2037 | Indian Localization | Excise | Identifying the Principal Item |  | NA
2038 | Indian Localization | Excise | Opening Entry |  | NA
2039 | Indian Localization | Excise | Excise Reports |  | NA
2040 | Indian Localization | Service Tax | Overview of Service Tax | 2 | Day-05 |  | 2015-04-09
2041 | Indian Localization | Service Tax | Basic Setup | 2 | Day-05 |  | 2015-04-09
2042 | Indian Localization | Service Tax | Calculating Service Tax and TDS using Journal Voucher | 2 | Day-05 |  | 2015-04-09
2043 | Indian Localization | Service Tax | Service Tax Implication while Making Payment to Vendor against Invoice | 2 | Day-05 |  | 2015-04-09
2044 | Indian Localization | Service Tax | Calculating Service Tax and TDS using Bank Payment Voucher for Advance Payments | 2 | Day-05 |  | 2015-04-09
2045 | Indian Localization | Service Tax | Service Tax Implication while creating Invoice against Advance Payment | 2 | Day-05 |  | 2015-04-09
2046 | Indian Localization | Service Tax | Service Tax Implication by Applying Advance Payment and Invoice from Vendor Ledger Entry | 2 | Day-05 |  | 2015-04-09
2047 | Indian Localization | Service Tax | Service Tax Implication by Applying Normal Payment and Invoice from Vendor Ledger Entry | 2 | Day-05 |  | 2015-04-09
2048 | Indian Localization | Service Tax | Reversal of Bank Payment Voucher which includes Service Tax | 2 | Day-05 |  | 2015-04-09
2049 | Indian Localization | Service Tax | Purchase Invoice with CENVAT taken on Inputs | 2 | Day-05 |  | 2015-04-09
2050 | Indian Localization | Service Tax | Purchase Invoice with CENVAT taken on Capital Goods | 2 | Day-05 |  | 2015-04-09
2051 | Indian Localization | Service Tax | Credit Received from Inter Unit Transfer by a LTU | 2 | Day-05 |  | 2015-04-09
2052 | Indian Localization | Service Tax | Purchase Invoice with Service Tax in case of Input Service Distributor | 2 | Day-05 |  | 2015-04-09
2053 | Indian Localization | Service Tax | Service Tax Distribution | 2 | Day-05 |  | 2015-04-09
2054 | Indian Localization | Service Tax | GTA Transaction in case of Service Receiver | 2 | Day-05 |  | 2015-04-09
2055 | Indian Localization | Service Tax | Refund of Advance Payment from Vendor with Service Tax | 2 | Day-05 |  | 2015-04-09
2056 | Indian Localization | Service Tax | Purchase Credit Memo with Service Tax | 2 | Day-05 |  | 2015-04-09
2057 | Indian Localization | Service Tax | Calculating Service Tax using Journal Voucher | 2 | Day-05 |  | 2015-04-09
2058 | Indian Localization | Service Tax | Service Tax Implication while Receiving Payment from Customer | 2 | Day-05 |  | 2015-04-09
2059 | Indian Localization | Service Tax | Calculating Service Tax on Advance Payment Received from Customer | 2 | Day-05 |  | 2015-04-09
2060 | Indian Localization | Service Tax | Service Tax Implication while creating Invoice against Advance Payment | 2 | Day-05 |  | 2015-04-09
2061 | Indian Localization | Service Tax | Service Tax Implication by Applying Advance Payment and Invoice from Customer Ledger Entry | 2 | Day-05 |  | 2015-04-09
2062 | Indian Localization | Service Tax | Service Tax Implication by Applying Normal Payment and Invoice from Customer Ledger Entry | 2 | Day-05 |  | 2015-04-09
2063 | Indian Localization | Service Tax | Reversal of Bank Receipt Voucher which includes Service Tax | 2 | Day-05 |  | 2015-04-09
2064 | Indian Localization | Service Tax | Export of Services using Sales Invoice | 2 | Day-05 |  | 2015-04-09
2065 | Indian Localization | Service Tax | Sale of Exempted Services | 2 | Day-05 |  | 2015-04-09
2066 | Indian Localization | Service Tax | ST Pure Agent | 2 | Day-05 |  | 2015-04-09
2067 | Indian Localization | Service Tax | Calculating Service Tax with Abatement Percentage | 2 | Day-05 |  | 2015-04-09
2068 | Indian Localization | Service Tax | Refund of Advance Payment to Customer with Service Tax | 2 | Day-05 |  | 2015-04-09
2069 | Indian Localization | Service Tax | Sales Credit Memo with Service Tax | 2 | Day-05 |  | 2015-04-09
2070 | Indian Localization | Service Tax | Calculation of Service Tax on Direct Payments/Receipts | 2 | Day-05 |  | 2015-04-09
2071 | Indian Localization | Service Tax | Service Tax Implication while applying Invoice and Payment with different Currency Exchange Rates | 2 | Day-05 |  | 2015-04-09
2072 | Indian Localization | Service Tax | Service Tax Opening | 2 | Day-05 |  | 2015-04-09
2073 | Indian Localization | Service Tax | Service Tax Adjustment | 2 | Day-05 |  | 2015-04-09
2074 | Indian Localization | Service Tax | Adjust Service Tax Credit | 2 | Day-05 |  | 2015-04-09
2075 | Indian Localization | Service Tax | Service Tax Payment | 2 | Day-05 |  | 2015-04-09
2076 | Indian Localization | Service Tax | ST3 Removed as such/LTU Dtls | 2 | Day-05 |  | 2015-04-09
2077 | Indian Localization | Service Tax | Service Tax Reports | 2 | Day-05 |  | 2015-04-09
2003 | Indian Localization | Structure | Overview of structure | 2 | Day-05 |  | 2015-04-09
2004 | Indian Localization | Structure | Basic Setup | 2 | Day-05 |  | 2015-04-09
2005 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Purchase Order with Structure | 2 | Day-05 |  | 2015-04-09
2006 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Sales Order with Structure | 2 | Day-05 |  | 2015-04-09
2007 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Purchase Return Order with Structure | 2 | Day-05 |  | 2015-04-09
2008 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Sales Return Order with Structure | 2 | Day-05 |  | 2015-04-09
2078 | Indian Localization | VAT / Sales Tax | Overview of Value Added Tax (VAT) | 2 | Day-06 |  | 2015-04-10
2079 | Indian Localization | VAT / Sales Tax | Basic Setup | 2 | Day-06 |  | 2015-04-10
2080 | Indian Localization | VAT / Sales Tax | Calculating VAT on purchase of goods | 2 | Day-06 |  | 2015-04-10
2081 | Indian Localization | VAT / Sales Tax | Calculating VAT if vendor has opted for Composition scheme | 2 | Day-06 |  | 2015-04-10
2082 | Indian Localization | VAT / Sales Tax | Calculating VAT if Retention limit is defined in the Tax Jurisdiction setup with Non ITC claimable Usage% defined | 2 | Day-06 |  | 2015-04-10
2083 | Indian Localization | VAT / Sales Tax | Calculating VAT able Purchase Tax on CST | 2 | Day-06 |  | 2015-04-10
2084 | Indian Localization | VAT / Sales Tax | Calculating VAT if Purchases are meant for Export or Deemed Export | 2 | Day-06 |  | 2015-04-10
2085 | Indian Localization | VAT / Sales Tax | Calculating VAT in case of capital item if deferment period is 1Y in the States setup with a checkmark in the Financial Year field | 2 | Day-06 |  | 2015-04-10
2086 | Indian Localization | VAT / Sales Tax | Calculating VAT in Purchase Credit Memo in case of normal item | 2 | Day-06 |  | 2015-04-10
2087 | Indian Localization | VAT / Sales Tax | Calculating VAT in case of Sales Order | 2 | Day-06 |  | 2015-04-10
2088 | Indian Localization | VAT / Sales Tax | Calculating VAT if standard deduction% is defined in the Tax Detail setup | 2 | Day-06 |  | 2015-04-10
2089 | Indian Localization | VAT / Sales Tax | Calculating VAT on sale of goods in case of VAT exempted or Export or Deemed Export | 2 | Day-06 |  | 2015-04-10
2090 | Indian Localization | VAT / Sales Tax | Calculating CST on sale of goods using sales order | 2 | Day-06 |  | 2015-04-10
2091 | Indian Localization | VAT / Sales Tax | Calculating VAT as per multiple tax jurisdictions in case of normal item | 2 | Day-06 |  | 2015-04-10
2092 | Indian Localization | VAT / Sales Tax | Adjustment of VAT (Lot no. wise) in case of normal item when VAT Adjustment type is Lost/Destroy | 2 | Day-06 |  | 2015-04-10
2093 | Indian Localization | VAT / Sales Tax | Adjustment of VAT (Serial No. Wise) in case of normal item When VAT Adjustment type is Consumed | 2 | Day-06 |  | 2015-04-10
2094 | Indian Localization | VAT / Sales Tax | Adjustment of VAT in case of Partial Branch Transfers through VAT Adjustment Journal | 2 | Day-06 |  | 2015-04-10
2095 | Indian Localization | VAT / Sales Tax | Adjustment of VAT in case of change in usage through VAT Adjustment Journal | 2 | Day-06 |  | 2015-04-10
2096 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of normal item | 2 | Day-06 |  | 2015-04-10
2097 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of capital goods containing VAT deferment with Settled Period | 2 | Day-06 |  | 2015-04-10
2098 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of capital goods containing VAT deferment without Settled period | 2 | Day-06 |  | 2015-04-10
2099 | Indian Localization | VAT / Sales Tax | Entering VAT opening on sale of goods | 2 | Day-06 |  | 2015-04-10
2100 | Indian Localization | VAT / Sales Tax | Calculating VAT through Purchase Credit Memo in case of Fixed Asset | 2 | Day-06 |  | 2015-04-10
2101 | Indian Localization | VAT / Sales Tax | Calculating VAT through Sales Credit Memo | 2 | Day-06 |  | 2015-04-10
2102 | Indian Localization | VAT / Sales Tax | VAT Settlement | 2 | Day-06 |  | 2015-04-10
2103 | Indian Localization | VAT / Sales Tax | VAT Reporting | 2 | Day-06 |  | 2015-04-10
928 | Finance Advance | Financial Reporting and Analysis | Analyze the Chart of Accounts | 2 | Day-07 |  | 2015-04-11
929 | Finance Advance | Financial Reporting and Analysis | Account Schedules | 2 | Day-07 |  | 2015-04-11
930 | Finance Advance | Financial Reporting and Analysis | Analysis by Dimensions | 2 | Day-07 |  | 2015-04-11
931 | Finance Advance | Financial Reporting and Analysis | Export Analysis Views to Microsoft Excel | 2 | Day-07 |  | 2015-04-11
932 | Finance Advance | Financial Reporting and Analysis | Dimension-Based Reports | 2 | Day-07 |  | 2015-04-11
933 | Finance Advance | Financial Reporting and Analysis | Combine Analysis Views with Account Schedules | 2 | Day-07 |  | 2015-04-11
934 | Finance Advance | Financial Reporting and Analysis | Finance Performance Charts | 2 | Day-07 |  | 2015-04-11
1077 | Fixed Assets | Fixed Asset Insurance | Setting Up Insurance Information | 2 | Day-07 |  | 2015-04-11
1078 | Fixed Assets | Fixed Asset Insurance | Attaching Assets to Insurance Policies | 2 | Day-07 |  | 2015-04-11
1079 | Fixed Assets | Fixed Asset Insurance | Monitoring Insurance Coverage | 2 | Day-07 |  | 2015-04-11
1080 | Fixed Assets | Fixed Asset Insurance | Updating Insurance Information | 2 | Day-07 |  | 2015-04-11
1081 | Fixed Assets | Fixed Asset Insurance | Indexing Insurance | 2 | Day-07 |  | 2015-04-11
1050 | Fixed Assets | Fixed Asset Reclassification | Asset Transfers | 2 | Day-07 |  | 2015-04-11
1051 | Fixed Assets | Fixed Asset Reclassification | Combining Assets | 2 | Day-07 |  | 2015-04-11
1001 | Fixed Assets | Fixed Asset Transactions | Journals for Fixed Assets | 2 | Day-07 |  | 2015-04-11
1002 | Fixed Assets | Fixed Asset Transactions | Purchase Fixed Assets | 2 | Day-07 |  | 2015-04-11
1003 | Fixed Assets | Fixed Asset Transactions | Calculate and Post Depreciation | 2 | Day-07 |  | 2015-04-11
1004 | Fixed Assets | Fixed Asset Transactions | Write-down and Appreciation of Fixed Assets | 2 | Day-07 |  | 2015-04-11
1005 | Fixed Assets | Fixed Asset Transactions | Fixed Asset Disposals | 2 | Day-07 |  | 2015-04-11
1006 | Fixed Assets | Fixed Asset Transactions | Correct an Entry | 2 | Day-07 |  | 2015-04-11
1007 | Fixed Assets | Fixed Asset Transactions | Document Fixed Asset Transactions | 2 | Day-07 |  | 2015-04-11
1008 | Fixed Assets | Fixed Asset Transactions | Fixed Asset Reports | 2 | Day-07 |  | 2015-04-11
1009 | Fixed Assets | Fixed Asset Transactions | Budget Fixed Asset Transactions | 2 | Day-07 |  | 2015-04-11
1010 | Fixed Assets | Fixed Asset Transactions | Cost Accounting Depreciation | 2 | Day-07 |  | 2015-04-11
1011 | Fixed Assets | Fixed Asset Transactions | Indexation | 2 | Day-07 |  | 2015-04-11
1012 | Fixed Assets | Fixed Asset Transactions | Minor Assets | 2 | Day-07 |  | 2015-04-11
1064 | Fixed Assets | Fixed Assets Maintenance | Setting Up Maintenance Information | 2 | Day-07 |  | 2015-04-11
1065 | Fixed Assets | Fixed Assets Maintenance | Maintenance Registration and Costs | 2 | Day-07 |  | 2015-04-11
1066 | Fixed Assets | Fixed Assets Maintenance | Maintenance Cost Reporting | 2 | Day-07 |  | 2015-04-11
975 | Fixed Assets | Fixed Assets Setup | Fixed Assets Process Flow | 2 | Day-07 |  | 2015-04-11
976 | Fixed Assets | Fixed Assets Setup | Fixed Assets Setup | 2 | Day-07 |  | 2015-04-11
977 | Fixed Assets | Fixed Assets Setup | Fixed Assets Posting Groups | 2 | Day-07 |  | 2015-04-11
978 | Fixed Assets | Fixed Assets Setup | Depreciation Books | 2 | Day-07 |  | 2015-04-11
979 | Fixed Assets | Fixed Assets Setup | Fixed Asset Card | 2 | Day-07 |  | 2015-04-11
980 | Fixed Assets | Fixed Assets Setup | Fixed Asset Allocation Keys | 2 | Day-07 |  | 2015-04-11
981 | Fixed Assets | Fixed Assets Setup | Main Assets and Asset Components | 2 | Day-07 |  | 2015-04-11
982 | Fixed Assets | Fixed Assets Setup | Record Open Transactions | 2 | Day-07 |  | 2015-04-11
983 | Fixed Assets | Fixed Assets Setup | Make Duplicate Entries | 2 | Day-07 |  | 2015-04-11
984 | Fixed Assets | Fixed Assets Setup | Copy Fixed Assets and FA Ledger Entries | 2 | Day-07 |  | 2015-04-11
909 | Finance Advance | Cash Flow Forecast | Functions of the Cash Flow Forecast | 2 | Day-06 |  | 2015-04-10
910 | Finance Advance | Cash Flow Forecast | Setting Up Cash Flow Forecasts | 2 | Day-06 |  | 2015-04-10
911 | Finance Advance | Cash Flow Forecast | Creating Cash Flow Forecasts | 2 | Day-06 |  | 2015-04-10
912 | Finance Advance | Cash Flow Forecast | Cash Flow Forecast Reporting | 2 | Day-06 |  | 2015-04-10
883 | Finance Advance | Cost Accounting | Workflow in Cost Accounting | 2 | Day-06 |  | 2015-04-10
884 | Finance Advance | Cost Accounting | Setting Up Cost Accounting | 2 | Day-06 |  | 2015-04-10
885 | Finance Advance | Cost Accounting | Cost Entries | 2 | Day-06 |  | 2015-04-10
886 | Finance Advance | Cost Accounting | Cost Budgets | 2 | Day-06 |  | 2015-04-10
887 | Finance Advance | Cost Accounting | Cost Allocation | 2 | Day-06 |  | 2015-04-10
888 | Finance Advance | Cost Accounting | Cost Accounting History | 2 | Day-06 |  | 2015-04-10
889 | Finance Advance | Cost Accounting | Cost Accounting Reporting | 2 | Day-06 |  | 2015-04-10
890 | Finance Advance | Cost Accounting | Tips and Tricks | 2 | Day-06 |  | 2015-04-10
1365 | Trade | Order Promising | Sales Order Promising Definitions and Calculations | 2 | Day-07 |  | 2015-04-11
1366 | Trade | Order Promising | Date Calculation Setup for Sales Orders | 2 | Day-07 |  | 2015-04-11
1367 | Trade | Order Promising | Promising Sales Order Delivery | 2 | Day-07 |  | 2015-04-11
1368 | Trade | Order Promising | Purchase Order Promising Definitions and Calculations | 2 | Day-07 |  | 2015-04-11
1369 | Trade | Order Promising | Date Calculation Setup for Purchase Orders | 2 | Day-07 |  | 2015-04-11
1370 | Trade | Order Promising | Estimating Purchase Order Receipts | 2 | Day-07 |  | 2015-04-11
1371 | Trade | Order Promising | Estimate a Transfer Order Receipt | 2 | Day-07 |  | 2015-04-11
1372 | Trade | Order Promising | Calendars | 2 | Day-07 |  | 2015-04-11
73 | Config-Tech | Manage User Rights and Profiles | Authentication | 3 | Day 05
74 | Config-Tech | Manage User Rights and Profiles | Set Up User Rights | 3 | Day 05
75 | Config-Tech | Manage User Rights and Profiles | Create a New Permission Set | 3 | Day 05
76 | Config-Tech | Manage User Rights and Profiles | Apply Security Filters | 3 | Day 05
77 | Config-Tech | Manage User Rights and Profiles | User-Specific Setup | 3 | Day 05
78 | Config-Tech | Manage User Rights and Profiles | User Profile Setup | 3 | Day 05
79 | Config-Tech | Manage User Rights and Profiles | Best Practices | 3 | Day 05
54 | Config-Tech | Set Up a Company by Using RapidStart Services | Manual Setup vs RapidStart Services | 3 | Day 05
55 | Config-Tech | Set Up a Company by Using RapidStart Services | Rapid Start Services Process Flow | 3 | Day 05
56 | Config-Tech | Set Up a Company by Using RapidStart Services | Create and Export a Configuration Package | 3 | Day 05
57 | Config-Tech | Set Up a Company by Using RapidStart Services | Configure a New Company by Using RapidStart Services | 3 | Day 05
58 | Config-Tech | Set Up a Company by Using RapidStart Services | Data Migration by Using Rapid Start Services | 3 | Day 05
59 | Config-Tech | Set Up a Company by Using RapidStart Services | Transfer Opening Balances by Using RapidStart Services | 3 | Day 05
160 | Config-Tech | Set Up and Manage Document Approvals | Set Up Document Approvals | 3 | Day 06
161 | Config-Tech | Set Up and Manage Document Approvals | Set Up the Notification System | 3 | Day 06
162 | Config-Tech | Set Up and Manage Document Approvals | Set Up a Sales Document Approvals System | 3 | Day 06
163 | Config-Tech | Set Up and Manage Document Approvals | Use the Document Approval System | 3 | Day 06
109 | Config-Tech | Set Up General Journals Templates and Batches | Journal Templates, Batches, and Lines | 3 | Day 06
110 | Config-Tech | Set Up General Journals Templates and Batches | Create Journal Templates and Batches | 3 | Day 06
95 | Config-Func | Set Up Number Series | Number Series | 3 | Day 06
117 | Config-Func | Set Up Posting Groups | Specific Posting Groups | 3 | Day 06
118 | Config-Func | Set Up Posting Groups | General Posting Groups | 3 | Day 06
119 | Config-Func | Set Up Posting Groups | General Posting Setup | 3 | Day 06
120 | Config-Func | Set Up Posting Groups | VAT Posting Groups | 3 | Day 06
121 | Config-Func | Set Up Posting Groups | VAT Posting Setup | 3 | Day 06
122 | Config-Func | Set Up Posting Groups | Best Practices | 3 | Day 06
123 | Config-Func | Set Up Posting Groups | Post and Review a Sales Transaction | 3 | Day 06
103 | Config-Func | Set Up Trail Codes | Source Code and Reason Codes | 3 | Day 06
104 | Config-Func | Set Up Trail Codes | Navigate the Audit Trail | 3 | Day 06
138 | Config-Func | Set Up Dimensions | Dimensions and Dimension Values | 3 | Day 07
139 | Config-Func | Set Up Dimensions | Setting Up Dimensions in General Ledger Setup | 3 | Day 07
140 | Config-Func | Set Up Dimensions | Dimension Combinations | 3 | Day 07
141 | Config-Func | Set Up Dimensions | Default Dimensions and Account Type Default Dimensions | 3 | Day 07
142 | Config-Func | Set Up Dimensions | Default Dimension Priority | 3 | Day 07
143 | Config-Func | Set Up Dimensions | Conflicting Default Dimensions | 3 | Day 07
2002 | Finance Advance | Cash Flow Forecast | Cash Flow Forecast Overview |  | Day 04 | Completed
833 | Finance Advance | Intrastat | Set up Intrastat |  | NA
834 | Finance Advance | Intrastat | Report Intrastat |  | NA
841 | Finance Advance | VAT Rate Change | Prepare for VAT Rate Change Tool |  | NA
842 | Finance Advance | VAT Rate Change | Set Up Using VAT Rate Change Tool |  | NA
843 | Finance Advance | VAT Rate Change | Perform VAT Rate Conversions |  | NA
954 | Finance Advance | XBRL | XBRL Terminology |  | NA
955 | Finance Advance | XBRL | XBRL Specifications and Taxonomies |  | NA
956 | Finance Advance | XBRL | Work with Linkbases |  | NA
957 | Finance Advance | XBRL | Enter XBRL Line Definitions |  | NA
958 | Finance Advance | XBRL | Export the XBRL Lines |  | NA
718 | Finance Essentials | VAT | VAT Calculation Types |  | NA
719 | Finance Essentials | VAT | Display VAT Amounts in Sales and Purchase Documents |  | NA
720 | Finance Essentials | VAT | Manually Adjust VAT Amounts in Sales and Purchase Documents and Journals |  | NA
721 | Finance Essentials | VAT | Unrealized VAT |  | NA
722 | Finance Essentials | VAT | VAT Statements |  | NA
723 | Finance Essentials | VAT | VAT Settlement |  | NA
1232 | Manufacturing | Advanced Capacity | Explains how to set up work centers and machine centers |  | NA
1233 | Manufacturing | Advanced Capacity | Shows how to set up shop calendars and capacity calendars |  | NA
1234 | Manufacturing | Advanced Capacity | Describes registered absences and how to use them |  | NA
1235 | Manufacturing | Advanced Capacity | Explains how to use capacity journals |  | NA
1117 | Manufacturing | Basic Capacities and Routings | Explains how to set up capacity |  | NA
1118 | Manufacturing | Basic Capacities and Routings | Shows how to create routings |  | NA
1119 | Manufacturing | Basic Capacities and Routings | Describes the advanced features for routings |  | NA
1120 | Manufacturing | Basic Capacities and Routings | Reviews the standard capacity and routing reports |  | NA
1169 | Manufacturing | Forecasting and Planning | Describe the production forecast functionality |  | NA
1170 | Manufacturing | Forecasting and Planning | Explain the integration between production forecasting and planning |  | NA
1171 | Manufacturing | Forecasting and Planning | Show how actual demand is netted against forecast demand |  | NA
1172 | Manufacturing | Forecasting and Planning | Describe forecasting by location, order tracking as it relates to forecasting, and forecasting setup |  | NA
1173 | Manufacturing | Forecasting and Planning | Review the forecast reports |  | NA
1253 | Manufacturing | Manufacturing - Additional Topics | Describes standard tasks and how to use them |  | NA
1254 | Manufacturing | Manufacturing - Additional Topics | Explains stop codes and how to use them |  | NA
1255 | Manufacturing | Manufacturing - Additional Topics | Reviews the various options for recording scrap and the relationships between the options |  | NA
1256 | Manufacturing | Manufacturing - Additional Topics | Defines non-productive time and shows how to use it in a production order |  | NA
1257 | Manufacturing | Manufacturing - Additional Topics | Shows how to reduce lead time |  | NA
1258 | Manufacturing | Manufacturing - Additional Topics | Consumption journal entries and output journal entries for multilevel production orders |  | NA
1259 | Manufacturing | Manufacturing - Additional Topics | Defines production families and shows how to use them in a production order |  | NA
1260 | Manufacturing | Manufacturing - Additional Topics | Describes standard tasks and how to use them |  | NA
1261 | Manufacturing | Manufacturing - Additional Topics | Explains stop codes and how to use them |  | NA
1262 | Manufacturing | Manufacturing - Additional Topics | Reviews the various options for recording scrap and the relationships between the options |  | NA
1263 | Manufacturing | Manufacturing - Additional Topics | Defines non-productive time and shows how to use it in a production order |  | NA
1264 | Manufacturing | Manufacturing - Additional Topics | Shows how to reduce lead time |  | NA
1265 | Manufacturing | Manufacturing - Additional Topics | Consumption journal entries and output journal entries for multilevel production orders |  | NA
1266 | Manufacturing | Manufacturing - Additional Topics | Defines production families and shows how to use them in a production order |  | NA
1182 | Manufacturing | Planning | Describes the general concepts of the planning system |  | NA
1183 | Manufacturing | Planning | Introduces the planning worksheet and related functions |  | NA
1184 | Manufacturing | Planning | Explains how to use regenerative planning |  | NA
1185 | Manufacturing | Planning | Shows how to use net change planning |  | NA
1186 | Manufacturing | Planning | Describes how parameters affect the planning process |  | NA
1187 | Manufacturing | Planning | Explains how to use order tracking and action messages |  | NA
1188 | Manufacturing | Planning | Describes the general concepts of the planning system |  | NA
1189 | Manufacturing | Planning | Introduces the planning worksheet and related functions |  | NA
1190 | Manufacturing | Planning | Explains how to use regenerative planning |  | NA
1191 | Manufacturing | Planning | Shows how to use net change planning |  | NA
1192 | Manufacturing | Planning | Describes how parameters affect the planning process |  | NA
1193 | Manufacturing | Planning | Explains how to use order tracking and action messages |  | NA
1196 | Manufacturing | Planning - Additional Topics | Defines item variants |  | NA
1197 | Manufacturing | Planning - Additional Topics | Explains how to use locations in planning |  | NA
1198 | Manufacturing | Planning - Additional Topics | Shows how to perform transfers between locations |  | NA
1199 | Manufacturing | Planning - Additional Topics | Describes how to use blanket sales orders in planning |  | NA
1200 | Manufacturing | Planning - Additional Topics | Explains how to use multilevel production orders |  | NA
1201 | Manufacturing | Planning - Additional Topics | Reviews how to filter the planning worksheet |  | NA
1202 | Manufacturing | Planning - Additional Topics | Shows how to change the replenishment system for a planning line |  | NA
1203 | Manufacturing | Planning - Additional Topics | Describes how to refresh planning lines |  | NA
1204 | Manufacturing | Planning - Additional Topics | Identifies the available planning reports |  | NA
1108 | Manufacturing | Production Bill of Materials | Describes the production BOM structure and its basic features |  | NA
1109 | Manufacturing | Production Bill of Materials | Explains and demonstrates production BOM advanced features |  | NA
1110 | Manufacturing | Production Bill of Materials | Shows production BOM reports |  | NA
1143 | Manufacturing | Production Order Processing | Reviews the flow of events as production orders move from release until they are finished |  | NA
1144 | Manufacturing | Production Order Processing | Options and procedures related to material consumption and production output |  | NA
1145 | Manufacturing | Production Order Processing | Shows how to pick components and put away finished goods in the warehouse |  | NA
1146 | Manufacturing | Production Order Processing | Explains the uses of the consumption journal, output journal, and production journal |  | NA
1128 | Manufacturing | Production Orders | Describes the different production order statuses |  | NA
1129 | Manufacturing | Production Orders | Explains how to create and schedule a production order |  | NA
1130 | Manufacturing | Production Orders | Different types of changes that you can make to a production order |  | NA
1131 | Manufacturing | Production Orders | Shows how to use the Production Order batch job |  | NA
1133 | Manufacturing | Production Orders | Reviews the production order listings and reports |  | NA
1132 | Manufacturing | Production Orders - Additional Topics | Reservations, statistics, phantom BOMs, and manufacturing batch units of measure |  | NA
1162 | Manufacturing | Sales Order Interface and Order Planning | Describes and demonstrates all aspects of sales order planning |  | NA
1163 | Manufacturing | Sales Order Interface and Order Planning | Explains and demonstrates all aspects of order planning |  | NA
1098 | Manufacturing | Sample Company Structure | Explains how to set the working date |  | NA
1099 | Manufacturing | Sample Company Structure | Shows how to change the default profile to Production Planner |  | NA
1100 | Manufacturing | Sample Company Structure | Describes license information |  | NA
1243 | Manufacturing | Shop Loading | Describes the basic tools that are used to manage shop loading |  | NA
1244 | Manufacturing | Shop Loading | Explains how to manage shop loading by assuming infinite capacity |  | NA
1245 | Manufacturing | Shop Loading | Shows how to manage shop loading by using finite capacity |  | NA
1246 | Manufacturing | Shop Loading | Reviews the reports that are related to shop loading |  | NA
1247 | Manufacturing | Shop Loading | Describes the basic tools that are used to manage shop loading |  | NA
1248 | Manufacturing | Shop Loading | Explains how to manage shop loading by assuming infinite capacity |  | NA
1249 | Manufacturing | Shop Loading | Shows how to manage shop loading by using finite capacity |  | NA
1250 | Manufacturing | Shop Loading | Reviews the reports that are related to shop loading |  | NA
1217 | Manufacturing | Subcontracting | Describes how to set up a subcontractor and define subcontractor costs |  | NA
1218 | Manufacturing | Subcontracting | Shows how to assign a subcontractor work center to a routing operation |  | NA
1219 | Manufacturing | Subcontracting | Explains how to use the subcontracting worksheet to issue purchase orders to subcontractors |  | NA
1220 | Manufacturing | Subcontracting | Describes how to post subcontracting purchase orders |  | NA
1221 | Manufacturing | Subcontracting | Shows how to review subcontracting ledger entries |  | NA
1222 | Manufacturing | Subcontracting | Reviews the Subcontractor – Dispatch List report |  | NA
1154 | Manufacturing | System Setup | Describes all fields on the Manufacturing Setup page |  | NA
1155 | Manufacturing | System Setup | Explains all fields on the item card that affect manufacturing |  | NA
1156 | Manufacturing | System Setup | Reviews all fields on the stock keeping unit card that affect manufacturing |  | NA
1157 | Manufacturing | System Setup | Describe all fields on the Manufacturing Setup page |  | NA
1158 | Manufacturing | System Setup | Explain all fields on the item card that affect manufacturing |  | NA
1159 | Manufacturing | System Setup | Review all fields on the stock keeping unit card that affect manufacturing |  | NA
1097 | Overview | Sample Company Structure | Overview of the demo company, CRONUS International |  | NA

## Objectives
S.No. | Course | Course Objectives
1 | Technical Setup | Navigate through the MS Dynamics NAV user interface
2 | Technical Setup | Understand the basic functionalities of MS Dynamics NAV
3 | Technical Setup | Personalizing the Screen for the User
4 | Technical Setup | Explain the dependencies between RapidStart Services and manual setup work
5 | Technical Setup | Describe the different components and processes of RapidStart Services
6 | Technical Setup | Explain and demonstrate all tasks in a RapidStart Services process
7 | Technical Setup | Create a configuration worksheet
8 | Technical Setup | Create a configuration package
9 | Technical Setup | Create a configuration questionnaire
10 | Technical Setup | Create a configuration template
11 | Technical Setup | Initialize a new company with a configuration package
12 | Technical Setup | Migrate customer data
13 | Technical Setup | Transfer opening balances
14 | Technical Setup | Explain how authentication works in Microsoft Dynamics NAV
15 | Technical Setup | Manage security for Windows client users
16 | Technical Setup | Set up a new user
17 | Technical Setup | Explain the concepts of permission sets and permissions
18 | Technical Setup | Create a new permission set, and assign permissions to it
19 | Technical Setup | Apply security filters in Microsoft Dynamics NAV
20 | Technical Setup | Perform user-specific setup
21 | Technical Setup | Create, assign, and work with user profiles
22 | Technical Setup | Explain the purpose of company-wide number series
23 | Technical Setup | Set up number series
24 | Technical Setup | Create number series relations
25 | Technical Setup | Explain and set up trail codes, source codes, and reason codes
26 | Technical Setup | Explain the purpose and organization of journal templates and journal batches
27 | Technical Setup | Create general journal templates and general journal batches
28 | Technical Setup | Explain and set up specific posting groups
29 | Technical Setup | Explain and set up general posting groups
30 | Technical Setup | Create a General posting setup
31 | Technical Setup | Create an Inventory posting setup
32 | Technical Setup | Explain and set up VAT posting groups
33 | Technical Setup | Create a VAT posting setup
34 | Technical Setup | Describe posting setups based on the chart of accounts
35 | Technical Setup | Demonstrate how posting groups direct a sales transaction
36 | Technical Setup | Explain and set up dimensions and dimension values
37 | Technical Setup | Explain and set up global and shortcut dimensions
38 | Technical Setup | Explain and show how dimension combinations are set up
39 | Technical Setup | Explain and show how single and multiple default dimensions are set up
40 | Technical Setup | Explain and show how account type default dimensions are set up
41 | Technical Setup | Explain and show how default dimension priorities are set up
42 | Technical Setup | Explain the possibility and resolution of conflicting default dimensions
43 | Technical Setup | Use dimension and dimension values in journals & documents under different dimension setup scenarios
44 | Technical Setup | Set up the general features of the document approval system
45 | Technical Setup | Set up approval templates
46 | Technical Setup | Set up user logons for use with document approvals
47 | Technical Setup | Set up approval users in a hierarchy
48 | Technical Setup | Set up the notification system for approvals
49 | Technical Setup | Send an approval request
50 | Technical Setup | Approve a sales or purchase document
51 | Technical Setup | Maintain substitute approvers
52 | Technical Setup | Manage overdue notifications
53 | Finance Essentials | Explain and set up the fields on the General Ledger Setup window
54 | Finance Essentials | Explain and set up Accounting Periods
55 | Finance Essentials | Explain how to use the Chart of Accounts
56 | Finance Essentials | Explain the elements of the G/L Account Card
57 | Finance Essentials | Explain the elements of the G/L Account Card ribbon
58 | Finance Essentials | Explain the elements of the Chart of Account ribbon
59 | Finance Essentials | Explain the general journal entry and posting system
60 | Finance Essentials | Create and post general journal entries
61 | Finance Essentials | Describe standard general journals
62 | Finance Essentials | Describe recurring general journals and include the fields and allocations
63 | Finance Essentials | Show how to use recurring journals with allocations and how to record accruals
64 | Finance Essentials | Explain how to reverse and correct journal entries
65 | Finance Essentials | Describe the Bank Account Card
66 | Finance Essentials | Explain the Payments FastTab on the customer card
67 | Finance Essentials | Explain the Payments FastTab on the vendor card
68 | Finance Essentials | Show how to enter and post payments received from customers, by using cash receipt journals
69 | Finance Essentials | Show how to enter and post payments to vendors by using the payment journal
70 | Finance Essentials | Explain the Suggest Vendor Payments batch job
71 | Finance Essentials | Explain how to print and post payables checks
72 | Finance Essentials | Explain and show how to financially void a check
73 | Finance Essentials | Explain how to void and reprint computer checks
74 | Finance Essentials | Explain how to apply entries to customer and vendor ledger entries
75 | Finance Essentials | Explain how to unapply entries to customer and vendor ledger entries
76 | Finance Essentials | Explain how to reverse customer ledger entries posted by using journals
77 | Finance Essentials | Review the Bank Account Reconciliation window and the options for populating the bank reconciliation lined
78 | Finance Essentials | Show how to process a bank reconciliation
79 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use payment discounts
80 | Finance Essentials | Process transactions for various situations that benefit from payment discounts
81 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use a payment discount tolerance
82 | Finance Essentials | Process transactions for various situations that benefit from using a payment discount tolerance
83 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use a payment tolerance
84 | Finance Essentials | Process transactions for various situations that benefit from using a payment tolerance
85 | Finance Essentials | Review how a payment discount tolerance and a payment tolerance are reflected in the detailed customer and vendor ledger entries
86 | Finance Essentials | Explain why and when Reminders and Finance Charge Memos are used
87 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use reminders
88 | Finance Essentials | Explain how to create and issue reminders
89 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use finance charge memos
90 | Finance Essentials | Explain how to create and issue finance charge memos
91 | Finance Essentials | Explain the different VAT calculation types
92 | Finance Essentials | Show how to reverse a VAT charge
93 | Finance Essentials | Describe how to correct a posted VAT entry
94 | Finance Essentials | Show how to record Import VAT
95 | Finance Essentials | Explain the Prices Including VAT fields on sales and purchase documents
96 | Finance Essentials | Explain how to adjust calculated VAT amounts in sales and purchase documents and journals
97 | Finance Essentials | Describe unrealized VAT
98 | Finance Essentials | Explain, create, and print a VAT Statement
99 | Finance Essentials | Explain and run the Calc and Post VAT Settlement batch job
100 | Finance Essentials | Explain the requirements for setting up prepayments
101 | Finance Essentials | Set up and assign prepayment General Ledger accounts
102 | Finance Essentials | Set up prepayment numbering for sales and purchases
103 | Finance Essentials | Set up default prepayment percentages on customers and vendors
104 | Finance Essentials | Set up default prepayment percentages for Customer-Item and Vendor-Item combinations
105 | Finance Essentials | Set up prepayment posting verification for sales and purchases
106 | Finance Essentials | Explain the prepayment processing flows for sales and purchase orders
107 | Finance Essentials | Describe the prepayment-specific fields on sales and purchase orders
108 | Finance Essentials | Create sales and purchase orders with prepayment percentages and amounts
109 | Finance Essentials | Create prepayment invoices that are from sales and purchase orders
110 | Finance Essentials | Explain the processes available to correct posted prepayment invoices
111 | Finance Essentials | Close the accounting periods for the fiscal year
112 | Finance Essentials | Explain and run the Close Income Statement batch job process
113 | Finance Essentials | Complete the closing process by posting the general journal
115 | Finance Essentials | Explain and set up Accounting Periods
116 | Finance Essentials | Review the Bank Account Reconciliation window and the options for populating the bank reconciliation lines
117 | Finance Essentials | Complete the closing process by posting the general journal
119 | Finance Advance | Set up Intrastat for use in Microsoft Dynamics NAV 2013
120 | Finance Advance | Explain how to run and submit Intrastat reports
121 | Finance Advance | Explain and demonstrate the preparation of the VAT rate change process
122 | Finance Advance | Explain and set up the VAT rate change tool
123 | Finance Advance | Explain and demonstrate how to perform a VAT rate change
124 | Finance Advance | Explain setup requirements for currencies and exchange rates when using multiple currencies
125 | Finance Advance | Explain setup requirements using multiple currencies with customers, vendors, and bank accounts
126 | Finance Advance | Describe steps and additional functionality for processing purchase and sales documents that use foreign currency
127 | Finance Advance | Describe steps and additional functionality for recording and posting multicurrency transactions in the cash receipts journal
128 | Finance Advance | Describe how to process multicurrency payments using the payments journal
129 | Finance Advance | Describe how to run the Adjust Exchange Rates batch job for customers, vendors, and bank accounts
130 | Finance Advance | Explain set up, viewing amounts, daily processing, and periodic processes when using an additionalreporting currency
131 | Finance Advance | Describe how to run the Adjust Exchange Rates batch job for G/L accounts
132 | Finance Advance | Describe how to view the Exchange Rate Adjustment Register
133 | Finance Advance | Explain the Budgets feature in Microsoft Dynamics NAV 2013
134 | Finance Advance | Explain the G/L Budgets page elements
135 | Finance Advance | Show how to set up budgets manually
136 | Finance Advance | Explain how to delete budget entries
137 | Finance Advance | Explain how to create budgets by using the Copy Budget function
138 | Finance Advance | Explain how to create budgets by using the Export Budget and Import Budget functions
139 | Finance Advance | Explain the workflow in Cost Accounting
140 | Finance Advance | Explain and set up Chart of Cost Types, Chart of Cost Centers, Chart of Cost Objects, and Cost Accounting setup
141 | Finance Advance | Explain the relationship between the cost accounting and general ledger application areas
142 | Finance Advance | Set up cost journals
143 | Finance Advance | Explain how to create cost entries either through a transfer from G/L entries or through posting the cost journal
144 | Finance Advance | Explain and set up cost budgets by using different copy functions
145 | Finance Advance | Explain the transfer from budget to actual
146 | Finance Advance | Explain and set up cost allocations
147 | Finance Advance | Explain static and dynamic allocations
148 | Finance Advance | Explain how to allocate costs and cost budgets
149 | Finance Advance | Explain the cost registers and cost budget registers
150 | Finance Advance | Explain the deletion of cost entries and cost budget entries
151 | Finance Advance | Explain different cost accounting reports
152 | Finance Advance | Provide tips and tricks
153 | Finance Advance | Explain the functions of the cash flow forecast
154 | Finance Advance | Explain the setup of the Chart of Cash Flow Account, Cash Flow Setup and Cash Flow Payment Terms
155 | Finance Advance | Explain how to create cash flow forecasts by using Cash Flow Forecast Cards and Cash Flow Manual Revenues and Expenses
156 | Finance Advance | Explain how the Cash Flow Worksheet is used
157 | Finance Advance | Review the registration of the cash flow through Cash Flow Forecast Entries
158 | Finance Advance | Explain the different Cash Flow Forecast Reporting possibilities
159 | Finance Advance | Describe filtering and analysis pages related to the chart of accounts
160 | Finance Advance | Explain how to set up an account schedule and explain other processes that relate to account schedules
161 | Finance Advance | Demonstrate cost account schedules
162 | Finance Advance | Demonstrate cash flow account schedules
163 | Finance Advance | Describe types of dimensions
164 | Finance Advance | Explain how to set up analysis views
165 | Finance Advance | Explain the process of exporting analysis views to Microsoft Office Excel 2007, and describe the elements of the exported file
166 | Finance Advance | Show how to generate analysis by dimensions and other dimension analysis reports
167 | Finance Advance | Show how to set up a Finance Performance chart
168 | Finance Advance | Explain the terminology associated with XBRL
169 | Finance Advance | Explain how to import and update taxonomies
170 | Finance Advance | Explain how to attach, update, and apply linkbases to taxonomies
171 | Finance Advance | Describe pages that are related to XBRL lines, and explain how to enter XBRL line definitions
172 | Finance Advance | Demonstrate how to export an instance document
174 | Finance Advance | Describe steps and additional functionality for recording and posting multicurrency transactions in the cash receipts journal.
175 | Finance Advance | Explain set up, viewing amounts, daily processing, and periodic processes when using an additional reporting currency.
176 | Finance Advance | Explain how to create cost entries either through a transfer from G/L entries or through posting the cost journal
177 | Finance Advance | Set up Fixed Assets
178 | Finance Advance | Perform a variety of Fixed Asset transactions
179 | Finance Advance | Reclassify Fixed Assets
180 | Finance Advance | Handle maintenance of their Fixed Assets
181 | Finance Advance | Handle insurance on their Fixed Assets
183 | Fixed Assets | Give a visual overview of a typical fixed asset life cycle.
184 | Fixed Assets | Describe the fields on the Fixed Assets setup page.
185 | Fixed Assets | Describe fixed asset posting groups.
186 | Fixed Assets | Explain depreciation books for fixed assets.
187 | Fixed Assets | Explain depreciation tables.
188 | Fixed Assets | Set up fixed assets journal templates.
189 | Fixed Assets | Set up a fixed asset card.
190 | Fixed Assets | Set up main assets with asset components.
191 | Fixed Assets | Explain how to record opening transactions.
192 | Fixed Assets | Explain how to duplicate entries to depreciation books.
193 | Fixed Assets | Explain how to copy fixed assets and FA ledger entries.
194 | Fixed Assets | Transfer a fixed asset.
195 | Fixed Assets | Split a fixed asset.
196 | Fixed Assets | Dispose of a part of a fixed asset.
197 | Fixed Assets | Combine assets.
198 | Fixed Assets | Set up maintenance information.
199 | Fixed Assets | Register maintenance costs.
200 | Fixed Assets | Review fixed asset maintenance by using the maintenance cost reports.
201 | Fixed Assets | Set up insurance information.
202 | Fixed Assets | Assign an asset to an insurance policy.
203 | Fixed Assets | Monitor insurance coverage.
204 | Fixed Assets | Update, correct, and delete insurance information.
205 | Fixed Assets | Set up insurance indexing.
207 | Trade | Review the setup of Sales Order Management. This includes customers, shipping options, reservation rules, customer posting groups, and salespeople.
208 | Trade | Explain and process sales quotes and blanket sales orders, and review sales order information.
209 | Trade | Describe how to reserve items on a sales order.
210 | Trade | Explain how to post a sales order shipment.
211 | Trade | Describe and show how to combine shipments into one invoice.
212 | Trade | Explain and demonstrate the drop shipment process.
213 | Trade | Show how to process prepayments on a sales order.
214 | Trade | Define sales prices and set up sales prices and customer price groups.
215 | Trade | Explain how to maintain sales prices by using the sales price worksheet.
216 | Trade | Describe and set up line discounts.
217 | Trade | Explain how invoice discounts are used.
218 | Trade | Describe how to set up and use item substitutions.
219 | Trade | Review the setup and use of item cross references.
220 | Trade | Explain how to set up nonstock items and create them manually.
221 | Trade | Describe how to sell nonstock items by using special orders.
223 | Trade | Review the setup of Purchase Order Management. This includes vendors, vendor posting groups, shipping and, or receiving options, and purchasers.
224 | Trade | Explain how to use purchase documents. This includes quotes, blanket orders, and purchase orders.
225 | Trade | Review purchase prices and discounts in relation to item costs.
226 | Trade | Explain purchase price setup and processing.
227 | Trade | Explain discount setup and processing.
228 | Trade | Describe how to process prepayments on a purchase order.
229 | Trade | Briefly describe requisition management setup and planning parameters.
230 | Trade | Explain the core functionality of the requisition worksheet and show how to calculate a plan and process proposed orders.
231 | Trade | Describe additional worksheet features including support for drop shipments and special orders, planning worksheet lines, and manually created lines.
232 | Trade | Describe the setup of item charges.
233 | Trade | Explain purchase item charges and show how to assign them to a posted purchase receipt.
234 | Trade | Describe sales item charges and show how to assign them to a posted sales shipment.
235 | Trade | Explain purchase and sales allowances and show how to record an item charge for a sales allowance on a credit memo.
236 | Trade | Describe the key concepts, field definitions, and date calculations for sales order promising.
237 | Trade | Explain the setup of time values and other parameters for sales order promising.
238 | Trade | Show order promising and date calculation functionality for sales order deliveries.
239 | Trade | Define the field definitions and date calculations for estimating purchase order receipts.
240 | Trade | Explain the setup of time value parameters for estimating purchase order receipts.
241 | Trade | Show how to estimate dates for purchase order receipts and the related calculations.
242 | Trade | Explain how transfer order receipts are estimated.
243 | Trade | Describe how to use the Calendars functionality to exclude nonworking days in date calculations.
244 | Trade | Describe the returns management setup for sales and purchases.
245 | Trade | Explain and show how to manage customer returns.
246 | Trade | Explain and show how to manage returns to vendors.
247 | Trade | Review assembly management setup, assembly items, and assembly bill of materials.
248 | Trade | Describe and show assemble-to-order functionality. This includes a full description of sales interface functionality, underlying links to assembly orders, and assembly quotes and blanket orders.
249 | Trade | Explain how to set up and use sales and purchase analysis reports.
250 | Trade | Show how to perform analysis by dimensions.
251 | Trade | Explain how to create and export budgets and use them in analysis reports
252 | Indian Localization | Create Structure for calculation of taxes like Excise, Value Added Tax, Service tax and other charges on sales and purchase transactions.
253 | Indian Localization | Calculate Excise on Purchase and Sale transactions.
254 | Indian Localization | Calculate Excise in case of MRP.
255 | Indian Localization | Payment of excise liability using the service tax credit.
256 | Indian Localization | Update ER 1 PLA payments and claim deferred Excise.
257 | Indian Localization | Enter the opening entry for RG23A/C part I and Part II.
258 | Indian Localization | Generate various reports related to excise including ER-1.
259 | Indian Localization | Calculate Service tax on Purchase and Sales transactions.
260 | Indian Localization | Calculate Service tax on Input Service Distributor and GTA.
261 | Indian Localization | Calculate Service tax in case of ST Pure Agent.
262 | Indian Localization | Do offline and on-line Application and Un-Application of Service tax entries.
263 | Indian Localization | Enter Service tax opening and make adjustments.
264 | Indian Localization | Pay Service Tax liability by utilizing Input Service Tax Credit and CENVAT credit.
265 | Indian Localization | Generate various reports related to Service tax including ST-3 return.
266 | Indian Localization | Calculate VAT on Purchase and Sale transactions.
267 | Indian Localization | Calculate CST on Purchase and Sale transactions.
268 | Indian Localization | Enter VAT opening and make VAT Adjustments.
269 | Indian Localization | Process VAT Settlement.
270 | Indian Localization | Generate various reports related to VAT.

## Lab Work
S. No. | Ref. No. | Course | Module | Lab Exercise
1 | 751 | Technical Setup | Manage User Rights and Profiles | Set Up New Users
2 | 766 | Technical Setup | Set Up Number Series | Create a Number Series
3 | 781 | Technical Setup | Set Up General Journals | Create a Journal Batch
4 | 793 | Technical Setup | Set Up Posting Groups | Set Up and Assign a Vendor Posting Group
5 | 793 | Technical Setup | Set Up Posting Groups | Set Up and Assign a Product Posting Group
6 | 793 | Technical Setup | Set Up Posting Groups | Copy a General Posting Setup Line
7 | 794 | Technical Setup | Set Up Posting Groups | Create and Assign a VAT Product Posting Group
8 | 794 | Technical Setup | Set Up Posting Groups | Copy a VAT Posting Setup
9 | 796 | Technical Setup | Set Up Posting Groups | Post and Review a Purchase Transaction
10 | 813 | Technical Setup | Set Up Dimensions | Set Up a Dimension with Dimension Values
11 | 813.1 | Technical Setup | Set Up Dimensions | Assign Default Dimensions to a Single Account
12 | 813.2 | Technical Setup | Set Up Dimensions | Set Up a Dimension Combination
13 | 814 | Technical Setup | Set Up Dimensions | Assign Default Dimensions to Multiple Accounts
14 | 815 | Technical Setup | Set Up Dimensions | Assign Vendor Account Type Default Dimensions
15 | 833 | Technical Setup | Set Up and Manage Document Approvals | Set Up a Purchase Document Approvals System
16 | 94 | Finance Essentials | Finance Management Setup | Accounting Periods
17 | 95 | Finance Essentials | Finance Management Setup | Create a Fiscal Year
18 | 97 | Finance Essentials | Finance Management Setup | Change the Starting Date
19 | 108 | Finance Essentials | Chart of Accounts | Create a Revenue Account
20 | 108 | Finance Essentials | Chart of Accounts | Assign a Dimension to Multiple Accounts
21 | 122 | Finance Essentials | General Journals | Create a Journal Entry
22 | 122 | Finance Essentials | General Journals | Create and Post a Recurring Journal
23 | 142 | Finance Essentials | Cash Management | Create a Bank Account
24 | 142 | Finance Essentials | Cash Management | Apply and Post Cash Receipts
25 | 144 | Finance Essentials | Cash Management | Enter, Apply, and Post the Cash Receipt Journal
26 | 145 | Finance Essentials | Cash Management | Enter and Post Manual Checks
27 | 146 | Finance Essentials | Cash Management | Enter, Apply and Post the Payment Journal Using Manual Checks
28 | 147 | Finance Essentials | Cash Management | Suggest Vendor Payments for a Single Vendor
29 | 147.1 | Finance Essentials | Cash Management | Financially Void a Check
30 | 147.2 | Finance Essentials | Cash Management | Void a Check
31 | 147.3 | Finance Essentials | Cash Management | Unapply Posted Ledger Entries
32 | 177 | Finance Essentials | Receivables and Payables Management | Post a Customer Payment with a Discount
33 | 177 | Finance Essentials | Receivables and Payables Management | Apply Posted Partial Customer Payments with Discounts
34 | 178 | Finance Essentials | Receivables and Payables Management | Set Up a Payment Tolerance
35 | 178 | Finance Essentials | Receivables and Payables Management | Process a Customer Payment Tolerance
36 | 178 | Finance Essentials | Receivables and Payables Management | Adjust the Vendor Payment Discount Amount
37 | 199 | Finance Essentials | Receivables Management | Set Up and Assign a Reminder Term
38 | 200 | Finance Essentials | Receivables Management | Create and Issue Reminders
39 | 200.1 | Finance Essentials | Receivables Management | Set Up and Assign a Finance Charge Term
40 | 200.2 | Finance Essentials | Receivables Management | Create and Issue Finance Charge Memos
41 | 239 | Finance Essentials | Prepayments | Set Up Prepayments for Sales
42 | 239 | Finance Essentials | Prepayments | Prepayment Sales Order Process with Payment Discount
43 | 240 | Finance Essentials | Prepayments | Create the Prepayment Sales Order and Process and Review the Prepayment Sales Invoice
44 | 241 | Finance Essentials | Prepayments | Adjust the Prepayment Sales Order and Process the Prepayment Sales Invoice
45 | 242 | Finance Essentials | Prepayments | Process Customer Prepayment
46 | 243 | Finance Essentials | Prepayments | Process and Review Final Invoice
47 | 244 | Finance Essentials | Prepayments | Prepayment Sales Order Process with Unrealized VAT
48 | 245 | Finance Essentials | Prepayments | Verify Unrealized VAT Setup
49 | 246 | Finance Essentials | Prepayments | Create the Prepayment Sales Order and Process and Review the Prepayment Sales Invoice
50 | 247 | Finance Essentials | Prepayments | Process and Review the Final Invoice
51 | 263 | Finance Essentials | Year End Closing Procedures | Post an Entry into a Closed Fiscal Year
52 | 383 | Finance Advance | Multicurrency | Process a Sales Invoice
53 | 383 | Finance Advance | Multicurrency | Post Expenses in Foreign Currency
54 | 383 | Finance Advance | Multicurrency | Update the USD:GBP Exchange Rate
55 | 403 | Finance Advance | Budgets | Create a budge Copy a budget
56 | 420 | Finance Advance | Cost Accounting | Using Cost Journals
57 | 420 | Finance Advance | Cost Accounting | Set Up a Cost Budget
58 | 420 | Finance Advance | Cost Accounting | Set Up Cost Allocation
59 | 445 | Finance Advance | Cash Flow Forecast | Creating a Cash Flow Forecast
60 | 447 | Finance Advance | Cash Flow Forecast | Entering Manual Revenues and Expenses
61 | 447.1 | Finance Advance | Cash Flow Forecast | Using the Cash Flow Worksheet
62 | 447.2 | Finance Advance | Cash Flow Forecast | Using the Cash Flow Worksheet
63 | 447.3 | Finance Advance | Cash Flow Forecast | Printing the Cash Flow Date List
64 | 465 | Finance Advance | Financial Reporting and Analysis | Create a Detailed Account Schedule
65 | 465.1 | Finance Advance | Financial Reporting and Analysis | Create a Cost Account Schedule
66 | 465.2 | Finance Advance | Financial Reporting and Analysis | Create a Cash Flow Account Schedule
67 | 465.3 | Finance Advance | Financial Reporting and Analysis | Create an Analysis View
68 | 465.4 | Finance Advance | Financial Reporting and Analysis | Create a Cash Flow Analysis View
69 | 466 | Finance Advance | Financial Reporting and Analysis | Export an Analysis View to Microsoft Excel
70 | 467 | Finance Advance | Financial Reporting and Analysis | Combine an Analysis View with an Account Schedule
71 | 539 | Fixed Assets | Fixed Assets Setup | Create a Fixed Asset Card
72 | 570 | Fixed Assets | Fixed Assets Transactions | Purchase a Fixed Asset Using the Purchase Invoice
73 | 571 | Fixed Assets | Fixed Assets Transactions | Post the Acquisition Cost through Purchase Invoice
74 | 572 | Fixed Assets | Fixed Assets Transactions | Increase the Cost of the Fixed Asset
75 | 573 | Fixed Assets | Fixed Assets Transactions | Post Additional Acquisition Cost
76 | 575 | Fixed Assets | Fixed Assets Transactions | Calculate and Post Depreciation
77 | 577 | Fixed Assets | Fixed Assets Transactions | Post a Write-down
78 | 579 | Fixed Assets | Fixed Assets Transactions | Dispose of a Whole Fixed Asset
79 | 581 | Fixed Assets | Fixed Assets Transactions | Cancel and Recalculate Depreciation
80 | 584 | Fixed Assets | Fixed Assets Transactions | Cancel an Entry
81 | 586 | Fixed Assets | Fixed Assets Transactions | Budget a Fixed Asset
82 | 587 | Fixed Assets | Fixed Assets Transactions | Manage a Minor Asset
83 | 612 | Fixed Assets | Fixed Asset Reclassification | Splitting a Fixed Asset & Partial disposal of an Asset
84 | 615 | Fixed Assets | Fixed Asset Reclassification | Disposing of a Part of an Asset
85 | 627 | Fixed Assets | Fixed Assets Maintenance | Posting Allocation Transactions
86 | 630 | Fixed Assets | Fixed Assets Maintenance | Posting Maintenance Transactions
87 | 1295 | Manufacturing | BOM | Create a New Production BOM and BOM Version
88 | 1325 | Manufacturing | Production Orders | Create a Firm Planned Production Order and Change It
89 | 1346 | Manufacturing | Production Order Processing | Combine Automatic and Manual Flushing
90 | 1378 | Manufacturing | Sales Order Interface and Order Planning | Use Order Planning to Create and Reserve Supply
91 | 1398 | Manufacturing | Forecasting and Planning | Create Production Forecast
92 | 1441 | Manufacturing | Planning | Plan for an Item Variant and Location SKU
93 | 1466 | Manufacturing | Subcontracting | Set up and Process a Subcontracting Operation
94 | 1580 | Trade | Sales Order Management | Create and Convert a Blanket Sales Order
95 | 1580 | Trade | Sales Order Management | Reserve an Item on a Sales Order
96 | 1580 | Trade | Sales Order Management | Ship and Invoice a Sales Order
97 | 1599 | Trade | Sales Prices and Discounts | Manage Sales PricesUpdate Sales Prices
98 | 1599 | Trade | Sales Prices and Discounts | Offer the Best Available Price to a Customer
99 | 1616 | Trade | Customer Service Features | Process a Sales Order with Item Substitutions
100 | 1616 | Trade | Customer Service Features | Process a Sales Order with Item Cross References
101 | 1630 | Trade | Purchase Order Management | Process a Purchase Quote to an Order
102 | 1630 | Trade | Purchase Order Management | Manage Alternative Purchase Prices
103 | 1630 | Trade | Purchase Order Management | Manage Purchase Line Discounts
104 | 1658 | Trade | Item Charges | Assign Freight Charges to an Open Purchase Order
105 | 1658 | Trade | Item Charges | Create an Item Charge Purchase Credit Memo
106 | 1676 | Trade | Order Prominsing | Promise Sales Order Delivery to a Customer
107 | 1676 | Trade | Order Prominsing | Purchase Order Promising
108 | 1692 | Trade | Returns Management | Process a Customer Return
109 | 1692 | Trade | Returns Management | Process a Vendor Return
110 | 1704 | Trade | Assembly Management | Create Assemble-to-Order Sales Order and Change Assembly Lines
111 | 1704 | Trade | Assembly Management | Create Partial Shipments on Sales Lines That Contain Both ATO Items and Inventory Items
112 | 1720 | Trade | Analysis and Reporting | Create an Analysis Report
113 | 1720 | Trade | Analysis and Reporting | Analyze Item Sales by Area
114 | 2001 | Indian Localization | Structure | Lab 1.1– Setup Tax/Charge Group
115 | 2002 | Indian Localization | Structure | Lab 1.2– Setup Tax/Charge Group Details
116 | 2003 | Indian Localization | Structure | Lab 1.3– Setup Structure
117 | 2004 | Indian Localization | Structure | Lab 1.4– Calculating Excise, VAT & Charges in Purchase Order with Structure
118 | 2005 | Indian Localization | Structure | Lab 1.5– Calculating Excise, VAT & Charges in Sales Order with Structure
119 | 2006 | Indian Localization | Structure | Lab 1.6– Calculating Excise, VAT & Charges in Purchase Return Order with Structure
120 | 2007 | Indian Localization | Structure | Lab 1.7– Calculating Excise, VAT & Charges in Sales Return Order with Structure
121 | 2008 | Indian Localization | Excise | Lab 2.1– Create Excise Posting Setup for New rates of Excise
122 | 2009 | Indian Localization | Excise | Lab 2.2– Calculate Excise in the Purchase Invoice
123 | 2010 | Indian Localization | Excise | Lab 2.3– Calculate Excise in the purchase invoice in case of trading
124 | 2011 | Indian Localization | Service Tax | Lab 3.1– Create Service Tax Setup for new rates of Service Tax
125 | 2012 | Indian Localization | Service Tax | Lab 3.2– Calculate Service Tax and TDS using Journal Voucher
126 | 2013 | Indian Localization | Service Tax | Lab 3.3– Calculate Service Tax and TDS using Bank Payment Voucher
127 | 2014 | Indian Localization | Service Tax | Lab 3.4– Purchase Invoice with Service Tax in case of ISD
128 | 2015 | Indian Localization | Service Tax | Lab 3.5– Calculate Service Tax using Journal Voucher
129 | 2016 | Indian Localization | Service Tax | Lab 3.6– Service Tax on Advance Payment Received from Customer
130 | 2017 | Indian Localization | Sales Tax / VAT | Lab 4.1– Create Deferment Period for the State
131 | 2018 | Indian Localization | Sales Tax / VAT | Lab 4.2– Create Tax Area
132 | 2019 | Indian Localization | Sales Tax / VAT | Lab 4.3– Create New Tax Area Location
133 | 2020 | Indian Localization | Sales Tax / VAT | Lab 4.4– Calculate VAT using Purchase Invoice
134 | 2021 | Indian Localization | Sales Tax / VAT | Lab 4.5– Calculate VAT with Retention limit defined in Tax Details level
135 | 2022 | Indian Localization | Sales Tax / VAT | Lab 4.6– Calculate VAT in case of Fixed Asset when Deferment Period is 6M
136 | 2023 | Indian Localization | Sales Tax / VAT | Lab 4.7– Calculate VAT in case of normal through Purchase Return Order
137 | 2024 | Indian Localization | Sales Tax / VAT | Lab 4.8– Calculate VAT using Sales Invoice
138 | 2025 | Indian Localization | Sales Tax / VAT | Lab 4.9– Calculate VAT using Sales Invoice with Standard Deduction
139 | 2026 | Indian Localization | Sales Tax / VAT | Lab 4.10– Calculate VAT in case of VAT Exempted option on sale of goods
140 | 2027 | Indian Localization | Sales Tax / VAT | Lab 4.11– Adjustment of VAT in case of capital item when VAT Adjustment Type is Lost or Destroy
141 | 2028 | Indian Localization | Sales Tax / VAT | Lab 4.12– Entering VAT opening in case of G/L account
142 | 2029 | Indian Localization | Sales Tax / VAT | Lab 4.13– Entering VAT opening in case of Fixed Asset
143 | 2030 | Indian Localization | Sales Tax / VAT | Lab 4.14– Entering VAT opening in case of G/L Account

## Lessons Learned
Positive
Parking Lot for topics not addressed
Topic Planning
Setting the working agreement & ground rules
Practice and examples given are good
Topic Coverage was satisfactory
Negative
Schedule not prepared and shared with participants
Recording could have happened for the sessions
Break Management not done properly
Lunch time should have been more
Improvements