## Version-Hist
Change # | Change Name | Sheet Modified | Date | Modifed By | Remarks
1 | Dates & Day Entry Col/Corrected. Status updated | Topics Covered | 2015-04-13 | Hari
2 | Planned Date/Acutal Date Concept Created | Training Plan | 2015-04-13 | Hari
3 | "Session" changed to "Day" | Training Attendees | 2015-04-13 | Hari
4 | MasterTable Sheet Created | MasterTable | 2015-04-13 | Hari
5 | Topics Covered Status update | Topics Covered | 2015-04-13 | Hari
6 | Scenarios-Trng Sheet Created and updated | Scenarios-Trng | 2015-04-14 | Hari
7 | Pivot Sheet Created | Pivot | 2015-04-14 | Hari
8 | Master-Sheet Table created | MasterTable | 2015-04-14 | Hari
9 | Training Sessions sheet updated | Training Sessions | 2015-04-14 | Hari
10 | Customization Efforts sheet created | Customization Efforts | 2015-04-14 | Hari
11 | Numbered and renamed all the sheets | All | 2015-04-14 | Hari
12 | Pivot (04) Sheet Renamed as Analysis Sheet | Analysis | 2015-04-15 | Hari
13 | Topics Covered Sheet Renamed "Training Topics" | Training Topics | 2015-04-15 | Hari
14 | Tech- C/Side topics added & Status updated in Training Topics | Training Topics | 2015-04-15 | Hari
15 | Schenarios-Trng sheet renamed to "Scenarios for Training" | Scenarios for Training | 2015-04-15 | Hari
16
17
18
19

## Master-Sheet
Sheet # | Sheet Name
01 | Training Plan
02 | Training Sessions
03 | Training Attendees
04 | Analysis
05 | Training Topics
06 | Scenarios for Training
07 | Objectives
08 | MasterTable
09 | Lab Work
10 | Lessons Learned
11 | Customization Efforts
12 | Parking Lot

## 01
Training Plan
Phase | Activity | Duration | Start Date | End Date | Act Start Date | Actual Finish Date | Status | Remarks
1 | Functional Training - Finance Essentials & Trade | 4 days | 2015-03-17 | 2015-03-20 | 2015-03-17 | 2015-03-20 | Done
Internal-1 | ISKCON to work on the Action Items and any pending decisions to be taken | 6 days | 2015-03-23 | 2015-03-28 | 2015-03-23 | 2015-03-28 | Done
2 | Functional Key User Training | 4 days | 2015-04-09 | 2015-04-15 | 2015-04-09 | 2015-04-15 | Done
Internal-2 | ISKCON users to pass entries and record scenarios which need to be addressed | 12 days | 2015-04-02 | 2015-04-17
3 | Technical Training | 3 days | 2015-04-20 | 2015-04-22 | 2015-04-13 | 2015-04-16
Deliverables
Phase | Deliverable | Who | Planned Finish Date | Actual Finish Date
1 | Training to the core team on the NAV features (essentials) | Venugopal | 2015-03-20 | 2015-03-20
1 | List of all features & reports in NAV | JNVD | 2015-03-20 | 2015-03-20
1 | List of Scenarios Discussed and the Solutions Proposed | Core Team | 2015-03-23
1 | List of Customization Required for Mandatory Features Expected | Core Team | 2015-03-23
2 | Master Data required for the administrative setup activities | Core Team
2 | Consolidated list of user stories for all trusts (GST, SST, TSG, TSF, ISK) | Core Team
2 | Check with Microsoft for getting 3 developer licenses (free of cost?) | SMVD
2 | Identify reporting requirements & map to the standard report features in NAV | Core Team
2 | Explore all features in detail | Core Team
2 | Complete the lab work connected to the different modules | Core Team
2 | Setup a system for query resolution during lab exercises | JNVD
3 | Setup the training environment with actual data | Srinivas
3 | Training to all key users on the respective modules | Core Team
Agenda
Phase | Agenda Item | Status
1 | Familarization of all modules to core team | Delivered
1 | List of customizations required | Delivered
1 | List of Masters Templates | Delivered
1 | Get List of Reports | Delivered
Internal-1 | Explore all the featuers in details Core Team
Internal-1 | Populate all masters
Internal-1 | Identify all reporting requirments by mapping to existing reports
Internal-1 | Estimate the efforts of cusomization
Internal-1 | Check with MS for Developer Licenses
Internal-1 | Check with MS for NAV 2015 Indian Version
Internal-1 | Consolidate all User Stories
Internal-1 | Consolidate all Master Data from Transaction
2 | To cover the agreed topics. | WIP
2 | To discuss the scenarios sent by finance and business team. Some of them may be a direct fit; or some of them may have some work around; | WIP
2 | Identify the customization if any and efforts | WIP
2 | To know what is required to complete the master data work | Delivered
2 | To complete the master data upload. | WIP
2 | Setup the testing environment with our sample data.
2 | Determine which the scenarios need to be deferred to the technical setup training. | Delivered
Internal-2 | Loading master data
Internal-2 | Learn configuration
Formulas:
Act Start Date = Table4[[#This Row],[Start Date]]
Actual Finish Date = Table4[[#This Row],[End Date]]

## 02
Training Sessions
S. No | Date | Start Time | End Time | Topic | Who
1 | 2015-03-17 | 10:30 | 13:30 | Overview of MS Dynamics NAV | Venugopal
|  |  |  | Finalizing the Training Methodology | Hari Prasad
2 | 2015-03-17 | 14:30 | 16:00 | Road map, methodology and team structure | JNVD
|  |  |  | Discuss the plan for next 3 days (feature mapping) | Hari Prasad
3 | 2015-03-17 | 10:00 | 18:00 | Finance Essentials | Venugopal
4 | 2015-03-18 | 10:00 | 18:00 | Trading and Manufacturing / Fixed Assets Overview | Venugopal
5 | 2015-03-19 | 10:00 | 18:00 | Finance Essentials | Venugopal
6 | 2015-03-20 | 10:00 | 13:00 | Finance Essentials | Venugopal
7 | 2015-03-20 | 14:00 | 18:00 | Trading | Venugopal
8 | 2015-04-09 | 10:00 | 14:00 |  | Vijay
9 | 2015-04-13 | 10:00 | 18:00 |  | Venugopal
10 | 2015-04-14 | 10:00 | 17:00 |  | Venugopal
11 | 2015-04-15 |  |  |  | Venugopal

## 03
Attendance Sheet | [5 empty] | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-04-09 | 2015-04-14 | 2015-04-15 | 2015-04-16
Trainee | Trust / Org | Department | Role | Mobile Number | e-Mail ID | Day-01 | Day-02 | Day-03 | Day-04 | Day-05 | Day-06 | Day-07 | Day-08
Shrihari C Vaidyakar | ISKCON | Accounts & Finance | Core Team |  | shrihari.cv@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16
Shyama Vallabha Dasa | ISKCON | Accounts & Finance | Core Team |  | smvd@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-15
Yuvaraj A | ISKCON | Accounts & Finance | Core Team | 9342928017 | yuvaraj.a@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-15
Ganesh M S | TSF-GIFT | Business Analyst | Core Team | 8884949238 | ganesh.mavathur@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16
Ayyappa Dasika | ISKCON | Information Technology | Core Team |  | ayyappa.dasika@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16
Janaki Vallabha Dasa | ISKCON | Information Technology | Core Team | 9342671724 | jnvd@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-15
Hari Prasad | VEDAVIT | PM Consultant | Core Team | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16
Nanjunda Swamy | TSF-GIFT | Purchase | Core Team | 9035792038 | nanjunda.swami@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-15
Raghavendra Rao Y | TSF-FOOD | Sales | Core Team | 9019420027 | raghavendra.rao@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14
Rashmi N | TSF-FOOD | Stores / Production | Core Team | 9663512164 | rashmi.n@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14
Basavaraj Basappa Doddamani | ISKCON | Accounts & Finance | Key User | 9481184494 | basavaraj.d@hkm-group.org | bar: 2015-03-17 to 2015-03-20; 2015-04-14
Krishna G | TSF-GIFT | Sales | Key User | bar: 2015-03-17 to 2015-03-20; 2015-04-14
Santosh P | TSF-FOOD | Sales | Key User | bar: 2015-03-17 to 2015-03-20; 2015-04-14
Pavan | VARNAAZ | Functional Training | Trainer | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-15
Srinivas | VARNAAZ | Technical Training | Trainer | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16
Venugopal | VARNAAZ | Functional Training | Trainer | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16
Vijay | VARNAAZ | Functional Training | Trainer | bar: 2015-03-17 to 2015-03-20; 2015-04-14 to 2015-04-16

## 04
Analysis
Count of Topics | Column Labels
Row Labels | Completed | Not Applicable | Parked | Remove this | (blank) | Grand Total
NA |  | 218 |  | 2 |  | 220
Phase-1 | 97 |  | 2 |  |  | 99
2015-03-17 | 4 |  |  |  |  | 4
2015-03-18 | 21 |  |  |  |  | 21
2015-03-19 | 33 |  | 2 |  |  | 35
2015-03-20 | 39 |  |  |  |  | 39
Phase-2 | 63 |  | 3 |  | 54 | 120
2015-04-09 | 14 |  |  |  |  | 14
2015-04-13 | 42 |  |  |  |  | 42
2015-04-14 | 7 |  |  |  |  | 7
2015-04-15 |  |  |  |  | 54 | 54
(blank) |  |  | 3 |  |  | 3
Phase-3 |  |  |  |  | 29 | 29
TBD |  |  |  |  | 29 | 29
Grand Total | 160 | 218 | 5 | 2 | 83 | 468

## 05
Training Topics
S. No. | Course | Module | Topics | Phase | Day | Status | (Re) Planned Date | Actual Date | Column1
617 | Finance Essentials | Chart of Accounts | Chart of Accounts Overview | Phase-1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
618 | Finance Essentials | Chart of Accounts | G/L Account Card | Phase-1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
607 | Finance Essentials | Finance Management Setup | General Ledger Setup | Phase-1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
608 | Finance Essentials | Finance Management Setup | Accounting Periods | Phase-1 | Day-01 | Completed | 2015-03-17 | 2015-03-17
2000 | Fixed Assets | Fixed Assets Setup | Fixed Assets Overview | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1413 | Trade | Analysis and Reporting | Sales and Purchase Budgets | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1397 | Trade | Assembly Management | Reservations and Item Tracking | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1316 | Trade | Customer Service Features | Item Substitutions | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1317 | Trade | Customer Service Features | Item Cross References | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1355 | Trade | Item Charges | Sales Item Charges | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1329 | Trade | Purchase Order Management | Manage Purchase Transactions | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1330 | Trade | Purchase Order Management | Purchase Prices and Discounts | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1331 | Trade | Purchase Order Management | Purchase Prices | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1332 | Trade | Purchase Order Management | Invoice and Line Discounts | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1345 | Trade | Requisition Management | Requisition Management Setup | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1346 | Trade | Requisition Management | Requisition Worksheet | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1386 | Trade | Returns Managements | Manage Customer Returns | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1286 | Trade | Sales Order Management | Set Up Sales Order Management | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1287 | Trade | Sales Order Management | Manage Sales Transactions | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1288 | Trade | Sales Order Management | Item Reservation | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1289 | Trade | Sales Order Management | Posting Orders | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1304 | Trade | Sales Prices and Discounts | Sales Prices | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1305 | Trade | Sales Prices and Discounts | Maintain Sales Prices | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1306 | Trade | Sales Prices and Discounts | Sales Line Discounts | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
1307 | Trade | Sales Prices and Discounts | Invoice Discounts | Phase-1 | Day-02 | Completed | 2015-03-18 | 2015-03-18
870 | Finance Advance | Budgets | Creating Budgets | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
871 | Finance Advance | Budgets | Copying Budgets | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
872 | Finance Advance | Budgets | Exporting and Importing Budgets | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
850 | Finance Advance | Multicurrency | Currency Card and Exchange Rates | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
851 | Finance Advance | Multicurrency | Set Up Multicurrency for Customers, Vendors, and Bank Accounts | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
642 | Finance Essentials | Cash Management - Receivables and Payables | Bank Account Overview | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
643 | Finance Essentials | Cash Management - Receivables and Payables | Customer Overview | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
644 | Finance Essentials | Cash Management - Receivables and Payables | Vendor Overview | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
645 | Finance Essentials | Cash Management - Receivables and Payables | Cash Receipt Journal and Payment Journal Overview | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
646 | Finance Essentials | Cash Management - Receivables and Payables | Suggest Vendor Payments | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
647 | Finance Essentials | Cash Management - Receivables and Payables | Print and Post Payables Checks | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
648 | Finance Essentials | Cash Management - Receivables and Payables | Voiding Checks | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
649 | Finance Essentials | Cash Management - Receivables and Payables | Applying Payments | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
650 | Finance Essentials | Cash Management - Receivables and Payables | Unapply Customer and Vendor Ledger Entries | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
651 | Finance Essentials | Cash Management - Receivables and Payables | Reversal of Posted Journals | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
675 | Finance Essentials | Cash Management - Reconciliation | Bank Reconciliation | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
676 | Finance Essentials | Cash Management - Reconciliation | Complete a Bank Reconciliation | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
619 | Finance Essentials | Chart of Accounts | G/L Account Card Ribbon | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
628 | Finance Essentials | General Journals | Creating and Posting Journal Entries | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
629 | Finance Essentials | General Journals | Standard Journals | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
630 | Finance Essentials | General Journals | Recurring Journals | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
631 | Finance Essentials | General Journals | Processing Recurring Journals | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
682 | Finance Essentials | Receivables and Paybales Management | Set Up Payment Discounts | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
683 | Finance Essentials | Receivables and Paybales Management | Process Payment Discounts | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
684 | Finance Essentials | Receivables and Paybales Management | Set Up and Process Payment Tolerances | Phase-1 | Day-03 | Parked | 2015-03-19 | 2015-03-19
685 | Finance Essentials | Receivables and Paybales Management | Review the Posted Payment Discount Tolerance and the Payment Tolerance Entries | Phase-1 | Day-03 | Parked | 2015-03-19 | 2015-03-19
686 | Finance Essentials | Receivables and Paybales Management | Review Customer and Vendor Statistics | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
769 | Finance Essentials | Year End Procedures | Closing a Fiscal Year | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
2001 | Finance Advance | Cost Accounting | Cost Accounting Overview | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
852 | Finance Advance | Multicurrency | Process Documents and Journals | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
853 | Finance Advance | Multicurrency | Adjust Exchange Rates Batch Job for Customers, Vendors, and Bank Accounts | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
854 | Finance Advance | Multicurrency | Reporting Currency | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
855 | Finance Advance | Multicurrency | View the Exchange Rate Adjustment Register | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
856 | Finance Advance | Multicurrency | Summary of Currency Exchange Rates | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
737 | Finance Essentials | Prepayments | Setting Up Prepayments | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
738 | Finance Essentials | Prepayments | Set Up Prepayment Percentages for Customers and Vendors | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
739 | Finance Essentials | Prepayments | Set Up Prepayment % for Customer-Item & Vendor-Item Combinations | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
740 | Finance Essentials | Prepayments | Set Up Prepayments Verification | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
741 | Finance Essentials | Prepayments | Prepayments Processing Flows | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
742 | Finance Essentials | Prepayments | Prepayment Sales and Purchase Orders Overview | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
743 | Finance Essentials | Prepayments | Process Prepayment Sales and Purchase Orders | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
744 | Finance Essentials | Prepayments | Prepayment Sales and Purchase Invoices | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
745 | Finance Essentials | Prepayments | Prepayment Purchase Order Process | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
699 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Reminder Terms | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
700 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Number Series for Reminders and Issue Reminders | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
701 | Finance Essentials | Receivables and Paybales Management | Create and Issue Reminders | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
702 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Finance Charge Terms | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
703 | Finance Essentials | Receivables and Paybales Management | Set Up and Assign Number Series for Finance Charge Terms | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
704 | Finance Essentials | Receivables and Paybales Management | Create and Issue Finance Charge Memos | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
705 | Finance Essentials | Receivables and Paybales Management | Calculate Interest on Reminders | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1411 | Trade | Analysis and Reporting | Analysis Views and Reports | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1412 | Trade | Analysis and Reporting | Analysis by Dimensions | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1395 | Trade | Assembly Management | Assembly Items and Assembly Bill of Materials | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1396 | Trade | Assembly Management | Assemble to Order | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1398 | Trade | Assembly Management | Selling ATO Items and Inventory Items Together | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1399 | Trade | Assembly Management | Assemble-to-Order Shipments | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1318 | Trade | Customer Service Features | Set Up and Create Nonstock Items | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1319 | Trade | Customer Service Features | Sell Nonstock Items | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1354 | Trade | Item Charges | Purchase Item Charges | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1356 | Trade | Item Charges | Purchase and Sales Allowances | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1328 | Trade | Purchase Order Management | Purchase Order Management Setup | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1333 | Trade | Purchase Order Management | Vendor Prepayments | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1347 | Trade | Requisition Management | Additional Worksheet Features | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1385 | Trade | Returns Managements | Returns Management Setup | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1387 | Trade | Returns Managements | Manage Returns to Vendors | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1290 | Trade | Sales Order Management | Drop Shipments | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
1291 | Trade | Sales Order Management | Customer Prepayments | Phase-1 | Day-04 | Completed | 2015-03-20 | 2015-03-20
138 | Config-Func | Set Up Dimensions | Dimensions and Dimension Values | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
139 | Config-Func | Set Up Dimensions | Setting Up Dimensions in General Ledger Setup | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
140 | Config-Func | Set Up Dimensions | Dimension Combinations | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
141 | Config-Func | Set Up Dimensions | Default Dimensions and Account Type Default Dimensions | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
142 | Config-Func | Set Up Dimensions | Default Dimension Priority | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
143 | Config-Func | Set Up Dimensions | Conflicting Default Dimensions | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
2002 | Finance Advance | Cash Flow Forecast | Cash Flow Forecast Overview | Phase-1 | Day-03 | Completed | 2015-03-19 | 2015-03-19
2003 | Indian Localization | Structure | Overview of structure | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2004 | Indian Localization | Structure | Basic Setup | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2005 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Purchase Order with Structure | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2006 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Sales Order with Structure | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2007 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Purchase Return Order with Structure | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2008 | Indian Localization | Structure | Calculating Excise, VAT & Charges in Sales Return Order with Structure | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2078 | Indian Localization | VAT / Sales Tax | Overview of Value Added Tax (VAT) | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2079 | Indian Localization | VAT / Sales Tax | Basic Setup | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2080 | Indian Localization | VAT / Sales Tax | Calculating VAT on purchase of goods | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2083 | Indian Localization | VAT / Sales Tax | Calculating VAT able Purchase Tax on CST | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2084 | Indian Localization | VAT / Sales Tax | Calculating VAT if Purchases are meant for Export or Deemed Export | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
2087 | Indian Localization | VAT / Sales Tax | Calculating VAT in case of Sales Order | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
885 | Finance Advance | Cost Accounting | Cost Entries | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
887 | Finance Advance | Cost Accounting | Cost Allocation | Phase-2 | Day-05 | Completed | 2015-04-09 | 2015-04-09
928 | Finance Advance | Financial Reporting and Analysis | Analyze the Chart of Accounts | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
929 | Finance Advance | Financial Reporting and Analysis | Account Schedules | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
930 | Finance Advance | Financial Reporting and Analysis | Analysis by Dimensions | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
931 | Finance Advance | Financial Reporting and Analysis | Export Analysis Views to Microsoft Excel | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
932 | Finance Advance | Financial Reporting and Analysis | Dimension-Based Reports | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
933 | Finance Advance | Financial Reporting and Analysis | Combine Analysis Views with Account Schedules | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1077 | Fixed Assets | Fixed Asset Insurance | Setting Up Insurance Information | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1078 | Fixed Assets | Fixed Asset Insurance | Attaching Assets to Insurance Policies | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1079 | Fixed Assets | Fixed Asset Insurance | Monitoring Insurance Coverage | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1080 | Fixed Assets | Fixed Asset Insurance | Updating Insurance Information | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1050 | Fixed Assets | Fixed Asset Reclassification | Asset Transfers | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1051 | Fixed Assets | Fixed Asset Reclassification | Combining Assets | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1001 | Fixed Assets | Fixed Asset Transactions | Journals for Fixed Assets | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1002 | Fixed Assets | Fixed Asset Transactions | Purchase Fixed Assets | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1003 | Fixed Assets | Fixed Asset Transactions | Calculate and Post Depreciation | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1004 | Fixed Assets | Fixed Asset Transactions | Write-down and Appreciation of Fixed Assets | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1005 | Fixed Assets | Fixed Asset Transactions | Fixed Asset Disposals | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1006 | Fixed Assets | Fixed Asset Transactions | Correct an Entry | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1007 | Fixed Assets | Fixed Asset Transactions | Document Fixed Asset Transactions | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1008 | Fixed Assets | Fixed Asset Transactions | Fixed Asset Reports | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1009 | Fixed Assets | Fixed Asset Transactions | Budget Fixed Asset Transactions | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1012 | Fixed Assets | Fixed Asset Transactions | Minor Assets | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1064 | Fixed Assets | Fixed Assets Maintenance | Setting Up Maintenance Information | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1065 | Fixed Assets | Fixed Assets Maintenance | Maintenance Registration and Costs | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1066 | Fixed Assets | Fixed Assets Maintenance | Maintenance Cost Reporting | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
975 | Fixed Assets | Fixed Assets Setup | Fixed Assets Process Flow | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
976 | Fixed Assets | Fixed Assets Setup | Fixed Assets Setup | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
977 | Fixed Assets | Fixed Assets Setup | Fixed Assets Posting Groups | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
978 | Fixed Assets | Fixed Assets Setup | Depreciation Books | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
979 | Fixed Assets | Fixed Assets Setup | Fixed Asset Card | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
980 | Fixed Assets | Fixed Assets Setup | Fixed Asset Allocation Keys | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
981 | Fixed Assets | Fixed Assets Setup | Main Assets and Asset Components | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
983 | Fixed Assets | Fixed Assets Setup | Make Duplicate Entries | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
984 | Fixed Assets | Fixed Assets Setup | Copy Fixed Assets and FA Ledger Entries | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1365 | Trade | Order Promising | Sales Order Promising Definitions and Calculations | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1366 | Trade | Order Promising | Date Calculation Setup for Sales Orders | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1367 | Trade | Order Promising | Promising Sales Order Delivery | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1368 | Trade | Order Promising | Purchase Order Promising Definitions and Calculations | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1369 | Trade | Order Promising | Date Calculation Setup for Purchase Orders | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1370 | Trade | Order Promising | Estimating Purchase Order Receipts | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1371 | Trade | Order Promising | Estimate a Transfer Order Receipt | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
1372 | Trade | Order Promising | Calendars | Phase-2 | Day-06 | Completed | 2015-04-13 | 2015-04-13
909 | Finance Advance | Cash Flow Forecast | Functions of the Cash Flow Forecast | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
910 | Finance Advance | Cash Flow Forecast | Setting Up Cash Flow Forecasts | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
911 | Finance Advance | Cash Flow Forecast | Creating Cash Flow Forecasts | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
912 | Finance Advance | Cash Flow Forecast | Cash Flow Forecast Reporting | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
884 | Finance Advance | Cost Accounting | Setting Up Cost Accounting | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
886 | Finance Advance | Cost Accounting | Cost Budgets | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
889 | Finance Advance | Cost Accounting | Cost Accounting Reporting | Phase-2 | Day-07 | Completed | 2015-04-14 | 2015-04-14
2097 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of capital goods containing VAT deferment with Settled Period | Phase-2 |  | Parked
2098 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of capital goods containing VAT deferment without Settled period | Phase-2 |  | Parked
888 | Finance Advance | Cost Accounting | Cost Accounting History | Phase-2 |  | Parked
2040 | Indian Localization | Service Tax | Overview of Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2041 | Indian Localization | Service Tax | Basic Setup | Phase-2 | Day-08 |  | 2015-04-15
2042 | Indian Localization | Service Tax | Calculating Service Tax and TDS using Journal Voucher | Phase-2 | Day-08 |  | 2015-04-15
2043 | Indian Localization | Service Tax | Service Tax Implication while Making Payment to Vendor against Invoice | Phase-2 | Day-08 |  | 2015-04-15
2044 | Indian Localization | Service Tax | Calculating Service Tax and TDS using Bank Payment Voucher for Advance Payments | Phase-2 | Day-08 |  | 2015-04-15
2045 | Indian Localization | Service Tax | Service Tax Implication while creating Invoice against Advance Payment | Phase-2 | Day-08 |  | 2015-04-15
2046 | Indian Localization | Service Tax | Service Tax Implication by Applying Advance Payment and Invoice from Vendor Ledger Entry | Phase-2 | Day-08 |  | 2015-04-15
2047 | Indian Localization | Service Tax | Service Tax Implication by Applying Normal Payment and Invoice from Vendor Ledger Entry | Phase-2 | Day-08 |  | 2015-04-15
2048 | Indian Localization | Service Tax | Reversal of Bank Payment Voucher which includes Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2049 | Indian Localization | Service Tax | Purchase Invoice with CENVAT taken on Inputs | Phase-2 | Day-08 |  | 2015-04-15
2050 | Indian Localization | Service Tax | Purchase Invoice with CENVAT taken on Capital Goods | Phase-2 | Day-08 |  | 2015-04-15
2051 | Indian Localization | Service Tax | Credit Received from Inter Unit Transfer by a LTU | Phase-2 | Day-08 |  | 2015-04-15
2052 | Indian Localization | Service Tax | Purchase Invoice with Service Tax in case of Input Service Distributor | Phase-2 | Day-08 |  | 2015-04-15
2053 | Indian Localization | Service Tax | Service Tax Distribution | Phase-2 | Day-08 |  | 2015-04-15
2054 | Indian Localization | Service Tax | GTA Transaction in case of Service Receiver | Phase-2 | Day-08 |  | 2015-04-15
2055 | Indian Localization | Service Tax | Refund of Advance Payment from Vendor with Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2056 | Indian Localization | Service Tax | Purchase Credit Memo with Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2057 | Indian Localization | Service Tax | Calculating Service Tax using Journal Voucher | Phase-2 | Day-08 |  | 2015-04-15
2058 | Indian Localization | Service Tax | Service Tax Implication while Receiving Payment from Customer | Phase-2 | Day-08 |  | 2015-04-15
2059 | Indian Localization | Service Tax | Calculating Service Tax on Advance Payment Received from Customer | Phase-2 | Day-08 |  | 2015-04-15
2060 | Indian Localization | Service Tax | Service Tax Implication while creating Invoice against Advance Payment | Phase-2 | Day-08 |  | 2015-04-15
2061 | Indian Localization | Service Tax | Service Tax Implication by Applying Advance Payment and Invoice from Customer Ledger Entry | Phase-2 | Day-08 |  | 2015-04-15
2062 | Indian Localization | Service Tax | Service Tax Implication by Applying Normal Payment and Invoice from Customer Ledger Entry | Phase-2 | Day-08 |  | 2015-04-15
2063 | Indian Localization | Service Tax | Reversal of Bank Receipt Voucher which includes Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2064 | Indian Localization | Service Tax | Export of Services using Sales Invoice | Phase-2 | Day-08 |  | 2015-04-15
2065 | Indian Localization | Service Tax | Sale of Exempted Services | Phase-2 | Day-08 |  | 2015-04-15
2066 | Indian Localization | Service Tax | ST Pure Agent | Phase-2 | Day-08 |  | 2015-04-15
2067 | Indian Localization | Service Tax | Calculating Service Tax with Abatement Percentage | Phase-2 | Day-08 |  | 2015-04-15
2068 | Indian Localization | Service Tax | Refund of Advance Payment to Customer with Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2069 | Indian Localization | Service Tax | Sales Credit Memo with Service Tax | Phase-2 | Day-08 |  | 2015-04-15
2070 | Indian Localization | Service Tax | Calculation of Service Tax on Direct Payments/Receipts | Phase-2 | Day-08 |  | 2015-04-15
2071 | Indian Localization | Service Tax | Service Tax Implication while applying Invoice and Payment with different Currency Exchange Rates | Phase-2 | Day-08 |  | 2015-04-15
2072 | Indian Localization | Service Tax | Service Tax Opening | Phase-2 | Day-08 |  | 2015-04-15
2073 | Indian Localization | Service Tax | Service Tax Adjustment | Phase-2 | Day-08 |  | 2015-04-15
2074 | Indian Localization | Service Tax | Adjust Service Tax Credit | Phase-2 | Day-08 |  | 2015-04-15
2075 | Indian Localization | Service Tax | Service Tax Payment | Phase-2 | Day-08 |  | 2015-04-15
2076 | Indian Localization | Service Tax | ST3 Removed as such/LTU Dtls | Phase-2 | Day-08 |  | 2015-04-15
2077 | Indian Localization | Service Tax | Service Tax Reports | Phase-2 | Day-08 |  | 2015-04-15
2081 | Indian Localization | VAT / Sales Tax | Calculating VAT if vendor has opted for Composition scheme | Phase-2 | Day-08 |  | 2015-04-15
2082 | Indian Localization | VAT / Sales Tax | Calculating VAT if Retention limit is defined in the Tax Jurisdiction setup with Non ITC claimable Usage% defined | Phase-2 | Day-08 |  | 2015-04-15
2085 | Indian Localization | VAT / Sales Tax | Calculating VAT in case of capital item if deferment period is 1Y in the States setup with a checkmark in the Financial Year field | Phase-2 | Day-08 |  | 2015-04-15
2086 | Indian Localization | VAT / Sales Tax | Calculating VAT in Purchase Credit Memo in case of normal item | Phase-2 | Day-08 |  | 2015-04-15
2088 | Indian Localization | VAT / Sales Tax | Calculating VAT if standard deduction% is defined in the Tax Detail setup | Phase-2 | Day-08 |  | 2015-04-15
2089 | Indian Localization | VAT / Sales Tax | Calculating VAT on sale of goods in case of VAT exempted or Export or Deemed Export | Phase-2 | Day-08 |  | 2015-04-15
2090 | Indian Localization | VAT / Sales Tax | Calculating CST on sale of goods using sales order | Phase-2 | Day-08 |  | 2015-04-15
2091 | Indian Localization | VAT / Sales Tax | Calculating VAT as per multiple tax jurisdictions in case of normal item | Phase-2 | Day-08 |  | 2015-04-15
2092 | Indian Localization | VAT / Sales Tax | Adjustment of VAT (Lot no. wise) in case of normal item when VAT Adjustment type is Lost/Destroy | Phase-2 | Day-08 |  | 2015-04-15
2093 | Indian Localization | VAT / Sales Tax | Adjustment of VAT (Serial No. Wise) in case of normal item When VAT Adjustment type is Consumed | Phase-2 | Day-08 |  | 2015-04-15
2094 | Indian Localization | VAT / Sales Tax | Adjustment of VAT in case of Partial Branch Transfers through VAT Adjustment Journal | Phase-2 | Day-08 |  | 2015-04-15
2095 | Indian Localization | VAT / Sales Tax | Adjustment of VAT in case of change in usage through VAT Adjustment Journal | Phase-2 | Day-08 |  | 2015-04-15
2100 | Indian Localization | VAT / Sales Tax | Calculating VAT through Purchase Credit Memo in case of Fixed Asset | Phase-2 | Day-08 |  | 2015-04-15
2101 | Indian Localization | VAT / Sales Tax | Calculating VAT through Sales Credit Memo | Phase-2 | Day-08 |  | 2015-04-15
2102 | Indian Localization | VAT / Sales Tax | VAT Settlement | Phase-2 | Day-08 |  | 2015-04-15
2103 | Indian Localization | VAT / Sales Tax | VAT Reporting | Phase-2 | Day-08 |  | 2015-04-15
73 | Config-Tech | Manage User Rights and Profiles | Authentication | Phase-3 |  |  | TBD
74 | Config-Tech | Manage User Rights and Profiles | Set Up User Rights | Phase-3 |  |  | TBD
75 | Config-Tech | Manage User Rights and Profiles | Create a New Permission Set | Phase-3 |  |  | TBD
76 | Config-Tech | Manage User Rights and Profiles | Apply Security Filters | Phase-3 |  |  | TBD
77 | Config-Tech | Manage User Rights and Profiles | User-Specific Setup | Phase-3 |  |  | TBD
78 | Config-Tech | Manage User Rights and Profiles | User Profile Setup | Phase-3 |  |  | TBD
79 | Config-Tech | Manage User Rights and Profiles | Best Practices | Phase-3 |  |  | TBD
54 | Config-Tech | Set Up a Company by Using RapidStart Services | Manual Setup vs RapidStart Services | Phase-3 |  |  | TBD
55 | Config-Tech | Set Up a Company by Using RapidStart Services | Rapid Start Services Process Flow | Phase-3 |  |  | TBD
56 | Config-Tech | Set Up a Company by Using RapidStart Services | Create and Export a Configuration Package | Phase-3 |  |  | TBD
57 | Config-Tech | Set Up a Company by Using RapidStart Services | Configure a New Company by Using RapidStart Services | Phase-3 |  |  | TBD
58 | Config-Tech | Set Up a Company by Using RapidStart Services | Data Migration by Using Rapid Start Services | Phase-3 |  |  | TBD
59 | Config-Tech | Set Up a Company by Using RapidStart Services | Transfer Opening Balances by Using RapidStart Services | Phase-3 |  |  | TBD
160 | Config-Tech | Set Up and Manage Document Approvals | Set Up Document Approvals | Phase-3 |  |  | TBD
161 | Config-Tech | Set Up and Manage Document Approvals | Set Up the Notification System | Phase-3 |  |  | TBD
162 | Config-Tech | Set Up and Manage Document Approvals | Set Up a Sales Document Approvals System | Phase-3 |  |  | TBD
163 | Config-Tech | Set Up and Manage Document Approvals | Use the Document Approval System | Phase-3 |  |  | TBD
109 | Config-Tech | Set Up General Journals Templates and Batches | Journal Templates, Batches, and Lines | Phase-3 |  |  | TBD
110 | Config-Tech | Set Up General Journals Templates and Batches | Create Journal Templates and Batches | Phase-3 |  |  | TBD
95 | Config-Func | Set Up Number Series | Number Series | Phase-3 |  |  | TBD
117 | Config-Func | Set Up Posting Groups | Specific Posting Groups | Phase-3 |  |  | TBD
118 | Config-Func | Set Up Posting Groups | General Posting Groups | Phase-3 |  |  | TBD
119 | Config-Func | Set Up Posting Groups | General Posting Setup | Phase-3 |  |  | TBD
120 | Config-Func | Set Up Posting Groups | VAT Posting Groups | Phase-3 |  |  | TBD
121 | Config-Func | Set Up Posting Groups | VAT Posting Setup | Phase-3 |  |  | TBD
122 | Config-Func | Set Up Posting Groups | Best Practices | Phase-3 |  |  | TBD
123 | Config-Func | Set Up Posting Groups | Post and Review a Sales Transaction | Phase-3 |  |  | TBD
103 | Config-Func | Set Up Trail Codes | Source Code and Reason Codes | Phase-3 |  |  | TBD
104 | Config-Func | Set Up Trail Codes | Navigate the Audit Trail | Phase-3 |  |  | TBD
934 | Finance Advance | Financial Reporting and Analysis | Finance Performance Charts | NA | NA | Not Applicable | NA
1010 | Fixed Assets | Fixed Asset Transactions | Cost Accounting Depreciation | NA | NA | Not Applicable | NA
883 | Finance Advance | Cost Accounting | Workflow in Cost Accounting | NA | NA | Not Applicable | NA
890 | Finance Advance | Cost Accounting | Tips and Tricks | NA | NA | Remove this | NA
1081 | Fixed Assets | Fixed Asset Insurance | Indexing Insurance | NA | NA | Not Applicable | NA
1011 | Fixed Assets | Fixed Asset Transactions | Indexation | NA | NA | Not Applicable | NA
982 | Fixed Assets | Fixed Assets Setup | Record Open Transactions | NA | NA | Remove this | NA
2096 | Indian Localization | VAT / Sales Tax | Entering VAT opening in case of normal item | NA | NA | Not Applicable | NA
2099 | Indian Localization | VAT / Sales Tax | Entering VAT opening on sale of goods | NA | NA | Not Applicable | NA
833 | Finance Advance | Intrastat | Set up Intrastat | NA | NA | Not Applicable | NA
834 | Finance Advance | Intrastat | Report Intrastat | NA | NA | Not Applicable | NA
841 | Finance Advance | VAT Rate Change | Prepare for VAT Rate Change Tool | NA | NA | Not Applicable | NA
842 | Finance Advance | VAT Rate Change | Set Up Using VAT Rate Change Tool | NA | NA | Not Applicable | NA
843 | Finance Advance | VAT Rate Change | Perform VAT Rate Conversions | NA | NA | Not Applicable | NA
954 | Finance Advance | XBRL | XBRL Terminology | NA | NA | Not Applicable | NA
955 | Finance Advance | XBRL | XBRL Specifications and Taxonomies | NA | NA | Not Applicable | NA
956 | Finance Advance | XBRL | Work with Linkbases | NA | NA | Not Applicable | NA
957 | Finance Advance | XBRL | Enter XBRL Line Definitions | NA | NA | Not Applicable | NA
958 | Finance Advance | XBRL | Export the XBRL Lines | NA | NA | Not Applicable | NA
718 | Finance Essentials | VAT | VAT Calculation Types | NA | NA | Not Applicable | NA
719 | Finance Essentials | VAT | Display VAT Amounts in Sales and Purchase Documents | NA | NA | Not Applicable | NA
720 | Finance Essentials | VAT | Manually Adjust VAT Amounts in Sales and Purchase Documents and Journals | NA | NA | Not Applicable | NA
721 | Finance Essentials | VAT | Unrealized VAT | NA | NA | Not Applicable | NA
722 | Finance Essentials | VAT | VAT Statements | NA | NA | Not Applicable | NA
723 | Finance Essentials | VAT | VAT Settlement | NA | NA | Not Applicable | NA
1232 | Manufacturing | Advanced Capacity | Explains how to set up work centers and machine centers | NA | NA | Not Applicable | NA
1233 | Manufacturing | Advanced Capacity | Shows how to set up shop calendars and capacity calendars | NA | NA | Not Applicable | NA
1234 | Manufacturing | Advanced Capacity | Describes registered absences and how to use them | NA | NA | Not Applicable | NA
1235 | Manufacturing | Advanced Capacity | Explains how to use capacity journals | NA | NA | Not Applicable | NA
1117 | Manufacturing | Basic Capacities and Routings | Explains how to set up capacity | NA | NA | Not Applicable | NA
1118 | Manufacturing | Basic Capacities and Routings | Shows how to create routings | NA | NA | Not Applicable | NA
1119 | Manufacturing | Basic Capacities and Routings | Describes the advanced features for routings | NA | NA | Not Applicable | NA
1120 | Manufacturing | Basic Capacities and Routings | Reviews the standard capacity and routing reports | NA | NA | Not Applicable | NA
1169 | Manufacturing | Forecasting and Planning | Describe the production forecast functionality | NA | NA | Not Applicable | NA
1170 | Manufacturing | Forecasting and Planning | Explain the integration between production forecasting and planning | NA | NA | Not Applicable | NA
1171 | Manufacturing | Forecasting and Planning | Show how actual demand is netted against forecast demand | NA | NA | Not Applicable | NA
1172 | Manufacturing | Forecasting and Planning | Describe forecasting by location, order tracking as it relates to forecasting, and forecasting setup | NA | NA | Not Applicable | NA
1173 | Manufacturing | Forecasting and Planning | Review the forecast reports | NA | NA | Not Applicable | NA
1253 | Manufacturing | Manufacturing - Additional Topics | Describes standard tasks and how to use them | NA | NA | Not Applicable | NA
1254 | Manufacturing | Manufacturing - Additional Topics | Explains stop codes and how to use them | NA | NA | Not Applicable | NA
1255 | Manufacturing | Manufacturing - Additional Topics | Reviews the various options for recording scrap and the relationships between the options | NA | NA | Not Applicable | NA
1256 | Manufacturing | Manufacturing - Additional Topics | Defines non-productive time and shows how to use it in a production order | NA | NA | Not Applicable | NA
1257 | Manufacturing | Manufacturing - Additional Topics | Shows how to reduce lead time | NA | NA | Not Applicable | NA
1258 | Manufacturing | Manufacturing - Additional Topics | Consumption journal entries and output journal entries for multilevel production orders | NA | NA | Not Applicable | NA
1259 | Manufacturing | Manufacturing - Additional Topics | Defines production families and shows how to use them in a production order | NA | NA | Not Applicable | NA
1260 | Manufacturing | Manufacturing - Additional Topics | Describes standard tasks and how to use them | NA | NA | Not Applicable | NA
1261 | Manufacturing | Manufacturing - Additional Topics | Explains stop codes and how to use them | NA | NA | Not Applicable | NA
1262 | Manufacturing | Manufacturing - Additional Topics | Reviews the various options for recording scrap and the relationships between the options | NA | NA | Not Applicable | NA
1263 | Manufacturing | Manufacturing - Additional Topics | Defines non-productive time and shows how to use it in a production order | NA | NA | Not Applicable | NA
1264 | Manufacturing | Manufacturing - Additional Topics | Shows how to reduce lead time | NA | NA | Not Applicable | NA
1265 | Manufacturing | Manufacturing - Additional Topics | Consumption journal entries and output journal entries for multilevel production orders | NA | NA | Not Applicable | NA
1266 | Manufacturing | Manufacturing - Additional Topics | Defines production families and shows how to use them in a production order | NA | NA | Not Applicable | NA
1182 | Manufacturing | Planning | Describes the general concepts of the planning system | NA | NA | Not Applicable | NA
1183 | Manufacturing | Planning | Introduces the planning worksheet and related functions | NA | NA | Not Applicable | NA
1184 | Manufacturing | Planning | Explains how to use regenerative planning | NA | NA | Not Applicable | NA
1185 | Manufacturing | Planning | Shows how to use net change planning | NA | NA | Not Applicable | NA
1186 | Manufacturing | Planning | Describes how parameters affect the planning process | NA | NA | Not Applicable | NA
1187 | Manufacturing | Planning | Explains how to use order tracking and action messages | NA | NA | Not Applicable | NA
1188 | Manufacturing | Planning | Describes the general concepts of the planning system | NA | NA | Not Applicable | NA
1189 | Manufacturing | Planning | Introduces the planning worksheet and related functions | NA | NA | Not Applicable | NA
1190 | Manufacturing | Planning | Explains how to use regenerative planning | NA | NA | Not Applicable | NA
1191 | Manufacturing | Planning | Shows how to use net change planning | NA | NA | Not Applicable | NA
1192 | Manufacturing | Planning | Describes how parameters affect the planning process | NA | NA | Not Applicable | NA
1193 | Manufacturing | Planning | Explains how to use order tracking and action messages | NA | NA | Not Applicable | NA
1196 | Manufacturing | Planning - Additional Topics | Defines item variants | NA | NA | Not Applicable | NA
1197 | Manufacturing | Planning - Additional Topics | Explains how to use locations in planning | NA | NA | Not Applicable | NA
1198 | Manufacturing | Planning - Additional Topics | Shows how to perform transfers between locations | NA | NA | Not Applicable | NA
1199 | Manufacturing | Planning - Additional Topics | Describes how to use blanket sales orders in planning | NA | NA | Not Applicable | NA
1200 | Manufacturing | Planning - Additional Topics | Explains how to use multilevel production orders | NA | NA | Not Applicable | NA
1201 | Manufacturing | Planning - Additional Topics | Reviews how to filter the planning worksheet | NA | NA | Not Applicable | NA
1202 | Manufacturing | Planning - Additional Topics | Shows how to change the replenishment system for a planning line | NA | NA | Not Applicable | NA
1203 | Manufacturing | Planning - Additional Topics | Describes how to refresh planning lines | NA | NA | Not Applicable | NA
1204 | Manufacturing | Planning - Additional Topics | Identifies the available planning reports | NA | NA | Not Applicable | NA
1108 | Manufacturing | Production Bill of Materials | Describes the production BOM structure and its basic features | NA | NA | Not Applicable | NA
1109 | Manufacturing | Production Bill of Materials | Explains and demonstrates production BOM advanced features | NA | NA | Not Applicable | NA
1110 | Manufacturing | Production Bill of Materials | Shows production BOM reports | NA | NA | Not Applicable | NA
1143 | Manufacturing | Production Order Processing | Reviews the flow of events as production orders move from release until they are finished | NA | NA | Not Applicable | NA
1144 | Manufacturing | Production Order Processing | Options and procedures related to material consumption and production output | NA | NA | Not Applicable | NA
1145 | Manufacturing | Production Order Processing | Shows how to pick components and put away finished goods in the warehouse | NA | NA | Not Applicable | NA
1146 | Manufacturing | Production Order Processing | Explains the uses of the consumption journal, output journal, and production journal | NA | NA | Not Applicable | NA
1128 | Manufacturing | Production Orders | Describes the different production order statuses | NA | NA | Not Applicable | NA
1129 | Manufacturing | Production Orders | Explains how to create and schedule a production order | NA | NA | Not Applicable | NA
1130 | Manufacturing | Production Orders | Different types of changes that you can make to a production order | NA | NA | Not Applicable | NA
1131 | Manufacturing | Production Orders | Shows how to use the Production Order batch job | NA | NA | Not Applicable | NA
1133 | Manufacturing | Production Orders | Reviews the production order listings and reports | NA | NA | Not Applicable | NA
1132 | Manufacturing | Production Orders - Additional Topics | Reservations, statistics, phantom BOMs, and manufacturing batch units of measure | NA | NA | Not Applicable | NA
1162 | Manufacturing | Sales Order Interface and Order Planning | Describes and demonstrates all aspects of sales order planning | NA | NA | Not Applicable | NA
1163 | Manufacturing | Sales Order Interface and Order Planning | Explains and demonstrates all aspects of order planning | NA | NA | Not Applicable | NA
1098 | Manufacturing | Sample Company Structure | Explains how to set the working date | NA | NA | Not Applicable | NA
1099 | Manufacturing | Sample Company Structure | Shows how to change the default profile to Production Planner | NA | NA | Not Applicable | NA
1100 | Manufacturing | Sample Company Structure | Describes license information | NA | NA | Not Applicable | NA
1243 | Manufacturing | Shop Loading | Describes the basic tools that are used to manage shop loading | NA | NA | Not Applicable | NA
1244 | Manufacturing | Shop Loading | Explains how to manage shop loading by assuming infinite capacity | NA | NA | Not Applicable | NA
1245 | Manufacturing | Shop Loading | Shows how to manage shop loading by using finite capacity | NA | NA | Not Applicable | NA
1246 | Manufacturing | Shop Loading | Reviews the reports that are related to shop loading | NA | NA | Not Applicable | NA
1247 | Manufacturing | Shop Loading | Describes the basic tools that are used to manage shop loading | NA | NA | Not Applicable | NA
1248 | Manufacturing | Shop Loading | Explains how to manage shop loading by assuming infinite capacity | NA | NA | Not Applicable | NA
1249 | Manufacturing | Shop Loading | Shows how to manage shop loading by using finite capacity | NA | NA | Not Applicable | NA
1250 | Manufacturing | Shop Loading | Reviews the reports that are related to shop loading | NA | NA | Not Applicable | NA
1217 | Manufacturing | Subcontracting | Describes how to set up a subcontractor and define subcontractor costs | NA | NA | Not Applicable | NA
1218 | Manufacturing | Subcontracting | Shows how to assign a subcontractor work center to a routing operation | NA | NA | Not Applicable | NA
1219 | Manufacturing | Subcontracting | Explains how to use the subcontracting worksheet to issue purchase orders to subcontractors | NA | NA | Not Applicable | NA
1220 | Manufacturing | Subcontracting | Describes how to post subcontracting purchase orders | NA | NA | Not Applicable | NA
1221 | Manufacturing | Subcontracting | Shows how to review subcontracting ledger entries | NA | NA | Not Applicable | NA
1222 | Manufacturing | Subcontracting | Reviews the Subcontractor – Dispatch List report | NA | NA | Not Applicable | NA
1154 | Manufacturing | System Setup | Describes all fields on the Manufacturing Setup page | NA | NA | Not Applicable | NA
1155 | Manufacturing | System Setup | Explains all fields on the item card that affect manufacturing | NA | NA | Not Applicable | NA
1156 | Manufacturing | System Setup | Reviews all fields on the stock keeping unit card that affect manufacturing | NA | NA | Not Applicable | NA
1157 | Manufacturing | System Setup | Describe all fields on the Manufacturing Setup page | NA | NA | Not Applicable | NA
1158 | Manufacturing | System Setup | Explain all fields on the item card that affect manufacturing | NA | NA | Not Applicable | NA
1159 | Manufacturing | System Setup | Review all fields on the stock keeping unit card that affect manufacturing | NA | NA | Not Applicable | NA
1097 | Overview | Sample Company Structure | Overview of the demo company, CRONUS International | NA | NA | Not Applicable | NA
2009 | Indian Localization | Excise | Overview of Excise | NA | NA | Not Applicable | NA
2010 | Indian Localization | Excise | Basic Setup | NA | NA | Not Applicable | NA
2011 | Indian Localization | Excise | Excise Calculation in Purchase order or Purchase Return order for CENVAT Items | NA | NA | Not Applicable | NA
2012 | Indian Localization | Excise | Excise Calculation in case of Capital Goods | NA | NA | Not Applicable | NA
2013 | Indian Localization | Excise | Excise calculation in case of Imported goods in Purchase Invoice and Return Order | NA | NA | Not Applicable | NA
2014 | Indian Localization | Excise | Excise Refund and Excise loading on Inventory | NA | NA | Not Applicable | NA
2015 | Indian Localization | Excise | Output entries for finished goods | NA | NA | Not Applicable | NA
2016 | Indian Localization | Excise | Excise calculation in Sales order or Sales invoice | NA | NA | Not Applicable | NA
2017 | Indian Localization | Excise | Supplementary Invoice | NA | NA | Not Applicable | NA
2018 | Indian Localization | Excise | Sales Cancellation | NA | NA | Not Applicable | NA
2019 | Indian Localization | Excise | Excise Calculation in Case of Sale of Capital Goods | NA | NA | Not Applicable | NA
2020 | Indian Localization | Excise | Excise Calculation in free sample given to Customer | NA | NA | Not Applicable | NA
2021 | Indian Localization | Excise | Sale of Goods which are Returned | NA | NA | Not Applicable | NA
2022 | Indian Localization | Excise | Depositing of PLA amount and creating of excise charge liability using the Tax Journal | NA | NA | Not Applicable | NA
2023 | Indian Localization | Excise | Direct debit to PLA/RG in Sales Invoice | NA | NA | Not Applicable | NA
2024 | Indian Localization | Excise | Excise Calculation in case Goods removed as such | NA | NA | Not Applicable | NA
2025 | Indian Localization | Excise | Excise Calculation in Sales Invoice as per MRP Provision of the Excise Act | NA | NA | Not Applicable | NA
2026 | Indian Localization | Excise | Transfer of Intermediate Goods from one Location to another Location | NA | NA | Not Applicable | NA
2027 | Indian Localization | Excise | Transfer of Raw material from one Location to another Location | NA | NA | Not Applicable | NA
2028 | Indian Localization | Excise | Calculation of Excise duty in case of Captive Consumption | NA | NA | Not Applicable | NA
2029 | Indian Localization | Excise | Purchase Invoice with Service Tax Credit taken on Input service | NA | NA | Not Applicable | NA
2030 | Indian Localization | Excise | Service tax Credit utilized for Excise payment | NA | NA | Not Applicable | NA
2031 | Indian Localization | Excise | Excise Payment | NA | NA | Not Applicable | NA
2032 | Indian Localization | Excise | Update ER 1 PLA Payments Type | NA | NA | Not Applicable | NA
2033 | Indian Localization | Excise | Excise calculation in Purchase order or Purchase Return order for CENVAT Items in case of Trading | NA | NA | Not Applicable | NA
2034 | Indian Localization | Excise | Excise calculation in Sales order or Sales Return order for CENVAT Items in case of Trading | NA | NA | Not Applicable | NA
2035 | Indian Localization | Excise | Transfer of Goods from Trading location to Manufacturing Location | NA | NA | Not Applicable | NA
2036 | Indian Localization | Excise | Transfer of goods from manufacturing location to trading location | NA | NA | Not Applicable | NA
2037 | Indian Localization | Excise | Identifying the Principal Item | NA | NA | Not Applicable | NA
2038 | Indian Localization | Excise | Opening Entry | NA | NA | Not Applicable | NA
2039 | Indian Localization | Excise | Excise Reports | NA | NA | Not Applicable | NA
289 | Tech- C/Side | Technical | Basic Objects in Microsoft Dynamics NAV 2013 | NA | NA | Not Applicable | NA
290 | Tech- C/Side | Technical | Object Designer Fundamentals | NA | NA | Not Applicable | NA
291 | Tech- C/Side | Technical | Team Development Features | NA | NA | Not Applicable | NA
292 | Tech- C/Side | Technical | The Physical and Logical Database | NA | NA | Not Applicable | NA
303 | Tech- C/Side | Technical | Tables Fundamentals | NA | NA | Not Applicable | NA
304 | Tech- C/Side | Technical | Primary and Secondary Keys | NA | NA | Not Applicable | NA
305 | Tech- C/Side | Technical | Table Relationships | NA | NA | Not Applicable | NA
306 | Tech- C/Side | Technical | Special Table Fields | NA | NA | Not Applicable | NA
317 | Tech- C/Side | Technical | Page Fundamentals | NA | NA | Not Applicable | NA
318 | Tech- C/Side | Technical | Page Designer | NA | NA | Not Applicable | NA
319 | Tech- C/Side | Technical | Page Types and Characteristics | NA | NA | Not Applicable | NA
334 | Tech- C/Side | Technical | C/AL Programming | NA | NA | Not Applicable | NA
335 | Tech- C/Side | Technical | Intrinsic Data Types | NA | NA | Not Applicable | NA
336 | Tech- C/Side | Technical | Identifiers, Variables and Syntax | NA | NA | Not Applicable | NA
337 | Tech- C/Side | Technical | Variable Scope | NA | NA | Not Applicable | NA
352 | Tech- C/Side | Technical | Assignment Statements | NA | NA | Not Applicable | NA
353 | Tech- C/Side | Technical | The Syntax of Statements | NA | NA | Not Applicable | NA
354 | Tech- C/Side | Technical | Automatic Type Conversions | NA | NA | Not Applicable | NA
355 | Tech- C/Side | Technical | Use Assignment Statements and the Symbol Menu | NA | NA | Not Applicable | NA
356 | Tech- C/Side | Technical | Expressions, Evaluations, Terms, and Operators | NA | NA | Not Applicable | NA
357 | Tech- C/Side | Technical | The String Operator | NA | NA | Not Applicable | NA
358 | Tech- C/Side | Technical | Function Calls in Expressions | NA | NA | Not Applicable | NA
359 | Tech- C/Side | Technical | Numeric Expressions | NA | NA | Not Applicable | NA
360 | Tech- C/Side | Technical | Arithmetic Operators | NA | NA | Not Applicable | NA
361 | Tech- C/Side | Technical | Relational and Logical Expressions | NA | NA | Not Applicable | NA
362 | Tech- C/Side | Technical | Relational Expressions for Comparison | NA | NA | Not Applicable | NA
363 | Tech- C/Side | Technical | Relational Expressions for Set Inclusion | NA | NA | Not Applicable | NA
364 | Tech- C/Side | Technical | Logical Expressions | NA | NA | Not Applicable | NA
388 | Tech- C/Side | Technical | Conditional Statement and Boolean Expressions | NA | NA | Not Applicable | NA
389 | Tech- C/Side | Technical | The IF Statement | NA | NA | Not Applicable | NA
390 | Tech- C/Side | Technical | The EXIT Statement | NA | NA | Not Applicable | NA
391 | Tech- C/Side | Technical | The CASE Statement | NA | NA | Not Applicable | NA
392 | Tech- C/Side | Technical | Compound Statements and Comments | NA | NA | Not Applicable | NA
393 | Tech- C/Side | Technical | The Syntax of Compound Statements | NA | NA | Not Applicable | NA
394 | Tech- C/Side | Technical | Compound Statements by Using Nested IF Statements | NA | NA | Not Applicable | NA
395 | Tech- C/Side | Technical | The Syntax of Comments | NA | NA | Not Applicable | NA
396 | Tech- C/Side | Technical | Practice: Nested IF | NA | NA | Not Applicable | NA
397 | Tech- C/Side | Technical | Arrays | NA | NA | Not Applicable | NA
398 | Tech- C/Side | Technical | The Syntax of Arrays | NA | NA | Not Applicable | NA
399 | Tech- C/Side | Technical | The Power of Arrays | NA | NA | Not Applicable | NA
400 | Tech- C/Side | Technical | Strings as Arrays of Characters | NA | NA | Not Applicable | NA
401 | Tech- C/Side | Technical | Repetitive Statements | NA | NA | Not Applicable | NA
402 | Tech- C/Side | Technical | The WITH Statement | NA | NA | Not Applicable | NA
424 | Tech- C/Side | Technical | Functions and Parameters | NA | NA | Not Applicable | NA
425 | Tech- C/Side | Technical | Review Built-in Functions | NA | NA | Not Applicable | NA
426 | Tech- C/Side | Technical | Data Access Functions | NA | NA | Not Applicable | NA
427 | Tech- C/Side | Technical | Sorting and Filtering Functions | NA | NA | Not Applicable | NA
428 | Tech- C/Side | Technical | Data Manipulation Functions | NA | NA | Not Applicable | NA
429 | Tech- C/Side | Technical | Working with Fields | NA | NA | Not Applicable | NA
430 | Tech- C/Side | Technical | Using Interaction Functions | NA | NA | Not Applicable | NA
431 | Tech- C/Side | Technical | Other Common C/AL Functions | NA | NA | Not Applicable | NA
432 | Tech- C/Side | Technical | Create Custom Functions | NA | NA | Not Applicable | NA
433 | Tech- C/Side | Technical | Local Functions, Variables and the EXIT Statement | NA | NA | Not Applicable | NA
454 | Tech- C/Side | Technical | Report Fundamentals | NA | NA | Not Applicable | NA
455 | Tech- C/Side | Technical | Report Design Process | NA | NA | Not Applicable | NA
456 | Tech- C/Side | Technical | Design the Data Model | NA | NA | Not Applicable | NA
457 | Tech- C/Side | Technical | Create a Data Model | NA | NA | Not Applicable | NA
458 | Tech- C/Side | Technical | Design the Layout | NA | NA | Not Applicable | NA
459 | Tech- C/Side | Technical | The Request Page Designer | NA | NA | Not Applicable | NA
460 | Tech- C/Side | Technical | Design the Request Options Page | NA | NA | Not Applicable | NA
461 | Tech- C/Side | Technical | Grouping and Totaling | NA | NA | Not Applicable | NA
462 | Tech- C/Side | Technical | Add Advanced Features | NA | NA | Not Applicable | NA
480 | Tech- C/Side | Technical | XMLport Fundamentals | NA | NA | Not Applicable | NA
481 | Tech- C/Side | Technical | Design XMLports | NA | NA | Not Applicable | NA
482 | Tech- C/Side | Technical | Importing and Exporting Plain Text | NA | NA | Not Applicable | NA
483 | Tech- C/Side | Technical | Using XMLports in C/AL Code | NA | NA | Not Applicable | NA
497 | Tech- C/Side | Technical | Codeunit Fundamentals | NA | NA | Not Applicable | NA
498 | Tech- C/Side | Technical | Design Codeunits | NA | NA | Not Applicable | NA
499 | Tech- C/Side | Technical | Use Codeunits | NA | NA | Not Applicable | NA
500 | Tech- C/Side | Technical | SMTP | NA | NA | Not Applicable | NA
509 | Tech- C/Side | Technical | The DotNetDataType | NA | NA | Not Applicable | NA
510 | Tech- C/Side | Technical | Datatype Mapping and Assignment | NA | NA | Not Applicable | NA
511 | Tech- C/Side | Technical | .NET Framework Interoperability C/AL functions | NA | NA | Not Applicable | NA
512 | Tech- C/Side | Technical | Streaming | NA | NA | Not Applicable | NA
527 | Tech- C/Side | Technical | Query Design | NA | NA | Not Applicable | NA
528 | Tech- C/Side | Technical | Accessing Queries from C/AL | NA | NA | Not Applicable | NA
529 | Tech- C/Side | Technical | Advanced Query Concepts | NA | NA | Not Applicable | NA

## 06
Scenarios to be discussed in Training (14-15-Apr’15)
1 |  | 1. Recurring Activities - AMC’s: The trust has got many AMC contracts and the trust wants to MANAGE the AMC’s through ERP.
2 |  | a. Pop-up message informing the due dates of the AMC as & when the same is due | Discussed
3 |  | b. Parallel posting of the monthly expenditure to the concerned accounts | Discussed
4 |  | c. Maintain a dash-board with the user department’s regarding the due date for the service and payments thereof. | Not possible
5 |  | d. Here both the VAT & service tax will be applicable; So the prices may be inclusive/exclusive of taxes | Discussed
6 |  | e. Handling AMC’s when a new asset is purchased which may extend beyond a financial year. | Manual
7 |  | f. View the ledger in which the posting is effected. | Discussed
8 |  | g. Create & view a monthly / yearly report. | Discussed
9 |  | 2. Recurring Activities – Statutory Payments: The Trust has to pay monthly statutory dues like ESI, PF, TDS …etc. and also yearly statutory payments like property tax, Asset Insurance…etc | Discussed
10 |  | a. Pop-up message informing the due dates of the Statutory Payments as & when the same is due. | Not possible
11 |  | b. Parallel posting of the monthly expenditure to the concerned accounts | Discussed
12 |  | c. Maintain a dash-board with the user department’s regarding the due date for the service and payments thereof. | Discussed
13 |  | d. View the ledger in which the posting is effected. | Discussed
14 |  | e. Create & view a monthly / yearly report. | Discussed
15 |  | f. In case of TDS generate an up-loadable document (xml file) for E-TDS returns. | Possible
16 |  | 3. Posting Accruals: | Dicussed
17 |  | a. Calculating the depreciation across the Trust’s assets on monthly basis as per Income Tax Act and as per the Comp. Act. | Dicussed
18 |  | b. Change the depreciation rates as per the requirements of the accounting policies of the Trust. | Dicussed
19 |  | c. Calculation of interest accrued on the Fixed Deposits and other investments. | Feature not available. So do manually
20 |  | 4. Managing Pre-paid expenses; Wherein the Trust pays certain expenses in advance and wants to manage the same | Discussed. Use recurring journals
21 |  | a. Posting the advance payments to the respective ledgers.
22 |  | b. Monthly posting from pre-paid expenses to the respective expenses account.
23 |  | c. Handling situations beyond financial year
24 |  | d. Maintain a auditable trail
25 |  | e. Example; Insurance Payments
26 |  | 5. Assets: Trust maintains huge fixed assets base and wants to tag these assets based on | Discussed
27 |  | a. Asset no.
28 |  | b. Location
29 |  | c. Type of the Asset
30 |  | d. Entity codes
31 |  | e. Person/Dept. – in – charge of the asset
32 |  | f. Maintain an exhaustive Fixed Asset Register
33 |  | g. Insurance monitoring for these assets
34 |  | h. AMC monitoring
35 |  | i. View the assets report
36 |  | 6. Asset Retirement/ Sale of Asset: the Trust periodically reviews and retires some of its assets from the active usage and sells them off (in exceptional cases – as scrap) | Discussed on 13-Apr
37 |  | a. Approval matrix tracking for approving the retirement
38 |  | b. How de-tagging w.r.t. entity codes, asset no. …etc. is done in case of asset retirement;
39 |  | c. How the exact profit/loss is calculated after considering the Acc. Dep & Cost of the asset.
40 |  | d. Maintain a auditable trail
41 |  | e. View the affecting ledger line items
42 |  | f. Create a report.
43 |  | 7. Scrap Sales: Scraps are generated thru production.
44 |  | a. Approval matrix for scrap disposal – how to incorporate within ERP | No automation possible. Only through regular generls
45 |  | b. Identifying which dept, which batch no, the scrap was generated | Use LOT to manage this. And get wastage % report.
46 |  | c. How to monitor production wastages | Pass negative entry with reason code to manage wastage.
47 |  | d. Monitor consumption wastages
48 |  | 8. Specific purpose donations related reporting needs: to check if ERP can accomdate the same | Discussed
49 |  | a. Managing Specific purpose funds; the Trust receives funds to be utilized for the specific purpose say for Annadana or particular seva’s which may be restricted to one financial year or beyond one financial year;
50 |  | i. Posting the receipt to a separate ledger.
51 |  | ii. Monitoring the funds utilization w.r.t. the particular activity (purpose)
52 |  | iii. Tagging the single expense head to different purpose/seva’s
53 |  | iv. Maintain a auditable trail
54 |  | v. Generate a utilization report
55 |  | b. Managing & tracking the ear-marked funds:
56 |  | i. Posting the receipt to a separate ledger.
57 |  | ii. Monitoring the funds utilization w.r.t. the particular activity (purpose)
58 |  | iii. Tagging the single expense head to different purpose/seva’s
59 |  | iv. Maintain a auditable trail
60 |  | v. Generate a utilization report
61 |  | 9. Handling Dimensions (view the expense report dimension-wise); As per the COA, all the sub-ledgers entity codes, project codes..etc are being managed thru dimensions; | Discussed (but need further discussion)
62 |  | a. How to make the dimension mandatory at posting level
63 |  | b. View the particular expense with different dimensions
64 |  | c. How to analyze/view the reports
65 |  | d. To have additional field for a particular dimensions | Customization 2 days
66 |  | 10. Handling Audit period postings: Upon the finalization of the accounts there will be corrections to the financial statements as per the audit requirements and will happen only after the financial year is closed; | Discussed
67 |  | a. How to post these entries in the previous financial year
68 |  | 11. Managing Treasury;
69 |  | a. Setup the cheque measurements for the Cheque printing. Avoiding and devoiding cheques. | Customization 2-3 Days
70 |  | b. How to enable automatic BRS say receive a file from the bank and upon upload BRS is done automatically | Customization 3-4 Days
71 |  | c. How to handle credit card receipts and payments | Discussed
72 |  | d. How to maintain No. Series in case of Sodexo Coupons received by the Trust and Gift Vouchers issued by the Trust | Discussed
73 |  | e. Missing receipt no printing | Customization 1-2 Days
74 |  | f. How to handle online transfers & RTGS/NEFT payments. | Customization 1-2 Days
75 |  | 12. Approval Matrix to be incorporated: there is an exhaustive ALM in place for each & every approval/actions to be performed;
76 |  | a. How to have a dual control for approval of expenditure | Customization 3-4 Days
77 |  | b. How to escalate/recommend for the approvals | Customization 3-4 Days
78 |  | 13. Managing stock transfers; the Trust has got many branches within. There are food stock transfer and item stock transfer either on cost basis or cost+profit basis | Discussed
79 |  | a. How to post the stock transfers
80 |  | b. How to identify & eliminate the profit element
81 |  | c. How to map the ledgers to the production data
82 |  | 14. Inter-trust transfers; Inter – Trust transfers are those transaction happens between two separate legal entities. This may include shared expense segregation, allocating global overheads, fund transfers, revenue sharing…etc | Customization 4-5 Days
83 |  | a. Map the shared expenses/incomes to the specific ledgers in the giving trust and receiving trust.
84 |  | b. Whether the effect of the transaction happens automatically?
85 |  | c. How to reconcile the ledgers.
86 |  | 15. Intra-trust transfers: Intra – Trust transfers are those transactions happen between two separate departments within same legal entity. | Possible/Discussed
87 |  | a. Where one expense may be apportioned between the diff. depts. on a pre-determined percentages
88 |  | b. How to define the percentages – on monthly basis or yearly basis
89 |  | c. Since the departments are handled in dimension level(entity codes) how the posting is done
90 |  | d. Say Electricity Bill is accounted and shared. In the electricity ledger full expense to be accounted first and then re-shared to different departments (dimensions).
91 |  | 16. How to create TAXES TYPE specific applicability to the Trust like Luxury Tax...etc. (Work around possible) | Discussed
92 |  | 17. Reminders to Debtors on their dues once the credit period limit exceeds. | 3-4 Days Customization
93 |  | 18. Vendor/Customer Database & protecting the confidentiality | Easy Configuration
94 |  | 19. User Profiles. | Part of Tech-Config Training
95 |  | a. Restrict the users from accessing the information and;
96 |  | b. To define the user hierarchy
97 |  | c. User defined screen layouts
98 |  | 20. Salaries: What are the basic features available in ERP as Salaries is a major component | Feature not available
99 |  | 21. Closing stock valuation : - in case of manufactured goods and directly purchased goods – if there is any change in valuation or in book quantity is there any approval mechanism, any audit trail possible?
Appendix by GNVD
100 | Cash Flow Forecast | Functions of the Cash Flow Forecast
101 | Cash Flow Forecast | Setting Up Cash Flow Forecasts
102 | Cash Flow Forecast | Creating Cash Flow Forecasts
103 | Cash Flow Forecast | Cash Flow Forecast Reporting
104 | Cost Accounting | Workflow in Cost Accounting
105 | Cost Accounting | Setting Up Cost Accounting
106 | Cost Accounting | Cost Entries | Done on 9-Apr
107 | Cost Accounting | Cost Budgets
108 | Cost Accounting | Cost Allocation | Done on 9-Apr
109 | Cost Accounting | Cost Accounting History
110 | Cost Accounting | Cost Accounting Reporting
111 | Cost Accounting | Tips and Tricks
112 | Order Promising | Sales Order Promising Definitions and Calculations Orders | Done on 9-Apr
113 | Order Promising | Date Calculation Setup for Sales Orders | Done on 9-Apr
114 | Order Promising | Promising Sales Order Delivery Orders | Done on 9-Apr
115 | Order Promising | Purchase Order Promising Definitions and Calculations Orders | Done on 9-Apr
116 | Order Promising | Date Calculation Setup for Purchase Orders Orders | Done on 9-Apr
117 | Order Promising | Estimating Purchase Order Receipts | Done on 9-Apr
118 | Order Promising | Estimate a Transfer Order Receipt | Done on 9-Apr
119 | Order Promising | Calendars | Done on 9-Apr
120 | Financial Reporting and Analysis | Analyze the Chart of Accounts | Done on 13-Apr
121 | Financial Reporting and Analysis | Account Schedules | Done on 13-Apr
122 | Financial Reporting and Analysis | Analysis by Dimensions | Done on 13-Apr
123 | Financial Reporting and Analysis | Export Analysis Views to Microsoft Excel | Done on 13-Apr
124 | Financial Reporting and Analysis | Dimension-Based Reports | Done on 13-Apr
125 | Financial Reporting and Analysis | Combine Analysis Views with Account Schedules | Done on 13-Apr
126 | Financial Reporting and Analysis | Finance Performance Charts
Ganesh (Scenarios) All Done on 14-Apr-15
127 |  | 1. How do we link Forecast to indent. Issues against indent? | Done on 14-Apr
128 |  | 2. How do we cancel the indents | Done on 14-Apr
129 |  | 3. Forecast vs Indent - vs issues | Done on 14-Apr
130 |  | 4. How to issue production Order against Sales Orders | Done on 14-Apr
131 |  | 5. Against Production order how to create production indent ( from Kitchen to RM Stores) | Done on 14-Apr
132 |  | 6. Need option to give issues against BOM / Direct indent | Done on 14-Apr
133 |  | 7. Can we link Forecast to planning | Done on 14-Apr
134 |  | 8. How to close purchase orders PO /CO wise / Item wise | Customization 2 Days
135 |  | 9. How to setup separate document series for external / internal job work orders | Done on 14-Apr
136 |  | 10. Production indents and RM issues are issued to sub Kitchens. | Done on 14-Apr
137 |  | 11. Need posting for respective cost centres in Finance | Done on 14-Apr
138 |  | 12. How do view pending Purchase orders Item wise / Vendor wise including partial delivery / order quantity | Done on 14-Apr
139 |  | 13. Brand tracking during receipts and issues ( Can we use Variants ) | Done on 14-Apr
140 |  | 14. BOM report required on actual BOM Cost and current purchase Cost. | Done on 14-Apr
141 |  | 15. Auto release of production / Assembly orders. Need to release the order manually | Done on 14-Apr
142 |  | 16. Ware house management. | Done on 14-Apr
143 |  | 17. Item Tracking | Done on 14-Apr
144 |  | 18. Item Conversion | Done on 14-Apr
145 |  | 19. Packing Slip during DC | Customization 4 Days
146 |  | 20. Confirmation on Posting Group setup General /Business / Inventory | Done on 14-Apr
147 |  | 21. Sales Tax Setup - State we can define only one tax. How do define multiple taxes | Done on 14-Apr
148 |  | 22. Complimentary Issues setup | Done on 14-Apr
149 |  | 23. How to disable rate edit. | Done on 14-Apr
150 |  | 24. Negetive stock issues setup enable /Disable. | Done on 14-Apr
151 |  | 25. Overview Roll centre setup | Done on 14-Apr
152 |  | 26. Overview of Advance seutp | Done on 14-Apr
153 |  | 27. How to link gatepass entry to Good Received Notes (GRN) | Pending
154 |  | 28. Barcode Printing for Labels | Done on 14-Apr

## 08
Master Table Data
[6 empty] | Total | 56 | 56 | 56 | 56
[6 empty] | Not Available | 4 | 0 | 0 | 0
[6 empty] | Provided | 34 | 29 | 30 | 0
[6 empty] | NR | 17 | 16 | 15 | 0
[6 empty] | Status % | 91.07% | 80.36% | 80.36% | 0%
[7 empty] | Data Provided Status |  |  |  |  | Import Status
# | Table By Varnaaz | Table No |  |  |  | Name | GST | TFS-Gift | TFS-Food | ISKCON | Remarks | GST | TFS-Gift | TFS-Food | ISKCON
8 | ISKCON-Tables | 6502 | Item | Done | ITEM | Item Traking Code | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
19 | ISKCON-Tables |  | Customer | Done | Location | Location | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
20 | ISKCON-Tables |  | Vendor | Done | Financial | Dimension | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
21 | ISKCON-Tables |  | GL Account | Done | Financial | Payments | NA | 2015-04-15 | 2015-04-15 | 2015-04-15
39 | ISKCON-Tables |  | Locations | Done | Financial | BankAccount | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
40 | ISKCON-Tables |  | Financial |  | Financial | BankAccountPostingGroup | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
42 | ISKCON-Tables |  | Setup |  | Financial | PaymentMetho | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
45 | ISKCON-Tables |  | Master | Done | Setup | NoSeries | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
48 | ISKCON-Tables |  |  |  | Financial | ICPartner | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
34 | ISKCON-Tables |  |  |  | Vendor | VendorPostingGroup | Yes | Yes | Yes | 2015-04-15
44 | ISKCON-Tables |  |  |  | Master | ReminderTerms | Yes | NR | NR | 2015-04-15
23 | ISKCON-Tables |  |  |  | Financial | FinanceChargeTerms | NR | NR | NR | 2015-04-15
14 | ISKCON-Tables | 6502 |  |  | ITEM | ItemTrackingCode | Yes | 2015-04-15 | 2015-04-15 | 2015-04-15
13 | ISKCON-Tables | 5904 |  |  | ITEM | ServiceItemGroup | Not Required | NR | Yes | 2015-04-15
1 | FA-Tables |  |  |  | Setup | Employee | NR | NR | NR | 2015-04-15
2 | FA-Tables |  |  |  | Financial | Fixed Assets | NR | NR | NR | 2015-04-15
3 | FA-Tables |  |  |  | Financial | FAPostingGroup | NR | NR | NR | 2015-04-15
4 | FA-Tables |  |  |  | Financial | FAClass | NR | NR | NR | 2015-04-15
5 | FA-Tables |  |  |  | Financial | FASubClass | NR | NR | NR | 2015-04-15
6 | FA-Tables |  |  |  | Financial | FALocation | NR | NR | NR | 2015-04-15
7 | FA-Tables |  |  |  | Financial | Dimention | NR | NR | NR | 2015-04-15
12 | ISKCON-Tables | 260 |  |  | ITEM | TariffNumber | NR | NR | NR | 2015-04-15
15 | ISKCON-Tables | 7305 |  |  | ITEM | SpecialEquipment | NR | NR | NR | 2015-04-15
16 | ISKCON-Tables | 7307 |  |  | Setup | Put away Template Header | NR | NR | NR | 2015-04-15
17 | ISKCON-Tables | 13710 |  |  | ITEM | Excise Product Posting Group | NR | NR | NR | 2015-04-15
18 | ISKCON-Tables | 99000763 |  |  | Setup | Routing Header | NR | NR | NR | 2015-04-15
49 | ISKCON-Tables |  |  |  | Master | Contact | NR | NR | NR | 2015-04-15
10 | ISKCON-Tables | 13792 |  |  | Setup | Structure Header | NA | Yes | Yes | 2015-04-15
11 | ISKCON-Tables | 99000771 |  |  | Setup | Production BOM Header | NA | 2015-04-15 | 2015-04-15 | 2015-04-15
9 | ISKCON-Tables | 7381 |  |  | Setup | PhyInvtCountingPeriod | Yes | Yes | Yes | 2015-04-15 | Sample record
47 | ISKCON-Tables |  |  |  | ITEM | ItemDiscountGroup | Yes | Yes | Yes | 2015-04-15
70 | ISKCON-Tables |  |  |  | ITEM | TaxGroupCode | NA | Yes | Yes | 2015-04-15
50 | ISKCON-Tables |  |  |  | Setup | Manufacturer | NR | Yes | Yes | 2015-04-15
71 | ISKCON-Tables |  |  |  | Master | VATBusinessPostingGroup | NR | Yes | Yes | 2015-04-15
75 | ISKCON-Tables |  |  |  | Setup | BOM | NR | Yes | Yes | 2015-04-15
22 | ISKCON-Tables |  |  |  | Financial | Currency | Yes | Yes | Yes | 2015-04-15
24 | ISKCON-Tables |  |  |  | Customer | CustomerPriceGroup | Yes | Yes | Yes | 2015-04-15
25 | ISKCON-Tables |  |  |  | Master | Language | Yes | Yes | Yes | 2015-04-15
26 | ISKCON-Tables |  |  |  | Master | CountryRegion | Yes | Yes | Yes | 2015-04-15
27 | ISKCON-Tables |  |  |  | Setup | ShipmentMethod | Yes | Yes | Yes | 2015-04-15
28 | ISKCON-Tables |  |  |  | Setup | SalespersonPurchaser | Yes | Yes | Yes | 2015-04-15
29 | ISKCON-Tables |  |  |  | Financial | GLAccount | Yes | Yes | Yes | 2015-04-15
30 | ISKCON-Tables |  |  |  | Customer | Customer | Yes | Yes | Yes | 2015-04-15
31 | ISKCON-Tables |  |  |  | Vendor | Vendor | Yes | Yes | Yes | 2015-04-15
32 | ISKCON-Tables |  |  |  | ITEM | Item | Yes | Yes | Yes | 2015-04-15
33 | ISKCON-Tables |  |  |  | Customer | CustomerPostingGroup | Yes | Yes | Yes | 2015-04-15
35 | ISKCON-Tables |  |  |  | ITEM | InventoryPostingGroup | Yes | Yes | Yes | 2015-04-15
36 | ISKCON-Tables |  |  |  | ITEM | UnitofMeasure | Yes | Yes | Yes | 2015-04-15
37 | ISKCON-Tables |  |  |  | Master | GenBusinessPostingGroup | Yes | Yes | Yes | 2015-04-15
38 | ISKCON-Tables |  |  |  | ITEM | GenProductPostingGroup | Yes | Yes | Yes | 2015-04-15
41 | ISKCON-Tables |  |  |  | Setup | Territory | Yes | Yes | Yes | 2015-04-15
43 | ISKCON-Tables |  |  |  | Setup | ShippingAgent | Yes | Yes | Yes | 2015-04-15
46 | ISKCON-Tables |  |  |  | Customer | CustomerDiscountGroup | Yes | Yes | Yes | 2015-04-15
51 | ISKCON-Tables |  |  |  | ITEM | ItemCategory | Yes | Yes | Yes | 2015-04-15
72 | ISKCON-Tables |  |  |  | ITEM | VATProductPostingGroup | Yes | Yes | Yes | 2015-04-15
76 | ISKCON-Tables |  |  |  | Financial | PaymentTerms | Yes | Yes | Yes | 2015-04-15

## 07
Objective
S.No. | Course | Course Objectives
1 | Technical Setup | Navigate through the MS Dynamics NAV user interface
2 | Technical Setup | Understand the basic functionalities of MS Dynamics NAV
3 | Technical Setup | Personalizing the Screen for the User
4 | Technical Setup | Explain the dependencies between RapidStart Services and manual setup work
5 | Technical Setup | Describe the different components and processes of RapidStart Services
6 | Technical Setup | Explain and demonstrate all tasks in a RapidStart Services process
7 | Technical Setup | Create a configuration worksheet
8 | Technical Setup | Create a configuration package
9 | Technical Setup | Create a configuration questionnaire
10 | Technical Setup | Create a configuration template
11 | Technical Setup | Initialize a new company with a configuration package
12 | Technical Setup | Migrate customer data
13 | Technical Setup | Transfer opening balances
14 | Technical Setup | Explain how authentication works in Microsoft Dynamics NAV
15 | Technical Setup | Manage security for Windows client users
16 | Technical Setup | Set up a new user
17 | Technical Setup | Explain the concepts of permission sets and permissions
18 | Technical Setup | Create a new permission set, and assign permissions to it
19 | Technical Setup | Apply security filters in Microsoft Dynamics NAV
20 | Technical Setup | Perform user-specific setup
21 | Technical Setup | Create, assign, and work with user profiles
22 | Technical Setup | Explain the purpose of company-wide number series
23 | Technical Setup | Set up number series
24 | Technical Setup | Create number series relations
25 | Technical Setup | Explain and set up trail codes, source codes, and reason codes
26 | Technical Setup | Explain the purpose and organization of journal templates and journal batches
27 | Technical Setup | Create general journal templates and general journal batches
28 | Technical Setup | Explain and set up specific posting groups
29 | Technical Setup | Explain and set up general posting groups
30 | Technical Setup | Create a General posting setup
31 | Technical Setup | Create an Inventory posting setup
32 | Technical Setup | Explain and set up VAT posting groups
33 | Technical Setup | Create a VAT posting setup
34 | Technical Setup | Describe posting setups based on the chart of accounts
35 | Technical Setup | Demonstrate how posting groups direct a sales transaction
36 | Technical Setup | Explain and set up dimensions and dimension values
37 | Technical Setup | Explain and set up global and shortcut dimensions
38 | Technical Setup | Explain and show how dimension combinations are set up
39 | Technical Setup | Explain and show how single and multiple default dimensions are set up
40 | Technical Setup | Explain and show how account type default dimensions are set up
41 | Technical Setup | Explain and show how default dimension priorities are set up
42 | Technical Setup | Explain the possibility and resolution of conflicting default dimensions
43 | Technical Setup | Use dimension and dimension values in journals & documents under different dimension setup scenarios
44 | Technical Setup | Set up the general features of the document approval system
45 | Technical Setup | Set up approval templates
46 | Technical Setup | Set up user logons for use with document approvals
47 | Technical Setup | Set up approval users in a hierarchy
48 | Technical Setup | Set up the notification system for approvals
49 | Technical Setup | Send an approval request
50 | Technical Setup | Approve a sales or purchase document
51 | Technical Setup | Maintain substitute approvers
52 | Technical Setup | Manage overdue notifications
53 | Finance Essentials | Explain and set up the fields on the General Ledger Setup window
54 | Finance Essentials | Explain and set up Accounting Periods
55 | Finance Essentials | Explain how to use the Chart of Accounts
56 | Finance Essentials | Explain the elements of the G/L Account Card
57 | Finance Essentials | Explain the elements of the G/L Account Card ribbon
58 | Finance Essentials | Explain the elements of the Chart of Account ribbon
59 | Finance Essentials | Explain the general journal entry and posting system
60 | Finance Essentials | Create and post general journal entries
61 | Finance Essentials | Describe standard general journals
62 | Finance Essentials | Describe recurring general journals and include the fields and allocations
63 | Finance Essentials | Show how to use recurring journals with allocations and how to record accruals
64 | Finance Essentials | Explain how to reverse and correct journal entries
65 | Finance Essentials | Describe the Bank Account Card
66 | Finance Essentials | Explain the Payments FastTab on the customer card
67 | Finance Essentials | Explain the Payments FastTab on the vendor card
68 | Finance Essentials | Show how to enter and post payments received from customers, by using cash receipt journals
69 | Finance Essentials | Show how to enter and post payments to vendors by using the payment journal
70 | Finance Essentials | Explain the Suggest Vendor Payments batch job
71 | Finance Essentials | Explain how to print and post payables checks
72 | Finance Essentials | Explain and show how to financially void a check
73 | Finance Essentials | Explain how to void and reprint computer checks
74 | Finance Essentials | Explain how to apply entries to customer and vendor ledger entries
75 | Finance Essentials | Explain how to unapply entries to customer and vendor ledger entries
76 | Finance Essentials | Explain how to reverse customer ledger entries posted by using journals
77 | Finance Essentials | Review the Bank Account Reconciliation window and the options for populating the bank reconciliation lined
78 | Finance Essentials | Show how to process a bank reconciliation
79 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use payment discounts
80 | Finance Essentials | Process transactions for various situations that benefit from payment discounts
81 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use a payment discount tolerance
82 | Finance Essentials | Process transactions for various situations that benefit from using a payment discount tolerance
83 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use a payment tolerance
84 | Finance Essentials | Process transactions for various situations that benefit from using a payment tolerance
85 | Finance Essentials | Review how a payment discount tolerance and a payment tolerance are reflected in the detailed customer and vendor ledger entries
86 | Finance Essentials | Explain why and when Reminders and Finance Charge Memos are used
87 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use reminders
88 | Finance Essentials | Explain how to create and issue reminders
89 | Finance Essentials | Set up Microsoft Dynamics NAV 2013 to use finance charge memos
90 | Finance Essentials | Explain how to create and issue finance charge memos
91 | Finance Essentials | Explain the different VAT calculation types
92 | Finance Essentials | Show how to reverse a VAT charge
93 | Finance Essentials | Describe how to correct a posted VAT entry
94 | Finance Essentials | Show how to record Import VAT
95 | Finance Essentials | Explain the Prices Including VAT fields on sales and purchase documents
96 | Finance Essentials | Explain how to adjust calculated VAT amounts in sales and purchase documents and journals
97 | Finance Essentials | Describe unrealized VAT
98 | Finance Essentials | Explain, create, and print a VAT Statement
99 | Finance Essentials | Explain and run the Calc and Post VAT Settlement batch job
100 | Finance Essentials | Explain the requirements for setting up prepayments
101 | Finance Essentials | Set up and assign prepayment General Ledger accounts
102 | Finance Essentials | Set up prepayment numbering for sales and purchases
103 | Finance Essentials | Set up default prepayment percentages on customers and vendors
104 | Finance Essentials | Set up default prepayment percentages for Customer-Item and Vendor-Item combinations
105 | Finance Essentials | Set up prepayment posting verification for sales and purchases
106 | Finance Essentials | Explain the prepayment processing flows for sales and purchase orders
107 | Finance Essentials | Describe the prepayment-specific fields on sales and purchase orders
108 | Finance Essentials | Create sales and purchase orders with prepayment percentages and amounts
109 | Finance Essentials | Create prepayment invoices that are from sales and purchase orders
110 | Finance Essentials | Explain the processes available to correct posted prepayment invoices
111 | Finance Essentials | Close the accounting periods for the fiscal year
112 | Finance Essentials | Explain and run the Close Income Statement batch job process
113 | Finance Essentials | Complete the closing process by posting the general journal
115 | Finance Essentials | Explain and set up Accounting Periods
116 | Finance Essentials | Review the Bank Account Reconciliation window and the options for populating the bank reconciliation lines
117 | Finance Essentials | Complete the closing process by posting the general journal
119 | Finance Advance | Set up Intrastat for use in Microsoft Dynamics NAV 2013
120 | Finance Advance | Explain how to run and submit Intrastat reports
121 | Finance Advance | Explain and demonstrate the preparation of the VAT rate change process
122 | Finance Advance | Explain and set up the VAT rate change tool
123 | Finance Advance | Explain and demonstrate how to perform a VAT rate change
124 | Finance Advance | Explain setup requirements for currencies and exchange rates when using multiple currencies
125 | Finance Advance | Explain setup requirements using multiple currencies with customers, vendors, and bank accounts
126 | Finance Advance | Describe steps and additional functionality for processing purchase and sales documents that use foreign currency
127 | Finance Advance | Describe steps and additional functionality for recording and posting multicurrency transactions in the cash receipts journal
128 | Finance Advance | Describe how to process multicurrency payments using the payments journal
129 | Finance Advance | Describe how to run the Adjust Exchange Rates batch job for customers, vendors, and bank accounts
130 | Finance Advance | Explain set up, viewing amounts, daily processing, and periodic processes when using an additionalreporting currency
131 | Finance Advance | Describe how to run the Adjust Exchange Rates batch job for G/L accounts
132 | Finance Advance | Describe how to view the Exchange Rate Adjustment Register
133 | Finance Advance | Explain the Budgets feature in Microsoft Dynamics NAV 2013
134 | Finance Advance | Explain the G/L Budgets page elements
135 | Finance Advance | Show how to set up budgets manually
136 | Finance Advance | Explain how to delete budget entries
137 | Finance Advance | Explain how to create budgets by using the Copy Budget function
138 | Finance Advance | Explain how to create budgets by using the Export Budget and Import Budget functions
139 | Finance Advance | Explain the workflow in Cost Accounting
140 | Finance Advance | Explain and set up Chart of Cost Types, Chart of Cost Centers, Chart of Cost Objects, and Cost Accounting setup
141 | Finance Advance | Explain the relationship between the cost accounting and general ledger application areas
142 | Finance Advance | Set up cost journals
143 | Finance Advance | Explain how to create cost entries either through a transfer from G/L entries or through posting the cost journal
144 | Finance Advance | Explain and set up cost budgets by using different copy functions
145 | Finance Advance | Explain the transfer from budget to actual
146 | Finance Advance | Explain and set up cost allocations
147 | Finance Advance | Explain static and dynamic allocations
148 | Finance Advance | Explain how to allocate costs and cost budgets
149 | Finance Advance | Explain the cost registers and cost budget registers
150 | Finance Advance | Explain the deletion of cost entries and cost budget entries
151 | Finance Advance | Explain different cost accounting reports
152 | Finance Advance | Provide tips and tricks
153 | Finance Advance | Explain the functions of the cash flow forecast
154 | Finance Advance | Explain the setup of the Chart of Cash Flow Account, Cash Flow Setup and Cash Flow Payment Terms
155 | Finance Advance | Explain how to create cash flow forecasts by using Cash Flow Forecast Cards and Cash Flow Manual Revenues and Expenses
156 | Finance Advance | Explain how the Cash Flow Worksheet is used
157 | Finance Advance | Review the registration of the cash flow through Cash Flow Forecast Entries
158 | Finance Advance | Explain the different Cash Flow Forecast Reporting possibilities
159 | Finance Advance | Describe filtering and analysis pages related to the chart of accounts
160 | Finance Advance | Explain how to set up an account schedule and explain other processes that relate to account schedules
161 | Finance Advance | Demonstrate cost account schedules
162 | Finance Advance | Demonstrate cash flow account schedules
163 | Finance Advance | Describe types of dimensions
164 | Finance Advance | Explain how to set up analysis views
165 | Finance Advance | Explain the process of exporting analysis views to Microsoft Office Excel 2007, and describe the elements of the exported file
166 | Finance Advance | Show how to generate analysis by dimensions and other dimension analysis reports
167 | Finance Advance | Show how to set up a Finance Performance chart
168 | Finance Advance | Explain the terminology associated with XBRL
169 | Finance Advance | Explain how to import and update taxonomies
170 | Finance Advance | Explain how to attach, update, and apply linkbases to taxonomies
171 | Finance Advance | Describe pages that are related to XBRL lines, and explain how to enter XBRL line definitions
172 | Finance Advance | Demonstrate how to export an instance document
174 | Finance Advance | Describe steps and additional functionality for recording and posting multicurrency transactions in the cash receipts journal.
175 | Finance Advance | Explain set up, viewing amounts, daily processing, and periodic processes when using an additional reporting currency.
176 | Finance Advance | Explain how to create cost entries either through a transfer from G/L entries or through posting the cost journal
177 | Finance Advance | Set up Fixed Assets
178 | Finance Advance | Perform a variety of Fixed Asset transactions
179 | Finance Advance | Reclassify Fixed Assets
180 | Finance Advance | Handle maintenance of their Fixed Assets
181 | Finance Advance | Handle insurance on their Fixed Assets
183 | Fixed Assets | Give a visual overview of a typical fixed asset life cycle.
184 | Fixed Assets | Describe the fields on the Fixed Assets setup page.
185 | Fixed Assets | Describe fixed asset posting groups.
186 | Fixed Assets | Explain depreciation books for fixed assets.
187 | Fixed Assets | Explain depreciation tables.
188 | Fixed Assets | Set up fixed assets journal templates.
189 | Fixed Assets | Set up a fixed asset card.
190 | Fixed Assets | Set up main assets with asset components.
191 | Fixed Assets | Explain how to record opening transactions.
192 | Fixed Assets | Explain how to duplicate entries to depreciation books.
193 | Fixed Assets | Explain how to copy fixed assets and FA ledger entries.
194 | Fixed Assets | Transfer a fixed asset.
195 | Fixed Assets | Split a fixed asset.
196 | Fixed Assets | Dispose of a part of a fixed asset.
197 | Fixed Assets | Combine assets.
198 | Fixed Assets | Set up maintenance information.
199 | Fixed Assets | Register maintenance costs.
200 | Fixed Assets | Review fixed asset maintenance by using the maintenance cost reports.
201 | Fixed Assets | Set up insurance information.
202 | Fixed Assets | Assign an asset to an insurance policy.
203 | Fixed Assets | Monitor insurance coverage.
204 | Fixed Assets | Update, correct, and delete insurance information.
205 | Fixed Assets | Set up insurance indexing.
207 | Trade | Review the setup of Sales Order Management. This includes customers, shipping options, reservation rules, customer posting groups, and salespeople.
208 | Trade | Explain and process sales quotes and blanket sales orders, and review sales order information.
209 | Trade | Describe how to reserve items on a sales order.
210 | Trade | Explain how to post a sales order shipment.
211 | Trade | Describe and show how to combine shipments into one invoice.
212 | Trade | Explain and demonstrate the drop shipment process.
213 | Trade | Show how to process prepayments on a sales order.
214 | Trade | Define sales prices and set up sales prices and customer price groups.
215 | Trade | Explain how to maintain sales prices by using the sales price worksheet.
216 | Trade | Describe and set up line discounts.
217 | Trade | Explain how invoice discounts are used.
218 | Trade | Describe how to set up and use item substitutions.
219 | Trade | Review the setup and use of item cross references.
220 | Trade | Explain how to set up nonstock items and create them manually.
221 | Trade | Describe how to sell nonstock items by using special orders.
223 | Trade | Review the setup of Purchase Order Management. This includes vendors, vendor posting groups, shipping and, or receiving options, and purchasers.
224 | Trade | Explain how to use purchase documents. This includes quotes, blanket orders, and purchase orders.
225 | Trade | Review purchase prices and discounts in relation to item costs.
226 | Trade | Explain purchase price setup and processing.
227 | Trade | Explain discount setup and processing.
228 | Trade | Describe how to process prepayments on a purchase order.
229 | Trade | Briefly describe requisition management setup and planning parameters.
230 | Trade | Explain the core functionality of the requisition worksheet and show how to calculate a plan and process proposed orders.
231 | Trade | Describe additional worksheet features including support for drop shipments and special orders, planning worksheet lines, and manually created lines.
232 | Trade | Describe the setup of item charges.
233 | Trade | Explain purchase item charges and show how to assign them to a posted purchase receipt.
234 | Trade | Describe sales item charges and show how to assign them to a posted sales shipment.
235 | Trade | Explain purchase and sales allowances and show how to record an item charge for a sales allowance on a credit memo.
236 | Trade | Describe the key concepts, field definitions, and date calculations for sales order promising.
237 | Trade | Explain the setup of time values and other parameters for sales order promising.
238 | Trade | Show order promising and date calculation functionality for sales order deliveries.
239 | Trade | Define the field definitions and date calculations for estimating purchase order receipts.
240 | Trade | Explain the setup of time value parameters for estimating purchase order receipts.
241 | Trade | Show how to estimate dates for purchase order receipts and the related calculations.
242 | Trade | Explain how transfer order receipts are estimated.
243 | Trade | Describe how to use the Calendars functionality to exclude nonworking days in date calculations.
244 | Trade | Describe the returns management setup for sales and purchases.
245 | Trade | Explain and show how to manage customer returns.
246 | Trade | Explain and show how to manage returns to vendors.
247 | Trade | Review assembly management setup, assembly items, and assembly bill of materials.
248 | Trade | Describe and show assemble-to-order functionality. This includes a full description of sales interface functionality, underlying links to assembly orders, and assembly quotes and blanket orders.
249 | Trade | Explain how to set up and use sales and purchase analysis reports.
250 | Trade | Show how to perform analysis by dimensions.
251 | Trade | Explain how to create and export budgets and use them in analysis reports
252 | Indian Localization | Create Structure for calculation of taxes like Excise, Value Added Tax, Service tax and other charges on sales and purchase transactions.
253 | Indian Localization | Calculate Excise on Purchase and Sale transactions.
254 | Indian Localization | Calculate Excise in case of MRP.
255 | Indian Localization | Payment of excise liability using the service tax credit.
256 | Indian Localization | Update ER 1 PLA payments and claim deferred Excise.
257 | Indian Localization | Enter the opening entry for RG23A/C part I and Part II.
258 | Indian Localization | Generate various reports related to excise including ER-1.
259 | Indian Localization | Calculate Service tax on Purchase and Sales transactions.
260 | Indian Localization | Calculate Service tax on Input Service Distributor and GTA.
261 | Indian Localization | Calculate Service tax in case of ST Pure Agent.
262 | Indian Localization | Do offline and on-line Application and Un-Application of Service tax entries.
263 | Indian Localization | Enter Service tax opening and make adjustments.
264 | Indian Localization | Pay Service Tax liability by utilizing Input Service Tax Credit and CENVAT credit.
265 | Indian Localization | Generate various reports related to Service tax including ST-3 return.
266 | Indian Localization | Calculate VAT on Purchase and Sale transactions.
267 | Indian Localization | Calculate CST on Purchase and Sale transactions.
268 | Indian Localization | Enter VAT opening and make VAT Adjustments.
269 | Indian Localization | Process VAT Settlement.
270 | Indian Localization | Generate various reports related to VAT.

## 09
Lab Work
S. No. | Ref. No. | Course | Module | Lab Exercise
1 | 751 | Technical Setup | Manage User Rights and Profiles | Set Up New Users
2 | 766 | Technical Setup | Set Up Number Series | Create a Number Series
3 | 781 | Technical Setup | Set Up General Journals | Create a Journal Batch
4 | 793 | Technical Setup | Set Up Posting Groups | Set Up and Assign a Vendor Posting Group
5 | 793 | Technical Setup | Set Up Posting Groups | Set Up and Assign a Product Posting Group
6 | 793 | Technical Setup | Set Up Posting Groups | Copy a General Posting Setup Line
7 | 794 | Technical Setup | Set Up Posting Groups | Create and Assign a VAT Product Posting Group
8 | 794 | Technical Setup | Set Up Posting Groups | Copy a VAT Posting Setup
9 | 796 | Technical Setup | Set Up Posting Groups | Post and Review a Purchase Transaction
10 | 813 | Technical Setup | Set Up Dimensions | Set Up a Dimension with Dimension Values
11 | 813.1 | Technical Setup | Set Up Dimensions | Assign Default Dimensions to a Single Account
12 | 813.2 | Technical Setup | Set Up Dimensions | Set Up a Dimension Combination
13 | 814 | Technical Setup | Set Up Dimensions | Assign Default Dimensions to Multiple Accounts
14 | 815 | Technical Setup | Set Up Dimensions | Assign Vendor Account Type Default Dimensions
15 | 833 | Technical Setup | Set Up and Manage Document Approvals | Set Up a Purchase Document Approvals System
16 | 94 | Finance Essentials | Finance Management Setup | Accounting Periods
17 | 95 | Finance Essentials | Finance Management Setup | Create a Fiscal Year
18 | 97 | Finance Essentials | Finance Management Setup | Change the Starting Date
19 | 108 | Finance Essentials | Chart of Accounts | Create a Revenue Account
20 | 108 | Finance Essentials | Chart of Accounts | Assign a Dimension to Multiple Accounts
21 | 122 | Finance Essentials | General Journals | Create a Journal Entry
22 | 122 | Finance Essentials | General Journals | Create and Post a Recurring Journal
23 | 142 | Finance Essentials | Cash Management | Create a Bank Account
24 | 142 | Finance Essentials | Cash Management | Apply and Post Cash Receipts
25 | 144 | Finance Essentials | Cash Management | Enter, Apply, and Post the Cash Receipt Journal
26 | 145 | Finance Essentials | Cash Management | Enter and Post Manual Checks
27 | 146 | Finance Essentials | Cash Management | Enter, Apply and Post the Payment Journal Using Manual Checks
28 | 147 | Finance Essentials | Cash Management | Suggest Vendor Payments for a Single Vendor
29 | 147.1 | Finance Essentials | Cash Management | Financially Void a Check
30 | 147.2 | Finance Essentials | Cash Management | Void a Check
31 | 147.3 | Finance Essentials | Cash Management | Unapply Posted Ledger Entries
32 | 177 | Finance Essentials | Receivables and Payables Management | Post a Customer Payment with a Discount
33 | 177 | Finance Essentials | Receivables and Payables Management | Apply Posted Partial Customer Payments with Discounts
34 | 178 | Finance Essentials | Receivables and Payables Management | Set Up a Payment Tolerance
35 | 178 | Finance Essentials | Receivables and Payables Management | Process a Customer Payment Tolerance
36 | 178 | Finance Essentials | Receivables and Payables Management | Adjust the Vendor Payment Discount Amount
37 | 199 | Finance Essentials | Receivables Management | Set Up and Assign a Reminder Term
38 | 200 | Finance Essentials | Receivables Management | Create and Issue Reminders
39 | 200.1 | Finance Essentials | Receivables Management | Set Up and Assign a Finance Charge Term
40 | 200.2 | Finance Essentials | Receivables Management | Create and Issue Finance Charge Memos
41 | 239 | Finance Essentials | Prepayments | Set Up Prepayments for Sales
42 | 239 | Finance Essentials | Prepayments | Prepayment Sales Order Process with Payment Discount
43 | 240 | Finance Essentials | Prepayments | Create the Prepayment Sales Order and Process and Review the Prepayment Sales Invoice
44 | 241 | Finance Essentials | Prepayments | Adjust the Prepayment Sales Order and Process the Prepayment Sales Invoice
45 | 242 | Finance Essentials | Prepayments | Process Customer Prepayment
46 | 243 | Finance Essentials | Prepayments | Process and Review Final Invoice
47 | 244 | Finance Essentials | Prepayments | Prepayment Sales Order Process with Unrealized VAT
48 | 245 | Finance Essentials | Prepayments | Verify Unrealized VAT Setup
49 | 246 | Finance Essentials | Prepayments | Create the Prepayment Sales Order and Process and Review the Prepayment Sales Invoice
50 | 247 | Finance Essentials | Prepayments | Process and Review the Final Invoice
51 | 263 | Finance Essentials | Year End Closing Procedures | Post an Entry into a Closed Fiscal Year
52 | 383 | Finance Advance | Multicurrency | Process a Sales Invoice
53 | 383 | Finance Advance | Multicurrency | Post Expenses in Foreign Currency
54 | 383 | Finance Advance | Multicurrency | Update the USD:GBP Exchange Rate
55 | 403 | Finance Advance | Budgets | Create a budge Copy a budget
56 | 420 | Finance Advance | Cost Accounting | Using Cost Journals
57 | 420 | Finance Advance | Cost Accounting | Set Up a Cost Budget
58 | 420 | Finance Advance | Cost Accounting | Set Up Cost Allocation
59 | 445 | Finance Advance | Cash Flow Forecast | Creating a Cash Flow Forecast
60 | 447 | Finance Advance | Cash Flow Forecast | Entering Manual Revenues and Expenses
61 | 447.1 | Finance Advance | Cash Flow Forecast | Using the Cash Flow Worksheet
62 | 447.2 | Finance Advance | Cash Flow Forecast | Using the Cash Flow Worksheet
63 | 447.3 | Finance Advance | Cash Flow Forecast | Printing the Cash Flow Date List
64 | 465 | Finance Advance | Financial Reporting and Analysis | Create a Detailed Account Schedule
65 | 465.1 | Finance Advance | Financial Reporting and Analysis | Create a Cost Account Schedule
66 | 465.2 | Finance Advance | Financial Reporting and Analysis | Create a Cash Flow Account Schedule
67 | 465.3 | Finance Advance | Financial Reporting and Analysis | Create an Analysis View
68 | 465.4 | Finance Advance | Financial Reporting and Analysis | Create a Cash Flow Analysis View
69 | 466 | Finance Advance | Financial Reporting and Analysis | Export an Analysis View to Microsoft Excel
70 | 467 | Finance Advance | Financial Reporting and Analysis | Combine an Analysis View with an Account Schedule
71 | 539 | Fixed Assets | Fixed Assets Setup | Create a Fixed Asset Card
72 | 570 | Fixed Assets | Fixed Assets Transactions | Purchase a Fixed Asset Using the Purchase Invoice
73 | 571 | Fixed Assets | Fixed Assets Transactions | Post the Acquisition Cost through Purchase Invoice
74 | 572 | Fixed Assets | Fixed Assets Transactions | Increase the Cost of the Fixed Asset
75 | 573 | Fixed Assets | Fixed Assets Transactions | Post Additional Acquisition Cost
76 | 575 | Fixed Assets | Fixed Assets Transactions | Calculate and Post Depreciation
77 | 577 | Fixed Assets | Fixed Assets Transactions | Post a Write-down
78 | 579 | Fixed Assets | Fixed Assets Transactions | Dispose of a Whole Fixed Asset
79 | 581 | Fixed Assets | Fixed Assets Transactions | Cancel and Recalculate Depreciation
80 | 584 | Fixed Assets | Fixed Assets Transactions | Cancel an Entry
81 | 586 | Fixed Assets | Fixed Assets Transactions | Budget a Fixed Asset
82 | 587 | Fixed Assets | Fixed Assets Transactions | Manage a Minor Asset
83 | 612 | Fixed Assets | Fixed Asset Reclassification | Splitting a Fixed Asset & Partial disposal of an Asset
84 | 615 | Fixed Assets | Fixed Asset Reclassification | Disposing of a Part of an Asset
85 | 627 | Fixed Assets | Fixed Assets Maintenance | Posting Allocation Transactions
86 | 630 | Fixed Assets | Fixed Assets Maintenance | Posting Maintenance Transactions
87 | 1295 | Manufacturing | BOM | Create a New Production BOM and BOM Version
88 | 1325 | Manufacturing | Production Orders | Create a Firm Planned Production Order and Change It
89 | 1346 | Manufacturing | Production Order Processing | Combine Automatic and Manual Flushing
90 | 1378 | Manufacturing | Sales Order Interface and Order Planning | Use Order Planning to Create and Reserve Supply
91 | 1398 | Manufacturing | Forecasting and Planning | Create Production Forecast
92 | 1441 | Manufacturing | Planning | Plan for an Item Variant and Location SKU
93 | 1466 | Manufacturing | Subcontracting | Set up and Process a Subcontracting Operation
94 | 1580 | Trade | Sales Order Management | Create and Convert a Blanket Sales Order
95 | 1580 | Trade | Sales Order Management | Reserve an Item on a Sales Order
96 | 1580 | Trade | Sales Order Management | Ship and Invoice a Sales Order
97 | 1599 | Trade | Sales Prices and Discounts | Manage Sales PricesUpdate Sales Prices
98 | 1599 | Trade | Sales Prices and Discounts | Offer the Best Available Price to a Customer
99 | 1616 | Trade | Customer Service Features | Process a Sales Order with Item Substitutions
100 | 1616 | Trade | Customer Service Features | Process a Sales Order with Item Cross References
101 | 1630 | Trade | Purchase Order Management | Process a Purchase Quote to an Order
102 | 1630 | Trade | Purchase Order Management | Manage Alternative Purchase Prices
103 | 1630 | Trade | Purchase Order Management | Manage Purchase Line Discounts
104 | 1658 | Trade | Item Charges | Assign Freight Charges to an Open Purchase Order
105 | 1658 | Trade | Item Charges | Create an Item Charge Purchase Credit Memo
106 | 1676 | Trade | Order Prominsing | Promise Sales Order Delivery to a Customer
107 | 1676 | Trade | Order Prominsing | Purchase Order Promising
108 | 1692 | Trade | Returns Management | Process a Customer Return
109 | 1692 | Trade | Returns Management | Process a Vendor Return
110 | 1704 | Trade | Assembly Management | Create Assemble-to-Order Sales Order and Change Assembly Lines
111 | 1704 | Trade | Assembly Management | Create Partial Shipments on Sales Lines That Contain Both ATO Items and Inventory Items
112 | 1720 | Trade | Analysis and Reporting | Create an Analysis Report
113 | 1720 | Trade | Analysis and Reporting | Analyze Item Sales by Area
114 | 2001 | Indian Localization | Structure | Lab 1.1– Setup Tax/Charge Group
115 | 2002 | Indian Localization | Structure | Lab 1.2– Setup Tax/Charge Group Details
116 | 2003 | Indian Localization | Structure | Lab 1.3– Setup Structure
117 | 2004 | Indian Localization | Structure | Lab 1.4– Calculating Excise, VAT & Charges in Purchase Order with Structure
118 | 2005 | Indian Localization | Structure | Lab 1.5– Calculating Excise, VAT & Charges in Sales Order with Structure
119 | 2006 | Indian Localization | Structure | Lab 1.6– Calculating Excise, VAT & Charges in Purchase Return Order with Structure
120 | 2007 | Indian Localization | Structure | Lab 1.7– Calculating Excise, VAT & Charges in Sales Return Order with Structure
121 | 2008 | Indian Localization | Excise | Lab 2.1– Create Excise Posting Setup for New rates of Excise
122 | 2009 | Indian Localization | Excise | Lab 2.2– Calculate Excise in the Purchase Invoice
123 | 2010 | Indian Localization | Excise | Lab 2.3– Calculate Excise in the purchase invoice in case of trading
124 | 2011 | Indian Localization | Service Tax | Lab 3.1– Create Service Tax Setup for new rates of Service Tax
125 | 2012 | Indian Localization | Service Tax | Lab 3.2– Calculate Service Tax and TDS using Journal Voucher
126 | 2013 | Indian Localization | Service Tax | Lab 3.3– Calculate Service Tax and TDS using Bank Payment Voucher
127 | 2014 | Indian Localization | Service Tax | Lab 3.4– Purchase Invoice with Service Tax in case of ISD
128 | 2015 | Indian Localization | Service Tax | Lab 3.5– Calculate Service Tax using Journal Voucher
129 | 2016 | Indian Localization | Service Tax | Lab 3.6– Service Tax on Advance Payment Received from Customer
130 | 2017 | Indian Localization | Sales Tax / VAT | Lab 4.1– Create Deferment Period for the State
131 | 2018 | Indian Localization | Sales Tax / VAT | Lab 4.2– Create Tax Area
132 | 2019 | Indian Localization | Sales Tax / VAT | Lab 4.3– Create New Tax Area Location
133 | 2020 | Indian Localization | Sales Tax / VAT | Lab 4.4– Calculate VAT using Purchase Invoice
134 | 2021 | Indian Localization | Sales Tax / VAT | Lab 4.5– Calculate VAT with Retention limit defined in Tax Details level
135 | 2022 | Indian Localization | Sales Tax / VAT | Lab 4.6– Calculate VAT in case of Fixed Asset when Deferment Period is 6M
136 | 2023 | Indian Localization | Sales Tax / VAT | Lab 4.7– Calculate VAT in case of normal through Purchase Return Order
137 | 2024 | Indian Localization | Sales Tax / VAT | Lab 4.8– Calculate VAT using Sales Invoice
138 | 2025 | Indian Localization | Sales Tax / VAT | Lab 4.9– Calculate VAT using Sales Invoice with Standard Deduction
139 | 2026 | Indian Localization | Sales Tax / VAT | Lab 4.10– Calculate VAT in case of VAT Exempted option on sale of goods
140 | 2027 | Indian Localization | Sales Tax / VAT | Lab 4.11– Adjustment of VAT in case of capital item when VAT Adjustment Type is Lost or Destroy
141 | 2028 | Indian Localization | Sales Tax / VAT | Lab 4.12– Entering VAT opening in case of G/L account
142 | 2029 | Indian Localization | Sales Tax / VAT | Lab 4.13– Entering VAT opening in case of Fixed Asset
143 | 2030 | Indian Localization | Sales Tax / VAT | Lab 4.14– Entering VAT opening in case of G/L Account

## 10
Lessons Learned
Phase | Type | Items
1 | Positive | Parking Lot for topics not addressed
1 | Positive | Topic Planning
1 | Positive | Setting the working agreement & ground rules
1 | Positive | Practice and examples given are good
1 | Positive | Topic Coverage was satisfactory
1 | Need Improvement | Schedule not prepared and shared with participants
1 | Need Improvement | Recording could have happened for the sessions
1 | Need Improvement | Break Management not done properly
1 | Need Improvement | Lunch time should have been more
2 | Need Improvement | When taking time from a consultant/trainer schedule a call between sales, trainer. Set expectation. Set agenda, timing etc.
2 | Need Improvement | Maintain checkin checkout time
2 | Need Improvement | Do not promise anything which is not possible.
2 | Need Improvement | Do not promise anything which you think is not required
Keep redefining ground rules for better facilation. E.g meaining of customization, parking lot etc.
Trainers

## 11
Customization Efforts
# | Work | Duration | 33
61 | 9. Handling Dimensions (view the expense report dimension-wise); As per the COA, all the sub-ledgers entity codes, project codes..etc are being managed thru dimensions; | Discussed (but need further discussion)
65 | d. To have additional field for a particular dimensions | Customization 2 days | 2
69 | a. Setup the cheque measurements for the Cheque printing. Avoiding and devoiding cheques. | Customization 2-3 Days | 3
70 | b. How to enable automatic BRS say receive a file from the bank and upon upload BRS is done automatically | Customization 3-4 Days | 4
73 | e. Missing receipt no printing | Customization 1-2 Days | 2
74 | f. How to handle online transfers & RTGS/NEFT payments. | Customization 1-2 Days | 2
76 | a. How to have a dual control for approval of expenditure | Customization 3-4 Days | 3
77 | b. How to escalate/recommend for the approvals | Customization 3-4 Days | 3
82 | 14. Inter-trust transfers; Inter – Trust transfers are those transaction happens between two separate legal entities. This may include shared expense segregation, allocating global overheads, fund transfers, revenue sharing…etc | Customization 4-5 Days | 4
92 | 17. Reminders to Debtors on their dues once the credit period limit exceeds. | 3-4 Days Customization | 3
134 | 8. How to close purchase orders PO /CO wise / Item wise | Customization 2 Days | 2
145 | 19. Packing Slip during DC | Customization 4 Days | 4
154 | 28. Barcode Printing for Labels | 1 Day Customization | 1
| Invoice Report - Tax Breakup | 4 hrs | 0.5
| Bifercation of export vs local entries of sales/purchase trans | 1 Hrs | 1

## 12
Parking Lot
# | Items | Status
1 | What is POT (Point of Taxation) in GL Setup | Closed
2 | GL entry locking in GL Setup | Closed
3 | Tax Info | Closed
4 | Check GL A/C Usage | Closed
5 | Tolerance A/C creation in GL Account | Closed
6 | Month on Month Closing and year end closing in A/Cing Period | Closed
7 | Global vs Short Cut Dimension in GL Setup | Closed
8 | Inventory Period Closed in A/C Period | Closed
9 | Posting Tab Fields/GL Account Card | Closed
10 | Blanket Discount For Group of Items for All customer group of Customer | Closed
11 | POS/Retail free items | Closed
12 | Sales projection at the time of purchase | Closed
13 | Customer classification, Barcode Printing | Closed
14 | Sales Forecast close Procurment | Closed
15 | How to Navigate through NaV | Closed
16 | Multiple cost sheets | Not able to recall
17 | How to change assignment- amount wise | Closed
18 | Sales Tax- Period Field in states to be explained | Closed
19 | Tax Posting for different Tax Rate | Closed
20 | Credit Memos of Privious Years | Closed
21 | Cost A/C History | Closed
22 | Role Centre/Responsbility Centre and Service Zone Code | Next Phase
23 | Change log in Fixed Assets
24 | Source Type in Cash flow mapping
25 | IB Purchase Examples-> Inclusive and exclusive
26 | Excise Related-> Inventory
27 | IC Series and IC company loan & reciavable & Payable A/C same block.
28 | Single ledger posting config with multiple taxes
29 | During transaction if we change VAT then how it affects ledger
30 | Point #14 of 14-Apr Training