## Plan
SEQUOIA CAPITAL INDIA ADVISORS (P) LTD- MICROSOFT DYNAMICS NAV 2013 IMPLEMENTATION PROJECT PLAN
MODULES COVERED - FINANCE, AR, AP & FIXED ASSETS
Proposal Ref | Title | Activities | Responsibility | Deliverable | Location |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | Status
[6 empty] | 2014-07-02 | 2014-07-07 | 2014-07-14 | 2014-07-21 | 2014-07-28 | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01
INITIATION
| KICK-OFF MEETING | PROJECT INITIATION
|  | PRESENTATION OF IMPLEMENTATION METHODOLOGY | ABS |  | SEQUOIA | [10 empty] | Completed
|  | REVIEW OF AVAILABLE RESOURCES-TEAM IDENTIFICATION (PROCESS OWNERS, PROJECT MANAGER, SIGNING AUTHORITY) | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed
|  | PRESENTATION & APPROVAL OF PROJECT PLAN | ABS&SEQUOIA | PROJECT PLAN | SEQUOIA | [10 empty] | Completed
4.2 | Requirement Analysis & Designing | ANALYSIS & DESIGN | bar: 2014-07-07 to 2014-07-21
|  | DATABASE-COMPANY STRUCTURE AWARENESS SESSION TO THE KEY USER GROUP | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PRODUCT CAPABILITY & UTILIZATION AWARENESS TO THE KEY USER GROUP | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | LEGAL ENTITIES STRUCTURE | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | FINANCIAL MANAGEMENT & ACCOUNTING STRUCTURE INCL. CHART OF ACCOUNTS & JOURNAL BATCHES - REQ. | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | BANK ACCOUNTS, TRANSACTIONS, CURRENCIES, ADDNL. REPORTING CURRENCY, EXCHANGE RATE & BRS REQ. | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | AR &AP REQ | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | FIXED ASSETS ACCOUNTING | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | SEQUOIA- FINANCIAL STATEMENTS & PERIODIC REPORTS- REQ | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | FUND COMPANY- CREATION - GENERAL INFORMATION AND SET UP- REQ. | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | FUND COMPANY -ACCOUNTING STRUCTURE, GENERAL ACCOUNTING & BANK ACCOUNT MANAGEMENT REQ. | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | INTERCOMPANY FINANCIAL TRANSACTIONS (BETWEEN SEQUOIA & GROUP/FUNDCOMPANY) REQ. | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | FINALYZING DIMENSIONS | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PROCESS FINALIZATION WORKSHOP | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | DATA CONVERSION & VOLUME MATRIX( OPB) | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | COLLECT VARIOUS TEST CASES & DOCUMENT FORMATS |  |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | FINANCIAL VOUCHERS, ADVICE, CHECK PRINTING DRN & CRN | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | SALES- TEST CASES & DOCUMENT FORMATS | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PURCHASE- TEST CASES & DOCUMENT FORMATS | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
| FUNCTIONAL REQ. DOCUMENTATION | FRD & FIT GAP | bar: 2014-07-07 to 2014-07-21
|  | PREPARATION OF FRD (FUNCTIONAL REQUIREMENT DOCUMENT) | ABS |  | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PREPARE GAP-FIT DOCUMENT (INCLUDING REPORTING REQUIREMENTS) | ABS |  | ABS | [10 empty] | Incorporated in FRD | bar: 2014-07-07 to 2014-07-21
|  | FRD PRESENTATION | ABS&SEQUOIA | FRD (Functional Requirement Document) | SEQUOIA | [10 empty] | To be signed off | bar: 2014-07-07 to 2014-07-21
|  | FRD SIGN OFF | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | GAP - FIT RESOLUTION WORKSHOP (PROCESS CONFIRMATION) | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | WORKSHOP ON FINANCE , AP, AR, BANK, FA | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PREPARE LIST OF CUSTOMISED DELIVERABLES (INCLUDING REPORTING REQUIREMENTS) | ABS | LIST OF DELIVERABLES | ABS | [10 empty] | Incorporated in FRD | bar: 2014-07-07 to 2014-07-21
|  | REVIEW IMPACT OF GAP-FIT RESOLUTION ON PROJECT PLAN | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
| SOLUTION DESIGN | CUSTOMISATION - TO BE BUILD | bar: 2014-07-07 to 2014-07-21
|  | IDENTIFY LIMITATIONS IN THE OUT-OF-BOX SOLUTION AND DISCUSS WORK AROUND | ABS |  | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PREPARATION OF ENTERPRISE DESIGN DOCUMENT (EDD) | ABS |  | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PRESENTATION OF EDD | ABS | EDD (Enterprise Design Document) | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | CUSTOMISATION | ABS |  | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | REPORTS (TO BE BUILD) | ABS |  | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | PREPARATION OF TEST CASES (SEQUOIA TO PROVIDE INFO) | ABS |  | ABS | [10 empty] | Completed | bar: 2014-07-07 to 2014-07-21
|  | UNIT TESTING | ABS |  | ABS | [10 empty] | In Progress | bar: 2014-07-07 to 2014-07-21
|  | COMPLETION OF STATEMENT OF WORK | ABS | TEST CASES | SEQUOIA | bar: 2014-07-07 to 2014-07-21
CONFIGURATION | bar: 2014-08-04 to 2014-08-11
| INSTALLATION & SYSTEM INITIALIZATION | INSTALLATION, DATABASE SETUP AND CONFIGURATION | bar: 2014-08-04 to 2014-08-11
|  | CLIENT ACCESS | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-11
| CREATE DB | CREATE NEW DB AND COMPANIES (LEGAL ENTITIES) | ABS |  | ABS | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-11
|  | SETTING UP COMPANIES | ABS |  | ABS | [10 empty] | Operations Companies completed. Fund in progress | bar: 2014-08-04 to 2014-08-11
| MIGRATE MASTER DATA | UPLOAD MASTERS- CUSTOMER, VENDOR, BANK, ACCOUNTS, DIMENSION | ABS |  | ABS | bar: 2014-08-04 to 2014-08-11
|  | ALL MASTERS VERIFICATION | ABS | RECORD STATISTICS | ABS | bar: 2014-08-04 to 2014-08-11
| VALIDITY CHECK | CHECK THE VALIDITY OF THE DATA CREATED/IMPORTED | ABS |  | ABS | bar: 2014-08-04 to 2014-08-11
|  | ROLE AND USER MATRIX FINALIZATION | ABS&SEQUOIA |  | SEQUOIA | bar: 2014-08-04 to 2014-08-11
|  | CUSTOMER CONFIRMATION ON MASTERDATA & SET UP | SEQUOIA | CONFIRMATION FROM CUSTOMER | SEQUOIA | bar: 2014-08-04 to 2014-08-11
|  | SUPER USER TRAINIG -AR.AP & GL SET UPS | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-11
| CRP | CRP WORKSHOP- PROCESS & TRANSACTIONS | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-11
|  | CRP-WORKSHOP- REPORTS | ABS&SEQUOIA |  | SEQUOIA | bar: 2014-08-04 to 2014-08-11
|  | OBTAIN CUSTOMER CONFIRMATION | ABS&SEQUOIA | CONFIRMATION FROM CUSTOMER | SEQUOIA | bar: 2014-08-04 to 2014-08-11
| OPB TEMPLATES | PROVIDING TEMPLATES FOR VARIOUS OPENING BALANCES | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-11
|  | PREPARATION OF CUSTOMISED USER MANUAL | ABS |  | ABS | [10 empty] | In progress | bar: 2014-08-04 to 2014-08-11
|  | DEPLOYMENT | [13 empty] | In progress | bar: 2014-08-04 to 2014-08-18
13 | TRAINING | TRAINING FOR USERS ON THE CUSTOMISED FINAL PRODUCT |  | USER MANUAL | bar: 2014-08-04 to 2014-08-18
|  | USER TRAINING | ABS&SEQUOIA |  | SEQUOIA | [10 empty] | In Progress | bar: 2014-08-04 to 2014-08-18
| USER ACCEPTANCE TEST | USER ACCEPTANCE TESTING OF SAMPLE SCENARIOS | bar: 2014-08-04 to 2014-08-18
|  | UAT INSTANCE SET UP | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-18
|  | INTERAGATION TESTING | SEQUOIA | TESTING STRATEGY DOCUMENT, LIST OF FUNCTIONALITIES, TRANSACTIONS & REPORTS | SEQUOIA | [10 empty] | Completed | bar: 2014-08-04 to 2014-08-18
|  | PERFORM UAT | SEQUOIA |  | SEQUOIA | [10 empty] | In progress | bar: 2014-08-04 to 2014-08-18
|  | GENERATE REPORTS | SEQUOIA |  | SEQUOIA | [10 empty] | In progress | bar: 2014-08-04 to 2014-08-18
|  | REVIEW RESULTS AND OBTAIN SIGN OFF | ABS&SEQUOIA |  | SEQUOIA | bar: 2014-08-04 to 2014-08-18
GO-LIVE | bar: 2014-08-25 to 2014-09-01
23 | SYSTEM READINESS | GO-LIVE SET UP | bar: 2014-08-25 to 2014-09-01
|  | PRODUCTION INSTANCE SET UP | ABS |  | SEQUOIA | [10 empty] | Completed | bar: 2014-08-25 to 2014-09-01
|  | ROLE AND USER MATRIX SET UP | ABS&SEQUOIA |  | SEQUOIA | bar: 2014-08-25 to 2014-09-01
|  | REPORTS ( CONFIGURABLE) | ABS |  | SEQUOIA | [10 empty] | In Progress | bar: 2014-08-25 to 2014-09-01
|  | FINALYZE CUT OVER AND GO-LIVE | ABS&SEQUOIA |  | SEQUOIA | bar: 2014-08-25 to 2014-09-01
|  | UPLOADING OPB | ABS | BALANCE CONFIRMATION FROM CUSTOMER | SEQUOIA | [10 empty] | Completed | bar: 2014-08-25 to 2014-09-01
|  | FINAL SET UP TESTING / CHECK UP | ABS&SEQUOIA | E MAIL CONFIRMATION FROM CUSTOMER | SEQUOIA | [10 empty] | Completed | bar: 2014-08-25 to 2014-09-01
| GO LIVE | GO LIVE - LIVE TRANSACTIONS | ABS&SEQUOIA | bar: 2014-08-25 to 2014-09-01
|  | LIVE TRANSACTION SUPPORT - ON SITE | ABS&SEQUOIA | QUICK REFERENCE FLOW CHARTS & PAMPHLETS | SEQUOIA | [10 empty] | Sept 1-15 provided | bar: 2014-08-25 to 2014-09-01
| SIGN OFF | PROJECT SIGN OFF & HAND OVER TO SUPPORT | ABS&SEQUOIA | CONCLUSION LETTER | SEQUOIA | bar: 2014-08-25 to 2014-09-01
ASSUMPTIONS
| 2 | 10 REPORTS WOULD BE CUSTOMISED AS PER SEQUOIA'S REQ.
| 3 | Effort upto 90 mandays is covered in the above plan. Further effort, if any would be charged on T&M basis
| 4 | Excel templates for Data migration would be provided by ABS assuming that SEQUOIA would provide the data as per the nav structure