## Configuration
Project Code | IT-ERP-BRAS | Document Code | Action Register
Updated By | Date | Purpose
Hari Thapliyal | 2015-01-06 | Putting Action Items of 05-Jan-15 Vendor Meeting
Hari Thapliyal | 2015-01-14 | Updated Action Items status as of 14-Jan-14

## Action-Status-Log
# | Source | Action | Actionee | Due Date | Status
AI-001 | MoM-02-Jan-14 | Setup an Information Radiator | JNVD | 2015-01-05 | Deferred
AI-002 | MoM-02-Jan-14 | Finalize Risk Register | JNVD | 2015-01-16 | WIP
AI-003 | MoM-02-Jan-14 | Finalize Business Case Template | Hari | 2015-01-14 | Open
AI-004 | MoM-05-Jan-14 | Send a sample of project plan of ABS to JNVD | ABS/Lakshmi | 2015-01-06 | Close
AI-005 | MoM-05-Jan-14 | Send a sample BRAS study document to JNVD | ABS/Lakshmi | 2015-01-06 | Close
AI-006 | MoM-05-Jan-14 | Send project Status Report to JNVD | ABS/Lakshmi | 2015-01-06 | Close
AI-007 | MoM-05-Jan-14 | Get the schedule of activities for the IT-ERP-BRAS project from ABS | ABS |  | Cancelled
AI-008 | MoM-05-Jan-14 | Share Cost components which covers TCO (Total cost of ownership) and their cost to JNVD | ABS/Ananad | 2015-01-09 | Open
AI-009 | MoM-05-Jan-14 | Share ERP implementation Architecture with JNVD | ABS/Ananad | 2015-01-06 | WIP
AI-010 | MoM-05-Jan-14 | Draft Presentation by ABS to ISKCON | ABS/Lakshmi | 2015-01-14 | Open
AI-011 | MoM-05-Jan-14 | Incorporate feedback and present to AAD | ABS | 2015-01-16 | Open
AI-012 | MoM-05-Jan-14 | Prepare list of challenges, risk and their address plan | ABS/Ananad | 2015-01-16 | Open
AI-013 | MoM-05-Jan-14 | Prepare a Project Benefit Plan from Technical and Operational perspective | ABS/Ananad | 2015-01-16 | Open
AI-014 | MoM-05-Jan-14 | Cost breakup of implementation department wise and business unit wise | ABS/Ananad | 2014-01-14 | Open
AI-015 | MoM-05-Jan-14 | Setup Configuration Management System in Google Drive & Provide Access permission to people | JNVD | 2015-01-05 | Close
AI-016 | MoM-05-Jan-14 | Prepare Project Document Access Permission Matrix | JNVD | 2015-01-16 | Open
AI-017 | MoM-05-Jan-14 | Prepare a Project Benefit Plan from Business & Org perspective | JNVD | 2015-01-06 | Open
AI-018 | MoM-05-Jan-14 | Upload all the documents shared by ABS into GoogleDrive | JNVD | 2015-01-06 | Close
AI-019 | MoM-05-Jan-14 | Share Scorecard with ABS | SVD | 2015-01-05 | Close
AI-020 | MoM-05-Jan-14 | Share IS Parameters with ABS | SVD | 2015-01-05 | Close
AI-021 | MoM-05-Jan-14 | Send business case template to ABS | Hari | 2015-01-05 | Close
AI-022 | MoM-05-Jan-14 | Present the Business Case before AAD | Hari | 2015-01-16 | Open
AI-023 | MoM-05-Jan-14 | Prepare Business Case PPT | Hari/JNVD | 2015-01-16 | Open
AI-024 | MoM-06-Jan-14 | Create PMO & Project Repository in CVS | JNVD | 2015-01-17 | Open
AI-025 | MoM-06-Jan-14 | Apply CMS process and upload documents there | JNVD | 2015-01-17 | Open
AI-026 | MoM-06-Jan-14 | Independently study scorecard & earlier BC. This is required to discuss BRAS study on 13-Jan-15 | JNVD/Hari | 2014-01-13 | Close
AI-027 | MoM-14-Jan-14 | Review Revised BRASS Report with JNVD | Hari | 2015-01-16 | Open
AI-028 | MoM-14-Jan-14 | Discussed Scorecard & Benefits with JNVD and ISKCON Management | Hari | 2015-01-16 | Open
AI-029 | MoM-14-Jan-14 | Finalized Management Presentation Template | Hari/JNVD | 2016-01-16 | Open
AI-030 | MoM-14-Jan-14 | Finalized Data for Management Presentation | Hari/JNVD | 2016-01-16 | Open

## Decision-Log
# | Decision | Board Name / Meeting Name | Date | Remarks
DC-001 | ABS need to share WIP Documents of the BRAS on daily basis with ISKON PM | Vendor Meeting | 2015-01-05
DC-002 | ABS need to share Daily Status Report with ISKON PM | Vendor Meeting | 2015-01-05