## Configuration
Project Code | IT-ERP-BRAS | Document Code | Risk Register
Author/Updation | Date | Reviewer | Date
Hari Thapliyal | 2015-01-02
2015-01-06

## BRAS-Phase
Impact
Risk ID | Risk Name | Risk Description | Risk Source | Scope | Time | Quality | Effort | Probablity | Impact | Exposure | Major Objective | Overall Indicator | Urgency | Mitigation | Contingency | Status | Last Updation Date
[8 empty] | 0.5 | 0.2 | 0.1 | Scope
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on J2: Hari Thapliyal: Refer "Impact Table" in "Master-Tables" Sheet to assign impact value
Note on L2: Hari Thapliyal: Select that objective which is getting maximum impacted

## Master-Tables
Impact Table
| 0.05 | 0.1 | 0.2 | 0.4 | 0.8 |  | Discuss this with Janarathanan and Modify this
Scope | <2% | >2% <4% | >4% <8% | >8% <10% | >10%
Time | <2% | >2% <4% | >4% <8% | >8% <10% | >10%
Cost | <2% | >2% <4% | >4% <8% | >8% <10% | >10%
Quality | Insignificant | Low | Medium | High | Very High
Risk Appetite
| Green |  | Yellow |  | Red
| Min | Max | Min | Max | Min | Max
Scope | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.99
Time | 0 | 0.2 | 0.2 | 0.3 | 0.3 | 0.99
Cost | 0 | 0.3 | 0.3 | 0.4 | 0.4 | 0.99
Quality | 0 | 0.2 | 0.2 | 0.3 | 0.3 | 0.99

## Implementation-Phase
Risk ID | Risk Name | Risk Description | Scope | Time | Quality | Effort | Risk Source | Probablity | Impact | Mitigation | Contingency
1 | Failure in business redesign process | Business requirements may change |  | 40% Days schedule increase | Fatal | 20% Effort increase | Management | 0.4
2 | Data Integration | Moving operation data into finance might cause wrong postings |  | 3+ Days schedule increase | Servere | 5% Effort increase
PROJECT Risks in ERP Implementation
Sl No | Risk Description | Impact | Risk Type | Suggestions
1 | Change in business / Redesign in business process might impact the implementation plan schedule. | Operation Head may not accept the redesign as he may feel it will impact the business. | High | Management should come with a clear vision for next 5 years on the expansion plans
After ERP implementation planning management may decide to close the units or add a new business.
2 | There will be risk in integration operational data with finance as operational data required proper controls. | Data coming to Finance without a proper checks and controls may impact on Financial statement. | High | Needs to clear with business policy and control on Data in the applications.
Improper definition of item categories / tax structure may impact on finance.
3 | Project implementation may change due to unexpected events in business. | Project plan will be delayed due to unexpected catering orders where operation team becomes busy with deliveries. | Medium | Need to have an alternative implementation ready as a stand by
4 | After training staff may leave the organisation. | As we have to train additional persons this may delay the implementation | Medium | Need to develop second in line in departments.
5 | As data has to get integrated seamlessly with a business policy project may get stuck due to lack of Business policy. | Business policy must be clear and operations team should adhere to the polices. They cannot deviates from the policies | Medium | Management should define clear policies on business
6 | Team acceptance of work around methods | In case ERP team suggest any work around for a specific team should accept and adopt the work around. | Medium | In case if straight method is not available they will suggest an alternative method to follow. Team should accept the same.
7 | Implementation team capability to understand Business and process | Process and business understanding implementation team is very important. | Medium | Project implementer should have a good business and process knowledge.