## Sheet1
| ISKCON | ABS | IB | TSF-G | TSF-P | GST | Status
Accounts & Finance | SMVD | Lakshmi A | 2015-01-02 | 2015-01-02 | 2015-01-02 | 2015-01-02 | In progress
Procurement to Payment | SMVD | Lakshmi A | 2014-12-24 | 2014-12-24 | 2014-12-30 | 2014-12-30 | Completed
Inventory & Stores Management | SMVD | Lakshmi A | 2014-12-24 | 2014-12-24 | 2014-12-30 | 2014-12-30 | Completed
Payroll & Human Resources Management | JNVD | Lakshmi A | 2014-12-24 | 2014-12-24 | 2014-12-24 | 2014-12-24 | Completed
Donations Management | JNVD | Lakshmi A | 2014-12-25 |  |  |  | Completed
Guest House & Convention Halls | JNVD | Lakshmi A | 2015-01-06
Facility Maintenance | JNVD / SMVD | Lakshmi A | 2015-01-06 | 2015-01-06 | 2015-01-06 | 2015-01-06
Project Management | JNVD / SMVD | Lakshmi A | 2015-01-07 | 2015-01-07 | 2015-01-07 | 2015-01-07 | Parked
Customer Relationship Management | JNVD | Lakshmi A | 2015-01-06
Sales Forecasting | SMVD | Lakshmi A |  | 2015-01-08 | 2015-01-08 | 2015-01-08 | Partial
Procurement Planning | SMVD | Lakshmi A |  | 2014-12-24 | 2015-01-08 | 2015-01-08 | Completed
Consignment Sales | SMVD | Lakshmi A |  | 2015-01-08 |  |  | Completed
Magazine Printing - Job Automation | JNVD | Lakshmi A |  | 2015-01-06 |  |  | In progress
Subscription Management for Magazines | JNVD | Lakshmi A |  | 2015-01-06 |  |  | Completed
Production Planning | SMVD | Lakshmi A |  |  |  |  | Completed
Sales Management | SMVD | Lakshmi A |  |  |  |  | Completed
Quality Control | SMVD | Lakshmi A |  |  |  |  | In progress
POS Requirements Study | JNVD / SMVD | Lakshmi A, Anand Murali, Ravindra Kini | 2015-01-06 | 2015-01-06 | 2015-01-06 | 2015-01-06 | In progress
Integration vs. Build Requirements | JNVD | Lakshmi A |  |  |  |  | In progress
Note on E17: Temple Counters / Mobile Vans / Online Sales / Export
Note on F17: Temple Counters / Outlets / Restaurants / Catering Orders
Note on G17: Exports / Distributors / Retail / Online
Note on A18: raw materials / production plants / finished goods stores

## Legends
Completed
Planned
Delayed
Not in Scope