## Sprint-Master
Sprint# | Week of Year | Sprint Duration (in Weeks) | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
2015-46 | Sprint01 | 1 | 2015-11-11 | 2015-11-17 | 3 | 7
2015-47 | Sprint01 | 1 | 2015-11-18 | 2015-11-24 | 3 | 7
2015-48 | Sprint02 | 3 | 2015-11-25 | 2015-12-01 | 3 | 7
2015-49 | Sprint02 | 3 | 2015-12-02 | 2015-12-08 | 3 | 7
2015-50 | Sprint02 | 3 | 2015-12-09 | 2015-12-15 | 3 | 7
2015-51 | Sprint03 | 1 | 2015-12-15 | 2015-12-21 | 4 | 7 | 130
2015-52 | Sprint04 | 1 | 2015-12-22 | 2015-12-28 | 4 | 7
2015-53 | Sprint05 | 1 | 2015-12-29 | 2016-01-04 | 4 | 7
Formulas:
Sprint# = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+1

## Resources
Week of Year | (Multiple Items)
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
CON#1 | Latha V | SME | LV | 1
CON#2 | Priya P | DOC | PP | 4.2
CON#3 | Sudha M | DOC | SUM | 5
F0101 | Seshan T R | SM | STR | 0.8
F100 | NT Nathan | SM | NTN | 0.2
F7303 | Senthil Nathan Sai | Dev | SNS | 0.8
FT13554 | Aashiq Hameed | Dev | AH | 0.2
Grand Total |  |  |  | 12.2

## PRA
Update this Every Weekend
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | Account
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | CON#2 | 0.2 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-48 | Sprint02 | 3 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-49 | Sprint02 | 4 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-50 | Sprint02 | 5 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | CON#1 | 0.2 | Latha V | LV | SME | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | CON#2 | 1 | Priya P | PP | DS | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | CON#3 | 1 | Sudha M | SUM | DS | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F7303 | 0.2 | Senthil Nathan Sai | SNS | Dev | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | FT13554 | 0.2 | Aashiq Hameed | AH | Dev | KE
KE.BBD.01 | 2015-51 | Sprint03 | 5 | F100 | 0.2 | NT Nathan | NTN | SM | KE
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Story ID | Story Name | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO
US.BBD.09 | Enrollment/Commit Process |  | Sprint01 | WIP
US.BBD.10 | Interfaces/Transmittals/COS Payroll |  | Sprint02 | WIP
US.BBD.02 | Set Up/Carrier Setup |  | Sprint01 | WIP
US.BBD.03 | Set Up/Client Setup |  | Sprint01 | WIP
US.BBD.04 | Set Up/Policy Setup / Carrier Group Setup |  | Sprint01 | WIP
US.BBD.05 | Set Up/Employer Group Setup |  | Sprint01 | WIP
US.BBD.06 | Set Up/Add Classification |  | Sprint01 | WIP
US.BBD.07 | Set Up/Add Location |  | Sprint01 | WIP
US.BBD.08 | Set Up/Add Occupation |  | Sprint01 | WIP
US.BBD.17 | Admin/Rate Updater |  | Sprint03 | WIP
US.BBD.20 | Admin/Salary Update |  | Sprint03 | WIP
US.BBD.24 | Enrollment/Open Enrollment (OE), Life Events (LE), New Hire (NH) |  | Sprint03 | WIP
US.BBD.01 | Introduction
US.BBD.11 | Set Up/Enrollment Rule
US.BBD.12 | Set Up/Rule Setup
US.BBD.13 | Set Up/Open Enrollment Setup
US.BBD.14 | Admin/Manage Subscribers
US.BBD.15 | Admin/Manage Dependents
US.BBD.16 | Admin/Manage Benefits
US.BBD.18 | Admin/Rate Updater for Type 2 plans
US.BBD.19 | Admin/Age Band Changes / Age Reduction
US.BBD.21 | Interfaces/Transmittals
US.BBD.22 | Interfaces/Recurring Multi-Client Import (RMCI)
US.BBD.23 | Interfaces/Web Import
Note on H2: Author: The primary user or stakeholder for the story
Note on I2: Author: The goal that the actor is trying to achieve in the story
Note on J2: Author: The actions performed by the actor.
Note on K2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
Current Wk# | Sprint03 | [6 empty] | Efforts |  |  |  | Development |  |  | Documentation |  |  | QA | Acceptance
Auto Calculation | [6 empty] | % Work Complete => |  |  | 22.22% | Actual | 4 | 1 | 0 | 11 | 0 | 0 | 0 | 0
No Entry | [5 empty] | 0 |  | 72 | 16 | 56 | Planned | 14 | 8 | 4 | 4 | 20 | 12 | 7 | 3
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Remaining Work | Type | Knowledge Transfer/ Demo | Pseduo Document | Review Pseduo Document | Draft Flow Chart of UI | Draft Flow chart of Pseudo Code | Mearge both Flow Chart | Review of Flowchart & Pseduo Code Doc | Demoed to PO
KE.BBD.01 | 2015-46 | Sprint01 | 1 | US.BBD.09 | Enrollment/Commit Process | 0 | Moved | 55 | 55 | 0 | Name |  | PP,SUM |  | PP, SUM, LV | PP, SUM, LV | PP, SUM | SNS, STR | STR
| 2015-46 | Sprint01 | [8 empty] | Status | NR | Done |  | Done | WIP | WIP | Done
| 2015-46 | Sprint01 | [8 empty] | Planned |  | 24 |  | 10 | 19 | 2
| 2015-46 | Sprint01 | [8 empty] | Actual |  | 24 |  | 10 | 19 | 2
KE.BBD.01 | 2015-46 | Sprint01 | 2 | US.BBD.10 | Interfaces/Transmittals/COS Payroll | 0 | Moved | 4 | 4 | 0 | Name |  | PP,SUM |  |  | PP, SUM, LV | PP, SUM | SNS, STR | STR
| 2015-46 | Sprint01 | [8 empty] | Status | NR | Done |  | NR | NS | NS | NS
| 2015-46 | Sprint01 | [8 empty] | Planned |  | 4 |  |  | ?? | ?? | ??
| 2015-46 | Sprint01 | [8 empty] | Actual |  | 4
KE.BBD.01 | 2015-47 | Sprint01 | 3 | US.BBD.09 | Enrollment/Commit Process | 0 | Moved | 45 | 45 | 0 | Name |  | PP,SUM |  | PP, SUM, LV | PP, SUM, LV | PP, SUM | SNS, STR | STR
| 2015-47 | Sprint01 | [8 empty] | Status | NR | Done |  | NR | WIP | WIP | Done
| 2015-47 | Sprint01 | [8 empty] | Planned |  | 24 |  |  | 19 | 2
| 2015-47 | Sprint01 | [8 empty] | Actual |  | 24 |  |  | 19 | 2
KE.BBD.01 | 2015-47 | Sprint01 | 4 | US.BBD.10 | Interfaces/Transmittals/COS Payroll | 0 | Moved | 4 | 4 | 0 | Name |  | PP,SUM |  | PP,SUM | PP, SUM | PP, SUM,LV | SNS, STR | STR
| 2015-47 | Sprint01 | [8 empty] | Status | NR | Done |  | NS | NS | NS | NS
| 2015-47 | Sprint01 | [8 empty] | Planned |  | 4 |  |  | ?? | ?? | ??
| 2015-47 | Sprint01 | [8 empty] | Actual |  | 4
KE.BBD.01 | 2015-48 | Sprint02 | 5 | US.BBD.09 | Enrollment/Commit Process | 0 | Moved | 32 | 38 | 0 | Name |  |  |  | PP,SUM | PP,SUM,LV | PP,SUM,LV
| 2015-48 | Sprint02 | [8 empty] | Status |  |  |  | NR | Done | WIP
| 2015-48 | Sprint02 | [8 empty] | Planned |  |  |  |  | 24 | 8
| 2015-48 | Sprint02 | [8 empty] | Actual |  |  |  |  | 28 | 10
KE.BBD.01 | 2015-48 | Sprint02 | 6 | US.BBD.10 | Interfaces/Transmittals/COS Payroll | 0 | Moved | 0 | 0 | 0 | Name |  |  |  | PP,SUM | PP,SUM,LV | PP,SUM,LV
| 2015-48 | Sprint02 | [8 empty] | Status |  |  |  | NS | NS | NS
| 2015-48 | Sprint02 | [8 empty] | Planned
| 2015-48 | Sprint02 | [8 empty] | Actual
KE.BBD.01 | 2015-49 | Sprint02 | 8 | US.BBD.09 | Enrollment/Commit Process | 0 | Moved | 3 | 5 | -2 | Name |  |  |  | PP,SUM | PP,SUM,LV | SUM
| 2015-49 | Sprint02 | [8 empty] | Status |  |  |  | Done | Done | Done
| 2015-49 | Sprint02 | [8 empty] | Planned | [5 empty] | 3
| 2015-49 | Sprint02 | [8 empty] | Actual | [5 empty] | 5
KE.BBD.01 | 2015-49 | Sprint02 | 9 | US.BBD.10 | Interfaces/Transmittals/COS Payroll | 0 | Moved | 42 | 50 | 0 | Name |  |  |  | PP,SUM | PP,SUM | PP,SUM,LV
| 2015-49 | Sprint02 | [8 empty] | Status |  |  |  | Done | WIP | WIP
| 2015-49 | Sprint02 | [8 empty] | Planned |  |  |  | 8 | 24 | 10
| 2015-49 | Sprint02 | [8 empty] | Actual |  |  |  | 10 | 28 | 12
KE.BBD.01 | 2015-50 | Sprint02 | 10 | US.BBD.09 | Enrollment/Commit Process | 0 | Moved | 0 | 0 | 0 | Name |  |  |  | PP,SUM | PP, SUM, LV | PP,SUM,LV
| 2015-50 | Sprint02 | [8 empty] | Status |  |  |  | Done | Done | Done
| 2015-50 | Sprint02 | [8 empty] | Planned
| 2015-50 | Sprint02 | [8 empty] | Actual
KE.BBD.01 | 2015-50 | Sprint02 | 12 | US.BBD.10 | Interfaces/Transmittals/COS Payroll | 0 | Moved | 36 | 44 | 0 | Name |  |  |  | PP,SUM | PP,SUM | PP,SUM,LV
| 2015-50 | Sprint02 | [8 empty] | Status |  |  |  | NR | Done | Done
| 2015-50 | Sprint02 | [8 empty] | Planned |  |  |  |  | 20 | 16
| 2015-50 | Sprint02 | [8 empty] | Actual |  |  |  |  | 24 | 20
KE.BBD.01 | 2015-51 | Sprint03 | 13 | US.BBD.17 | Admin/Rate Updater | 0 | WIP | 34 | 13 | 21 | Name | SNS | AH | SNS | SUM,PP | SUM,PP | LV | NTN | STR
| 2015-51 | Sprint03 | [8 empty] | Status | WIP | WIP | NS | WIP | NS | NS | NS | NS
| 2015-51 | Sprint03 | [8 empty] | Planned | 8 | 4 | 2 | 4 | 8 | 4 | 3 | 1
| 2015-51 | Sprint03 | [8 empty] | Actual | 2 |  |  | 11
KE.BBD.01 | 2015-51 | Sprint03 | 14 | US.BBD.20 | Admin/Salary Update | 0 | WIP | 25 | 3 | 22 | Name | SNS | AH | SNS |  | SUM,PP | LV | NTN | STR
| 2015-51 | Sprint03 | [8 empty] | Status | WIP | WIP | NS | NR | NS | NS | NS | NS
| 2015-51 | Sprint03 | [8 empty] | Planned | 6 | 4 | 2 |  | 6 | 4 | 2 | 1
| 2015-51 | Sprint03 | [8 empty] | Actual | 2 | 1
KE.BBD.01 | 2015-51 | Sprint03 | 15 | US.BBD.24 | Enrollment/Open Enrollment (OE), Life Events (LE), New Hire (NH) | 0 | WIP | 13 | 0 | 13 | Name | SNS |  |  | SUM,PP |  |  | NTN | STR
| 2015-51 | Sprint03 | [8 empty] | Status | Done | NR | NR | Done | NR | NR | NS | NS
| 2015-51 | Sprint03 | [8 empty] | Planned |  |  |  |  | 6 | 4 | 2 | 1
| 2015-51 | Sprint03 | [8 empty] | Actual
Note on L6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes