## Objectives
Code | Objective
TB | Team Binding
PF | Project Focussed
RP | Retention of Performers
AEL | Auto Expulsion of Laggers
NCCPQ | No competion at the cost of Product Quality
QD | Quality Delivery
TD | Timely Delivery
B4O | Binding for the Organization
DUPL | Discourage unplanned off from work
VCC | Value creation for Customer
VCO | Value creation for Organization
TP | Team Play
AT | Agility in Team
HTP | High Team Productivity
TEW | Team Enjoy Working

## Score
|  |  | Update this Every Weekend After Retrospective |  |  |  |  | Update this Every Weekend After Retrospective
|  |  | Project Code | KE.BBPE.1 | Final Score | 68.38% |  | Project Code | KE.BBPE.1 | Final Score | 74.16%
|  |  | Sprint # | 1 | Wk#-> | 2015-47 |  | Sprint # | 1 | Wk#-> | 2015-48
|  |  | Sprint Start Date | 2015-11-16 | Sprint End Date | 2015-11-20 |  | Sprint Start Date | 2015-11-23 | Sprint End Date | 2015-11-29
|  |  | Sprint Duration (Days) | 5 | No of Resources | 5 |  | Sprint Duration (Days) | 5 | No of Resources | 3
|  |  |  | 100% | 0% |  |  |  | 100% | 0%
| Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total
| Team Living Agile Values | 33% |  | 3.54 | 5 | 23.36% | 33% |  | 3.73 | 5 | 24.62%
| Team is Focussed |  |  | 3.75 | 5 |  |  |  | 4.13 | 5
| Team is Committed to Sprint Goal |  |  | 3.5 | 5 |  |  |  | 3.63 | 5
| Team has Courage to take risk and make decisions |  |  | 4 | 5 |  |  |  | 3.88 | 5
| Close Communications |  |  | 3.5 | 5 |  |  |  | 3.13 | 5
| Team is Respect practices, other values, other people's value |  |  | 2.25 | 5 |  |  |  | 3.88 | 5
| Team is living opennes/transparency value |  |  | 4.25 | 5 |  |  |  | 3.75 | 5
| Team Living Agile Principles | 34% |  | 2.98 | 5 | 20.26% | 34% |  | 3.5 | 5 | 23.8%
| Continuous Value Delivery |  |  | 0.5 | 5 |  |  |  | 3.5 | 5
| Welcome Change |  |  | 3.25 | 5 |  |  |  | 3.88 | 5
| Deliver Frequently |  |  | 0 | 5 |  |  |  | 2.88 | 5
| Scrum Team Working Together |  |  | 4.25 | 5 |  |  |  | 3.63 | 5
| Team members are Highly Motivated |  |  | 4.25 | 5 |  |  |  | 3.38 | 5
| Sustainable Pace |  |  | 3 | 5 |  |  |  | 3.63 | 5
| Technical Excellence |  |  | 3.75 | 5 |  |  |  | 3.75 | 5
| Architecutre is Evolving |  |  | 4 | 5 |  |  |  | 3.5 | 5
| Regular Cadence |  |  | 2.75 | 5 |  |  |  | 3.25 | 5
| Adjusting Behaviour |  |  | 4 | 5 |  |  |  | 3.63 | 5
| Competency and Enjoying Work | 33% |  | 3.75 | 5 | 24.75% | 33% |  | 3.9 | 5 | 25.74%
| Great Team |  |  | 4.75 | 5 |  |  |  | 4.13 | 5
| Moral of the team |  |  | 4.5 | 5 |  |  |  | 3.75 | 5
| Helpfulness of team to each other |  |  | 4.75 | 5 |  |  |  | 4.63 | 5
| Ability to solve impediments |  |  | 4.25 | 5 |  |  |  | 4 | 5
| Team Proactiveness |  |  | 4.25 | 5 |  |  |  | 3.13 | 5
| Team's ability to deliver the commitments |  |  | 0 | 5 |  |  |  | 3.75 | 5
Benchmark | Productivity, Quality | 0% |  |  |  | 0% | 0% |  |  |  | 0%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5% | 5% | 0.5 | 100% |  | 5%
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Test Coverage | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
1 | Number of Product Demos | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | Issues in the issue log | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5% | 5% | 25 | 100% |  | 5%
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
Note on E7: Enter between 1 - 5
Note on F7: Enter between 1 - 5
Note on J7: Enter between 1 - 5
Note on K7: Enter between 1 - 5
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## Score-Summary
Project Id | Sprint St Date | Sprint End Date | Year Wk# | Project Wk# | Sprint# | Values | Principle | Enjoy Work | Productivity | Score | Duration | Resources
KE.BBPE.1 | 2015-11-16 | 2015-11-20 | 2015-47 | 1 | Sprint01 | 3.54 | 2.98 | 3.75 | Not Measured | 68% | 5 | 5
KE.BBPE.1 | 2015-11-23 | 2015-11-30 | 2015-48 | 2 | Sprint02 | 3.73 | 3.5 | 3.9 | Not Measured | 74% | 5 | 3
Formulas:
Year Wk# = YEAR([Sprint St Date])&"-"&WEEKNUM([Sprint St Date])

## Lessons-Log
Team Learning Register
Date | ProjectID | Soruces | Type | Particular | Actionee | Date
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Must start doing sprint planning
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Impediments must be identified, assigned and resolved within the SLA time.
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Scrum Board must be updated regularly
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Implement FxCop tool duing built to monitor code quality
2015-11-23 | KE.BBPE.1 | Retrospective | Best Practices | Learned unit testing so continue.
2015-11-23 | KE.BBPE.1 | Retrospective | Best Practices | Focus on code quality improvement. So remain conscious about code quality while doing coding.
2015-11-23 | KE.BBPE.1 | Retrospective | Best Practices | Technical discussion for learning new technology trends
2015-11-23 | KE.BBPE.1 | Retrospective | Stop Doing | Changing resource in the middle of sprint.
2015-11-30 | KE.BBPE.1 | Retrospective | Improvement | SM - Retrospective to 9.30 to 10.30 and then Sprint planning 10.30 to 11.30
2015-11-30 | KE.BBPE.1 | Retrospective | Improvement | Planned demo with client on scheduled time on Friday
2015-11-30 | KE.BBPE.1 | Retrospective | Improvement | Sprint duration 2 weeks