## Sprint-Master
Week of Year | Sprint# | Sprint Duration (in Weeks) | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
2015-45 | Sprint01 | 1 | 2015-11-03 | 2015-11-09 | 8 | 7 |  |  |  |  | No Sprint Plan
2015-46 | Sprint02 | 2 | 2015-11-10 | 2015-11-16 | 8 | 7 |  |  |  |  | No Sprint Plan
2015-47 | Sprint02 | 2 | 2015-11-17 | 2015-11-23 | 9 | 7 |  |  |  |  | No Sprint Plan
2015-48 | Sprint03 | 3 | 2015-11-24 | 2015-11-30 | 9 | 7 | 320 | 293 | 180 | 0
2015-49 | Sprint03 | 3 | 2015-12-01 | 2015-12-07 | 9 | 7
2015-50 | Sprint03 | 3 | 2015-12-08 | 2015-12-14 | 9 | 7
2015-51 | Sprint04 | 2 | 2015-12-15 | 2015-12-21 | 9 | 7
2015-52 | Sprint04 | 2 | 2015-12-22 | 2015-12-28 | 9 | 7
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+1

## Resources
Week of Year | 2015-51
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
F16839 | Nadem Manohar | Dev | NM | 1
F14580 | Braj Mohan Goud | Dev | BM | 1
F16520 | Pramod Kumar Matam | Dev | PKM | 1
F12175 | Thirupathi Kusa | Dev | TK | 1
FT14752 | Ramakrishnan | QA | RKN | 1
F8614 | Suresh V | Dev | SUV | 1
F17107 | Sampath Rao Tirumala Ratnagiri Raju | SM | SR | 1
F17018 | Murali Krishna J | Dev | KJ | 1
F15463 | Sai Prasanth | Dev | SP | 1
Client03 | Tanbeer Ahmed | PO | TA | 1
Grand Total |  |  |  | 10

## PRA
Update this Every Weekend
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | Account
KE.DWBI.1 | 2015-45 | Sprint01 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-45 | Sprint01 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-46 | Sprint02 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-48 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-49 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-50 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev | KE
KE.DWBI.1 | 2015-51 | Sprint03 |  | Client03 | 1 | Tanbeer Ahmed | TA | PO | KE
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Category | Frequency | Story Name | Resource | Effort (Planned) | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Estimator1 | Estimator2 | Estimator3 | Estimator4 | Status
US.DWBI.SUP.001 | Support | Daily | ODS3 Job data loading and verifying BR | TK | 6 |  | NA
US.DWBI.SUP.002 | Support | Daily | Download the data from agency blocks and loading into QA & Prod env | TK | 1 |  | NA
US.DWBI.SUP.003 | Support | Daily | Monitoirng EBS jobs and verify BP files & monitor jobs | SV | 1 |  | NA
US.DWBI.SUP.004 | Support | One Time | Test all ETL jobs in linux QA env. | SV, TK | 48 |  | NA
US.DWBI.SUP.005 | Support | Friday | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | BM | ?? |  | NA
US.DWBI.SUP.006 | Support | Daily | Status monitoring of all the server- Daily | BM | ?? |  | NA
US.DWBI.SUP.007 | Support | Daily | Explorer reports and other BI reports refresh & verfication - Daily. | BM | ?? |  | NA
US.DWBI.SUP.008 | Support | Monthly | BI & BW production server backup- Monthly | BM | ?? |  | NA
US.DWBI.SUP.009 | Support | Daily | Ivos to prudential job monitoring | BM | 0.5 |  | NA
US.DWBI.SUP.010 | Support | One Time | Update visual cut application on QA server for Monthly report busting process | BM | ?? |  | NA
US.DWBI.SUP.011 | Support | Demand Basis | Migration of dashboard as per the request | BM | ?? |  | NA
US.DWBI.SUP.012 | Support | Monthly | WCIR Monthend process | TK | 8 |  | NA
US.DWBI.SUP.013 | Support | Monthly | ODS2 Monthend process & Report Bursting Process | BM | 8 |  | NA
US.DWBI.SUP.014 | Support | Monthly | WCIR Nov 2015 monthend BR issue analysis | TK,SUV | 18 |  | NA
US.DWBI.SUP.015 | Support | One time | Updateing ODS3 mapping document | TK |  |  | NA
US.DWBI.QLT.001 | Support | Tuesday | Data quality testing - Tuesday | SP, RKN |  |  | NA
US.DWBI.QLT.002 | Support |  | Verifying lacers FM dashboard | SP, RKN |  |  | NA
US.DWBI.LDB.001 | User Story |  | Laser dashboard for health management desktop version | PM |  | 40 | Sprint03 | [7 empty] | 40 | 40 | 40
US.DWBI.LDB.002 | User Story |  | Laser dashboard for health management mobile version | PM |  | 40 | Sprint03 | [7 empty] | 40
US.DWBI.LDB.001.D01 | Defect Fix |  | Laser financial dashboard fix | KJ |  | 20 | Sprint03
US.DWBI.RPT.001 | User Story |  | Agency Report | NM | 20 |  | Sprint03
US.DWBI.DEV.001 | User Story |  | Job_Load_WC_AGG1 Improvement | NM | 18 |  | Sprint03
US.DWBI.DEV.001.D02 | Defect Fix |  | HM desktop dashboard issues fix | PM | 20 |  | Sprint04
US.DWBI.LDB.001.D03 | Defect Fix |  | Laser financial dashboard fix | KJ | 20 |  | Sprint04
US.DWBI.DEV.001.D02 | Defect Fix |  | HM desktop dashboard issues fix | PM | 36 |  | Sprint04
US.DWBI.LDB.001.D03 | Defect Fix |  | Laser financial dashboard fix | KJ | 36 |  | Sprint04
Note on L2: Author: The primary user or stakeholder for the story
Note on M2: Author: The goal that the actor is trying to achieve in the story
Note on N2: Author: The actions performed by the actor.
Note on O2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.
Note on F13: Depends on Volume
Note on F14: Depends on Volume
Note on F15: Depends on Volume

## DWSB-Support
Current Wk# | Sprint04 | [6 empty] | Efforts |  |  |  | Support
Auto Calculation | [10 empty] | Actual | 14 | 12 | 8 | 0 | 0 | 0 | 0
No Entry | [7 empty] | 85 | 28 |  | Planned | 14 | 12 | 11 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Frequency | Status | Planned | Acutal | Remaining | Type | Mon | Tue | Wed | Thu | Fri | Sat | Sun
KE.DWBI.1 | 2015-48 | Sprint03 | 1 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | Accepted | 14 | 14 |  | Name | TK | TK | TK | TK | TK
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [8 empty] | Planned | 2 | 3 | 3 | 3 | 3
| 2015-48 | Sprint03 | [8 empty] | Actual | 2 | 3 | 3 | 3 | 3
KE.DWBI.1 | 2015-48 | Sprint03 | 2 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | Accepted | 5 | 5 |  | Name | TK | TK | TK | TK | TK
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [8 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-48 | Sprint03 | [8 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-48 | Sprint03 | 3 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | Accepted | 5 | 5 |  | Name | SUV | SUV | SUV | SUV | SUV
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [8 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-48 | Sprint03 | [8 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-48 | Sprint03 | 4 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | Accepted | 57 | 57 |  | Name | SUV, TK | SUV, TK | SUV, TK | SUV, TK | SUV, TK
| 2015-48 | Sprint03 | [8 empty] | Status | WIP | WIP | WIP | WIP | WIP
| 2015-48 | Sprint03 | [8 empty] | Planned | 12 | 12 | 11 | 11 | 11
| 2015-48 | Sprint03 | [8 empty] | Actual | 12 | 12 | 11 | 11 | 11
KE.DWBI.1 | 2015-48 | Sprint03 | 5 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | Accepted | 5 | 5 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | Done | NR | NR | NR | Done
| 2015-48 | Sprint03 | [8 empty] | Type: Planned; Mon: 2; Fri: 3
| 2015-48 | Sprint03 | [8 empty] | Type: Actual; Mon: 2; Fri: 3
KE.DWBI.1 | 2015-48 | Sprint03 | 6 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | Accepted | 10 | 5 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-48 | Sprint03 | [8 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-48 | Sprint03 | 7 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | Accepted | 11 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 3 | 2
| 2015-48 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-48 | Sprint03 | 8 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | Accepted | 6 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | NS | WIP | WIP | WIP | NS
| 2015-48 | Sprint03 | [8 empty] | Type: Planned; Tue: 2; Wed: 2; Thu: 2
| 2015-48 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-48 | Sprint03 | 9 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | Accepted | 5 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [8 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-48 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-48 | Sprint03 | 10 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | Accepted | 3 | 3 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | WIP | WIP | WIP | NS | NS
| 2015-48 | Sprint03 | [8 empty] | Type: Planned; Mon: 1; Tue: 1; Wed: 1
| 2015-48 | Sprint03 | [8 empty] | Type: Actual; Mon: 1; Tue: 1; Wed: 1
KE.DWBI.1 | 2015-48 | Sprint03 | 11 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [8 empty] | Status | NA | NA | NA | NA | NA
| 2015-48 | Sprint03 | [8 empty] | Type: Planned
| 2015-48 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-49 | Sprint03 | 12 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | Accepted | 12 | 12 |  | Name | TK | TK | TK | TK | TK
| 2015-49 | Sprint03 | [8 empty] | Status | Done |  | Done | Done | Done
| 2015-49 | Sprint03 | [8 empty] | Planned | 2 |  | 3 | 4 | 3
| 2015-49 | Sprint03 | [8 empty] | Actual | 2 |  | 3 | 4 | 3
KE.DWBI.1 | 2015-49 | Sprint03 | 13 | US.DWBI.SUP.012 | WCIR Monthend process | Monthly | Accepted | 8 | 8 |  | Type: Name; Tue: TK
| 2015-49 | Sprint03 | [8 empty] | Type: Status; Tue: Done
| 2015-49 | Sprint03 | [6 empty] | 66 |  | Type: Planned; Tue: 8
| 2015-49 | Sprint03 | [8 empty] | Type: Actual; Tue: 8
KE.DWBI.1 | 2015-49 | Sprint03 | 14 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | Accepted | 0 | 0 |  | Type: Name
| 2015-49 | Sprint03 | [8 empty] | Type: Status
| 2015-49 | Sprint03 | [8 empty] | Type: Planned
| 2015-49 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-49 | Sprint03 | 15 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | Accepted | 16 | 16 |  | Name | SUV, TK | SUV, TK | SUV, TK | SUV, TK | SUV, TK
| 2015-49 | Sprint03 | [8 empty] | Status | WIP |  | WIP | WIP | WIP
| 2015-49 | Sprint03 | [8 empty] | Planned | 4 |  | 4 | 4 | 4
| 2015-49 | Sprint03 | [8 empty] | Actual | 4 |  | 4 | 4 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | 16 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | Accepted | 5 | 5 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Type: Status; Mon: Done; Fri: Done
| 2015-49 | Sprint03 | [8 empty] | Type: Planned; Mon: 2; Fri: 3
| 2015-49 | Sprint03 | [8 empty] | Type: Actual; Mon: 2; Fri: 3
KE.DWBI.1 | 2015-49 | Sprint03 | 17 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | Accepted | 10 | 10 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-49 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-49 | Sprint03 | [8 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-49 | Sprint03 | 18 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | Accepted | 10 | 10 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-49 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-49 | Sprint03 | [8 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-49 | Sprint03 | 19 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Status | NS | NS | NS | NS | NS
| 2015-49 | Sprint03 | [8 empty] | Type: Planned
| 2015-49 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-49 | Sprint03 | 20 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | Accepted | 2.5 | 2.5 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-49 | Sprint03 | [8 empty] | Planned | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 2015-49 | Sprint03 | [8 empty] | Actual | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
KE.DWBI.1 | 2015-49 | Sprint03 | 21 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Status | WIP | WIP | WIP | WIP | WIP
| 2015-49 | Sprint03 | [8 empty] | Type: Planned
| 2015-49 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-49 | Sprint03 | 22 | US.DWBI.SUP.013 | ODS2 Monthend process & Report Bursting Process | Monthly | Accepted | 8 | 8 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Type: Status; Tue: Done; Wed: Done
| 2015-49 | Sprint03 | [8 empty] | Type: Planned; Tue: 4; Wed: 4
| 2015-49 | Sprint03 | [8 empty] | Type: Actual; Tue: 4; Wed: 4
KE.DWBI.1 | 2015-49 | Sprint03 | 23 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [8 empty] | Status | NA | NA | NA | NA | NA
| 2015-49 | Sprint03 | [8 empty] | Type: Planned
| 2015-49 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-50 | Sprint03 | 24 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | Accepted | 15 | 15 |  | Name | TK | TK | TK | TK | TK
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 2 | 3 | 3 | 4 | 3
| 2015-50 | Sprint03 | [8 empty] | Actual | 2 | 3 | 3 | 4 | 3
KE.DWBI.1 | 2015-50 | Sprint03 | 25 | US.DWBI.SUP.014 | WCIR Nov 2015 monthend BR issue analysis | Monthly | Accepted | 18 | 18 |  | Type: Name; Mon: SUV; Tue: SUV; Wed: TK,SUV
| 2015-50 | Sprint03 | [8 empty] | Type: Status; Mon: WIP; Tue: WIP; Wed: Done
| 2015-50 | Sprint03 | [8 empty] | Type: Planned; Mon: 6; Tue: 6; Wed: 6
| 2015-50 | Sprint03 | [8 empty] | Type: Actual; Mon: 6; Tue: 6; Wed: 6
KE.DWBI.1 | 2015-50 | Sprint03 | 26 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | Accepted | 5 | 5 |  | Name | TK | TK | TK | TK | TK
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-50 | Sprint03 | [8 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-50 | Sprint03 | 27 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | Accepted | 5 | 5 |  | Name | SUV | SUV | SUV | SUV | SUV
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-50 | Sprint03 | [8 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-50 | Sprint03 | 28 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | Accepted | 10 | 10 |  | Name | SUV,TK | SUV,TK | SUV,TK | SUV,TK | SUV,TK
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-50 | Sprint03 | [8 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-50 | Sprint03 | 29 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | Accepted | 5 | 5 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Type: Status; Mon: Done; Fri: Done
| 2015-50 | Sprint03 | [8 empty] | Type: Planned; Mon: 2; Fri: 3
| 2015-50 | Sprint03 | [8 empty] | Type: Actual; Mon: 2; Fri: 3
KE.DWBI.1 | 2015-50 | Sprint03 | 30 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | Accepted | 10 | 10 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-50 | Sprint03 | [8 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-50 | Sprint03 | 31 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | Accepted | 10 | 10 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-50 | Sprint03 | [8 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-50 | Sprint03 | 32 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Status | NS | NS | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Type: Planned
| 2015-50 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-50 | Sprint03 | 33 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | Accepted | 2.5 | 2.5 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [8 empty] | Planned | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 2015-50 | Sprint03 | [8 empty] | Actual | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
KE.DWBI.1 | 2015-50 | Sprint03 | 34 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Status | WIP | WIP | WIP | WIP | WIP
| 2015-50 | Sprint03 | [8 empty] | Type: Planned
| 2015-50 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-50 | Sprint03 | 35 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | Accepted | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-50 | Sprint03 | [8 empty] | Status | NA | NA | NA | NA | NA
| 2015-50 | Sprint03 | [8 empty] | Type: Planned
| 2015-50 | Sprint03 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 36 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | WIP | 9 | 6 |  | Name | TK | TK | TK | TK | TK
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: Done; Tue: Done; Wed: WIP
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 3; Tue: 3; Wed: 3
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 3; Tue: 3
KE.DWBI.1 | 2015-51 | Sprint04 | 37 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | WIP | 3 | 3 |  | Name | TK | TK | TK | TK | TK
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: Done; Tue: Done; Wed: Done
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 1; Tue: 1; Wed: 1
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 1; Tue: 1; Wed: 1
KE.DWBI.1 | 2015-51 | Sprint04 | 38 | US.DWBI.SUP.015 | Updateing ODS3 mapping document | One time | WIP |  |  |  | Name | TK | TK | TK | TK | TK
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: WIP; Tue: WIP; Wed: WIP
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 3; Tue: 3
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 3; Tue: 3
KE.DWBI.1 | 2015-51 | Sprint04 | 39 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | WIP | 3 | 3 |  | Name | SUV | SUV | SUV | SUV | SUV
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: Done; Tue: Done; Wed: Done
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 1; Tue: 1; Wed: 1
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 1; Tue: 1; Wed: 1
KE.DWBI.1 | 2015-51 | Sprint04 | 40 | US.DWBI.SUP.004 | Analysis on the payments job performance improvement | One Time | WIP | 60 | 6 |  | Name | SUV,TK | SUV,TK | SUV,TK | SUV,TK | SUV,TK
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Wed: WIP
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Wed: 6
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Wed: 6
KE.DWBI.1 | 2015-51 | Sprint04 | 41 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | WIP | 2 | 2 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: Done
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 2
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 2
KE.DWBI.1 | 2015-51 | Sprint04 | 42 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | WIP | 4 | 4 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: Done; Tue: Done
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 2; Tue: 2
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 2; Tue: 2
KE.DWBI.1 | 2015-51 | Sprint04 | 43 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | WIP | 4 | 4 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status; Mon: Done; Tue: Done
| 2015-51 | Sprint04 | [8 empty] | Type: Planned; Mon: 2; Tue: 2
| 2015-51 | Sprint04 | [8 empty] | Type: Actual; Mon: 2; Tue: 2
KE.DWBI.1 | 2015-51 | Sprint04 | 44 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status
| 2015-51 | Sprint04 | [8 empty] | Type: Planned
| 2015-51 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 45 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status
| 2015-51 | Sprint04 | [8 empty] | Type: Planned
| 2015-51 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 46 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status
| 2015-51 | Sprint04 | [8 empty] | Type: Planned
| 2015-51 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 47 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-51 | Sprint04 | [8 empty] | Type: Status
| 2015-51 | Sprint04 | [8 empty] | Type: Planned
| 2015-51 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 48 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | WIP | 0 | 0 |  | Type: Name
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 49 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | WIP | 0 | 0 |  | Type: Name
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 50 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | WIP | 0 | 0 |  | Type: Name
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 51 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | WIP | 0 | 0 |  | Type: Name
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 52 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 53 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 54 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 55 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 56 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 57 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
KE.DWBI.1 | 2015-52 | Sprint04 | 58 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | WIP | 0 | 0 |  | Name | BM | BM | BM | BM | BM
| 2015-52 | Sprint04 | [8 empty] | Type: Status
| 2015-52 | Sprint04 | [8 empty] | Type: Planned
| 2015-52 | Sprint04 | [8 empty] | Type: Actual
Note on L6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L58: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L62: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L66: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L70: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L74: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L78: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L82: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L86: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L90: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L94: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L98: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L102: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L106: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L110: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L114: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L118: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L122: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L126: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L130: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L134: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L138: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L142: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L146: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L150: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L154: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L158: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L162: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L166: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L170: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L174: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L178: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L182: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L186: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L190: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L194: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L198: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L202: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L206: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L210: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L214: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L218: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L222: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L226: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L230: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L234: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## SB-Sprints
Current Sprint# | Sprint03 | [6 empty] | Efforts |  |  |  | Development | [7 empty] | QA |  |  | Acceptance Testing
Auto Calculation | [6 empty] | % Work Complete => |  |  | 100% | Actual | 57 | 47 | 60 | 136 | 36 | 104 | 8 | 42 | 0 | 0 | 0 | 0 | 0
No Entry | [5 empty] | 340 |  | 668 | 490 | 0 | Planned | 63 | 51 | 116 | 192 | 44 | 118 | 8 | 64 | 12 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Remaining Work | Type | Analyse Existing Work | Analyse Requirement | Update Spread Sheet | Change Components | Visualize Change | Implement Change | Test Data Prep | Unit Testing | Prepare QA Test Case | Compare UI with Prev | Compare DB data with Output | UA Test Cases | Demo to PO
KE.DWBI.1 | 2015-48 | Sprint03 | 1 | US.DWBI.LDB.001 | Laser dashboard for health management desktop version | 40 | Moved | 73 | 49 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM |  | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | WIP | WIP | Done | WIP | NA | WIP | NS | NS | NS
| 2015-48 | Sprint03 | [8 empty] | Planned | 3 | 2 | 24 | 24 | 4 | 4 |  | 8 | 4 | ?? | ??
| 2015-48 | Sprint03 | [8 empty] | Actual | 3 | 2 | 16 | 16 | 4 | 2 |  | 6
KE.DWBI.1 | 2015-48 | Sprint03 | 2 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | Moved | 53 | 0 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-48 | Sprint03 | [8 empty] | Status | NS | NS | NS | NS | NS | NS | NS | NS | NA | NA | NA
| 2015-48 | Sprint03 | [8 empty] | Planned | 3 | 2 | 16 | 16 | 4 | 4 |  | 8
| 2015-48 | Sprint03 | [8 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | 3 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | Moved | 47 | 47 | 0 | Name | KJ | KJ | KJ | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-48 | Sprint03 | [8 empty] | Planned | 3 | 2 | 0 | 16 | 4 | 16 | 2 | 4
| 2015-48 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | 1 | US.DWBI.LDB.001 | Laser dashboard for health management desktop version | 40 | Moved | 73 | 49 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM |  | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | WIP | WIP | Done | WIP | NA | WIP | NS | NS | NS
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 2 | 24 | 24 | 4 | 4 |  | 8 | 4 | ?? | ??
| 2015-49 | Sprint03 | [8 empty] | Actual | 3 | 2 | 16 | 16 | 4 | 2 |  | 6
KE.DWBI.1 | 2015-49 | Sprint03 | 2 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | Moved | 53 | 0 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-49 | Sprint03 | [8 empty] | Status | NS | NS | NS | NS | NS | NS | NS | NS | NA | NA | NA
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 2 | 16 | 16 | 4 | 4 |  | 8
| 2015-49 | Sprint03 | [8 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | 3 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | Moved | 47 | 47 | 0 | Name | KJ | KJ | KJ | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 2 | 0 | 16 | 4 | 16 | 2 | 4
| 2015-49 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | 4 | US.DWBI.RPT.001 | Agency Report | 0 | Accepted | 34 | 34 | 0 | Name | NM | NM | NM | NM | NM | NM | NM | NM | SP |  | SP | SR | SR
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done | Done | Done | Done | Done | NR | Done | Done
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 3 |  | 12 | 4 | 12
| 2015-49 | Sprint03 | [8 empty] | Actual | 3 | 3 |  | 12 | 4 | 12
KE.DWBI.1 | 2015-49 | Sprint03 | 5 | US.DWBI.DEV.001 | Job_Load_WC_AGG1 Improvement | 0 | Completed | 36 | 36 | 0 | Name | NM | NM | NM | NM | NM | NM | NM | NM
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | WIP | NR | NR | Done | NS | NS | NR | NR | NR | NR
| 2015-49 | Sprint03 | [8 empty] | Planned | 16 | 12 |  |  |  | 8
| 2015-49 | Sprint03 | [8 empty] | Actual | 16 | 12 |  |  |  | 8
KE.DWBI.1 | 2015-50 | Sprint03 | 6 | US.DWBI.LDB.001 | Laser dashboard for health management desktop version | 40 | Moved | 73 | 49 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM |  | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | WIP | WIP | Done | WIP | NA | WIP | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 | 24 | 24 | 4 | 4 |  | 8 | 4 | ?? | ??
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 | 16 | 16 | 4 | 2 |  | 6
KE.DWBI.1 | 2015-50 | Sprint03 | 7 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | Moved | 45 | 45 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done | Done | NS | Done | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 | 12 | 12 | 4 | 4 |  | 8
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 | 12 | 12 | 4 | 4 |  | 8
KE.DWBI.1 | 2015-50 | Sprint03 | 8 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | Moved | 47 | 47 | 0 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-50 | Sprint03 | 8 | US.DWBI.LDB.003 | HM Dashboard | 40 | Moved | 47 | 47 | 0 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-51 | Sprint04 | 7 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | WIP | 0 | 0 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP | SR | SR
| 2015-51 | Sprint04 | [8 empty] | Status | Done | Done | Done | Done | Done | Done | NS | Done | NS | NS | NS | NS
| 2015-51 | Sprint04 | [8 empty] | Planned
| 2015-51 | Sprint04 | [8 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 8 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | WIP | 18 | 0 | 18 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP | SR | SR
| 2015-51 | Sprint04 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-51 | Sprint04 | [8 empty] | Planned | [8 empty] | 6 | 6 | 6
| 2015-51 | Sprint04 | [8 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 8 | US.DWBI.LDB.003 | HM Dashboard | 40 | WIP | 18 | 0 | 18 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP | TA | TA
| 2015-51 | Sprint04 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-51 | Sprint04 | [8 empty] | Planned | [8 empty] | 6 | 6 | 6
| 2015-51 | Sprint04 | [8 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | 5 | US.DWBI.DEV.001 | Job_load_daily_extract_fact_load | 0 | Completed | 40 | 40 | 0 | Name | NM | NM | NM | NM | NM | NM | NM | NM
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | NA | NA | NA | Done | NS | NS | NR | NR | NR | NR
| 2015-50 | Sprint03 | [8 empty] | Planned | 14 | 16 |  |  |  | 10
| 2015-50 | Sprint03 | [8 empty] | Actual | 14 | 16 |  |  |  | 10
KE.DWBI.1 | 2015-51 | Sprint04 | 5 | US.DWBI.DEV.001 | ods_load_wcir_base_view | 0 | WIP | 36 | 20 | 16 | Name | NM | NM | NM | NM | NM | NM | NM | NM
| 2015-51 | Sprint04 | [8 empty] | Status | WIP | WIP | NA | NA | NA | WIP | NR | NR | NR | NR | NR | NR
| 2015-51 | Sprint04 | [8 empty] | Planned | 10 | 8 |  | 8 |  | 10
| 2015-51 | Sprint04 | [8 empty] | Actual | 4 | 4 |  | 6 |  | 6
Note on L6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L58: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L62: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L66: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L70: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes