## Sprint-Master
Week of Year | Sprint# | Sprint Duration (in Weeks) | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
2015-50 | Sprint01 | 1 | 2015-12-10 | 2015-12-17 | 18 | 8 | 1000
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1

## Resources
Week of Year | 2015-47 |  |  | 7 | 210
Emp ID# | (Multiple Items)
Sum of Present
Emp Name | Scrum Role | Initial | Total
Ashok S | Dev | AS | 1
Dilip Prasad J | Dev | DP | 1
Karthikeyan V | Dev | KV | 1
Sanjana Babu | QA | SB | 1
Sathish V | QA | SV | 1
Shreya Gupta | BA | SG | 1
Rajeshkanna P | Dev | RK | 1
Grand Total |  |  | 7

## PRA
Update this Every Weekend
Project Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | Account
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F16305 | 1 | Dilip Prasad J | DP | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F15435 | 1 | Sathish V | SV | QA | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F16707 | 1 | Rajeshkanna P | RK | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F14101 | 1 | Nivedha C | NC | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F17044 | 1 | Naresh Narava | NN | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F15762 | 1 | Ramachandran Ganesan | RG | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F15856 | 1 | Deepika Ranganathan | DR | QA | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#4 | 1 | Dileep (ACT) | DIL | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#5 | 1 | Rajesh (ACT) | RJ | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | TMP01 | 1 | Meenakashi Sundaram | MS | SM | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#6 | 1 | Karthikeyan (INF) | KAR | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#7 | 1 | Subananthan (INF) | SUB1 | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#8 | 1 | Subramanian (INF) | SUB2 | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#9 | 1 | Jai Thileeben (INF) | JT | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#10 | 1 | Jeya Kumar (INF) | JK | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | CON#11 | 1 | Saravanan (INF) | SAR | Dev | KE
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | F7423 | 2 | Sugumar | RS | QA | KE
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Story ID | Story Name | Story Points | Priority | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | TFS-ID | Related US-ID | Remarks1 | Remarks2
US.MYC.001 | Mycompany>Company Detail/After Clicking update, the bread crumbs vanish and go back to the view page. |  |  |  | Discussed | Benefit Manager | I want to get the details of my organization for the determining cadillac tax due to my ogranzation. So that I could estimate cadillac tax of my organization. | When I log in the system, calculator can pull the details like client name, plans , premium types into the calculator | Correct information being pulled | As per Bharat, all this information comes from a webservice and will provide the sql query for pulling this information.
US.MYC.002 | Mycompany>Company Detail/Upload control for Logo and Banner needs to be increased and should be one below the other |  |  |  | Discussed | Benefit Manager | I want to see thresholds for various cover types | When I open calc, I see ref table | Constants. | Static Page | Whether data will come from Webservice or table?
US.MYC.003 | Mycompany>Location/On clicking EDIT, the URL is broken, need to correct <ahref = .. |  |  |  | Discussed | Benefit Manager | I should be able to create/modify the threshold values of Cadillac Tax |  |  | Added by Estimation Team
US.MYC.004 | Mycompany>Location/Cancel button under add location broken URL
US.MYC.005 | Mycompany>Location/ON clicking delete, it should pop up a model instead of a JS alert
US.MYC.006 | Mycompany>Department/Delete button missing in the grid under Action
US.MYC.007 | Mycompany>Authorized Signatory/Under Edit there should also be an option to upload a signature
US.MYC.008 | Mycompany>Authorized Signatory/Add Button has a broken URL
US.MYC.009 | Mycompany>Holiday/Date field should be mandatory
US.MYC.010 | Mycompany>Holiday/Create a rule so that user cannot enter any holidays in the past
US.MYC.011 | Mycompany>Holiday/All state names are not there need to populate the dropdown with all the states
US.MYC.012 | Mycompany>Document Tempelates/Only Edit and delete in the grid
US.MYC.013 | Mycompany>Document Tempelates/Remove default and custom and hard code it to default on the backend
US.MYC.014 | Mycompany>Document Tempelates/Remove Full Name and Title in Add and view and edit and also from the grid
US.MYC.015 | Mycompany>Employment handbook/Create hyperlink in the Document type name (name) to the document
US.MYC.016 | Mycompany>Bank information/Enter the labels Bank name, routing number, account number and account type
US.MYC.017 | Mycompany>Location/City field is missing
US.MYC.018 | Mycompany>Document Tempelates/Save button not working URL error
US.MYC.019 | Mycompany>Employment handbook/Save button not working URL error
US.MYC.020 | Mycompany>Bank information/Routing # should be 9 digits numeric length
US.MYC.021 | Mycompany>Holiday/If Partial holiday is selected, need to ensure that start time and end time fields are active and user can enter the time in 24 hr format
US.EMP.001 | Employee>View Employee>demographic/Move the language option from other to personal information
US.EMP.002 | Employee>View Employee>demographic/Dependent not getting added
US.EMP.003 | Employee>View Employee>demographic/Adjust the dropdown menu for dependent
US.EMP.004 | Employee>View Employee>Employment/Compensation type drop down should have the following values : Hourly, Non-Hourly, Exempt and Non-Exempt
US.EMP.005 | Employee>View Employee>Employment/Instead of Policy, rename label to PTO Policy
US.EMP.006 | Employee all tabs and pages/Center elements in the grid
US.EMP.007 | Employee>View Employee>demographic/Last name is grayed out
US.EMP.008 | Employee>View Employee>demographic/City field is missing from personal information form
US.EMP.009 | Employee>View Employee>demographic/Update is not working, URL/Runtime error
US.EMP.010 | Employee>View Employee>demographic/Dependent not saving
US.EMP.011 | Employee>View Employee>demographic/Education not saving
US.EMP.012 | Employee>View Employee>demographic/Unable to save certification
US.EMP.013 | Employee>View Employee>demographic/For primary and secondary name, make it as first name and last name
US.EMP.014 | Employee>View Employee>demographic/Emergency contact, Instead of primary name, it should be nameRemove word 'Primary'
US.EMP.015 | Employee>View Employee>demographic/Skills from OTHER tab required????
US.EMP.016 | Employee>View Employee>Employment/Update is not working, URL/Runtime error
US.EMP.017 | Employee>View Employee>Employment/Under bank tab, payment method dropdown should have Direct 'Deposit' and 'Check' values
US.EMP.018 | Employee>View Employee>Employment/Bank Details not updating URL Runtime error
US.EMP.019 | Employee>View Employee>Employment/Text fields needed to be added for Bank name, routing number, bank number, bank address under the bank tab
US.EMP.020 | Employee>View Employee>Employment/Ability to upload a void check under the bank tab
US.EMP.021 | Employee>View Employee>Employment/Tax tab, update not working, runtime error
US.EMP.022 | Employee>View Employee>Employment/Document submit not working udner document tab
US.EMP.023 | Employee>View Employee>Terminate/Terminate button not working, runtime error
US.EMP.024 | Employee>Bulk Download/Bulk Download needs to be renamed to EXPORT
US.EMP.025 | Employee>My Profile/Remove My Profile Option from the left panel
US.EMP.026 | Employee>Timesheet/Timesheet not saving
US.CNTR.001 | Contractor>Add/Breadcrumb for contractor add needs to be add instead of Create
US.CNTR.002 | Contractor>Add/Create contractor label needs to be add contractor
US.CNTR.003 | Contractor>Add/Contractor name should be first name and last name two separate fields
US.CNTR.004 | Contractor>Add/After selecting type of contract, the label below it disappears
US.CNTR.005 | Contractor>Add/Need to add Contract start date and Contract end date fields
US.CNTR.006 | Contractor>Add/Agreement upload not working, should also display file name
US.CNTR.007 | Contractor>Add/Add1, Zipcode, state, Fed tax SSN should be marked mandatory
US.CNTR.008 | Contractor>Add/Routing # should be 9 digits only (numeric)
US.CNTR.009 | Contractor>Add/Document upload and Photo upload not working should also display file name once uploaded
US.CNTR.010 | Contractor>Add/Save is not wokring, runtime error
US.CNTR.011 | Contractor>Add/Under bank informatino, account type, not accounting type should have the dropdown values as Checking or Saving
US.CNTR.012 | Contractor/Grid values need to be centred
US.CNTR.013 | Contractor/Action column should also include delete option
US.CNTR.014 | Contractor/Grid should also display the office location of the contractor
US.PTO.001 | PTO>Personal Leave/Total of balances label is displayed twice, one should be Liability Amount ($)
US.PTO.002 | PTO>Personal Leave>Request/Employee denied grid is missing
US.PTO.003 | PTO>approve/deny/Approve/deny should move up
US.PTO.004 | PTO>Personal leave/PTO Personal Leave and PTO Medical leave needs to be merged
US.PAYR.002 | Payroll>EDIT setup/Account type should be Checking or savings
US.PAYR.003 | Payroll>EDIT setup/Routing # should be 9 digits only (numeric)
US.PAYR.004 | Payroll>Generate Payroll/Pay period should have an start date and end date
US.PAYR.005 | Payroll>Generate Payroll/Edit text label: Approve all timesheets for the period
US.MYPR.001 | MyProfile/Tab layout not proper
US.PTO.005 | PTO/Breadcrumb missing for all the links
US.PTO.006 | PTO>Mypolicy/MyPolicy not workign
US.MYPR.002 | MyProfile/Update is not working, URL/Runtime error
US.TS.001 | Timesheet/Timesheet needs to be the same as Employer, with the option for choosing daily, weekly monthly
US.DB.001 | Dashboard/Employee must be able to view his Agreement, view docs and handbook. This should be added under a new dashboard link saying 'View docs'
US.PTO.007 | PTO/Under timesheet, add a new tab where an employee can view how many leaves are remaining in terms of days, hours and leave types.
US.PTO.008 | PTO/Under timesheet, employee should be able to view which leave requests are still pending, and which ones are approved/denied.
US.ALLP.001 | ALL PAGES IN EMPLOYER AND EMPLOYEE/In all the pages, on the grid page whenever user clicks on delete, it should pop up a model instead of a JS alert
US.PAYR.006 | PAYROLL/Bank Info Service Code Implementaion
US.ALLP.002 | Logo/Logo sizing issue in header
US.EMP.027 | View Employee > Demographics/Employement submenu view itself is not loading
US.SIGN.001 | Signup/Step 3 fix
US.PAYR.007 | PAYROLL/Principal Info Service code implementation
US.PAYR.008 | PAYROLL/Pay Frequency Serivce code integration
US.PAYR.009 | PAYROLL/PayRoll Provider Service Code integration
US.PAYR.010 | PAYROLL/Generate payroll Service Code Intergration
US.PAYR.011 | PAYROLL/Validation for Bank Information Page
US.PAYR.012 | PAYROLL/Validation for Principal Information page
US.PAYR.013 | PAYROLL/Validation for Pay frequency page
US.PAYR.014 | PAYROLL/Validation for generate payroll page
US.PAYR.015 | PAYROLL/Sitemap Navigation for Payroll module
US.PTO.009 | PTO/Employer-> Edit/Delete PTO Request
US.PTO.010 | PTO/PTO Policy Service Implementaion
US.PTO.011 | PTO/PTO Balance Calculation & PTO Balnce Disaply in required places
US.PTO.012 | PTO /PTO Policy Create
US.PARY.001 | PAYROLL/Pay Frequency Save Functionality
US.EMPL.001 | Employee login/Timesheet functionality is missing
US.EMPL.002 | Employee login/Benefits Add dependant is missing
US.EMPL.003 | Employee login/View Documents ability to view Handbook, Offer letter and other documents
US.EMPL.004 | Employee login/My Profile Add dependant
US.EMPL.005 | Employee login/My Profile Certificate is getting saved 2 times
US.EMPL.006 | Employee login/My Profile Primary contact info not getting saved
Note on G2: Author: The primary user or stakeholder for the story
Note on H2: Author: The goal that the actor is trying to achieve in the story
Note on I2: Author: The actions performed by the actor.
Note on J2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
Current Sprint# | Sprint01 | [6 empty] | Efforts |  |  |  | Development | [8 empty] | QA |  |  |  | Acceptance Testing
Auto Calculation | [6 empty] | % Work Complete => |  |  | #DIV/0! | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No Entry | [5 empty] | 0 |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Remaining Work | Type | Impact Analysis | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | Built & Deploy | QA Test Case | Integration Testing | Functional Testing | Regression Testing | Acceptance Test Case | Demoed to PO
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | US.MYC.001 | Mycompany>Company Detail/After Clicking update, the bread crumbs vanish and go back to the view page. | 0 | Moved | 0 | 0 | 0 | Name
KE.HRIS.1 | 2015-50 | Sprint01 | [8 empty] | Status
KE.HRIS.1 | 2015-50 | Sprint01 | [8 empty] | Planned
KE.HRIS.1 | 2015-50 | Sprint01 | [8 empty] | Actual
KE.HRIS.1 | 2015-50 | Sprint01 | 1 | US.MYC.002 | Mycompany>Company Detail/Upload control for Logo and Banner needs to be increased and should be one below the other | 0 | Moved | 0 | 0 | 0 | Name
KE.HRIS.1 | 2015-50 | Sprint01 | [8 empty] | Status
KE.HRIS.1 | 2015-50 | Sprint01 | [8 empty] | Planned
KE.HRIS.1 | 2015-50 | Sprint01 | [8 empty] | Actual
Note on L6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes