## Sprint-Master
Week of Year | Sprint# | Sprint Duration (in Weeks) | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
2015-44 | Sprint01 | 1 | 2015-10-26 | 2015-11-01 | 7 | 7
2015-45 | Sprint02 | 1 | 2015-11-02 | 2015-11-08 |  | 7
2015-46 | Sprint03 | 1 | 2015-11-09 | 2015-11-15 |  | 7
2015-47 | Sprint04 | 1 | 2015-11-16 | 2015-11-22 |  | 7
2015-48 | Sprint05 | 1 | 2015-11-23 | 2015-11-29 | 4 | 7
2015-49 | Sprint06 | 2 | 2015-12-01 | 2015-12-07 | 5 | 7 | 152 | 64
2015-50 | Sprint06 | 2 | 2015-12-08 | 2015-12-14 |  | 7
2015-51 | Sprint07 | 1 | 2015-12-15 | 2015-12-21 |  | 7
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+1

## Resources
Week of Year | 2015-49
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
F15435 | Sathish V | QA | SV | 0.2
F16707 | Rajeshkanna P | Dev | RK | 1
F0101 | Seshan T R | SM | STR | 0.2
F15856 | Deepika Ranganathan | QA | DR | 1
F13676 | Ravindra Kumar Tiwary | Dev | RKT | 1
FT16751 | Gowher John A S | Dev | GJ | 1
Grand Total |  |  |  | 4.4

## PRA
Update this Every Weekend
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | Account
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15435 | 1 | Sathish V | SV | QA | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15856 | 1 | Deepika Ranganathan | DR | QA | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16453 | 1 | Ashok S | AS | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16305 | 1 | Dilip Prasad J | DP | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16039 | 1 | Karthikeyan V | KV | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16707 | 1 | Rajeshkanna P | RK | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F13676 | 0.2 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.MP.001 | 2015-44 | Sprint01 | 16 | F0101 | 1 | Seshan T R | STR | SM | KE
KE.MP.001 | 2015-48 | Sprint05 | 17 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F0101 | 0.2 | Seshan T R | STR | SM | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F16707 | 1 | Rajeshkanna P | RK | Dev | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F15435 | 0.2 | Sathish V | SV | QA | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | F15856 | 1 | Deepika Ranganathan | DR | QA | KE
KE.MP.001 | 2015-49 | Sprint06 | 18 | FT16751 | 1 | Gowher John A S | GJ | Dev | KE
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Priority | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Nivedha | Ram | Roshan | Karthikeyan | Sathish | Shreya | Ravindra | TFS-ID/ Squish-ID | Related US-ID | Remarks1 | Remarks2
US.GQ.SC.01 | Subsidy Calculator (Get Quote Page) | 40 |  | Sprint05 |  | Web User | Calculate and display subsidy amount based on applicant data and family data | User should enter zip code and family income, age and tobacco use status | subsidy amount should be displayed as per connecture based on provided data. | [9 empty] | 40
US.DEF.0001 | Changes for Keenan Direct |  | 5 | Sprint06 |  | When i click on dental page | The title should change as per given title and description | When i click on the dental page the title has changed | Then now the action has done (the title and description has changed) | [10 empty] | 45
US.DEF.0002 | Agent Role to place orders for customer |  | 5 | [16 empty] | 27
US.DEF.0003 | Add Logs Marketplace code |  | 5 | [16 empty] | 43
US.DEF.0004 | Change Connection string to Integrate security - Marketplace |  | 5 | Sprint06 | [15 empty] | 37
US.DEF.0005 | Home Page - Enrollment Verbiage |  | 5 | [16 empty] | 20
US.DEF.0006 | Create DB Job to purge logs |  | 5 | [16 empty] | 36
US.DEF.0007 | Subsidy Calculator - Provide Hyper link or call our agent to take to the get quote |  | 5 | [16 empty] | 19
US.DEF.0008 | Collect additional information |  | 5 | [16 empty] | 35
US.DEF.0009 | Making site PCI compliance |  | 5 | [16 empty] | 34
US.DEF.0010 | Calstar Integration |  | 5 | [16 empty] | 32
US.DEF.0011 | Add Operating Hours |  | 5 | [16 empty] | 31
US.DEF.0012 | My Cart - Generate Cart Link |  | 5 | [16 empty] | 30
US.DEF.0013 | Send Joinme Link to Agent |  | 5 | [16 empty] | 25
US.DEF.0014 | Email Plan Comparison Information |  | 5 | [16 empty] | 24
US.DEF.0015 | Process Loader Needs to be Changed |  | 5 | [16 empty] | 22
US.DEF.0016 | Home page - Slider issues |  | 5 | [16 empty] | 48
US.DEF.0017 | Marketplace- Footer issue |  | 5 | [16 empty] | 47
US.DEF.0018 | Correction in Keenan Direct |  | 5 | Sprint06 |  | There are some edits in Resources (basics plan medicare and glossary) like space between (healthcare) | as per the given content edits should change | When i click on medicare and glossary the edits has done | Now the changes has done in the resources (medicare and glossary) | [10 empty] | 46
US.DEF.0019 | Enroll Page login Redirects to Home Page |  | 5 | Sprint06 | [15 empty] | 29
US.DEF.0020 | Object reference error |  | 5 | Sprint06 | Dropped | [14 empty] | 39
US.DEF.0021 | Fix the unwanted errors in Application |  | 5 | Sprint06 | [15 empty] | 41
US.DEF.0022 | /favicon.ico' was not found |  | 5 | Sprint06 | [15 empty] | 38
US.DEF.0023 | Problem with Applicant information |  | 5 | [16 empty] | 40
US.DEF.0024 | KD- Removing wrong attributes |  | 5 | [16 empty] | 5
US.DEF.0025 | Performance - Add to Cart |  | 5 | [16 empty] | 26
US.DEF.0026 | Performance Problem - Getquote to Plan filters |  | 5 | [16 empty] | 23
US.DEF.0027 | Redundant host name issue for Keenan Direct |  | 5 | [16 empty] | 17
US.DEF.0028 | Speed Recommendations-Browser cache |  | 5 | [16 empty] | 7
US.DEF.0029 | Speed Recommendations-Optimize images |  | 5 | [16 empty] | 9
US.DEF.0030 | Request to Add ELMAH for Internal quotit service |  | 5 | [16 empty] | 13
US.DEF.0031 | Use Production version of Internal Quotit Service |  | 5 | [16 empty] | 15
US.DEF.0032 | Speed Recommendations- Enable compression |  | 5 | [16 empty] | 11
US.DEF.0033 | Speed Recommendations-Reduce server response time |  | 5 | [16 empty] | 10
US.DEF.0034 | Speed Recommendations-Eliminate render-blocking JavaScript |  | 5 | [16 empty] | 8
US.DEF.0035 | KD-Other HTML attributes correction |  | 5 | [16 empty] | 6
US.DEF.0036 | Redundant host name issue |  | 5 | [16 empty] | 1
US.CAPI.01 | Analysis of connecture API with marketplace |  |  | Sprint06
US.ABI.0023 | Agency Bloc Integration | 20 | 1 | Sprint06 |  | When I enroll plan(s) in keenan | Then the lead record should be inserted in AgencyBloc | When I click on Enrollment | In success of enrollment, I should see personal information captured as lead in AgencyBloc | [9 empty] | 20 | 51
US.DEF.0037 | Quotit system is down |  |  | Sprint06
US.DEF.0038 | Add carrier logo calchoice |  |  | Sprint06
Note on G2: Author: The primary user or stakeholder for the story
Note on H2: Author: The goal that the actor is trying to achieve in the story
Note on I2: Author: The actions performed by the actor.
Note on J2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
Current Wk# | Sprint05 | [6 empty] | Efforts |  |  |  | Development | [8 empty] | QA |  |  |  | Acceptance Testing
Auto Calculation | [6 empty] | % Work Complete => |  |  | 67.57% | Actual | 0 | 0 | 20 | 6 | 8 | 4 | 8 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
No Entry | [5 empty] | 40 |  | 74 | 50 | 24 | Planned | 0 | 0 | 20 | 8 | 8 | 4 | 8 | 0 | 0 | 5 | 5 | 8 | 8 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Remaining Work | Type | Analysis | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | Built & Deploy | QA Test Case | Integration Testing | Functional Testing | Regression Testing | Acceptance Test Case | Demoed to PO
KE.MP.001 | 2015-48 | Sprint05 | 1 | US.GQ.SC.01 | Subsidy Calculator (Get Quote Page) | 40 | Moved | 74 | 50 | 24 | Name |  |  | RKT | RKT | RKT | RKT | RKT |  |  | SV | SV | SV |  |  | RKT
KE.MP.001 | 2015-48 | Sprint05 | [8 empty] | Status | NR | NR | Done | WIP | Done | Done | Done | NR | NS | NS | NS | NS | NS | NR | NS
KE.MP.001 | 2015-48 | Sprint05 | [8 empty] | Planned |  |  | 20 | 8 | 8 | 4 | 8 |  |  | 5 | 5 | 8 | 8
KE.MP.001 | 2015-48 | Sprint05 | [8 empty] | Actual |  |  | 20 | 6 | 8 | 4 | 8 |  |  |  |  | 4
KE.MP.001 | 2015-49 | Sprint06 | 2 | US.DEF.0001 | Changes for Keenan Direct | 0 |  | 14 | 0 | 14 | Name | GJ | GJ | GJ | GJ | [5 empty] | DR |  | DR | DR
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | NR | NS | Done | Done | NR | NR | NR | NR | Done | NS | NR | NS | NS
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned |  | 2 | 2 | 4 | [5 empty] | 2 |  | 2 | 2
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 3 | US.DEF.0004 | Change Connection string to Integrate security - Marketplace | 0 |  | 5 | 0 | 5 | Name | GJ | GJ | GJ | GJ
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | NS | NS | NS | NS | NR | NR | NR | NR
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned | 1 | 1 | 1 | 2
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 4 | US.DEF.0018 | Correction in Keenan Direct | 0 |  | 7 | 0 | 7 | Name |  | GJ | GJ | GJ | [5 empty] | DR |  | DR | DR
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | NR | Done | Done | Done | NR | NR | NR | NR | Done | NS | NR | NS | NS
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned |  | 1 | 1 | 2 | [5 empty] | 1 |  | 1 | 1
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 5 | US.DEF.0019 | Enroll Page login Redirects to Home Page | 0 |  | 11 | 0 | 11 | Name |  | GJ | GJ | GJ | [5 empty] | DR |  | DR | DR
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | NR | WIP | WIP | WIP | NR | NR | NR | NR | WIP | NS | NR | NS | NS
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned |  | 2 | 2 | 2 | [5 empty] | 1 |  | 2 | 2
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 6 | US.DEF.0020 | Object reference error | 0 |  | 16 | 0 | 16 | Name | GJ | GJ | GJ | GJ | [5 empty] | DR |  | DR | DR
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | WIP | WIP | WIP | WIP | NR | NR | NR | WIP | NS | NS | NR | NS | NS
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned | 2 | 2 | 2 | 2 |  |  |  | 3 |  | 1 |  | 2 | 2
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 7 | US.DEF.0021 | Fix the unwanted errors in Application | 0 |  | 0 | 0 | 0 | Name
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 8 | US.DEF.0022 | /favicon.ico' was not found | 0 |  | 11 | 0 | 11 | Name | GJ | GJ | GJ | GJ | [7 empty] | DR | DR
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | Done | Done | Done | Done | NR | NR | NR | NR | Done | NR | NR | NS | NS
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned | 2 | 2 | 2 | 3 | [7 empty] | 1 | 1
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual
KE.MP.001 | 2015-49 | Sprint06 | 9 | US.CAPI.01 | Analysis of connecture API with marketplace | 0 |  | 16 | 6 | 10 | Name | RKT
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | WIP | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned | 16
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual | 6
KE.MP.001 | 2015-49 | Sprint06 | 10 | US.ABI.0023 | Agency Bloc Integration | 20 |  | 16 | 16 | 0 | Name | RKT |  | RKT | RKT |  |  | RKT |  | RKT
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Status | Done | NA | Done | Done | NA | NA | Done | NA | Done | NA | NA | NA | NA | NA | NA
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Planned | 1 |  | 12 | 1 |  |  | 1.5 |  | 0.5
KE.MP.001 | 2015-49 | Sprint06 | [8 empty] | Actual | 1 |  | 12 | 1 |  |  | 1.5 |  | 0.5
KE.MP.001 | 2015-50 | Sprint06 | 11 | US.DEF.0038 | Add carrier logo calchoice | 0 |  | 4.5 | 4.5 | 0 | Name | GJ |  | GJ | GJ |  |  | GJ |  | GJ | DR | DR | DR | DR | RKT | RKT
KE.MP.001 | 2015-50 | Sprint06 | [8 empty] | Status | Done | NA | Done | Done | NA | NA | Done | NA | Done | NS | NS | NS | NS | NS | NS
KE.MP.001 | 2015-50 | Sprint06 | [8 empty] | Planned | 0.5 |  | 1 | 1 |  |  | 1 |  | 1
KE.MP.001 | 2015-50 | Sprint06 | [8 empty] | Actual | 0.5 |  | 1 | 1 |  |  | 1 |  | 1
Note on L6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes