## Objectives
Code | Objective
TB | Team Binding
PF | Project Focussed
RP | Retention of Performers
AEL | Auto Expulsion of Laggers
NCCPQ | No competion at the cost of Product Quality
QD | Quality Delivery
TD | Timely Delivery
B4O | Binding for the Organization
DUPL | Discourage unplanned off from work
VCC | Value creation for Customer
VCO | Value creation for Organization
TP | Team Play
AT | Agility in Team
HTP | High Team Productivity
TEW | Team Enjoy Working

## Score
|  |  | Update this Every Weekend After Retrospective |  |  |  |  | Update this Every Weekend After Retrospective
|  |  | Project Code | KE.MP.001 | Final Score | 72.5% |  | Project Code | KE.MP.001 | Final Score | 81.8%
|  |  | Sprint # | 1 | Wk#-> | 44 |  | Sprint # | 1 | Wk#-> | 2015-48
|  |  | Sprint Start Date | 2015-10-26 | Sprint End Date | 2015-10-30 |  | Sprint Start Date | 2015-11-23 | Sprint End Date | 2015-11-30
|  |  | Sprint Duration (Days) | 5 | No of Resources | 7 |  | Sprint Duration (Days) | 5 | No of Resources | 4
|  |  |  | 100% | 0% |  |  |  | 100% | 0%
| Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total
| Team Living Agile Values | 33% |  | 3.84 | 5 | 25.34% | 33% |  | 3.78 | 5 | 24.95%
| Team is Focussed |  |  | 4.57 | 5 |  |  |  | 4 | 5
| Team is Committed to Sprint Goal |  |  | 4.85 | 5 |  |  |  | 4 | 5
| Team has Courage to take risk and make decisions |  |  | 3.5 | 5 |  |  |  | 4 | 5
| Close Communications |  |  | 3.21 | 5 |  |  |  | 3.33 | 5
| Team is Respect practices, other values, other people's value |  |  | 2.92 | 5 |  |  |  | 4 | 5
| Team is living opennes/transparency value |  |  | 4 | 5 |  |  |  | 3.33 | 5
| Team Living Agile Principles | 33% |  | 3.22 | 5 | 21.25% | 33% |  | 4.06 | 5 | 26.8%
| Continuous Value Delivery |  |  | 3.5 | 5 |  |  |  | 4 | 5
| Welcome Change |  |  | 3.5 | 5 |  |  |  | 5 | 5
| Deliver Frequently |  |  | 4.28 | 5 |  |  |  | 3.16 | 5
| Scrum Team Working Together |  |  | 3.28 | 5 |  |  |  | 4.4 | 5
| Team members are Highly Motivated |  |  | 3.78 | 5 |  |  |  | 3.84 | 5
| Sustainable Pace |  |  | 1 | 5 |  |  |  | 4.17 | 5
| Technical Excellence |  |  | 3.4 | 5 |  |  |  | 3.5 | 5
| Architecutre is Evolving |  |  | 2.6 | 5 |  |  |  | 4.34 | 5
| Regular Cadence |  |  | 3 | 5 |  |  |  | 3.34 | 5
| Adjusting Behaviour |  |  | 3.85 | 5 |  |  |  | 4.84 | 5
| Competency and Enjoying Work | 34% |  | 3.81 | 5 | 25.91% | 34% |  | 4.42 | 5 | 30.06%
| Great Team |  |  | 3 | 5 |  |  |  | 5 | 5
| Moral of the team |  |  | 2.92 | 5 |  |  |  | 3.83 | 5
| Helpfulness of team to each other |  |  | 4.35 | 5 |  |  |  | 5 | 5
| Ability to solve impediments |  |  | 4.28 | 5 |  |  |  | 4 | 5
| Team Proactiveness |  |  | 4 | 5 |  |  |  | 4 | 5
| Team's ability to deliver the commitments |  |  | 4.28 | 5 |  |  |  | 4.66 | 5
Benchmark | Productivity, Quality | 0% |  |  |  | 0% | 0% |  |  |  | 0%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5% | 5% | 0.5 | 100% |  | 5%
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Test Coverage | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
1 | Number of Product Demos | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | Issues in the issue log | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5% | 5% | 25 | 100% |  | 5%
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
Note on E7: Enter between 1 - 5
Note on F7: Enter between 1 - 5
Note on J7: Enter between 1 - 5
Note on K7: Enter between 1 - 5
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## Score-Summary
Project Id | Sprint St Date | Sprint End Date | Year Wk# | Project Wk# | Sprint# | Values | Principle | Enjoy Work | Productivity | Score | Duration | Resources
KE.MP.001 | 2015-10-26 | 2015-10-30 | 2015-44 | 16 | Sprint01 | 3.84 | 3.22 | 3.81 | Not Measured | 73% | 5 | 7
KE.MP.001 | 2015-11-23 | 2015-12-01 | 2015-48 | 20 | Sprint02 | 3.78 | 4.06 | 4.42 | Not Measured | 82% | 5 | 4
Formulas:
Year Wk# = YEAR([Sprint St Date])&"-"&WEEKNUM([Sprint St Date])

## Lessons-Log
Team Learning Register
Date | ProjectID | Soruces | Type | Particular | Actionee | Date
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Tight Deadlines
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Tough Calls
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of sprint process
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Long working hours (weekdays)
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No Clear deployment plan communication for Prod Environment code push
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Re-open items again
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Weekend Work
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Security testing could have been done on Tuesday & Wednesday
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Last minute code change for security fixes
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of tools to test security fixes inn test environment
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of awareness for secure application development
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No clear requirements for sprints
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No Plans for sprint.
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Product owner’s responsibility
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Need a deployment plan (timings, technical docs)
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Developers should do integration testing in the dev environment
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Developers should write unit test cases
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Discussed risks in implementing functionality with product owner as and when needed
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Security testing has to be done as a regular activity of sprint
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Every sprint must have to be started with sprint planning
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Deployment checklist has to be created and deployment has to be done on rotational basis following same procedures.
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Prepare deployment checklist – Team (11/03/2015) | Dev. Team | 2015-11-04
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Start Integration testing (Functional Flow) | Dev. Team | 2015-11-04
2015-12-01 | KE.MP.001 | Retrospective | Best Practices | Using Sqish for work management
2015-12-01 | KE.MP.001 | Retrospective | Improvement | Perform Sprint Planning
2015-12-01 | KE.MP.001 | Retrospective | Improvement | Deployment must happen everyday morning. Dev team should send email to QA that what is being deployed as and when deployment is happening. If there is no deployment then Dev team must inform that there is no Deployment today. Give 4 min hour for regression testing before Demo.
2015-12-01 | KE.MP.001 | Retrospective | Improvement | Prioritizaiton from 1-10 not Low, High Medium