## Projects
Status
# | Project_ID | Project Name | Description | Category | Project Type | Scrum Master | Accountable | Dev Resources | QA Resources | Support Res | Project Sponsor | Planned Effort | Planned Dur. | Pending PBL Items | Pending Sprint Items | Burndown Efforts for Sprint | Planned St Date | Planned End Date | Replanned End Date | Overall | Schedule | Cost | Quality | Scope | Remarks
1 | KE.BBCB.1 | Benefit Bridge/CBMS |  | Dev & Support | Regular | ?? | Seshan | 6 | 2 |  | Bharat | [6 empty] | 2016-01-01
2 | KE.DWBI.1 | DWBI | BI Reporting & Dashboards for Keenan Insurance, Claim etc. | Dev & Support | Regular | Sampath | Seshan | 6 | 0 | 0 | Tanbeer
3 | KE.CEC.01 | Cadillac Excel Calculator |  | Dev & Support | Need Basis | Shreya | Seshan |  |  |  | Bharat
4 | KE.SERP.1 | SERP |  | Dev & Support | Need Basis | Seshan | Veeren | 1 |  |  | Sanjeev
5 | KE.BBPE.1 | Benefit Bridge/Private Exchange |  | Development | Regular | Seshan | Veeren | 3 | 2 |  | Bharat | [13 empty] | Working on HCR Calculator
6 | KE.MP.001 | Market Place |  | Development | Regular | Seshan | Veeren | 5 | 4 |  | Bharat | [5 empty] | 2015-07-15 | 2015-10-01 | 2015-10-30 |  | -29 | -180 | 70 |  | 70 Defects
7 | KE.PPCB.1 | Portal PCB Rel 6.0 |  | Full Testing | Regular | Sathish | Seshan |  |  |  | Sanjeev | [5 empty] | 2015-05-15 | 2015-11-01
8 | KE.PQNR.1 | Portal QnR Revamp |  | Full Testing | Regular | Sathish | Seshan |  |  |  | Sanjeev | [5 empty] | 2015-05-15 | 2015-11-01
9 | KE.PS.001 | Portal Sprint (#1) |  | Support/Ticket Based | Regular | Sathish | Seshan |  |  |  | Sanjeev | [5 empty] | 2015-03-01 | 2015-11-06
10 | KE.IFP.01 | IFP Commission |  | Support | Need Basis | Shreya | Veeren |  |  | 1 | Bharat
11 | KE.DE.001 | Data Exchange |  | Dev & Support | Regular | Seshan | Veeren | 1 |  | 2 | Bharat | [5 empty] | ?? | 2015-11-30
12 | KE.BBD.01 | Benefit Bridge Documentation |  | Documentation | Regular | Latha | Seshan | 2 | 2 | 3 | Bharat | 352 | 32 | 22 | Need To Plan | 352 | 2015-11-19 | 2015-11-26
[8 empty] | 24 | 10 | 6
Formulas:
Cost = 5*(WEEKNUM([Planned End Date])-WEEKNUM([Replanned End Date]))*([Dev Resources]+[QA Resources])

## Accounts
Code | Account Name
KE | Keenan
SP | Second Phase

## Impediments
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## Res-Assignment
As Per Seshan. As of 5-Nov-15
| KE.BBCB.1 | KE.DWBI.1 | KE.CEC.01 | KE.SERP.1 | KE.BBPE.1 | KE.MP.001 | KE.PPCB.1 | KE.PQNR.1 | KE.PS.001 | KE.IFP.01 | KE.DE.001 | KE.BBD.01
Alexander |  | ?? |  |  |  |  | ?? | ?? | ??
Andrew |  | ?? |  |  |  |  | ?? | ?? | ??
Seshan T R | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Sathish V |  |  |  |  | Yes | Yes | Yes | Yes | Yes
Ramakrishnan |  | Yes |  |  |  |  | Yes | Yes | Yes
Asan Mohamed A | Yes | [5 empty] | Yes | Yes | Yes
Sai Prasath | [6 empty] | Yes | Yes | Yes
Sanjana S | [6 empty] | Yes | Yes | Yes
Gowher John A S |  |  |  |  | Yes | Yes | [5 empty] | Yes
Sanjana Babu |  |  |  |  | Yes | Yes |  |  |  | Yes
Ashok S | [5 empty] | Yes
Deepika Ranganathan | [5 empty] | Yes
Dilip Prasad J | [5 empty] | Yes
Rajeshkanna P | [5 empty] | Yes
Ravindra Kumar Tiwary | [5 empty] | Yes
Shreya Gupta |  |  | Yes | Yes | Yes |  |  |  |  | Yes
Karthikeyan V |  |  |  |  | Yes
Naresh Narava |  |  |  |  | Yes
Nivedha C |  |  |  |  | Yes
Ramachandran Ganesan |  |  |  |  | Yes | [5 empty] | Yes
Braj Mohan Goud |  | Yes
Krishna M |  | Yes
Nadem Manohar |  | Yes
Pramod Kumar Matam |  | Yes
Sampath |  | Yes
Suresh V |  | Yes
Thirupathi Kusa |  | Yes
Aashiq Hameed | Yes
Allwin A | Yes
Dilip | Yes | [9 empty] | Yes
Kuzhal Malan S | Yes
Rajesh | Yes | [9 empty] | Yes
Senthil Nathan Sai | Yes
Sugumar | Yes
Krishna Avadhani Trv | [9 empty] | Yes
Priya | [11 empty] | Yes
Roshan Ara A W
Sudha | [11 empty] | Yes

## PM Practices
Owner | Who Should Do | Practice | Frequency | Remarks
Scrum Master | Scrum Master | Should maintain a daily log for all the project he is managing. | Daily Basis
Scrum Master | Scrum Master | Should maintain a log of requirement clearification at project level. | As and when requirement elicitation happens
Scrum Master | Development Team | Daily Stand Up Call | Daily same time, same location
Scrum Master | Development Team | Maintain Scrum Board | Daily Basis | Scrum Board= Kanban/ Burndown Charts/ Team Members/ Impediments
Scrum Master | Development Team | Sprint Planning at the start of every sprint | Once in a sprint
Scrum Master | Development Team | Test Driven Development | Daily Basis
Scrum Master | Product Owner | Product Demo | Once in a sprint
Scrum Master | Development Team | Continuous Functional & Integration Testing | As soon as code is checked in
Scrum Master | Product Owner | Product Backlog Grooming | During sprint after sprint planning and before Product demo.
Scrum Master | Scrum Master | Discuss issues which need management attention with possible proposed solutions | On Need Basis
Scrum Master | Development Team | Perform Retrospective at the end of every sprint | Once in a sprint
Scrum Master | Project Co-ordinator | Collect project data on regular basis | As and when needed
Scrum Master | Scrum Master | Update project dashboard on regular basis | Everyday morning (only if needed)
Scrum Master | Scrum Team | Keep risk register updated / plan risk response/ ensure action are taken | On Need Basis
Scrum Master | Scrum Team | Configuration Management System in Place | On Daily Basis | Document naming, version numbering, location, storage, archival, access permission, redundancy

## Challenges
Input from PM
Challenges from PM Angle
Requirment documents missing
Scope is not defined
Micro management
Communication gap/ Communication Management Strategy missing
Reporting structure is not planned
Change management not in place
Configuration management System is not being used
Adhoc work by customer
We are not estimating the work but timeline is given to us
PM is not coordinating all work/ PM bypassed
Issue management is not effective
No proper risk management
Challenges from Bharat Angle
Not getting right information at right time
Quality of project management
Planned vs Actual work progress report is not visible
Resource Loading Info is Missing
Ticket Status Information
Quality of Testing is not upto the mark
Coding quality is bad
General
Upto 12-Sep (before Bharat came to India) everything was good. He appreciated PM on 11-Sep.
18-19-Sep

## RISK
Risk-ID | Risk-Name | Risk-Description | Probablity | Impact-Schedule | Impact-Cost | Impact-Quality | Impact-Scope | Mitigation Plan | Contigency Plan | Risk Owner | Risk status | Risk Updated Date