## Sheet1
Team Learning Register (Org Level)
Date | ProjectID | Soruces | Type | Particular | Actionee | Date
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Must start doing sprint planning
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Impediments must be identified, assigned and resolved within the SLA time.
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Scrum Board must be updated regularly
2015-11-23 | KE.BBPE.1 | Retrospective | Improvement | Implement FxCop tool duing built to monitor code quality
2015-11-23 | KE.BBPE.1 | Retrospective | Best Practices | Learned unit testing so continue.
2015-11-23 | KE.BBPE.1 | Retrospective | Best Practices | Focus on code quality improvement. So remain conscious about code quality while doing coding.
2015-11-23 | KE.BBPE.1 | Retrospective | Best Practices | Technical discussion for learning new technology trends
2015-11-23 | KE.BBPE.1 | Retrospective | Stop Doing | Changing resource in the middle of sprint.
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Estimation the work and negotiate the timeline and resources with customer | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Conduct team sessions twice a week for 1 hour each for improving technical know how about customer business. | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Understand sprint planning and perform sprint planning | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Daily standup meeting | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Best Practices | Daily call with customer
2015-11-24 | KE.DWBI.1 | Retrospective | Best Practices | Continuous demo of the work performed to the customer
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Tight Deadlines
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Tough Calls
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of sprint process
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Long working hours (weekdays)
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No Clear deployment plan communication for Prod Environment code push
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Re-open items again
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Weekend Work
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Security testing could have been done on Tuesday & Wednesday
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Last minute code change for security fixes
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of tools to test security fixes inn test environment
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of awareness for secure application development
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No clear requirements for sprints
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No Plans for sprint.
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Product owner’s responsibility
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Need a deployment plan (timings, technical docs)
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Developers should do integration testing in the dev environment
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Developers should write unit test cases
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Discussed risks in implementing functionality with product owner as and when needed
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Security testing has to be done as a regular activity of sprint
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Every sprint must have to be started with sprint planning
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Deployment checklist has to be created and deployment has to be done on rotational basis following same procedures.
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Prepare deployment checklist – Team (11/03/2015) | Dev. Team | 2015-11-04
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Start Integration testing (Functional Flow) | Dev. Team | 2015-11-04
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | Must do the sprint planning
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | Know my delivery goal
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | I want to know who is the audience of this document.
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | Identify and finalze tool for flowcharting
2015-11-25 | KE.BBD.01 | Retrospective | Best Practices | End of every day review.
2015-11-25 | KE.BBD.01 | Retrospective | Best Practices | Team resolves impediments immediately.
2015-11-25 | KE.BBD.01 | Retrospective | Best Practices | Transparancy about the work progress