## Sprint-Master
Sprint# | Week of Year | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
Sprint01 | 2015-46 | 2015-11-11 | 2015-11-25 | 3 | 14
Sprint02 | 2015-48 | 2015-11-26 | 2015-12-02 | 3 | 7
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1

## Resources
Week of Year | (All)
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
CON#1 | Latha V | SM | LV | 2
CON#2 | Priya | DOC | PR | 2
CON#3 | Sudha | DOC | SUD | 2
Grand Total |  |  |  | 6

## PRA
Update this Every Weekend | [8 empty] | Project Coordinator Must Update this Sheet on Every Friday
Projet Resource Assignment | [8 empty] | Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#1 | 1 | Latha V | LV | SM
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#2 | 1 | Priya P | PP | DOC
KE.BBD.01 | 2015-46 | Sprint01 | 2 | CON#3 | 1 | Sudha M | SUM | DOC
KE.BBD.01 | 2015-48 | Sprint01 | 3 | CON#1 | 1 | Latha V | LV | SM
KE.BBD.01 | 2015-48 | Sprint01 | 3 | CON#2 | 1 | Priya P | PP | DOC
KE.BBD.01 | 2015-48 | Sprint01 | 3 | CON#3 | 1 | Sudha M | SUM | DOC
KE.BBD.01 | 2015-48 | Sprint01 | 3 | F7303 | 1 | Senthil Nathan Sai | SNS | Dev
KE.BBD.01 | 2015-48 | Sprint01 | 3 | F0101 | 1 | Seshan T R | STR | SM

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Karthikeyan | Sathish | Shreya | Ravindra | Status
US.BBD.COM.01 | As a Software Developer I want documentation for commit process as pseudo code so that I can maintain the code |  | Sprint01
US.BBD.COM.02 | As a Business Analyst I want flow chart of commit process so that I can visualize the complete business process |  | Sprint01
US.BBD.COS.01 | As a software developer I want document for COS payroll as pseudo code so that I can maintain the code |  | Sprint01
US.BBD.COS.02 | As a Business Analyst I want flow chart of COS Payroll so that I can visualize the complete business process |  | Sprint01
US.BBD.COS.03 | As a System User I want User Instruction Manual of COS Payroll so that I can execute the process |  | Sprint01
Note on H2: Author: The primary user or stakeholder for the story
Note on I2: Author: The goal that the actor is trying to achieve in the story
Note on J2: Author: The actions performed by the actor.
Note on K2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
Scrum Board
|  |  |  | Auto Calculation |  |  |  | Efforts |  |  | Development | [5 empty] | QA | Acceptance
|  |  |  | No Entry |  |  |  | 0 | 0 | WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Type | Knowledge Transfer/ Demo | Draft Document | Draft Flow Chart of UI | Pseudo Document | Draft Flow chart of Pseudo Code | Mearge both Flow Chart | Tech Review | Demoed to PO
KE.BBD.01 | 2015-48 | Sprint02 | 1 | US.BBD.COM.01 | As a Software Developer I want documentation for commit process as pseudo code so that I can maintain the code | 0 | WIP |  |  |  | SNS |  |  | SNS |  |  | SNS, STR | STR
| 2015-48 | [9 empty] | Done | NR | NR | Done | NR | NR | Done
| 2015-48 | [8 empty] | Planned
| 2015-48 | [8 empty] | Actual
KE.BBD.01 | 2015-48 | Sprint02 | 2 | US.BBD.COM.02 | As a Business Analyst I want flow chart of commit process so that I can visualize the complete business process | 0 | WIP |  |  |  |  | PP,SUM | PP, SUM, LV | SNS | PP, SUM, LV | PP, SUM | SNS, STR | STR
| 2015-48 | [9 empty] | NR | Done | Done | Done | Done | Done | Done
| 2015-48 | [10 empty] | 24 | 10 |  | 19 | 2
| 2015-48 | [10 empty] | 24 | 10 |  | 19 | 2
KE.BBD.01 | 2015-48 | Sprint02 | 3 | US.BBD.COS.01 | As a software developer I want document for COS payroll as pseudo code so that I can maintain the code | 0 | WIP |  |  |  | SNS, PP, SUM, LV |  |  | SNS |  |  | SNS, STR | STR
| 2015-48 | [9 empty] | Done | NR | NR | Done | NR | NR | Done
2015-48
2015-48
KE.BBD.01 | 2015-48 | Sprint02 | 4 | US.BBD.COS.02 | As a Business Analyst I want flow chart of COS Payroll so that I can visualize the complete business process | 0 | WIP |  |  |  |  | PP,SUM |  | SNS | PP, SUM, LV | PP, SUM | SNS, STR | STR
| 2015-48 | [9 empty] | NR | Done | NR | NS | NS | NS | NS
| 2015-48 | [10 empty] | 4 |  |  | ?? | ?? | ??
| 2015-48 | [10 empty] | 4
KE.BBD.01 | 2015-48 | Sprint02 | 5 | US.BBD.COS.03 | As a System User I want User Instruction Manual of COS Payroll so that I can execute the process | 0 | WIP |  |  |  | SNS, PP | PP, SUM | ?? | SNS | PP, SUM, LV | PP, SUM
| 2015-48 | [9 empty] | NS |  | NR | NR | NS | NS | NS
| 2015-48 | [10 empty] | ?? | ??
2015-48
Note on K3: WIP Limit Status ==>>
Note on K6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes