## Objectives
Code | Objective
TB | Team Binding
PF | Project Focussed
RP | Retention of Performers
AEL | Auto Expulsion of Laggers
NCCPQ | No competion at the cost of Product Quality
QD | Quality Delivery
TD | Timely Delivery
B4O | Binding for the Organization
DUPL | Discourage unplanned off from work
VCC | Value creation for Customer
VCO | Value creation for Organization
TP | Team Play
AT | Agility in Team
HTP | High Team Productivity
TEW | Team Enjoy Working

## Score
Update this Every Weekend After Retrospective
|  |  | Project Code | KE.BBD.01 | Final Score | 90.19%
|  |  | Sprint # | 1 | Wk#-> | 46
|  |  | Sprint Start Date | 2015-11-11 | Sprint End Date | 2015-11-25
|  |  | Sprint Duration (Days) | 10 | No of Resources | 3
|  |  |  | 100% | 0%
| Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total
| Team Living Agile Values | 33% |  | 4 | 5 | 26.4%
| Team is Focussed |  |  | 5 | 5
| Team is Committed to Sprint Goal |  |  | 0 | 5
| Team has Courage to take risk and make decisions |  |  | 4 | 5
| Close Communications |  |  | 5 | 5
| Team is Respect practices, other values, other people's value |  |  | 5 | 5
| Team is living opennes/transparency value |  |  | 5 | 5
| Team Living Agile Principles | 34% |  | 4.8 | 5 | 32.64%
| Continuous Value Delivery |  |  | 5 | 5
| Welcome Change |  |  | 5 | 5
| Deliver Frequently |  |  | 5 | 5
| Scrum Team Working Together |  |  | 5 | 5
| Team members are Highly Motivated |  |  | 5 | 5
| Sustainable Pace |  |  | 5 | 5
| Technical Excellence |  |  | 4.67 | 5
| Architecutre is Evolving |  |  | 5 | 5
| Regular Cadence |  |  | 4.67 | 5
| Adjusting Behaviour |  |  | 3.67 | 5
| Competency and Enjoying Work | 33% |  | 4.72 | 5 | 31.15%
| Great Team |  |  | 5 | 5
| Moral of the team |  |  | 4 | 5
| Helpfulness of team to each other |  |  | 5 | 5
| Ability to solve impediments |  |  | 5 | 5
| Team Proactiveness |  |  | 5 | 5
| Team's ability to deliver the commitments |  |  | 4.33 | 5
Benchmark | Productivity, Quality | 0% |  |  |  | 0%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5%
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5%
100% | Test Coverage | 5% | 100% | 100% |  | 5%
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5%
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5%
1 | Number of Product Demos | 5% | 1 | 100% |  | 5%
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5%
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5%
1 | Issues in the issue log | 5% | 1 | 100% |  | 5%
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5%
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5%
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## Score-Summary
Project Id | Sprint St Date | Sprint End Date | Year Wk# | Project Wk# | Sprint# | Values | Principle | Enjoying Work | Score | Duration | Resources
KE.BBD.01 | 2015-11-11 | 2015-11-25 | 2015-46 | 1 | 1 | 4 | 4.8 | 4.72 | 90% | 10 | 3
Formulas:
Year Wk# = YEAR([Sprint St Date])&"-"&WEEKNUM([Sprint St Date])

## Lessons-Log
Team Learning Register
Date | ProjectID | Soruces | Type | Particular | Actionee | Date
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | Must do the sprint planning
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | Know my delivery goal
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | I want to know who is the audience of this document.
2015-11-25 | KE.BBD.01 | Retrospective | Improvement | Identify and finalze tool for flowcharting
2015-11-25 | KE.BBD.01 | Retrospective | Best Practices | End of every day review.
2015-11-25 | KE.BBD.01 | Retrospective | Best Practices | Team resolves impediments immediately.
2015-11-25 | KE.BBD.01 | Retrospective | Best Practices | Transparancy about the work progress