## Sprint-Master
Sprint# | Week of Year | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
Sprint01 | 2015-47 | 2015-11-16 | 2015-11-20 | 2 | 5 | 210 | 47 | 47 | 0 | 16-Nov Heavy Rain | HCR Calculator Should be delivered
Sprint02 | 2015-48 | 2015-11-23 | 2015-11-27 | 3 | 5 | 66 | 57 | 49 |  |  | HCR Fully Insured / Self Funded separating depending upon the client.
Sprint03 | 2015-49 | 2015-11-30 | 2015-12-11 | 6 | 10 | 320 | 175
Sprint4 | 2015-51 | 2015-12-14 | 2015-12-18 |  | 5
Sprint5 | 2015-52 | 2015-12-21 | 2015-12-25 |  | 5
Sprint6 | 2015-53 | 2015-12-28 | 2016-01-01 |  | 5
Sprint7 | 2016-02 | 2016-01-04 | 2016-01-08 |  | 5
Sprint8 | 2016-03 | 2016-01-11 | 2016-01-15 |  | 5
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+3

## Resources
Week of Year | 2015-47 |  |  | 7 | 210
Emp ID# | (Multiple Items)
Sum of Present
Emp Name | Scrum Role | Initial | Total
Ashok S | Dev | AS | 1
Dilip Prasad J | Dev | DP | 1
Karthikeyan V | Dev | KV | 1
Sanjana Babu | QA | SB | 1
Sathish V | QA | SV | 1
Shreya Gupta | BA | SG | 1
Rajeshkanna P | Dev | RK | 1
Grand Total |  |  | 7

## PRA
Update this Every Weekend
Project Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16039 | 1 | Karthikeyan V | KV | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16305 | 1 | Dilip Prasad J | DP | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16453 | 1 | Ashok S | AS | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F15435 | 1 | Sathish V | SV | QA
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F15600 | 1 | Sanjana Babu | SB | QA
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | FT12358 | 1 | Shreya Gupta | SG | BA
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16707 | 1 | Rajeshkanna P | RK | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F0101 | 1 | Seshan T R | STR | SM
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F16453 | 1 | Ashok S | AS | Dev
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F16707 | 0.2 | Rajeshkanna P | RK | Dev
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F15600 | 1 | Sanjana Babu | SB | QA
KE.BBPE.1 | 2015-48 | Sprint02 | 2 | F0101 | 1 | Seshan T R | STR | SM
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F16453 | 1 | Ashok S | AS | Dev
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F15600 | 0.4 | Sanjana Babu | SB | QA
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F14101 | 1 | Nivedha C | NC | Dev
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F17044 | 1 | Naresh Narava | NN | Dev
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F15762 | 1 | Ramachandran Ganesan | RG | Dev
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F15658 | 1 | Roshan Ara A W | RAA | QA
KE.BBPE.1 | 2015-49 | Sprint03 | 2 | F0101 | 1 | Seshan T R | STR | SM
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F16453 | 1 | Ashok S | AS | Dev
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F15600 | 0.4 | Sanjana Babu | SB | QA
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F14101 | 1 | Nivedha C | NC | Dev
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F17044 | 1 | Naresh Narava | NN | Dev
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F15762 | 0.8 | Ramachandran Ganesan | RG | Dev
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F15658 | 1 | Roshan Ara A W | RAA | QA
KE.BBPE.1 | 2015-50 | Sprint03 | 2 | F0101 | 1 | Seshan T R | STR | SM
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Priority | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Nivedha | Ram | Roshan | Karthikeyan | Sathish | Shreya | Ravindra | TFS-ID | Related US-ID | Remarks1 | Remarks2
US.PE.CAD.01 | Get client name, plan type and premium tire details | 20 |  |  | Discussed | Benefit Manager | I want to get the details of my organization for the determining cadillac tax due to my ogranzation. So that I could estimate cadillac tax of my organization. | When I log in the system, calculator can pull the details like client name, plans , premium types into the calculator | Correct information being pulled | As per Bharat, all this information comes from a webservice and will provide the sql query for pulling this information. |  | 20 |  |  |  | 20 | 13 | 13
US.PE.CAD.02 | Threshold Reference table | 13 |  |  | Discussed | Benefit Manager | I want to see thresholds for various cover types | When I open calc, I see ref table | Constants. | Static Page | Whether data will come from Webservice or table? | 13 |  |  |  | 13 | 8 | 13
US.PE.CAD.03 | Create/Modify Threhold Values | 20 |  |  | Discussed | Benefit Manager | I should be able to create/modify the threshold values of Cadillac Tax |  |  | Added by Estimation Team |  | 13 |  |  |  | 20 | 13 | 13
US.PE.CAD.04 | Default rates | 20 |  |  | Discussed | Benefit Manager | I should be able to see the default values of various rates (i.e. HCAP, COLA etc) and overide if required. | When I see this section, default rate is already present but I should be able to edit it, if I wish too. | Default should be one that is stored in the system.It should be only in percentage. Values should be editable. |  |  | 20 |  |  |  | 20 | 20 | 20
US.PE.CAD.05 | User inputs -Rate | 20 |  |  | Discussed | Benefit Manager | I should be able to create/modify default rate of Trend, Medical account contribution growth, Health Cost Adjustment Percentage Factor (HCAP), Age and Gender Adjustment Factor ,Cost of Living Adjustment Factor (COLA). So that values can be populated in the calculator at the time of Cadillac Tax Calcuation. These values becomes default system values for calculation purpose. | System should store the rates for Cadillac Tax calculation | Should only be numeric and in percent format |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.06 | Tooltips | 13 |  |  | Discussed | Benefit Manager | I want to get more information about the terms used in the calculator as a tooltip message. So that I know what is the meaning of a particular term. | When I hover over the label and its textbox, corresponding tooltip should pop. | Tool tips should only be for the term on which mouse is hovered. It should be as per the approved wireframe |  |  | 13 |  |  |  | 13 | 8 | 8
US.PE.CAD.07 | User input- Coverage type | 13 |  |  | Discussed | Benefit Manager | I want select the coverage type from the drop down menu. There are 3 coverage types | The cadillac tax will be calculated based on the selected coverage | Coverage type should be the ones from the threshold reference table |  |  | 13 |  |  |  | 13 | 8 | 8
US.PE.CAD.08 | Display HCAP,Age and Gender Adjustment Factor and COLA rate | 5 |  |  | Discussed | Benefit Manager | I want see what are the rate I have entered in input data for HCAP,Age and Gender Adjustment Factor and COLA so that I know correct rates are being used for calculation. | Display | System should show these value which I have entered using userstory PE.BM.CAD.05 |  |  | 5 |  |  |  | 5 | 5 | 2
US.PE.CAD.09 | Calculate Annual Dollar Limit (ADL) with Adjustments | 8 |  |  | Discussed | Benefit Manager | I want that system should calculate ADL 2018 with adjustments using the formula for calculation | It should be calculated using the formula: ADL * (1+HCAP) * (1+Age and gender adjustment factor) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. |  |  | 8 |  |  |  | 8 | 8 | 8
US.PE.CAD.10 | Load appropriate user input sections for different Premium tire |  |  |  | Discussed | Benefit Manager | I want the all the premium tire's to be fetched | When I load this page, by then the calculator should already know my premium tires and load appropriate input sections | Premium tire should display and textbox should be loaded with calculated vlaues of premium, FSA, HRA, HAS and MSA. This should allow me to change the values. | this needs to be analysed for estimation |  | 40 |  |  |  | 100 | 100 | 40
US.PE.CAD.11 | Default Values for Total Premium, FSA, HRA, HSA and MSA | 20 |  |  | Discussed | Benefit Manager | I want to get default values of FSA, HRA etc along with premium from the system, so that this can be used for calculation. | When I see this section, default value is already present but I should be able to edit it, if I wish too. | Default should be one that is present in the template. For the one I enter, it should be amount in dollar rounded to two decimal. |  |  | 20 |  |  |  | 20 | 20 | 20
US.PE.CAD.12 | Edit User inputs -Premium, FSA, HRA, HSA and MSA amounts | 3 |  |  | Discussed | Benefit Manager | So that I can enter Premium, FSA, HRA, HSA and MSA amounts in the calculator. | System should store the amounts for Cadillac Tax calculation | It should be amount in dollar rounded to two decimal |  | Need to know if the modified entered value needs to be saved only for session or future? | 3 |  |  |  | 3 | 3 | 3
US.PE.CAD.13 | User input - Number of Employees | 13 |  |  | Discussed | Benefit Manager | So that I can enter the number of employees | System should store the count for Cadillac Tax calculation | Should only be an integer |  | Need to know if the modified entered value needs to be saved only for session or future? | 13 |  |  |  | 13 | 5 | 13
US.PE.CAD.14 | Load appropriate sections to show premium tire wise break down in cadiallc tax | 13 |  |  | Discussed | Benefit Managar | I can see for next 5 years from 2018 the premium tire wise, break down of entire calculation | Once Calculate Cadillac Tax button is clicked the Calculator should show below breakdown of calculation for next 5 years from 2018 the CAC, Threshold Limit Applicable Dollar Limit,Amount Over Threshold,Excise Tax (40%),Number of Employees,Total Projected Tax | For all the Premium tire, all the values (CAC, Threshold Limit Applicable Dollar Limit,Amount Over Threshold,Excise Tax (40%),Number of Employees,Total Projected Tax) should get calculated and I should be able to see the breakdown for next 5 years from 2018 |  |  | 13 |  |  |  | 8 | 13 | 13
US.PE.CAD.15 | Formula for Projected Premium (CAC) for self | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | (CAC of Self)*(1+Trend) ^(Year-Current Year)+(FSA of Self + HRA of Self + HAS of Self + MSA of Self)*(1+ Medical account contribution growth)^ )^(Year-Current Year) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals | In formulas below, to explain calculation for multiple premium tires I have taken example of 2 premium types: 1) Self and 2) Other than self only. (It could by more than this. The calculation remains similar to the ones given in next few user stories) |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.16 | Formula for Projected Premium (CAC) for ‘Other than Self Only’ | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | (CAC of Self)*(1+Trend) ^(Year-Current Year)+(FSA of Self + HRA of Self + HAS of Self + MSA of Self)*(1+ Medical account contribution growth)^ )^(Year-Current Year) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.17 | Formula for Threshold Limit Applicable Dollar Limit (2018, Self) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | It should come equal to Annual Dollar Limit (ADL) of self. | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.18 | Formula for Threshold Limit Applicable Dollar Limit (2018, Other than self only) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | It should come equal to Annual Dollar Limit (ADL) of other that self only. | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.19 | Formula for Threshold Limit Applicable Dollar Limit (2019, self) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of self*(1+ Cost of Living Adjustment Factor+1%) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.20 | Formula for Threshold Limit Applicable Dollar Limit (2019, Other than self only) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of other than self only *(1+ Cost of Living Adjustment Factor+1%) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.21 | Formula for Threshold Limit Applicable Dollar Limit (2020-2022,Self) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of self *(1+ Cost of Living Adjustment Factor+1%) ^(Year for which this is being calculated – 2019) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.22 | Formula for Threshold Limit Applicable Dollar Limit (2020-2022, Other than self only) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of other than self only*(1+ Cost of Living Adjustment Factor+1%) ^(Year for which this is being calculated – 2019) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.23 | Formula for Amount Over Threshold (2018 -2022) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | It should statisfy the logic: If (Projected Premium - Threshold Limit Applicable Dollar Limit > 0) then: Amount Over Threshold = Projected Premium - Threshold Limit Applicable Dollar Limit Else: Amount Over Threshold =0 | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.24 | Formula for Excise Tax (40%) | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Amount Over Threshold* 40% | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.25 | Formula for Number of Employees | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Number of Employees (FN1)*(1+Employee Growth) ^(Year for which this is being calculated – 2019) | The result should only be an integer value. |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.26 | Formula for Total Projected Tax | 13 |  |  | Discussed | Benefit Manager | I can see the calculated value using the appropriate formula | Excise Tax* Number of Employees | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.27 | Formula for Total of Total Projected Tax | 13 |  |  | Discussed | Benefit Manager | This should give me total of all the projected tax, for all the premium tier) | Sum( Total Projected Tax of Self+Total Projected Tax of other than self) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 |  |  |  | 20 | 20 | 13
US.PE.CAD.28 | Help | 8 |  |  | Discussed | Benefit Manager | I can get explanation about the technical terms used in the calculator. | When I click on help, this definations and footnates should pop up. | It should given information only about the terms used in this calculator. |  |  | 8 |  |  |  | 8 | 8 | 2
US.PE.HCR.01 | Both-Pull Essential data from the service | 40 |  | Sprint02 | Discussed | Benefit Manager | I should fetch the information from the service | It should pull the client name, Total Plan Participants, Estimated 2016 Annual Premium, type of insured(self funded, fully or both) from the database. | Correct information should be pulled |  |  | 40 |  |  |  | 40 | 40 | 40
US.PE.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 |  | Sprint02 | Discussed | Benefit Manager | I should see the details fetched from the service and it should be read-only. | Data showing this information should be pulled from the database and should be displayed on the webpage | Correct information should be displayed on the calculator |  | Need to know if the calulcation needs to be done Total Plan Particupants * 5000? What is the 5000? | 8 |  |  |  | 5 | 8 | 8
US.PE.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 |  | Sprint02 | Discussed | Benefit Manager | I should see the details calculated based on the 3.5 % of "Estimated 2016 annual premium" | Data should be calculated based on the data available for estimated 2016 annual premium | Correct information should be pulled |  |  | 8 |  |  |  | 5 | 8 | 8
US.PE.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 |  | Sprint02 | Discussed | Benefit Manager | I should fetch the information from the service and display the information | Data showing this information should be pulled from the database and should be displayed on the webpage | Correct information should be pulled |  |  | 20 |  |  |  | 20 | 13 | 13
US.PE.HCR.05 | Both-Identify and Run the model that needs to be run | 13 |  | Sprint02 | Discussed | Benefit Manager | I should choose the right calculator based on theinsured type to perform the calculations amongst the two. | Webpage should pull the insured type from the service and depending on the type selected and run the model | If the employee is fully insured, fully insured model should run. If the employee is self-funded, self-funded model should run. If there partially fully insured and partially self-funded each part is run separately |  | Is there possiblity for both options to be displayed in screen or will it be one at a time? | 8 |  |  |  | 8 | 13 | 20
US.PE.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 |  | Sprint02 | Discussed | Benefit Manager | Calculator should calculate using the appropriate formula and should show me the result | Calculator should calculate this using the formula: Estimated 2016 Annual Premium * % of annual premium | The amount should be in dollars. |  |  | 8 |  |  |  | 8 | 8 | 5
US.PE.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 |  | Sprint02 | Discussed | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: Total Plan Participants * amount of per plan participant per year | The amount should be in dollars. |  |  | 8 |  |  |  | 8 | 8 | 5
US.PE.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 |  | Sprint02 | Discussed | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: Total Plan Participants* amount of per plan participant in 2016. | The amount should be in dollars. |  |  | 8 |  |  |  | 8 | 8 | 5
US.PE.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 |  | Sprint02 | Discussed | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | This will be sum of Health Insurer Assessment, Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | The amount should be in dollars. |  |  | 8 |  |  |  | 8 | 8 | 5
US.PE.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 |  | Sprint02 | Discussed | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: (Total Estimated HCR Fees/ Estimated 2016 Annual Premium)*100 | Should be a percent value. |  |  | 8 |  |  |  | 8 | 8 | 5
US.PE.HCR.11 | Both-Pie Chart |  |  | Sprint02 | Discussed | Benefit Manager | To display the graphical representation in pie-chart by using the data provided for Total Estimated HCR Fees ($) of Total Plan Cost without HCR | Pie chart should calculate using the below logic and show pie representation of the data. Total Estimated HCR Fees ($) +Total Plan Cost without HCR = Estimated 2016 Annual Premium | Pie chart should display both the value in the pie, label showing distribution of pie both inn terms of amount as well as percent | This needs to be analysed for estimation |  | 100 |  |  |  | 100 | 100 | 20
US.PE.HCR.12 | Fully-insured-Bar Chart |  |  | Sprint02 | Discussed | Benefit Manager | To Display the Bar-Chart with the values provided. So that I can visualise and compare the values | Bar Chart should show bars for Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | X axis - labels; y axis - Amount($) scale; and bars. Label to show each bar value should alse be available. | This needs to be analysed for estimation |  | 100 |  |  |  | 100 | 100 | 40
US.PE.HCR.13 | Self-funded-Bar Chart |  |  | Sprint02 | Discussed | Benefit Manager | To Display the Bar-Chart with the values provided. So that I can visualise and compare the values | Bar Chart should show bars for Health Insurer Assessment, Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | X axis - labels; y axis - Amount($) scale; and bars. Label to show each bar value should alse be available. | This needs to be analysed for estimation |  | 20 |  |  |  | 40 | 20 | 40
US.PE.EEOE.01 | individualevent_life_calculator |  | 10 | [16 empty] | 756 |  |  | Padmanabhan
US.PE.EEOE.02 | Integrating EOI with Prudential | 40 | 1 | Sprint03 | Need Input | Employee | Employee should complete the online EOI Questionnaire and return back to enrollment flow. | When the requested amount is greater than the GI |  |  | Prudential can be done. Need clarity from PO on Aflac. Discussed with PO and awatiing information from PO. | [8 empty] | 733 |  |  | Nivedha
US.PE.EEOE.03 | Enrollment Bundle | 40 | 1 | [16 empty] | 734 |  |  | Nivedha
US.PE.EEOE.04 | Help Content |  | 10 | [16 empty] | 729 |  |  | Padmanabhan
US.PE.EEOE.05 | Site Map |  | 10 | [16 empty] | 741 |  |  | Padmanabhan
US.PE.EEOE.06 | Queing up OE during NH when OE is active | 20 | 1 | Sprint03 | [15 empty] | 742 |  |  | Nivedha
US.PE.EEOE.07 | OE is Open, removing dependent needs to do unenroll from all the plans the dependent got enrolled and then submit | 40 | 1 | Sprint03 | [15 empty] | 747 |  |  | Ram
US.PE.EEOE.08 | Add Beneficiary should pop up a model window similar to add dependent and should display any life plan for which the beneficiary required and add the person and equally distribute | 13 | 10 | [16 empty] | 748 |  |  | Ram
US.PE.EEOE.09 | OE it not active now, doing Add/Remove dependents should not take go to dependent Screen, it has to take the user to LE screen | 8 | 1 | [16 empty] | 749 |  |  | Ram
US.PE.EEOE.10 | Generate PDF (Use Tall PDF) and Opens the PDF as a last page | 40 | 1 | [7 empty] | Refer https://www.tallcomponents.com/pdfkit. Clarity needed: jSON limitation + PDF UI needed from UI team | 40 | 40 | 40 | 8 |  |  |  |  | 752 |  |  | Naresh
US.PE.EEOE.11 | Use https://github.com/nnnick/Chart.js for Pie Chartchart.js-master in Summary page image. | 40 | 1 | [16 empty] | 817 |  |  | Dilip
US.PE.EEOE.12 | Incorporate HSA , FSA related changes done by Senthil in existing EEOE | 40 | 1 | [16 empty] | 819 |  |  | Nivedha
US.PE.EEOE.13 | Work Flow screen needs to come in the same way like Existing EEOE | 40 | 1 | [16 empty] | 820 |  |  | Ram
US.PE.EEOE.14 | Work Flow needs to be triggered for all plans | 40 | 1 | [16 empty] | 821 |  |  | Nivedha
US.PE.EEOE.15 | The user should be able to start typing and the dropdown should move to that part of the list | 13 | 1 | [16 empty] | 822 |  |  | Naresh
US.PE.EEOE.16 | The state should not be prefilled to AA – the user should select. | 2 | 1 | [16 empty] | 823 |  |  | Naresh
US.PE.EEOE.17 | 0 plans have price changes, 1 plan has a price change, 2 plans have price changes 0 plans are no longer available (should never be displayed), 1 plan is no longer available, 2 plans are no longer available 0 new plans are available, 1 new plan is available, 2 new plans are available | 3 | 1 | [16 empty] | 824 |  |  | Naresh
US.PE.EEOE.18 | Integrate Documents similar to Verbiage | 20 | 1 | Sprint03 | [7 empty] | 20 | 13 | 20 | 20 |  |  |  |  | TFSID#1
US.PE.EEOE.19 | Add Package next to Employee in the Vertical Menu | 5 | 1 | Sprint03 | [7 empty] | 5 | 5 | 5 | 5 |  |  |  |  | TFSID#2 |  |  | Naresh
US.PE.EEOE.20 | Current vs upcoming. Show Only for OE and LE not for NH. Don't display for NH navigate directly to Benefit Screen | 5 | 1 | Sprint03 | [7 empty] | 5 | 5 | 5 | 5 |  |  |  |  | 834 |  | Show Only for OE and LE not for NH. Don't display for NH navigate directly to Benefit Screen | Ram
US.PE.EEOE.21 | benefit section link. Dead on the change account screen. should be related to update my account info unable to understand the issue |  | 1 |  | Need Input | [14 empty] | TFSID#3 |  | Pad will confirm the behavior | Padmanabhan
US.PE.EEOE.22 | Medical Plan Screen - covered dependents and related information |  | 1 | [16 empty] | TFSID#4 |  | Contact Business. Responsibility Pad. | Padmanabhan
US.PE.EEOE.23 | type 3 plans - need to have deduction information |  | 1 | [16 empty] | TFSID#5 |  | Contact Business. Responsibility Pad. | Padmanabhan
US.PE.EEOE.24 | county vision plan no details - Vision plan |  | 1 | [16 empty] | TFSID#6 |  | Contact Business. Responsibility Pad. | Padmanabhan
US.PE.EEOE.25 | Account setup - post registration skip login. Implement Similar to Market Place | 5 | 1 | Sprint03 | [7 empty] | 5 | 5 | 5 | 5 |  |  |  |  | TFSID#7 |  |  | Ram
US.PE.EEOE.26 | Message Center - Are employer messages showing here now | 13 | 1 | Sprint03 | Need Input | [5 empty] | Need info on the logic which sends mail so that I can implement it. | 13 | 13 | 13 | 13 |  |  |  |  | TFSID#8 |  |  | Ram
US.PE.EEOE.27 | Message Center - Are employer messages showing here now - Attachment currently not implemented | 8 | 1 | [8 empty] | 8 | 8 | 8 | 8 |  |  |  |  | TFSID#9 |  | Attachment currently not implemented. Dependent on user story US.PE.EEOE.10 | Ram
US.PE.EEOE.28 | column formatting off with log plan numbers - Compare screen | 3 | 1 | Sprint03 | [7 empty] | 3 | 3 | 3 | 3 |  |  |  |  | TFSID#10 |  | Unable to reproduce the issue. UI team correction needed. Ram to work with PO to get reproduce | Ram
US.PE.EEOE.29 | Implement Comparison Screen in All Plans | 8 | 1 | Sprint03 | [7 empty] | 8 | 8 | 8 | 8 |  |  |  |  | TFSID#11 |  |  | Ram
US.PE.EEOE.30 | Integrating EOI with AFLAC |  | 1 |  | Need Input | Employee | Employee should complete the online EOI Questionnaire and return back to enrollment flow. | When the requested amount is greater than the GI |  |  | Prudential can be done. Need clarity from PO on Aflac. Discussed with PO and awatiing information from PO. | [8 empty] | 733 |  |  | Nivedha
Note on G2: Author: The primary user or stakeholder for the story
Note on H2: Author: The goal that the actor is trying to achieve in the story
Note on I2: Author: The actions performed by the actor.
Note on J2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z
Auto Calculation |  |  |  |  | Current Wk# | Sprint03 |  |  |  |  | Development | [8 empty] | QA |  |  |  | Acceptance Testing
No Entry | [5 empty] | 159 |  | 175.5 | 0 | WIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Type | Impact Analysis | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | Built & Deploy | QA Test Case | Integration Testing | Functional Testing | Regression Testing | Acceptance Test Case | Demoed to PO
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | US.PE.HCR.01 | Both-Pull Essential data from the service | 0 | Moved | 16.3 | 16.3 | Name |  |  | KV, AS | KV |  |  |  | KV |  |  | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | NS | WIP |  | NA | NA | NA | Done |  | NR | Done | Done |  | NR | NR
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  |  | 8 | 6 |  |  |  | 2 |  |  | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  |  | 8 | 6 |  |  |  | 2 |  |  | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 2 | US.PE.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 0 | Moved | 3.8 | 3.8 | Name |  |  | AS | AS | [5 empty] | SB | SB | SB |  | PD | DP
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  |  | Done | Done | [5 empty] | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  |  | 2 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  |  | 2 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 3 | US.PE.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 0 | Moved | 3.8 | 3.8 | Name |  | AS | AS | AS | [5 empty] | SB | SB | SB |  | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 4 | US.PE.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 0 | Moved | 4.8 | 4.8 | Name |  | AS | AS | AS | [5 empty] | SB | SB | SB |  | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 2 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 2 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 5 | US.PE.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 0 | Moved | 3.8 | 3.8 | Name |  | RJ | RJ | RJ | [5 empty] | SB | SB | SB |  | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 6 | US.PE.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 0 | Moved | 3.8 | 3.8 | Name |  | RJ | RJ | RJ | [5 empty] | SB | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 7 | US.PE.HCR.08 | Formula for Both-Transitional Reinsurance Program | 0 | Moved | 3.8 | 3.8 | Name |  | AS | AS | AS | [5 empty] | SB | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 8 | US.PE.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 0 | Moved | 3.8 | 3.8 | Name |  | RJ | RJ | RJ | [5 empty] | SB | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | Sprint01 | 9 | US.PE.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 0 | Moved | 3.8 | 3.8 | Name |  | AS | AS | AS | [5 empty] | SB | SB | SB
KE.BBPE.1 | 2015-47 | [8 empty] | Status |  | Done | Done | Done | NR | NR | NA | NA |  | Done | Done | Done |  | NS | NS
KE.BBPE.1 | 2015-47 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-47 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | Sprint02 | 10 | US.PE.HCR.01 | Both-Pull Essential data from the service | 40 | WIP | 7.8 | 6.8 | Name |  |  | AS | AS |  |  | AS |  |  | SB | SB | SB |  |  | DP
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | NA | Done | Done | NR | NR | Done | NR |  | Done | Done | Done |  |  | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  |  | 4 | 1 |  |  | 2 |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  |  | 3 | 1 |  |  | 2 |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | Sprint02 | 11 | US.PE.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 | WIP | 3.8 | 2.8 | Name |  |  | AS | AS | [5 empty] | SB | SB | SB |  |  | DP
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | NA | Done | Done |  | NR |  |  |  | Done | Done | Done |  |  | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  |  | 2 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  |  | 1 | 1 | [5 empty] | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | Sprint02 | 12 | US.PE.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 | WIP | 4.8 | 4.8 | Name |  | AS | AS | AS | AS |  |  |  |  | SB | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | Done | NR |  |  |  | Done | Done | Done
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | Sprint02 | 13 | US.PE.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 | WIP | 4.8 | 4.8 | Name |  | AS | AS | AS | AS |  |  |  |  | SB | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | Done | NR |  |  |  | Done | Done | Done
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | Sprint02 | 14 | US.PE.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 | WIP | 4.8 | 4.8 | Name |  | AS | AS | AS | AS |  |  |  |  | SB | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | Done | NR |  |  |  | Done | Done | Done
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.5 | 0.15 | 0.15
KE.BBPE.1 | 2015-48 | Sprint02 | 15 | US.PE.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 | WIP | 4 | 4 | Name |  | AS | AS | AS | [5 empty] | SB | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | NS | NR |  |  |  | Done | Done | Done
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 1 | 1 | [5 empty] | 0.5 | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | Sprint02 | 16 | US.PE.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 | WIP | 3.5 | 3 | Name |  | AS | AS | As |  | AS |  |  |  | SB | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | NR | Done |  |  |  | Done | Done | Done
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 0.5 | 0.5 | 0.5 |  | 1 |  |  |  | 0.5 | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 0.5 | 0.5 | 0.5 |  | 1 |  |  |  | 0.5
KE.BBPE.1 | 2015-48 | Sprint02 | 17 | US.PE.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 | WIP | 3 | 2.5 | Name |  | AS | AS | AS | [6 empty] | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | NR | NR |  |  |  |  | NS | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 1 | 0.5 | [6 empty] | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 1 | 0.5
KE.BBPE.1 | 2015-48 | Sprint02 | 18 | US.PE.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 | WIP | 4.5 | 4 | Name |  | AS | AS | AS |  | RJ |  |  |  |  | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | NR | Done |  |  |  |  | NS | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 1 | 1 |  | 1 |  |  |  |  | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 1 | 1 |  | 1
KE.BBPE.1 | 2015-48 | Sprint02 | 19 | US.PE.HCR.11 | Both-Pie Chart | 0 | WIP | 4.5 | 4 | Name |  |  | AS | AS | AS | RJ |  |  |  |  | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | NR | Done |  | Done | Done |  |  |  |  | NS | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  |  | 1 | 1 | 1 | 1
KE.BBPE.1 | 2015-48 | Sprint02 | 20 | US.PE.HCR.12 | Fully-insured-Bar Chart | 0 | WIP | 1.5 | 1 | Name | [5 empty] | RJ |  |  |  |  | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | NR | NR | NR | NR | Done |  |  |  |  | NS | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned | [5 empty] | 1 |  |  |  |  | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual | [5 empty] | 1
KE.BBPE.1 | 2015-48 | Sprint02 | 21 | US.PE.HCR.13 | Self-funded-Bar Chart | 0 | WIP | 1.5 | 1 | Name | [5 empty] | RJ |  |  |  |  | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | NR | NR | NR | NR | Done |  |  |  |  | NS | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned | [5 empty] | 1 |  |  |  |  | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual | [5 empty] | 1
KE.BBPE.1 | 2015-48 | Sprint02 | 22 | US.PE.HCR.05 | Both-Identify and Run the model that needs to be run | 13 | WIP | 9 | 6 | Name |  | AS | AS | AS | [5 empty] | SB | SB | SB
KE.BBPE.1 | 2015-48 | [8 empty] | Status |  | Done | Done | Done | NR |  |  |  |  | Done | NS | NS
KE.BBPE.1 | 2015-48 | [8 empty] | Planned |  | 1 | 5 | 2 | [5 empty] | 0.5 | 0.25 | 0.25
KE.BBPE.1 | 2015-48 | [8 empty] | Actual |  | 1 | 3 | 2
KE.BBPE.1 | 2015-49 | Sprint03 | 23 | US.PE.EEOE.02 | Integrating EOI with Prudential | 40 | WIP |  |  | Name |  | NC | NC | NC | NC | NC | NC | NC
KE.BBPE.1 | 2015-48 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  | 5 | 24 |  | 15 | 20 | 4 | 15 |  | 0.5 | 0.25 | 0.25
KE.BBPE.1 | 2015-49 | [8 empty] | Actual |  | 1 | 3 | 2
KE.BBPE.1 | 2015-49 | Sprint03 | 24 | US.PE.EEOE.06 | Queing up OE during NH when OE is active | 20 | WIP | 0 | 0 | Name
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 25 | US.PE.EEOE.07 | OE is Open, removing dependent needs to do unenroll from all the plans the dependent got enrolled and then submit | 40 | WIP | 67 | 0 | Name |  | RG | RG | RG |  |  | RG | RG |  | RAA | RAA | RAA
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  | 10 | 15 | 10 |  |  | 5 | 20 |  | 1 | 3 | 3
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 26 | US.PE.EEOE.18 | Integrate Documents similar to Verbiage | 20 | WIP | 8 | 0 | Name |  | NC | NC | NC | NC | NC | NC | NC
KE.BBPE.1 | 2015-49 | [8 empty] | Status |  | Done | Done | WIP | Done | Done | Done | Done
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  |  |  | 8
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 27 | US.PE.EEOE.19 | Add Package next to Employee in the Vertical Menu | 5 | WIP | 5 | 0 | Name | [9 empty] | RAA | RAA | RAA
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned | [9 empty] | 1 | 2 | 2
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 28 | US.PE.EEOE.20 | Current vs upcoming. Show Only for OE and LE not for NH. Don't display for NH navigate directly to Benefit Screen | 5 | WIP | 12 | 0 | Name |  | NN | NN | [6 empty] | RAA | RAA | RAA
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  | 2 | 5 | [6 empty] | 1 | 2 | 2
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 29 | US.PE.EEOE.25 | Account setup - post registration skip login. Implement Similar to Market Place | 5 | WIP | 32 | 0 | Name |  | NN | NN |  |  |  | NN | NN |  | SB | SB | SB
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  | 2 | 15 |  |  |  | 5 | 5 |  | 1 | 2 | 2
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 30 | US.PE.EEOE.26 | Message Center - Are employer messages showing here now | 13 | WIP | 5 | 0 | Name | [9 empty] | SB | SB | SB
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned | [9 empty] | 1 | 2 | 2
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 31 | US.PE.EEOE.28 | column formatting off with log plan numbers - Compare screen | 3 | WIP | 8.5 | 0 | Name |  | RG |  | RG | [5 empty] | RAA | RAA | RAA
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  | 1 |  | 5 | [5 empty] | 0.5 | 1 | 1
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
KE.BBPE.1 | 2015-49 | Sprint03 | 32 | US.PE.EEOE.29 | Implement Comparison Screen in All Plans | 8 | WIP | 38 | 0 | Name |  | RG | RG | RG | RG |  |  |  |  | SB | SB | SB
KE.BBPE.1 | 2015-49 | [8 empty] | Status
KE.BBPE.1 | 2015-49 | [8 empty] | Planned |  | 5 | 15 | 5 | 8 |  |  |  |  | 1 | 2 | 2
KE.BBPE.1 | 2015-49 | [8 empty] | Actual
Note on K3: WIP Limit Status ==>>
Note on K6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K58: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K62: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K66: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K70: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K74: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K78: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K82: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K86: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K90: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K94: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K98: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K102: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K106: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K110: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K114: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K118: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K122: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K126: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on K130: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes