## Sprint-Master
Sprint# | Week of Year | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
Sprint01 | 2015-47 | 2015-11-16 | 2015-11-20 | 2 | 5 | 200 | 45 | 45 | 0 | 16-Nov Heavy Rain | HCR Calculator Should be delivered
Sprint02 | 2015-48 | 2015-11-23 | 2015-11-27 | 3 | 5 | 120 | 28 |  |  |  | HCR Fully Insured / Self Funded separating depending upon the client.
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+3

## Resources
Week of Year | 2015-48
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
F15600 | Sanjana Babu | QA | SB | 1
F16453 | Ashok S | Dev | AS | 1
F16707 | Rajesh Kanna P | Dev | RK | 0.2
F0101 | Seshan T R | SM | STR | 1
Grand Total |  |  |  | 3.2

## PRA
Update this Every Weekend
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16039 | 1 | Karthikeyan V | KV | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16305 | 1 | Dilip Prasad J | DP | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16453 | 1 | Ashok S | AS | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F15435 | 1 | Sathish V | SV | QA
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F15600 | 1 | Sanjana Babu | SB | QA
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | FT12358 | 1 | Shreya Gupta | SG | BA
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F16707 | 1 | Rajeshkanna P | RK | Dev
KE.BBPE.1 | 2015-47 | Sprint01 | 1 | F0101 | 1 | Seshan T R | STR | SM
KE.BBPE.1 | 2015-48 | Sprint02 | 1 | F16453 | 1 | Ashok S | AS | Dev
KE.BBPE.1 | 2015-48 | Sprint02 | 1 | F16707 | 0.2 | Rajeshkanna P | RK | Dev
KE.BBPE.1 | 2015-48 | Sprint02 | 1 | F15600 | 1 | Sanjana Babu | SB | QA
KE.BBPE.1 | 2015-48 | Sprint02 | 1 | F0101 | 1 | Seshan T R | STR | SM
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Karthikeyan | Sathish | Shreya | Ravindra | Status
US.BM.CAD.01 | Get client name, plan type and premium tire details | 20 |  |  | Benefit Manager | I want to get the details of my organization for the determining cadillac tax due to my ogranzation. So that I could estimate cadillac tax of my organization. | When I log in the system, calculator can pull the details like client name, plans , premium types into the calculator | Correct information being pulled | As per Bharat, all this information comes from a webservice and will provide the sql query for pulling this information. |  | 20 | 20 | 13 | 13 |  | Discussed
US.BM.CAD.02 | Threshold Reference table | 13 |  |  | Benefit Manager | I want to see thresholds for various cover types | When I open calc, I see ref table | Constants. | Static Page | Whether data will come from Webservice or table? | 13 | 13 | 8 | 13 |  | Discussed
US.BM.CAD.03 | ??? | 20 |  |  | Benefit Manager | I should be able to create/modify the threshold values of Cadillac Tax |  |  | Added by Estimation Team |  | 13 | 20 | 13 | 13 |  | Discussed
US.BM.CAD.04 | Default rates | 20 |  |  | Benefit Manager | I should be able to see the default values of various rates (i.e. HCAP, COLA etc) and overide if required. | When I see this section, default rate is already present but I should be able to edit it, if I wish too. | Default should be one that is stored in the system.It should be only in percentage. Values should be editable. |  |  | 20 | 20 | 20 | 20 |  | Discussed
US.BM.CAD.05 | User inputs -Rate | 20 |  |  | Benefit Manager | I should be able to create/modify default rate of Trend, Medical account contribution growth, Health Cost Adjustment Percentage Factor (HCAP), Age and Gender Adjustment Factor ,Cost of Living Adjustment Factor (COLA). So that values can be populated in the calculator at the time of Cadillac Tax Calcuation. These values becomes default system values for calculation purpose. | System should store the rates for Cadillac Tax calculation | Should only be numeric and in percent format |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.06 | Tooltips | 13 |  |  | Benefit Manager | I want to get more information about the terms used in the calculator as a tooltip message. So that I know what is the meaning of a particular term. | When I hover over the label and its textbox, corresponding tooltip should pop. | Tool tips should only be for the term on which mouse is hovered. It should be as per the approved wireframe |  |  | 13 | 13 | 8 | 8 |  | Discussed
US.BM.CAD.07 | User input- Coverage type | 13 |  |  | Benefit Manager | I want select the coverage type from the drop down menu. There are 3 coverage types | The cadillac tax will be calculated based on the selected coverage | Coverage type should be the ones from the threshold reference table |  |  | 13 | 13 | 8 | 8 |  | Discussed
US.BM.CAD.08 | Display HCAP,Age and Gender Adjustment Factor and COLA rate | 5 |  |  | Benefit Manager | I want see what are the rate I have entered in input data for HCAP,Age and Gender Adjustment Factor and COLA so that I know correct rates are being used for calculation. | Display | System should show these value which I have entered using userstory PE.BM.CAD.05 |  |  | 5 | 5 | 5 | 2 |  | Discussed
US.BM.CAD.09 | Calculate Annual Dollar Limit (ADL) with Adjustments | 8 |  |  | Benefit Manager | I want that system should calculate ADL 2018 with adjustments using the formula for calculation | It should be calculated using the formula: ADL * (1+HCAP) * (1+Age and gender adjustment factor) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. |  |  | 8 | 8 | 8 | 8 |  | Discussed
US.BM.CAD.10 | Load appropriate user input sections for different Premium tire |  |  |  | Benefit Manager | I want the all the premium tire's to be fetched | When I load this page, by then the calculator should already know my premium tires and load appropriate input sections | Premium tire should display and textbox should be loaded with calculated vlaues of premium, FSA, HRA, HAS and MSA. This should allow me to change the values. | this needs to be analysed for estimation |  | 40 | 100 | 100 | 40 |  | Discussed
US.BM.CAD.11 | Default Values for Total Premium, FSA, HRA, HSA and MSA | 20 |  |  | Benefit Manager | I want to get default values of FSA, HRA etc along with premium from the system, so that this can be used for calculation. | When I see this section, default value is already present but I should be able to edit it, if I wish too. | Default should be one that is present in the template. For the one I enter, it should be amount in dollar rounded to two decimal. |  |  | 20 | 20 | 20 | 20 |  | Discussed
US.BM.CAD.12 | Edit User inputs -Premium, FSA, HRA, HSA and MSA amounts | 3 |  |  | Benefit Manager | So that I can enter Premium, FSA, HRA, HSA and MSA amounts in the calculator. | System should store the amounts for Cadillac Tax calculation | It should be amount in dollar rounded to two decimal |  | Need to know if the modified entered value needs to be saved only for session or future? | 3 | 3 | 3 | 3 |  | Discussed
US.BM.CAD.13 | User input - Number of Employees | 13 |  |  | Benefit Manager | So that I can enter the number of employees | System should store the count for Cadillac Tax calculation | Should only be an integer |  | Need to know if the modified entered value needs to be saved only for session or future? | 13 | 13 | 5 | 13 |  | Discussed
US.BM.CAD.14 | Load appropriate sections to show premium tire wise break down in cadiallc tax | 13 |  |  | Benefit Managar | I can see for next 5 years from 2018 the premium tire wise, break down of entire calculation | Once Calculate Cadillac Tax button is clicked the Calculator should show below breakdown of calculation for next 5 years from 2018 the CAC, Threshold Limit Applicable Dollar Limit,Amount Over Threshold,Excise Tax (40%),Number of Employees,Total Projected Tax | For all the Premium tire, all the values (CAC, Threshold Limit Applicable Dollar Limit,Amount Over Threshold,Excise Tax (40%),Number of Employees,Total Projected Tax) should get calculated and I should be able to see the breakdown for next 5 years from 2018 |  |  | 13 | 8 | 13 | 13 |  | Discussed
US.BM.CAD.15 | Formula for Projected Premium (CAC) for self | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | (CAC of Self)*(1+Trend) ^(Year-Current Year)+(FSA of Self + HRA of Self + HAS of Self + MSA of Self)*(1+ Medical account contribution growth)^ )^(Year-Current Year) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals | In formulas below, to explain calculation for multiple premium tires I have taken example of 2 premium types: 1) Self and 2) Other than self only. (It could by more than this. The calculation remains similar to the ones given in next few user stories) |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.16 | Formula for Projected Premium (CAC) for ‘Other than Self Only’ | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | (CAC of Self)*(1+Trend) ^(Year-Current Year)+(FSA of Self + HRA of Self + HAS of Self + MSA of Self)*(1+ Medical account contribution growth)^ )^(Year-Current Year) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.17 | Formula for Threshold Limit Applicable Dollar Limit (2018, Self) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | It should come equal to Annual Dollar Limit (ADL) of self. | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.18 | Formula for Threshold Limit Applicable Dollar Limit (2018, Other than self only) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | It should come equal to Annual Dollar Limit (ADL) of other that self only. | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.19 | Formula for Threshold Limit Applicable Dollar Limit (2019, self) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of self*(1+ Cost of Living Adjustment Factor+1%) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.20 | Formula for Threshold Limit Applicable Dollar Limit (2019, Other than self only) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of other than self only *(1+ Cost of Living Adjustment Factor+1%) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.21 | Formula for Threshold Limit Applicable Dollar Limit (2020-2022,Self) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of self *(1+ Cost of Living Adjustment Factor+1%) ^(Year for which this is being calculated – 2019) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.22 | Formula for Threshold Limit Applicable Dollar Limit (2020-2022, Other than self only) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of other than self only*(1+ Cost of Living Adjustment Factor+1%) ^(Year for which this is being calculated – 2019) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.23 | Formula for Amount Over Threshold (2018 -2022) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | It should statisfy the logic: If (Projected Premium - Threshold Limit Applicable Dollar Limit > 0) then: Amount Over Threshold = Projected Premium - Threshold Limit Applicable Dollar Limit Else: Amount Over Threshold =0 | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.24 | Formula for Excise Tax (40%) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Amount Over Threshold* 40% | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.25 | Formula for Number of Employees | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Number of Employees (FN1)*(1+Employee Growth) ^(Year for which this is being calculated – 2019) | The result should only be an integer value. |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.26 | Formula for Total Projected Tax | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Excise Tax* Number of Employees | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.27 | Formula for Total of Total Projected Tax | 13 |  |  | Benefit Manager | This should give me total of all the projected tax, for all the premium tier) | Sum( Total Projected Tax of Self+Total Projected Tax of other than self) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 |  | Discussed
US.BM.CAD.28 | Help | 8 |  |  | Benefit Manager | I can get explanation about the technical terms used in the calculator. | When I click on help, this definations and footnates should pop up. | It should given information only about the terms used in this calculator. |  |  | 8 | 8 | 8 | 2 |  | Discussed
US.BM.HCR.01 | Both-Pull Essential data from the service | 40 | Sprint1 |  | Benefit Manager | I should fetch the information from the service | It should pull the client name, Total Plan Participants, Estimated 2016 Annual Premium, type of insured(self funded, fully or both) from the database. | Correct information should be pulled |  |  | 40 | 40 | 40 | 40 |  | Discussed
US.BM.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 | Sprint1 |  | Benefit Manager | I should see the details fetched from the service and it should be read-only. | Data showing this information should be pulled from the database and should be displayed on the webpage | Correct information should be displayed on the calculator |  | Need to know if the calulcation needs to be done Total Plan Particupants * 5000? What is the 5000? | 8 | 5 | 8 | 8 |  | Discussed
US.BM.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 | Sprint1 |  | Benefit Manager | I should see the details calculated based on the 3.5 % of "Estimated 2016 annual premium" | Data should be calculated based on the data available for estimated 2016 annual premium | Correct information should be pulled |  |  | 8 | 5 | 8 | 8 |  | Discussed
US.BM.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 | Sprint1 |  | Benefit Manager | I should fetch the information from the service and display the information | Data showing this information should be pulled from the database and should be displayed on the webpage | Correct information should be pulled |  |  | 20 | 20 | 13 | 13 |  | Discussed
US.BM.HCR.05 | Both-Identify and Run the model that needs to be run | 13 | Sprint1 |  | Benefit Manager | I should choose the right calculator based on theinsured type to perform the calculations amongst the two. | Webpage should pull the insured type from the service and depending on the type selected and run the model | If the employee is fully insured, fully insured model should run. If the employee is self-funded, self-funded model should run. If there partially fully insured and partially self-funded each part is run separately |  | Is there possiblity for both options to be displayed in screen or will it be one at a time? | 8 | 8 | 13 | 20 |  | Discussed
US.BM.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate using the appropriate formula and should show me the result | Calculator should calculate this using the formula: Estimated 2016 Annual Premium * % of annual premium | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 |  | Discussed
US.BM.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: Total Plan Participants * amount of per plan participant per year | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 |  | Discussed
US.BM.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: Total Plan Participants* amount of per plan participant in 2016. | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 |  | Discussed
US.BM.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | This will be sum of Health Insurer Assessment, Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 |  | Discussed
US.BM.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: (Total Estimated HCR Fees/ Estimated 2016 Annual Premium)*100 | Should be a percent value. |  |  | 8 | 8 | 8 | 5 |  | Discussed
US.BM.HCR.11 | Both-Pie Chart |  | Sprint1 |  | Benefit Manager | To display the graphical representation in pie-chart by using the data provided for Total Estimated HCR Fees ($) of Total Plan Cost without HCR | Pie chart should calculate using the below logic and show pie representation of the data. Total Estimated HCR Fees ($) +Total Plan Cost without HCR = Estimated 2016 Annual Premium | Pie chart should display both the value in the pie, label showing distribution of pie both inn terms of amount as well as percent | This needs to be analysed for estimation |  | 100 | 100 | 100 | 20 |  | Discussed
US.BM.HCR.12 | Fully-insured-Bar Chart |  | Sprint1 |  | Benefit Manager | To Display the Bar-Chart with the values provided. So that I can visualise and compare the values | Bar Chart should show bars for Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | X axis - labels; y axis - Amount($) scale; and bars. Label to show each bar value should alse be available. | This needs to be analysed for estimation |  | 100 | 100 | 100 | 40 |  | Discussed
US.BM.HCR.13 | Self-funded-Bar Chart |  | Sprint1 |  | Benefit Manager | To Display the Bar-Chart with the values provided. So that I can visualise and compare the values | Bar Chart should show bars for Health Insurer Assessment, Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | X axis - labels; y axis - Amount($) scale; and bars. Label to show each bar value should alse be available. | This needs to be analysed for estimation |  | 20 | 40 | 20 | 40 |  | Discussed
Note on H2: Author: The primary user or stakeholder for the story
Note on I2: Author: The goal that the actor is trying to achieve in the story
Note on J2: Author: The actions performed by the actor.
Note on K2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
Scrum Board
|  |  | Auto Calculation |  |  |  | Efforts |  |  | Development | [6 empty] | QA |  |  | Acceptance Testing
|  |  | No Entry |  |  |  | 72.5 | 45 | WIP | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# | Sprint# | Week of Year | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Type | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO
1 | Sprint01 | 2015-47 | US.BM.HCR.01 | Both-Pull Essential data from the service | 40 | WIP | 16 | 16 | Name |  | KV, AS | KV |  |  |  | KV |  |  | DR | PD | DP
|  | 2015-47 | [6 empty] | Status | NS | WIP |  | NA | NA | NA | Done | NR | NR | NR | NR | NR
|  | 2015-47 | [6 empty] | Planned |  | 8 | 6 |  |  |  | 2
|  | 2015-47 | [6 empty] | Actual |  | 8 | 6 |  |  |  | 2
2 | Sprint01 | 2015-47 | US.BM.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 | WIP | 3.5 | 3.5 | Name |  | AS | AS |  |  |  |  | DR |  | DR | PD | DP
|  | 2015-47 | [6 empty] | Status |  | Done | Done |  |  |  |  | Done |  | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned |  | 2 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual |  | 2 | 1 |  |  |  |  | 0.5
3 | Sprint01 | 2015-47 | US.BM.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 | WIP | 3.5 | 3.5 | Name | AS | AS | AS |  |  |  |  | SB |  | SB | SB | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 1 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 1 | 1 |  |  |  |  | 0.5
4 | Sprint01 | 2015-47 | US.BM.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 | WIP | 4.5 | 4.5 | Name | AS | AS | AS |  |  |  |  | SB |  | SB | SB | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 2 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 2 | 1 |  |  |  |  | 0.5
5 | Sprint01 | 2015-47 | US.BM.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 | WIP | 3.5 | 3.5 | Name | RJ | RJ | RJ |  |  |  |  | SB |  | SB | SB | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 1 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 1 | 1 |  |  |  |  | 0.5
6 | Sprint01 | 2015-47 | US.BM.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 | WIP | 3.5 | 3.5 | Name | RJ | RJ | RJ |  |  |  |  | SB |  | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 1 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 1 | 1 |  |  |  |  | 0.5
7 | Sprint01 | 2015-47 | US.BM.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 | WIP | 3.5 | 3.5 | Name | AS | AS | AS |  |  |  |  | SB |  | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 1 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 1 | 1 |  |  |  |  | 0.5
8 | Sprint01 | 2015-47 | US.BM.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 | WIP | 3.5 | 3.5 | Name | RJ | RJ | RJ |  |  |  |  | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 1 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 1 | 1 |  |  |  |  | 0.5
9 | Sprint01 | 2015-47 | US.BM.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 | WIP | 3.5 | 3.5 | Name | AS | AS | AS |  |  |  |  | SB
|  | 2015-47 | [6 empty] | Status | Done | Done | Done | NS | NS | NA | NA | Done | NS | NS | NS | NS
|  | 2015-47 | [6 empty] | Planned | 1 | 1 | 1 |  |  |  |  | 0.5
|  | 2015-47 | [6 empty] | Actual | 1 | 1 | 1 |  |  |  |  | 0.5
10 | Sprint02 | 2015-48 | US.BM.HCR.01 | Both-Pull Essential data from the service | 40 |  | 2 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.5 | 0.5
|  | 2015-48 | [6 empty] | Actual
11 | Sprint02 | 2015-48 | US.BM.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
12 | Sprint02 | 2015-48 | US.BM.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
13 | Sprint02 | 2015-48 | US.BM.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
14 | Sprint02 | 2015-48 | US.BM.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
15 | Sprint02 | 2015-48 | US.BM.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
16 | Sprint02 | 2015-48 | US.BM.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
17 | Sprint02 | 2015-48 | US.BM.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 |  | 1.5 | 0 | Name |  |  |  |  | AS |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
18 | Sprint02 | 2015-48 | US.BM.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 |  | 1.5 | 0 | Name |  |  |  |  | RJ |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
19 | Sprint02 | 2015-48 | US.BM.HCR.11 | Both-Pie Chart | 0 |  | 1.5 | 0 | Name |  |  |  |  | RJ |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
20 | Sprint02 | 2015-48 | US.BM.HCR.12 | Fully-insured-Bar Chart | 0 |  | 1.5 | 0 | Name |  |  |  |  | RJ |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
21 | Sprint02 | 2015-48 | US.BM.HCR.13 | Self-funded-Bar Chart | 0 |  | 1.5 | 0 | Name |  |  |  |  | RJ |  |  |  | SB | SB
|  | 2015-48 | [6 empty] | Status |  |  |  |  | NS |  |  |  | NS | NS
|  | 2015-48 | [6 empty] | Planned |  |  |  |  | 1 |  |  |  | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
22 | Sprint02 | 2015-48 | US.BM.HCR.05 | Both-Identify and Run the model that needs to be run | 13 |  | 9 | 0 | Name | AS | AS | AS |  |  |  |  | SB | SB | SB
|  | 2015-48 | [6 empty] | Status | NS | NS | NS |  |  |  |  | Done | NS | NS
|  | 2015-48 | [6 empty] | Planned | 1 | 5 | 2 |  |  |  |  | 0.5 | 0.25 | 0.25
|  | 2015-48 | [6 empty] | Actual
Note on J3: WIP Limit Status ==>>
Note on J6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J58: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J62: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J66: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J70: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J74: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J78: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J82: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J86: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on J90: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## Master
# | Sprint# | Week of Year | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO | Dev Team Status | Completed Complexity | Delivered Complexity
1 | Sprint01 | 2015-47 | US.BM.HCR.01 | Both-Pull Essential data from the service | 40 | WIP | 16 | 16 | Actual | 8 | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | NR | 0 | 0
2 | Sprint01 | 2015-47 | US.BM.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 | WIP | 3.5 | 3.5 | Actual | 2 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
3 | Sprint01 | 2015-47 | US.BM.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 | WIP | 3.5 | 3.5 | Actual | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
4 | Sprint01 | 2015-47 | US.BM.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 | WIP | 4.5 | 4.5 | Actual | 2 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
5 | Sprint01 | 2015-47 | US.BM.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 | WIP | 3.5 | 3.5 | Actual | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
6 | Sprint01 | 2015-47 | US.BM.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 | WIP | 3.5 | 3.5 | Actual | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
7 | Sprint01 | 2015-47 | US.BM.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 | WIP | 3.5 | 3.5 | Actual | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
8 | Sprint01 | 2015-47 | US.BM.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 | WIP | 3.5 | 3.5 | Actual | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
9 | Sprint01 | 2015-47 | US.BM.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 | WIP | 3.5 | 3.5 | Actual | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | NS | 0 | 0
10 | Sprint02 | 2015-48 | US.BM.HCR.01 | Both-Pull Essential data from the service | 40 | 0 | 2 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
11 | Sprint02 | 2015-48 | US.BM.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
12 | Sprint02 | 2015-48 | US.BM.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
13 | Sprint02 | 2015-48 | US.BM.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
14 | Sprint02 | 2015-48 | US.BM.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
15 | Sprint02 | 2015-48 | US.BM.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
16 | Sprint02 | 2015-48 | US.BM.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
17 | Sprint02 | 2015-48 | US.BM.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
18 | Sprint02 | 2015-48 | US.BM.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
19 | Sprint02 | 2015-48 | US.BM.HCR.11 | Both-Pie Chart | 0 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
20 | Sprint02 | 2015-48 | US.BM.HCR.12 | Fully-insured-Bar Chart | 0 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
21 | Sprint02 | 2015-48 | US.BM.HCR.13 | Self-funded-Bar Chart | 0 | 0 | 1.5 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0
22 | Sprint02 | 2015-48 | US.BM.HCR.05 | Both-Identify and Run the model that needs to be run | 13 | 0 | 9 | 0 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NS | 0 | 0

## Charts
Week of Year | 2015-48
Row Labels | Sum of Complexity | Sum of Planned | Sum of Acutal | Sum of Completed Complexity | Sum of Delivered Complexity
Sprint2 | 129 | 27.5 | 0 | 0 | 0
PE.BM.HCR.01 | 40 | 2 | 0 | 0 | 0
PE.BM.HCR.02 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.03 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.04 | 20 | 1.5 | 0 | 0 | 0
PE.BM.HCR.05 | 13 | 9 | 0 | 0 | 0
PE.BM.HCR.06 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.07 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.08 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.09 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.10 | 8 | 1.5 | 0 | 0 | 0
PE.BM.HCR.11 | 0 | 1.5 | 0 | 0 | 0
PE.BM.HCR.12 | 0 | 1.5 | 0 | 0 | 0
PE.BM.HCR.13 | 0 | 1.5 | 0 | 0 | 0
Grand Total | 129 | 27.5 | 0 | 0 | 0

## M
3 | <== Actual Effort Rows
# | # | Sprint# | Week of Year | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO | Completed Complexity
64 | A | B | C | D | E | F | G | H | I | J | L | M | N | O | P | Q | R | S | T | U | V | T
Col # in Scrum Board | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 20
5 | ='SB-Sprints'!A5 | ='SB-Sprints'!B5 | ='SB-Sprints'!C5 | ='SB-Sprints'!D5 | ='SB-Sprints'!E5 | ='SB-Sprints'!F5 | ='SB-Sprints'!G5 | ='SB-Sprints'!H5 | ='SB-Sprints'!I5 | ='SB-Sprints'!J8 | ='SB-Sprints'!L8 | ='SB-Sprints'!M8 | ='SB-Sprints'!N8 | ='SB-Sprints'!O8 | ='SB-Sprints'!P8 | ='SB-Sprints'!Q8 | ='SB-Sprints'!R8 | ='SB-Sprints'!S8 | ='SB-Sprints'!T8 | ='SB-Sprints'!U8 | ='SB-Sprints'!V8 | ='SB-Sprints'!T6
9 | ='SB-Sprints'!A9 | ='SB-Sprints'!B9 | ='SB-Sprints'!C9 | ='SB-Sprints'!D9 | ='SB-Sprints'!E9 | ='SB-Sprints'!F9 | ='SB-Sprints'!G9 | ='SB-Sprints'!H9 | ='SB-Sprints'!I9 | ='SB-Sprints'!J12 | ='SB-Sprints'!L12 | ='SB-Sprints'!M12 | ='SB-Sprints'!N12 | ='SB-Sprints'!O12 | ='SB-Sprints'!P12 | ='SB-Sprints'!Q12 | ='SB-Sprints'!R12 | ='SB-Sprints'!S12 | ='SB-Sprints'!T12 | ='SB-Sprints'!U12 | ='SB-Sprints'!V12 | ='SB-Sprints'!T10
13 | ='SB-Sprints'!A13 | ='SB-Sprints'!B13 | ='SB-Sprints'!C13 | ='SB-Sprints'!D13 | ='SB-Sprints'!E13 | ='SB-Sprints'!F13 | ='SB-Sprints'!G13 | ='SB-Sprints'!H13 | ='SB-Sprints'!I13 | ='SB-Sprints'!J16 | ='SB-Sprints'!L16 | ='SB-Sprints'!M16 | ='SB-Sprints'!N16 | ='SB-Sprints'!O16 | ='SB-Sprints'!P16 | ='SB-Sprints'!Q16 | ='SB-Sprints'!R16 | ='SB-Sprints'!S16 | ='SB-Sprints'!T16 | ='SB-Sprints'!U16 | ='SB-Sprints'!V16 | ='SB-Sprints'!T14
17 | ='SB-Sprints'!A17 | ='SB-Sprints'!B17 | ='SB-Sprints'!C17 | ='SB-Sprints'!D17 | ='SB-Sprints'!E17 | ='SB-Sprints'!F17 | ='SB-Sprints'!G17 | ='SB-Sprints'!H17 | ='SB-Sprints'!I17 | ='SB-Sprints'!J20 | ='SB-Sprints'!L20 | ='SB-Sprints'!M20 | ='SB-Sprints'!N20 | ='SB-Sprints'!O20 | ='SB-Sprints'!P20 | ='SB-Sprints'!Q20 | ='SB-Sprints'!R20 | ='SB-Sprints'!S20 | ='SB-Sprints'!T20 | ='SB-Sprints'!U20 | ='SB-Sprints'!V20 | ='SB-Sprints'!T18
21 | ='SB-Sprints'!A21 | ='SB-Sprints'!B21 | ='SB-Sprints'!C21 | ='SB-Sprints'!D21 | ='SB-Sprints'!E21 | ='SB-Sprints'!F21 | ='SB-Sprints'!G21 | ='SB-Sprints'!H21 | ='SB-Sprints'!I21 | ='SB-Sprints'!J24 | ='SB-Sprints'!L24 | ='SB-Sprints'!M24 | ='SB-Sprints'!N24 | ='SB-Sprints'!O24 | ='SB-Sprints'!P24 | ='SB-Sprints'!Q24 | ='SB-Sprints'!R24 | ='SB-Sprints'!S24 | ='SB-Sprints'!T24 | ='SB-Sprints'!U24 | ='SB-Sprints'!V24 | ='SB-Sprints'!T22
25 | ='SB-Sprints'!A25 | ='SB-Sprints'!B25 | ='SB-Sprints'!C25 | ='SB-Sprints'!D25 | ='SB-Sprints'!E25 | ='SB-Sprints'!F25 | ='SB-Sprints'!G25 | ='SB-Sprints'!H25 | ='SB-Sprints'!I25 | ='SB-Sprints'!J28 | ='SB-Sprints'!L28 | ='SB-Sprints'!M28 | ='SB-Sprints'!N28 | ='SB-Sprints'!O28 | ='SB-Sprints'!P28 | ='SB-Sprints'!Q28 | ='SB-Sprints'!R28 | ='SB-Sprints'!S28 | ='SB-Sprints'!T28 | ='SB-Sprints'!U28 | ='SB-Sprints'!V28 | ='SB-Sprints'!T26
29 | ='SB-Sprints'!A29 | ='SB-Sprints'!B29 | ='SB-Sprints'!C29 | ='SB-Sprints'!D29 | ='SB-Sprints'!E29 | ='SB-Sprints'!F29 | ='SB-Sprints'!G29 | ='SB-Sprints'!H29 | ='SB-Sprints'!I29 | ='SB-Sprints'!J32 | ='SB-Sprints'!L32 | ='SB-Sprints'!M32 | ='SB-Sprints'!N32 | ='SB-Sprints'!O32 | ='SB-Sprints'!P32 | ='SB-Sprints'!Q32 | ='SB-Sprints'!R32 | ='SB-Sprints'!S32 | ='SB-Sprints'!T32 | ='SB-Sprints'!U32 | ='SB-Sprints'!V32 | ='SB-Sprints'!T30
33 | ='SB-Sprints'!A33 | ='SB-Sprints'!B33 | ='SB-Sprints'!C33 | ='SB-Sprints'!D33 | ='SB-Sprints'!E33 | ='SB-Sprints'!F33 | ='SB-Sprints'!G33 | ='SB-Sprints'!H33 | ='SB-Sprints'!I33 | ='SB-Sprints'!J36 | ='SB-Sprints'!L36 | ='SB-Sprints'!M36 | ='SB-Sprints'!N36 | ='SB-Sprints'!O36 | ='SB-Sprints'!P36 | ='SB-Sprints'!Q36 | ='SB-Sprints'!R36 | ='SB-Sprints'!S36 | ='SB-Sprints'!T36 | ='SB-Sprints'!U36 | ='SB-Sprints'!V36 | ='SB-Sprints'!T34
37 | ='SB-Sprints'!A37 | ='SB-Sprints'!B37 | ='SB-Sprints'!C37 | ='SB-Sprints'!D37 | ='SB-Sprints'!E37 | ='SB-Sprints'!F37 | ='SB-Sprints'!G37 | ='SB-Sprints'!H37 | ='SB-Sprints'!I37 | ='SB-Sprints'!J40 | ='SB-Sprints'!L40 | ='SB-Sprints'!M40 | ='SB-Sprints'!N40 | ='SB-Sprints'!O40 | ='SB-Sprints'!P40 | ='SB-Sprints'!Q40 | ='SB-Sprints'!R40 | ='SB-Sprints'!S40 | ='SB-Sprints'!T40 | ='SB-Sprints'!U40 | ='SB-Sprints'!V40 | ='SB-Sprints'!T38
41 | ='SB-Sprints'!A41 | ='SB-Sprints'!B41 | ='SB-Sprints'!C41 | ='SB-Sprints'!D41 | ='SB-Sprints'!E41 | ='SB-Sprints'!F41 | ='SB-Sprints'!G41 | ='SB-Sprints'!H41 | ='SB-Sprints'!I41 | ='SB-Sprints'!J44 | ='SB-Sprints'!L44 | ='SB-Sprints'!M44 | ='SB-Sprints'!N44 | ='SB-Sprints'!O44 | ='SB-Sprints'!P44 | ='SB-Sprints'!Q44 | ='SB-Sprints'!R44 | ='SB-Sprints'!S44 | ='SB-Sprints'!T44 | ='SB-Sprints'!U44 | ='SB-Sprints'!V44 | ='SB-Sprints'!T42
45 | ='SB-Sprints'!A45 | ='SB-Sprints'!B45 | ='SB-Sprints'!C45 | ='SB-Sprints'!D45 | ='SB-Sprints'!E45 | ='SB-Sprints'!F45 | ='SB-Sprints'!G45 | ='SB-Sprints'!H45 | ='SB-Sprints'!I45 | ='SB-Sprints'!J48 | ='SB-Sprints'!L48 | ='SB-Sprints'!M48 | ='SB-Sprints'!N48 | ='SB-Sprints'!O48 | ='SB-Sprints'!P48 | ='SB-Sprints'!Q48 | ='SB-Sprints'!R48 | ='SB-Sprints'!S48 | ='SB-Sprints'!T48 | ='SB-Sprints'!U48 | ='SB-Sprints'!V48 | ='SB-Sprints'!T46
49 | ='SB-Sprints'!A49 | ='SB-Sprints'!B49 | ='SB-Sprints'!C49 | ='SB-Sprints'!D49 | ='SB-Sprints'!E49 | ='SB-Sprints'!F49 | ='SB-Sprints'!G49 | ='SB-Sprints'!H49 | ='SB-Sprints'!I49 | ='SB-Sprints'!J52 | ='SB-Sprints'!L52 | ='SB-Sprints'!M52 | ='SB-Sprints'!N52 | ='SB-Sprints'!O52 | ='SB-Sprints'!P52 | ='SB-Sprints'!Q52 | ='SB-Sprints'!R52 | ='SB-Sprints'!S52 | ='SB-Sprints'!T52 | ='SB-Sprints'!U52 | ='SB-Sprints'!V52 | ='SB-Sprints'!T50
53 | ='SB-Sprints'!A53 | ='SB-Sprints'!B53 | ='SB-Sprints'!C53 | ='SB-Sprints'!D53 | ='SB-Sprints'!E53 | ='SB-Sprints'!F53 | ='SB-Sprints'!G53 | ='SB-Sprints'!H53 | ='SB-Sprints'!I53 | ='SB-Sprints'!J56 | ='SB-Sprints'!L56 | ='SB-Sprints'!M56 | ='SB-Sprints'!N56 | ='SB-Sprints'!O56 | ='SB-Sprints'!P56 | ='SB-Sprints'!Q56 | ='SB-Sprints'!R56 | ='SB-Sprints'!S56 | ='SB-Sprints'!T56 | ='SB-Sprints'!U56 | ='SB-Sprints'!V56 | ='SB-Sprints'!T54
57 | ='SB-Sprints'!A57 | ='SB-Sprints'!B57 | ='SB-Sprints'!C57 | ='SB-Sprints'!D57 | ='SB-Sprints'!E57 | ='SB-Sprints'!F57 | ='SB-Sprints'!G57 | ='SB-Sprints'!H57 | ='SB-Sprints'!I57 | ='SB-Sprints'!J60 | ='SB-Sprints'!L60 | ='SB-Sprints'!M60 | ='SB-Sprints'!N60 | ='SB-Sprints'!O60 | ='SB-Sprints'!P60 | ='SB-Sprints'!Q60 | ='SB-Sprints'!R60 | ='SB-Sprints'!S60 | ='SB-Sprints'!T60 | ='SB-Sprints'!U60 | ='SB-Sprints'!V60 | ='SB-Sprints'!T58
61 | ='SB-Sprints'!A61 | ='SB-Sprints'!B61 | ='SB-Sprints'!C61 | ='SB-Sprints'!D61 | ='SB-Sprints'!E61 | ='SB-Sprints'!F61 | ='SB-Sprints'!G61 | ='SB-Sprints'!H61 | ='SB-Sprints'!I61 | ='SB-Sprints'!J64 | ='SB-Sprints'!L64 | ='SB-Sprints'!M64 | ='SB-Sprints'!N64 | ='SB-Sprints'!O64 | ='SB-Sprints'!P64 | ='SB-Sprints'!Q64 | ='SB-Sprints'!R64 | ='SB-Sprints'!S64 | ='SB-Sprints'!T64 | ='SB-Sprints'!U64 | ='SB-Sprints'!V64 | ='SB-Sprints'!T62
65 | ='SB-Sprints'!A65 | ='SB-Sprints'!B65 | ='SB-Sprints'!C65 | ='SB-Sprints'!D65 | ='SB-Sprints'!E65 | ='SB-Sprints'!F65 | ='SB-Sprints'!G65 | ='SB-Sprints'!H65 | ='SB-Sprints'!I65 | ='SB-Sprints'!J68 | ='SB-Sprints'!L68 | ='SB-Sprints'!M68 | ='SB-Sprints'!N68 | ='SB-Sprints'!O68 | ='SB-Sprints'!P68 | ='SB-Sprints'!Q68 | ='SB-Sprints'!R68 | ='SB-Sprints'!S68 | ='SB-Sprints'!T68 | ='SB-Sprints'!U68 | ='SB-Sprints'!V68 | ='SB-Sprints'!T66
69 | ='SB-Sprints'!A69 | ='SB-Sprints'!B69 | ='SB-Sprints'!C69 | ='SB-Sprints'!D69 | ='SB-Sprints'!E69 | ='SB-Sprints'!F69 | ='SB-Sprints'!G69 | ='SB-Sprints'!H69 | ='SB-Sprints'!I69 | ='SB-Sprints'!J72 | ='SB-Sprints'!L72 | ='SB-Sprints'!M72 | ='SB-Sprints'!N72 | ='SB-Sprints'!O72 | ='SB-Sprints'!P72 | ='SB-Sprints'!Q72 | ='SB-Sprints'!R72 | ='SB-Sprints'!S72 | ='SB-Sprints'!T72 | ='SB-Sprints'!U72 | ='SB-Sprints'!V72 | ='SB-Sprints'!T70
73 | ='SB-Sprints'!A73 | ='SB-Sprints'!B73 | ='SB-Sprints'!C73 | ='SB-Sprints'!D73 | ='SB-Sprints'!E73 | ='SB-Sprints'!F73 | ='SB-Sprints'!G73 | ='SB-Sprints'!H73 | ='SB-Sprints'!I73 | ='SB-Sprints'!J76 | ='SB-Sprints'!L76 | ='SB-Sprints'!M76 | ='SB-Sprints'!N76 | ='SB-Sprints'!O76 | ='SB-Sprints'!P76 | ='SB-Sprints'!Q76 | ='SB-Sprints'!R76 | ='SB-Sprints'!S76 | ='SB-Sprints'!T76 | ='SB-Sprints'!U76 | ='SB-Sprints'!V76 | ='SB-Sprints'!T74
77 | ='SB-Sprints'!A77 | ='SB-Sprints'!B77 | ='SB-Sprints'!C77 | ='SB-Sprints'!D77 | ='SB-Sprints'!E77 | ='SB-Sprints'!F77 | ='SB-Sprints'!G77 | ='SB-Sprints'!H77 | ='SB-Sprints'!I77 | ='SB-Sprints'!J80 | ='SB-Sprints'!L80 | ='SB-Sprints'!M80 | ='SB-Sprints'!N80 | ='SB-Sprints'!O80 | ='SB-Sprints'!P80 | ='SB-Sprints'!Q80 | ='SB-Sprints'!R80 | ='SB-Sprints'!S80 | ='SB-Sprints'!T80 | ='SB-Sprints'!U80 | ='SB-Sprints'!V80 | ='SB-Sprints'!T78
81 | ='SB-Sprints'!A81 | ='SB-Sprints'!B81 | ='SB-Sprints'!C81 | ='SB-Sprints'!D81 | ='SB-Sprints'!E81 | ='SB-Sprints'!F81 | ='SB-Sprints'!G81 | ='SB-Sprints'!H81 | ='SB-Sprints'!I81 | ='SB-Sprints'!J84 | ='SB-Sprints'!L84 | ='SB-Sprints'!M84 | ='SB-Sprints'!N84 | ='SB-Sprints'!O84 | ='SB-Sprints'!P84 | ='SB-Sprints'!Q84 | ='SB-Sprints'!R84 | ='SB-Sprints'!S84 | ='SB-Sprints'!T84 | ='SB-Sprints'!U84 | ='SB-Sprints'!V84 | ='SB-Sprints'!T82
85 | ='SB-Sprints'!A85 | ='SB-Sprints'!B85 | ='SB-Sprints'!C85 | ='SB-Sprints'!D85 | ='SB-Sprints'!E85 | ='SB-Sprints'!F85 | ='SB-Sprints'!G85 | ='SB-Sprints'!H85 | ='SB-Sprints'!I85 | ='SB-Sprints'!J88 | ='SB-Sprints'!L88 | ='SB-Sprints'!M88 | ='SB-Sprints'!N88 | ='SB-Sprints'!O88 | ='SB-Sprints'!P88 | ='SB-Sprints'!Q88 | ='SB-Sprints'!R88 | ='SB-Sprints'!S88 | ='SB-Sprints'!T88 | ='SB-Sprints'!U88 | ='SB-Sprints'!V88 | ='SB-Sprints'!T86
89 | ='SB-Sprints'!A89 | ='SB-Sprints'!B89 | ='SB-Sprints'!C89 | ='SB-Sprints'!D89 | ='SB-Sprints'!E89 | ='SB-Sprints'!F89 | ='SB-Sprints'!G89 | ='SB-Sprints'!H89 | ='SB-Sprints'!I89 | ='SB-Sprints'!J92 | ='SB-Sprints'!L92 | ='SB-Sprints'!M92 | ='SB-Sprints'!N92 | ='SB-Sprints'!O92 | ='SB-Sprints'!P92 | ='SB-Sprints'!Q92 | ='SB-Sprints'!R92 | ='SB-Sprints'!S92 | ='SB-Sprints'!T92 | ='SB-Sprints'!U92 | ='SB-Sprints'!V92 | ='SB-Sprints'!T90

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes