## Sprint-Master
Sprint# | Scrum Board | Start Date | End Date | Resources | Duration | Available Hours | Actual Hours | Remarks | Goal
Sprint1 | SB-Sprint1 | 2015-11-16 | 2015-11-20 | 2 | 5 | 200 |  | 16-Nov Heavy Rain | HCR Calculator Should be delivered
Sprint2 |  | 2015-11-23 | 2015-11-27 |  | 5
Sprint3 |  | 2015-11-30 | 2015-12-04 |  | 5
Sprint4 |  | 2015-12-07 | 2015-12-11 |  | 5
Sprint5 |  | 2015-12-14 | 2015-12-18 |  | 5
Sprint6 |  | 2015-12-21 | 2015-12-25 |  | 5
Sprint7 |  | 2015-12-28 | 2016-01-01 |  | 5
Sprint8 |  | 2016-01-04 | 2016-01-08 |  | 5
Formulas:
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+3

## Resources
EmpId | Name | Intial | Typer
F16039 | Karthikeyan V | KV | Dev
F16305 | Dilip Prasad J | DP | Dev
F16453 | Ashok S | AS | Dev
F15435 | Sathish V | SV | QA
F15856 | Deepika Ranganathan | DR | QA
FT12358 | Shreya Gupta | SG
Vendor | Eshwar | ES | UI

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Karthikeyan | Sathish | Shreya | Status
PE.BM.CAD.01 | Get client name, plan type and premium tire details | 20 |  |  | Benefit Manager | I want to get the details of my organization for the determining cadillac tax due to my ogranzation. So that I could estimate cadillac tax of my organization. | When I log in the system, calculator can pull the details like client name, plans , premium types into the calculator | Correct information being pulled | As per Bharat, all this information comes from a webservice and will provide the sql query for pulling this information. |  | 20 | 20 | 13 | 13 | Discussed
PE.BM.CAD.02 | Threshold Reference table | 13 |  |  | Benefit Manager | I want to see thresholds for various cover types | When I open calc, I see ref table | Constants. | Static Page | Whether data will come from Webservice or table? | 13 | 13 | 8 | 13 | Discussed
PE.BM.CAD.03 | ??? | 20 |  |  | Benefit Manager | I should be able to create/modify the threshold values of Cadillac Tax |  |  | Added by Estimation Team |  | 13 | 20 | 13 | 13 | Discussed
PE.BM.CAD.04 | Default rates | 20 |  |  | Benefit Manager | I should be able to see the default values of various rates (i.e. HCAP, COLA etc) and overide if required. | When I see this section, default rate is already present but I should be able to edit it, if I wish too. | Default should be one that is stored in the system.It should be only in percentage. Values should be editable. |  |  | 20 | 20 | 20 | 20 | Discussed
PE.BM.CAD.05 | User inputs -Rate | 20 |  |  | Benefit Manager | I should be able to create/modify default rate of Trend, Medical account contribution growth, Health Cost Adjustment Percentage Factor (HCAP), Age and Gender Adjustment Factor ,Cost of Living Adjustment Factor (COLA). So that values can be populated in the calculator at the time of Cadillac Tax Calcuation. These values becomes default system values for calculation purpose. | System should store the rates for Cadillac Tax calculation | Should only be numeric and in percent format |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.06 | Tooltips | 13 |  |  | Benefit Manager | I want to get more information about the terms used in the calculator as a tooltip message. So that I know what is the meaning of a particular term. | When I hover over the label and its textbox, corresponding tooltip should pop. | Tool tips should only be for the term on which mouse is hovered. It should be as per the approved wireframe |  |  | 13 | 13 | 8 | 8 | Discussed
PE.BM.CAD.07 | User input- Coverage type | 13 |  |  | Benefit Manager | I want select the coverage type from the drop down menu. There are 3 coverage types | The cadillac tax will be calculated based on the selected coverage | Coverage type should be the ones from the threshold reference table |  |  | 13 | 13 | 8 | 8 | Discussed
PE.BM.CAD.08 | Display HCAP,Age and Gender Adjustment Factor and COLA rate | 5 |  |  | Benefit Manager | I want see what are the rate I have entered in input data for HCAP,Age and Gender Adjustment Factor and COLA so that I know correct rates are being used for calculation. | Display | System should show these value which I have entered using userstory PE.BM.CAD.05 |  |  | 5 | 5 | 5 | 2 | Discussed
PE.BM.CAD.09 | Calculate Annual Dollar Limit (ADL) with Adjustments | 8 |  |  | Benefit Manager | I want that system should calculate ADL 2018 with adjustments using the formula for calculation | It should be calculated using the formula: ADL * (1+HCAP) * (1+Age and gender adjustment factor) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. |  |  | 8 | 8 | 8 | 8 | Discussed
PE.BM.CAD.10 | Load appropriate user input sections for different Premium tire |  |  |  | Benefit Manager | I want the all the premium tire's to be fetched | When I load this page, by then the calculator should already know my premium tires and load appropriate input sections | Premium tire should display and textbox should be loaded with calculated vlaues of premium, FSA, HRA, HAS and MSA. This should allow me to change the values. | this needs to be analysed for estimation |  | 40 | 100 | 100 | 40 | Discussed
PE.BM.CAD.11 | Default Values for Total Premium, FSA, HRA, HSA and MSA | 20 |  |  | Benefit Manager | I want to get default values of FSA, HRA etc along with premium from the system, so that this can be used for calculation. | When I see this section, default value is already present but I should be able to edit it, if I wish too. | Default should be one that is present in the template. For the one I enter, it should be amount in dollar rounded to two decimal. |  |  | 20 | 20 | 20 | 20 | Discussed
PE.BM.CAD.12 | Edit User inputs -Premium, FSA, HRA, HSA and MSA amounts | 3 |  |  | Benefit Manager | So that I can enter Premium, FSA, HRA, HSA and MSA amounts in the calculator. | System should store the amounts for Cadillac Tax calculation | It should be amount in dollar rounded to two decimal |  | Need to know if the modified entered value needs to be saved only for session or future? | 3 | 3 | 3 | 3 | Discussed
PE.BM.CAD.13 | User input - Number of Employees | 13 |  |  | Benefit Manager | So that I can enter the number of employees | System should store the count for Cadillac Tax calculation | Should only be an integer |  | Need to know if the modified entered value needs to be saved only for session or future? | 13 | 13 | 5 | 13 | Discussed
PE.BM.CAD.14 | Load appropriate sections to show premium tire wise break down in cadiallc tax | 13 |  |  | Benefit Managar | I can see for next 5 years from 2018 the premium tire wise, break down of entire calculation | Once Calculate Cadillac Tax button is clicked the Calculator should show below breakdown of calculation for next 5 years from 2018 the CAC, Threshold Limit Applicable Dollar Limit,Amount Over Threshold,Excise Tax (40%),Number of Employees,Total Projected Tax | For all the Premium tire, all the values (CAC, Threshold Limit Applicable Dollar Limit,Amount Over Threshold,Excise Tax (40%),Number of Employees,Total Projected Tax) should get calculated and I should be able to see the breakdown for next 5 years from 2018 |  |  | 13 | 8 | 13 | 13 | Discussed
PE.BM.CAD.15 | Formula for Projected Premium (CAC) for self | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | (CAC of Self)*(1+Trend) ^(Year-Current Year)+(FSA of Self + HRA of Self + HAS of Self + MSA of Self)*(1+ Medical account contribution growth)^ )^(Year-Current Year) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals | In formulas below, to explain calculation for multiple premium tires I have taken example of 2 premium types: 1) Self and 2) Other than self only. (It could by more than this. The calculation remains similar to the ones given in next few user stories) |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.16 | Formula for Projected Premium (CAC) for ‘Other than Self Only’ | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | (CAC of Self)*(1+Trend) ^(Year-Current Year)+(FSA of Self + HRA of Self + HAS of Self + MSA of Self)*(1+ Medical account contribution growth)^ )^(Year-Current Year) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.17 | Formula for Threshold Limit Applicable Dollar Limit (2018, Self) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | It should come equal to Annual Dollar Limit (ADL) of self. | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.18 | Formula for Threshold Limit Applicable Dollar Limit (2018, Other than self only) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | It should come equal to Annual Dollar Limit (ADL) of other that self only. | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.19 | Formula for Threshold Limit Applicable Dollar Limit (2019, self) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of self*(1+ Cost of Living Adjustment Factor+1%) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.20 | Formula for Threshold Limit Applicable Dollar Limit (2019, Other than self only) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of other than self only *(1+ Cost of Living Adjustment Factor+1%) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.21 | Formula for Threshold Limit Applicable Dollar Limit (2020-2022,Self) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of self *(1+ Cost of Living Adjustment Factor+1%) ^(Year for which this is being calculated – 2019) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.22 | Formula for Threshold Limit Applicable Dollar Limit (2020-2022, Other than self only) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Threshold Limit Applicable Dollar Limit of other than self only*(1+ Cost of Living Adjustment Factor+1%) ^(Year for which this is being calculated – 2019) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.23 | Formula for Amount Over Threshold (2018 -2022) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | It should statisfy the logic: If (Projected Premium - Threshold Limit Applicable Dollar Limit > 0) then: Amount Over Threshold = Projected Premium - Threshold Limit Applicable Dollar Limit Else: Amount Over Threshold =0 | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.24 | Formula for Excise Tax (40%) | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Amount Over Threshold* 40% | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.25 | Formula for Number of Employees | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Number of Employees (FN1)*(1+Employee Growth) ^(Year for which this is being calculated – 2019) | The result should only be an integer value. |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.26 | Formula for Total Projected Tax | 13 |  |  | Benefit Manager | I can see the calculated value using the appropriate formula | Excise Tax* Number of Employees | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.27 | Formula for Total of Total Projected Tax | 13 |  |  | Benefit Manager | This should give me total of all the projected tax, for all the premium tier) | Sum( Total Projected Tax of Self+Total Projected Tax of other than self) | 1. It should properly pick the values required for the calculation. 2. Formula calculation should be correct. 3. The amount should be in dollar. Rounded to two decimals |  |  | 13 | 20 | 20 | 13 | Discussed
PE.BM.CAD.28 | Help | 8 |  |  | Benefit Manager | I can get explanation about the technical terms used in the calculator. | When I click on help, this definations and footnates should pop up. | It should given information only about the terms used in this calculator. |  |  | 8 | 8 | 8 | 2 | Discussed
PE.BM.HCR.01 | Both-Pull Essential data from the service | 40 | Sprint1 |  | Benefit Manager | I should fetch the information from the service | It should pull the client name, Total Plan Participants, Estimated 2016 Annual Premium, type of insured(self funded, fully or both) from the database. | Correct information should be pulled |  |  | 40 | 40 | 40 | 40 | Discussed
PE.BM.HCR.02 | Both-Display client name, Total Plan Participants, Estimated 2016 Annual Premium on calculator | 8 | Sprint1 |  | Benefit Manager | I should see the details fetched from the service and it should be read-only. | Data showing this information should be pulled from the database and should be displayed on the webpage | Correct information should be displayed on the calculator |  | Need to know if the calulcation needs to be done Total Plan Particupants * 5000? What is the 5000? | 8 | 5 | 8 | 8 | Discussed
PE.BM.HCR.03 | Fully-insured-Display Estimated 2016 Annual Premium on calculator | 8 | Sprint1 |  | Benefit Manager | I should see the details calculated based on the 3.5 % of "Estimated 2016 annual premium" | Data should be calculated based on the data available for estimated 2016 annual premium | Correct information should be pulled |  |  | 8 | 5 | 8 | 8 | Discussed
PE.BM.HCR.04 | Self-funded-Display Fully Insured Equivalent Rate | 20 | Sprint1 |  | Benefit Manager | I should fetch the information from the service and display the information | Data showing this information should be pulled from the database and should be displayed on the webpage | Correct information should be pulled |  |  | 20 | 20 | 13 | 13 | Discussed
PE.BM.HCR.05 | Both-Identify and Run the model that needs to be run | 13 | Sprint1 |  | Benefit Manager | I should choose the right calculator based on theinsured type to perform the calculations amongst the two. | Webpage should pull the insured type from the service and depending on the type selected and run the model | If the employee is fully insured, fully insured model should run. If the employee is self-funded, self-funded model should run. If there partially fully insured and partially self-funded each part is run separately |  | Is there possiblity for both options to be displayed in screen or will it be one at a time? | 8 | 8 | 13 | 20 | Discussed
PE.BM.HCR.06 | Formula for fully-insured-Health Insurer Assessment | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate using the appropriate formula and should show me the result | Calculator should calculate this using the formula: Estimated 2016 Annual Premium * % of annual premium | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 | Discussed
PE.BM.HCR.07 | Formula for Both-Comparative Effectiveness Research (PCORI) Fee | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: Total Plan Participants * amount of per plan participant per year | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 | Discussed
PE.BM.HCR.08 | Formula for Both-Transitional Reinsurance Program | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: Total Plan Participants* amount of per plan participant in 2016. | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 | Discussed
PE.BM.HCR.09 | Formula for Both-Total Estimated HCR Fees ($): | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | This will be sum of Health Insurer Assessment, Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | The amount should be in dollars. |  |  | 8 | 8 | 8 | 5 | Discussed
PE.BM.HCR.10 | Formula for Both-HCR Fees as a % of Annual Premium: | 8 | Sprint1 |  | Benefit Manager | Calculator should calculate usig the appropriate formula and should show me the result | Calculator should calculate this using the formula: (Total Estimated HCR Fees/ Estimated 2016 Annual Premium)*100 | Should be a percent value. |  |  | 8 | 8 | 8 | 5 | Discussed
PE.BM.HCR.11 | Both-Pie Chart |  | Sprint1 |  | Benefit Manager | To display the graphical representation in pie-chart by using the data provided for Total Estimated HCR Fees ($) of Total Plan Cost without HCR | Pie chart should calculate using the below logic and show pie representation of the data. Total Estimated HCR Fees ($) +Total Plan Cost without HCR = Estimated 2016 Annual Premium | Pie chart should display both the value in the pie, label showing distribution of pie both inn terms of amount as well as percent | This needs to be analysed for estimation |  | 100 | 100 | 100 | 20 | Discussed
PE.BM.HCR.12 | Fully-insured-Bar Chart |  | Sprint1 |  | Benefit Manager | To Display the Bar-Chart with the values provided. So that I can visualise and compare the values | Bar Chart should show bars for Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | X axis - labels; y axis - Amount($) scale; and bars. Label to show each bar value should alse be available. | This needs to be analysed for estimation |  | 100 | 100 | 100 | 40 | Discussed
PE.BM.HCR.13 | Self-funded-Bar Chart |  | Sprint1 |  | Benefit Manager | To Display the Bar-Chart with the values provided. So that I can visualise and compare the values | Bar Chart should show bars for Health Insurer Assessment, Comparative Effectiveness Research (PCORI) Fee and Transitional Reinsurance Program amounts. | X axis - labels; y axis - Amount($) scale; and bars. Label to show each bar value should alse be available. | This needs to be analysed for estimation |  | 20 | 40 | 20 | 40 | Discussed
Note on H2: Author: The primary user or stakeholder for the story
Note on I2: Author: The goal that the actor is trying to achieve in the story
Note on J2: Author: The actions performed by the actor.
Note on K2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprint1
Scrum Board
| Auto Calculation |  |  | Efforts |  |  | Development | [6 empty] | QA |  |  | Acceptance Testing
| No Entry | WIP Status ==>> |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# | User Story-ID | User Stories Description | Complexity | Planned | Acutal | Type | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO | US Status
1 | PE.BM.HCR.01 | Both-Pull Essential data from the service | 40 | 0 | 0 | Name
Status
Planned
Actual
Note on G6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## Master
Col # in Scrum Board |  | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
5 | 'SB-Sprint1' | ='SB-Sprint1'!$B$5 | ='SB-Sprint1'!$D$5 | ='SB-Sprint1'!$E$5 | ='SB-Sprint1'!$F$5 | ='SB-Sprint1'!$G$5 | ='SB-Sprint1'!$H$5 | ='SB-Sprint1'!$I$5 | ='SB-Sprint1'!$J$5 | ='SB-Sprint1'!$K$5 | ='SB-Sprint1'!$L$5 | ='SB-Sprint1'!$M$5 | ='SB-Sprint1'!$N$5 | ='SB-Sprint1'!$O$5 | ='SB-Sprint1'!$P$5 | ='SB-Sprint1'!$Q$5 | ='SB-Sprint1'!$R$5 | ='SB-Sprint1'!$S$5 | ='SB-Sprint1'!$T$5
# | Scrum Board | User Story-ID | Complexity | Planned | Acutal | Type | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO | US Status
1 | SB-Sprint1 | PE.BM.HCR.01 | 40 | 0 | 0 | Name | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0