## Sprint-Master
Sprint# | Week of Year | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
Sprint01 | 2015-45 | 2015-11-03 | 2015-11-09 | 8 | 7
Sprint02 | 2015-46 | 2015-11-10 | 2015-11-16 | 8 | 7
Sprint03 | 2015-47 | 2015-11-17 | 2015-11-23 | 9 | 7 | 320 | 293 | 180 | 0
Sprint03 | 2015-48 | 2015-11-24 | 2015-11-30 | 9 | 7
Sprint03 | 2015-49 | 2015-12-01 | 2015-12-07 | 9 | 7
Sprint03 | 2015-50 | 2015-12-08 | 2015-12-14 | 9 | 7
Sprint04 | 2015-51 | 2015-12-15 | 2015-12-21 |  | 7
Sprint04 | 2015-52 | 2015-12-22 | 2015-12-28 |  | 7
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+1

## Resources
Week of Year | 2015-51
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
F16839 | Nadem Manohar | Dev | NM | 1
F14580 | Braj Mohan Goud | Dev | BM | 1
F16520 | Pramod Kumar Matam | Dev | PKM | 1
F12175 | Thirupathi Kusa | Dev | TK | 1
FT14752 | Ramakrishnan | QA | RKN | 1
F8614 | Suresh V | Dev | SUV | 1
F17107 | Sampath Rao Tirumala Ratnagiri Raju | SM | SR | 1
F17018 | Murali Krishna J | Dev | KJ | 1
F15463 | Sai Prasanth | Dev | SP | 1
Client03 | Tanbeer Ahmed | PO | TA | 1
Grand Total |  |  |  | 10

## PRA
Update this Every Weekend
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role
KE.DWBI.1 | 2015-45 | Sprint01 |  | F16839 | 1 | Nadem Manohar | NM | Dev
KE.DWBI.1 | 2015-45 | Sprint01 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev
KE.DWBI.1 | 2015-45 | Sprint01 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM
KE.DWBI.1 | 2015-45 | Sprint01 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev
KE.DWBI.1 | 2015-45 | Sprint01 |  | F17018 | 1 | Murali Krishna J | KJ | Dev
KE.DWBI.1 | 2015-45 | Sprint01 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev
KE.DWBI.1 | 2015-45 | Sprint01 |  | FT14752 | 1 | Ramakrishnan | RKN | QA
KE.DWBI.1 | 2015-45 | Sprint01 |  | F15463 | 1 | Sai Prasanth | SP | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | F16839 | 1 | Nadem Manohar | NM | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM
KE.DWBI.1 | 2015-46 | Sprint02 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | F17018 | 1 | Murali Krishna J | KJ | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | FT14752 | 1 | Ramakrishnan | RKN | QA
KE.DWBI.1 | 2015-46 | Sprint02 |  | F15463 | 1 | Sai Prasanth | SP | Dev
KE.DWBI.1 | 2015-46 | Sprint02 |  | F8614 | 1 | Suresh V | SUV | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM
KE.DWBI.1 | 2015-48 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA
KE.DWBI.1 | 2015-48 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev
KE.DWBI.1 | 2015-48 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM
KE.DWBI.1 | 2015-49 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA
KE.DWBI.1 | 2015-49 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev
KE.DWBI.1 | 2015-49 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM
KE.DWBI.1 | 2015-50 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA
KE.DWBI.1 | 2015-50 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev
KE.DWBI.1 | 2015-50 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | F17107 | 1 | Sampath Rao Tirumala Ratnagiri Raju | SR | SM
KE.DWBI.1 | 2015-51 | Sprint03 |  | F16839 | 1 | Nadem Manohar | NM | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | F14580 | 1 | Braj Mohan Goud | BM | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | F16520 | 1 | Pramod Kumar Matam | PKM | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | F17018 | 1 | Murali Krishna J | KJ | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | F12175 | 1 | Thirupathi Kusa | TK | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | FT14752 | 1 | Ramakrishnan | RKN | QA
KE.DWBI.1 | 2015-51 | Sprint03 |  | F15463 | 1 | Sai Prasanth | SP | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | F8614 | 1 | Suresh V | SUV | Dev
KE.DWBI.1 | 2015-51 | Sprint03 |  | Client03 | 1 | Tanbeer Ahmed | TA | PO
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Category | Frequency | Story Name | Resource | Effort (Planned) | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Estimator1 | Estimator2 | Estimator3 | Estimator4 | Status
US.DWBI.SUP.001 | Support | Daily | ODS3 Job data loading and verifying BR | TK | 6 |  | NA
US.DWBI.SUP.002 | Support | Daily | Download the data from agency blocks and loading into QA & Prod env | TK | 1 |  | NA
US.DWBI.SUP.003 | Support | Daily | Monitoirng EBS jobs and verify BP files & monitor jobs | SV | 1 |  | NA
US.DWBI.SUP.004 | Support | One Time | Test all ETL jobs in linux QA env. | SV, TK | 48 |  | NA
US.DWBI.SUP.005 | Support | Friday | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | BM | ?? |  | NA
US.DWBI.SUP.006 | Support | Daily | Status monitoring of all the server- Daily | BM | ?? |  | NA
US.DWBI.SUP.007 | Support | Daily | Explorer reports and other BI reports refresh & verfication - Daily. | BM | ?? |  | NA
US.DWBI.SUP.008 | Support | Monthly | BI & BW production server backup- Monthly | BM | ?? |  | NA
US.DWBI.SUP.009 | Support | Daily | Ivos to prudential job monitoring | BM | 0.5 |  | NA
US.DWBI.SUP.010 | Support | One Time | Update visual cut application on QA server for Monthly report busting process | BM | ?? |  | NA
US.DWBI.SUP.011 | Support | Demand Basis | Migration of dashboard as per the request | BM | ?? |  | NA
US.DWBI.SUP.012 | Support | Monthly | WCIR Monthend process | TK | 8 |  | NA
US.DWBI.SUP.013 | Support | Monthly | ODS2 Monthend process & Report Bursting Process | BM | 8 |  | NA
US.DWBI.QLT.001 | Support | Tuesday | Data quality testing - Tuesday | SP, RKN |  |  | NA
US.DWBI.QLT.002 | Support |  | Verifying lacers FM dashboard | SP, RKN |  |  | NA
US.DWBI.LDB.001 | User Story |  | Laser dashboard for health management desktop version | PM |  | 40 | Sprint03 | [7 empty] | 40 | 40 | 40
US.DWBI.LDB.002 | User Story |  | Laser dashboard for health management mobile version | PM |  | 40 | Sprint03 | [7 empty] | 40
US.DWBI.LDB.001.D01 | Defect Fix |  | Laser financial dashboard fix | KM |  | 20 | Sprint03
US.DWBI.RPT.001 | User Story |  | Agency Report
US.DWBI.DEV.001 | User Story |  | Job_Load_WC_AGG1 Improvement
Note on L2: Author: The primary user or stakeholder for the story
Note on M2: Author: The goal that the actor is trying to achieve in the story
Note on N2: Author: The actions performed by the actor.
Note on O2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.
Note on F13: Depends on Volume
Note on F14: Depends on Volume
Note on F15: Depends on Volume

## DWSB-Support
Auto Calculation |  |  | Current Wk# | Sprint04 |  | Efforts |  |  | Support
No Entry | [5 empty] | 0 | 0 | Actual Work | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | User Story-ID | User Stories Description | Frequency | Planned | Acutal | Type | Mon | Tue | Wed | Thu | Fri | Sat | Sun
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | 14 | 14 | Name | TK | TK | TK | TK | TK
| 2015-48 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 2 | 3 | 3 | 3 | 3
| 2015-48 | Sprint03 | [5 empty] | Actual | 2 | 3 | 3 | 3 | 3
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | 5 | 5 | Name | TK | TK | TK | TK | TK
| 2015-48 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-48 | Sprint03 | [5 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | 5 | 5 | Name | SUV | SUV | SUV | SUV | SUV
| 2015-48 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-48 | Sprint03 | [5 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | 57 | 57 | Name | SUV, TK | SUV, TK | SUV, TK | SUV, TK | SUV, TK
| 2015-48 | Sprint03 | [5 empty] | Status | WIP | WIP | WIP | WIP | WIP
| 2015-48 | Sprint03 | [5 empty] | Planned | 12 | 12 | 11 | 11 | 11
| 2015-48 | Sprint03 | [5 empty] | Actual | 12 | 12 | 11 | 11 | 11
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | 5 | 3 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | Done | NR | NR | NR | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 2 |  |  |  | 3
| 2015-48 | Sprint03 | [5 empty] | Actual |  |  |  |  | 3
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | 10 | 0 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-48 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | 11 | 0 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 2 | 2 | 2 | 3 | 2
| 2015-48 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | 6 | 0 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | NS | WIP | WIP | WIP | NS
| 2015-48 | Sprint03 | [5 empty] | Planned |  | 2 | 2 | 2
| 2015-48 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | 5 | 0 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-48 | Sprint03 | [5 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-48 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | 3 | 0 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | WIP | WIP | WIP | NS | NS
| 2015-48 | Sprint03 | [5 empty] | Planned | 1 | 1 | 1
| 2015-48 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | 0 | 0 | Name | BM | BM | BM | BM | BM
| 2015-48 | Sprint03 | [5 empty] | Status | NS | NS | NS | NS | NS
| 2015-48 | Sprint03 | [5 empty] | Planned
| 2015-48 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | 12 | 12 | Name | TK | TK | TK | TK | TK
| 2015-49 | Sprint03 | [5 empty] | Status | Done |  | Done | Done | Done
| 2015-49 | Sprint03 | [5 empty] | Planned | 2 |  | 3 | 4 | 3
| 2015-49 | Sprint03 | [5 empty] | Actual | 2 |  | 3 | 4 | 3
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.012 | WCIR Monthend process | Monthly | 8 | 8 | Name |  | TK
| 2015-49 | Sprint03 | [5 empty] | Status |  | Done
| 2015-49 | Sprint03 |  |  |  |  | 66 | Planned |  | 8
| 2015-49 | Sprint03 | [5 empty] | Actual |  | 8
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | 0 | 0 | Name
| 2015-49 | Sprint03 | [5 empty] | Status
| 2015-49 | Sprint03 | [5 empty] | Planned
| 2015-49 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | 16 | 16 | Name | SUV, TK | SUV, TK | SUV, TK | SUV, TK | SUV, TK
| 2015-49 | Sprint03 | [5 empty] | Status | WIP |  | WIP | WIP | WIP
| 2015-49 | Sprint03 | [5 empty] | Planned | 4 |  | 4 | 4 | 4
| 2015-49 | Sprint03 | [5 empty] | Actual | 4 |  | 4 | 4 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | 0 | 0 | Name
| 2015-49 | Sprint03 | [5 empty] | Status
| 2015-49 | Sprint03 | [5 empty] | Planned
| 2015-49 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | 10 | 10 | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-49 | Sprint03 | [5 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-49 | Sprint03 | [5 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | 10 | 10 | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-49 | Sprint03 | [5 empty] | Planned | 2 | 2 | 2 | 2 | 2
| 2015-49 | Sprint03 | [5 empty] | Actual | 2 | 2 | 2 | 2 | 2
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | 0 | 0 | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [5 empty] | Status | NS | NS | NS | NS | NS
| 2015-49 | Sprint03 | [5 empty] | Planned
| 2015-49 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | 2.5 | 2.5 | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-49 | Sprint03 | [5 empty] | Planned | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 2015-49 | Sprint03 | [5 empty] | Actual | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | 0 | 0 | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [5 empty] | Status | WIP | WIP | WIP | WIP | WIP
| 2015-49 | Sprint03 | [5 empty] | Planned
| 2015-49 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.013 | ODS2 Monthend process & Report Bursting Process | Monthly | 8 | 8 | Name | BM | BM | BM | BM | BM
| 2015-49 | Sprint03 | [5 empty] | Status |  | Done | Done
| 2015-49 | Sprint03 | [5 empty] | Planned |  | 4 | 4
| 2015-49 | Sprint03 | [5 empty] | Actual |  | 4 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | 0 | 0 | Name
| 2015-49 | Sprint03 | [5 empty] | Status
| 2015-49 | Sprint03 | [5 empty] | Planned
| 2015-49 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | 15 | 15 | Name | TK | TK | TK | TK | TK
| 2015-50 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [5 empty] | Planned | 2 | 3 | 3 | 4 | 3
| 2015-50 | Sprint03 | [5 empty] | Actual | 2 | 3 | 3 | 4 | 3
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | 5 | 5 | Name | TK | TK | TK | TK | TK
| 2015-50 | Sprint03 | [5 empty] | Status | Done | Done | Done | Done | Done
| 2015-50 | Sprint03 | [5 empty] | Planned | 1 | 1 | 1 | 1 | 1
| 2015-50 | Sprint03 | [5 empty] | Actual | 1 | 1 | 1 | 1 | 1
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-50 | Sprint03 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | 0 | 0 | Name
| 2015-50 | Sprint03 | [5 empty] | Status
| 2015-50 | Sprint03 | [5 empty] | Planned
| 2015-50 | Sprint03 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | 0 | 0 | Name
| 2015-51 | Sprint04 | [5 empty] | Status
| 2015-51 | Sprint04 | [5 empty] | Planned
| 2015-51 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.001 | ODS3 Job data loading and verifying BR | Daily | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.002 | Download the data from agency blocks and loading into QA & Prod env | Daily | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.003 | Monitoirng EBS jobs and verify BP files & monitor jobs | Daily | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.004 | Test all ETL jobs in linux QA env. | One Time | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.005 | Weekly maintenance activity - Monitoring all BI/BW server disk space (On Monday) and Clearing caches on Prod on Friday | Friday | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.006 | Status monitoring of all the server- Daily | Daily | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.007 | Explorer reports and other BI reports refresh & verfication - Daily. | Daily | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.008 | BI & BW production server backup- Monthly | Monthly | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.009 | Ivos to prudential job monitoring | Daily | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.010 | Update visual cut application on QA server for Monthly report busting process | One Time | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
KE.DWBI.1 | 2015-52 | Sprint04 | US.DWBI.SUP.011 | Migration of dashboard as per the request | Demand Basis | 0 | 0 | Name
| 2015-52 | Sprint04 | [5 empty] | Status
| 2015-52 | Sprint04 | [5 empty] | Planned
| 2015-52 | Sprint04 | [5 empty] | Actual
Note on I6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I58: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I62: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I66: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I70: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I74: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I78: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I82: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I86: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I90: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I94: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I98: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I102: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I106: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I110: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I114: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I118: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I122: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I126: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I130: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I134: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I138: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I142: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I146: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I150: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I154: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I158: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I162: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I166: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I170: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I174: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I178: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I182: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I186: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I190: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I194: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I198: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I202: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I206: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I210: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I214: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I218: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I222: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on I226: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## SB-Sprints
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | T | U | V | W | X | Y | Z
Auto Calculation |  |  |  |  | Current Wk# | Sprint04 | [5 empty] | Development | [7 empty] | QA |  |  | Acceptance Testing
No Entry | [5 empty] | 100 |  | 36 | 0 | 36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Remaining Work | Type | Analyse Existing Work | Analyse Requirement | Update Spread Sheet | Change Components | Visualize Change | Implement Change | Test Data Prep | Unit Testing | Prepare QA Test Case | Compare UI with Prev | Compare DB data with Output | UA Test Cases | Demo to PO
KE.DWBI.1 | 2015-48 | Sprint03 | 1 | US.DWBI.LDB.001 | Laser dashboard for health management desktop version | 40 | Moved | 73 | 49 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM |  | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | WIP | WIP | Done | WIP | NA | WIP | NS | NS | NS
| 2015-48 | Sprint03 | [8 empty] | Planned | 3 | 2 | 24 | 24 | 4 | 4 |  | 8 | 4 | ?? | ??
| 2015-48 | Sprint03 | [8 empty] | Actual | 3 | 2 | 16 | 16 | 4 | 2 |  | 6
KE.DWBI.1 | 2015-48 | Sprint03 | 2 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | Moved | 53 | 0 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-48 | Sprint03 | [8 empty] | Status | NS | NS | NS | NS | NS | NS | NS | NS | NA | NA | NA
| 2015-48 | Sprint03 | [8 empty] | Planned | 3 | 2 | 16 | 16 | 4 | 4 |  | 8
| 2015-48 | Sprint03 | [8 empty] | Actual
KE.DWBI.1 | 2015-48 | Sprint03 | 3 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | Moved | 47 | 47 | 0 | Name | KJ | KJ | KJ | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-48 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-48 | Sprint03 | [8 empty] | Planned | 3 | 2 | 0 | 16 | 4 | 16 | 2 | 4
| 2015-48 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | 1 | US.DWBI.LDB.001 | Laser dashboard for health management desktop version | 40 | Moved | 73 | 49 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM |  | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | WIP | WIP | Done | WIP | NA | WIP | NS | NS | NS
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 2 | 24 | 24 | 4 | 4 |  | 8 | 4 | ?? | ??
| 2015-49 | Sprint03 | [8 empty] | Actual | 3 | 2 | 16 | 16 | 4 | 2 |  | 6
KE.DWBI.1 | 2015-49 | Sprint03 | 2 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | Moved | 53 | 0 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-49 | Sprint03 | [8 empty] | Status | NS | NS | NS | NS | NS | NS | NS | NS | NA | NA | NA
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 2 | 16 | 16 | 4 | 4 |  | 8
| 2015-49 | Sprint03 | [8 empty] | Actual
KE.DWBI.1 | 2015-49 | Sprint03 | 3 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | Moved | 47 | 47 | 0 | Name | KJ | KJ | KJ | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 2 | 0 | 16 | 4 | 16 | 2 | 4
| 2015-49 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-49 | Sprint03 | 4 | US.DWBI.RPT.001 | Agency Report | 0 | Accepted | 34 | 34 | 0 | Name | NM | NM | NM | NM | NM | NM | NM | NM | SP |  | SP | SR | SR
| 2015-49 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done | Done | Done | Done | Done | NR | Done | Done
| 2015-49 | Sprint03 | [8 empty] | Planned | 3 | 3 |  | 12 | 4 | 12
| 2015-49 | Sprint03 | [8 empty] | Actual | 3 | 3 |  | 12 | 4 | 12
KE.DWBI.1 | 2015-49 | Sprint03 | 5 | US.DWBI.DEV.001 | Job_Load_WC_AGG1 Improvement | 0 | Moved | 7 | 7 | 0 | Name | NM | NM | NM | NM | NM | NM | NM | NM
| 2015-49 | Sprint03 | [8 empty] | Status | WIP | Done | WIP | Done | NS | NS | NS | NS | NR | NR | NR | NR
| 2015-49 | Sprint03 | [8 empty] | Planned | 4 | 3
| 2015-49 | Sprint03 | [8 empty] | Actual | 4 | 3
KE.DWBI.1 | 2015-50 | Sprint03 | 6 | US.DWBI.LDB.001 | Laser dashboard for health management desktop version | 40 | Moved | 73 | 49 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM |  | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | WIP | WIP | Done | WIP | NA | WIP | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 | 24 | 24 | 4 | 4 |  | 8 | 4 | ?? | ??
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 | 16 | 16 | 4 | 2 |  | 6
KE.DWBI.1 | 2015-50 | Sprint03 | 7 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | Moved | 45 | 45 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | Done | Done | Done | Done | NS | Done | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 | 12 | 12 | 4 | 4 |  | 8
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 | 12 | 12 | 4 | 4 |  | 8
KE.DWBI.1 | 2015-50 | Sprint03 | 8 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | Moved | 47 | 47 | 0 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-50 | Sprint03 | 8 | US.DWBI.LDB.003 | HM Dashboard | 40 | Moved | 47 | 47 | 0 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP
| 2015-50 | Sprint03 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-50 | Sprint03 | [8 empty] | Planned | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
| 2015-50 | Sprint03 | [8 empty] | Actual | 3 | 2 |  | 16 | 4 | 16 | 2 | 4
KE.DWBI.1 | 2015-51 | Sprint04 | 7 | US.DWBI.LDB.002 | Laser dashboard for health management mobile version | 40 | WIP | 0 | 0 | 0 | Name | PKM | PKM | PKM | PKM | PKM | PKM | PKM | PKM | RKN, SP | RKN, SP | RKN, SP | SR | SR
| 2015-51 | Sprint04 | [8 empty] | Status | Done | Done | Done | Done | Done | Done | NS | Done | NS | NS | NS | NS
| 2015-51 | Sprint04 | [8 empty] | Planned
| 2015-51 | Sprint04 | [8 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 8 | US.DWBI.LDB.001.D01 | Laser financial dashboard fix | 20 | WIP | 18 | 0 | 18 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP | SR | SR
| 2015-51 | Sprint04 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-51 | Sprint04 | [8 empty] | Planned | [8 empty] | 6 | 6 | 6
| 2015-51 | Sprint04 | [8 empty] | Actual
KE.DWBI.1 | 2015-51 | Sprint04 | 8 | US.DWBI.LDB.003 | HM Dashboard | 40 | WIP | 18 | 0 | 18 | Name | KJ | KJ |  | KJ | KJ | KJ | KJ | KJ | RKN, SP | RKN, SP | RKN, SP | TA | TA
| 2015-51 | Sprint04 | [8 empty] | Status | Done | Done | NA | Done | Done | Done | Done | Done | NS | NS | NS
| 2015-51 | Sprint04 | [8 empty] | Planned | [8 empty] | 6 | 6 | 6
| 2015-51 | Sprint04 | [8 empty] | Actual
Note on L3: WIP Limit Status ==>>
Note on L6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L10: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L14: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L18: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L22: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L26: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L30: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L34: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L38: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L42: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L46: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L50: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L54: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L58: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required
Note on L62: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes