## Objectives
Code | Objective
TB | Team Binding
PF | Project Focussed
RP | Retention of Performers
AEL | Auto Expulsion of Laggers
NCCPQ | No competion at the cost of Product Quality
QD | Quality Delivery
TD | Timely Delivery
B4O | Binding for the Organization
DUPL | Discourage unplanned off from work
VCC | Value creation for Customer
VCO | Value creation for Organization
TP | Team Play
AT | Agility in Team
HTP | High Team Productivity
TEW | Team Enjoy Working

## Parameters-Example
| Project Coordinator Must Update this Sheet After Every Sprint Retrospective |  | Update this Every Weekend After Retrospective
|  |  | Project Code | KE.DWBI.1 | Final Score | 97.25%
|  |  | Sprint # | 1 | Wk#-> | 41
|  |  | Sprint Start Date | 2015-10-05 | Sprint End Date | 2015-10-11
|  |  | Sprint Duration (Days) | 5 | No of Resources | 3
|  |  |  | 50% | 50%
Benchmark | Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total | When to Get? | Objective
| Team Living Agile Values | 15% |  | 4.17 | 4.5 | 13%
| Team is Focussed |  |  | 4 | 4 |  | Retrospective
| Team is Committed to Sprint Goal |  |  | 4 | 4 |  | Retrospective
| Team has Courage to take risk and make decisions |  |  | 4 | 4 |  | Retrospective
| Close Communications |  |  | 5 | 5 |  | Retrospective
| Team is Respect practices, other values, other people's value |  |  | 4 | 5 |  | Retrospective
| Team is living opennes/transparency value |  |  | 4 | 5 |  | Retrospective
| Team Living Agile Principles | 15% |  | 5 | 4.5 | 14.25%
| Continuous Value Delivery |  |  | 5 | 5 |  | Retrospective
| Welcome Change |  |  | 5 | 4 |  | Retrospective
| Deliver Frequently |  |  | 5 | 4 |  | Retrospective
| Scrum Team Working Together |  |  | 5 | 4 |  | Retrospective
| Team members are Highly Motivated |  |  | 5 | 4 |  | Retrospective
| Sustainable Pace |  |  | 5 | 4 |  | Retrospective
| Technical Excellence |  |  | 5 | 5 |  | Retrospective
| Architecutre is Evolving |  |  | 5 | 5 |  | Retrospective
| Regular Cadence |  |  | 5 | 5 |  | Retrospective
| Adjusting Behaviour |  |  | 5 | 5 |  | Retrospective
| Competency and Enjoying Work | 15% |  | 5 | 5 | 15%
| Great Team |  |  | 5 | 5 |  | Sprint Review
| Moral of the team |  |  | 5 | 5 |  | Retrospective
| Helpfulness of team to each other |  |  | 5 | 5 |  | Retrospective
| Ability to solve impediments |  |  | 5 | 5 |  | Retrospective
| Team Proactiveness |  |  | 5 | 5 |  | Retrospective
| Team's ability to deliver the commitments |  |  | 5 | 5 |  | Retrospective
Benchmark | Productivity, Quality | 55% |  |  |  | 55%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5% | Before Retrospective
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5% | Retrospective
100% | Test Coverage | 5% | 100% | 100% |  | 5% | Before Retrospective
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5% | Before Retrospective
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5% | Sprint Review End
1 | Number of Product Demos | 5% | 1 | 100% |  | 5% | Sprint Review
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5% | Retrospective
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5% | Retrospective
1 | Issues in the issue log | 5% | 1 | 100% |  | 5% | Retrospective
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5% | Next Sprint Planning
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5% | Retrospective
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## PSA
Update this Every Weekend | [6 empty] | Project Coordinator Must Update this Sheet on Every Friday
Projet Resource Assignment | [6 empty] | Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1
KE.MP.001 | 2015-44 | 1 | ?? | F15435 | 1 | Sathish V
KE.MP.001 | 2015-44 | 1 | ?? | F16453 | 1 | Ashok S
KE.DWBI.1 | 2015-45 | 1 | ?? | F16839 | 1 | Nadem Manohar
KE.DWBI.1 | 2015-45 | 1 | ?? | F14580 | 1 | Braj Mohan Goud
KE.DWBI.1 | 2015-45 | 1 | ?? | EMP#08 | 1 | Sampath
KE.DWBI.1 | 2015-45 | 1 | ?? | F16520 | 1 | Pramod Kumar Matam
KE.DWBI.1 | 2015-45 | 1 | ?? | EMP#04 | 1 | Krishna M
KE.DWBI.1 | 2015-45 | 1 | ?? | F12175 | 1 | Thirupathi Kusa
KE.DWBI.1 | 2015-45 | 1 | ?? | FT14752 | 1 | Ramakrishnan
KE.DWBI.1 | 2015-45 | 1 | ?? | EMP#07 | 1 | Sai Prasath

## Score
Update this Every Weekend After Retrospective
|  |  | Project Code | KE.DWBI.1 | Final Score | 73.47%
|  |  | Sprint # | 1 | Wk# of Year-> | 2015-45
|  |  | Sprint Start Date | 2015-11-02 | Sprint End Date | 2015-11-06
|  |  | Sprint Duration (Days) | 5 | No of Resources | 7
|  |  |  | 100% | 0%
| Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total
| Team Living Agile Values | 33% |  | 3.63 | 5 | 23.96%
| Team is Focussed |  |  | 3.125 | 5
| Team is Committed to Sprint Goal |  |  | 3.625 | 5
| Team has Courage to take risk and make decisions |  |  | 3.75 | 5
| Close Communications |  |  | 3.25 | 5
| Team is Respect practices, other values, other people's value |  |  | 4.5 | 5
| Team is living opennes/transparency value |  |  | 3.5 | 5
| Team Living Agile Principles | 33% |  | 3.34 | 5 | 22.04%
| Continuous Value Delivery |  |  | 3 | 5
| Welcome Change |  |  | 4.25 | 5
| Deliver Frequently |  |  | 2 | 5
| Scrum Team Working Together |  |  | 2.875 | 5
| Team members are Highly Motivated |  |  | 3.5 | 5
| Sustainable Pace |  |  | 4.5 | 5
| Technical Excellence |  |  | 3.625 | 5
| Architecutre is Evolving |  |  | 2.5 | 5
| Regular Cadence |  |  | 3.375 | 5
| Adjusting Behaviour |  |  | 3.75 | 5
| Competency and Enjoying Work | 34% |  | 4.04 | 5 | 27.47%
| Great Team |  |  | 4 | 5
| Moral of the team |  |  | 3.5 | 5
| Helpfulness of team to each other |  |  | 4.75 | 5
| Ability to solve impediments |  |  | 4.25 | 5
| Team Proactiveness |  |  | 3.375 | 5
| Team's ability to deliver the commitments |  |  | 4.375 | 5
Benchmark | Productivity, Quality | 0% |  |  |  | 0%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5%
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5%
100% | Test Coverage | 5% | 100% | 100% |  | 5%
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5%
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5%
1 | Number of Product Demos | 5% | 1 | 100% |  | 5%
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5%
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5%
1 | Issues in the issue log | 5% | 1 | 100% |  | 5%
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5%
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5%
Improvement Identified
Best Practices
Stop Doing
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## Score-Summary
Project Id | Sprint St Date | Sprint End Date | Year Wk# | Project Wk# | Sprint# | Score | Duration | Resources
KE.DWBI.1 | 2015-11-02 | 2015-11-06 | 2015-45 | 16 | 1 | 73% | 5 | 8
Formulas:
Sprint End Date = [Sprint St Date]+[Duration]-1
Year Wk# = YEAR([Sprint St Date])&"-"&WEEKNUM([Sprint St Date])