## Objectives
Code | Objective
TB | Team Binding
PF | Project Focussed
RP | Retention of Performers
AEL | Auto Expulsion of Laggers
NCCPQ | No competion at the cost of Product Quality
QD | Quality Delivery
TD | Timely Delivery
B4O | Binding for the Organization
DUPL | Discourage unplanned off from work
VCC | Value creation for Customer
VCO | Value creation for Organization
TP | Team Play
AT | Agility in Team
HTP | High Team Productivity
TEW | Team Enjoy Working

## Score
|  |  | Update this Every Weekend After Retrospective |  |  |  |  | Update this Every Weekend After Retrospective
| 3.5714 |  | Project Code | KE.DWBI.1 | Final Score | 73.47% |  | Project Code | KE.DWBI.1 | Final Score | 84.28%
|  |  | Sprint # | 1 | Wk# of Year-> | 2015-45 |  | Sprint # | 2 | Wk# of Year-> | 2015-46
|  |  | Sprint Start Date | 2015-11-02 | Sprint End Date | 2015-11-06 |  | Sprint Start Date | 2015-11-10 | Sprint End Date | 2015-11-23
|  |  | Sprint Duration (Days) | 5 | No of Resources | 7 |  | Sprint Duration (Days) | 14 | No of Resources | 7
|  |  |  | 100% | 0% |  |  |  | 100% | 0%
| Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total
| Team Living Agile Values | 33% |  | 3.63 | 5 | 23.96% | 33% |  | 4.29 | 5 | 28.31%
| Team is Focussed |  |  | 3.125 | 5 |  |  |  | 4.43 | 5
| Team is Committed to Sprint Goal |  |  | 3.625 | 5 |  |  |  | 4.86 | 5
| Team has Courage to take risk and make decisions |  |  | 3.75 | 5 |  |  |  | 4.29 | 5
| Close Communications |  |  | 3.25 | 5 |  |  |  | 3.43 | 5
| Team is Respect practices, other values, other people's value |  |  | 4.5 | 5 |  |  |  | 4.14 | 5
| Team is living opennes/transparency value |  |  | 3.5 | 5 |  |  |  | 4.57 | 5
| Team Living Agile Principles | 33% |  | 3.34 | 5 | 22.04% | 33% |  | 4.09 | 5 | 26.99%
| Continuous Value Delivery |  |  | 3 | 5 |  |  |  | 4.29 | 5
| Welcome Change |  |  | 4.25 | 5 |  |  |  | 4.29 | 5
| Deliver Frequently |  |  | 2 | 5 |  |  |  | 3.86 | 5
| Scrum Team Working Together |  |  | 2.875 | 5 |  |  |  | 4.43 | 5
| Team members are Highly Motivated |  |  | 3.5 | 5 |  |  |  | 3.57 | 5
| Sustainable Pace |  |  | 4.5 | 5 |  |  |  | 4.14 | 5
| Technical Excellence |  |  | 3.625 | 5 |  |  |  | 4.14 | 5
| Architecutre is Evolving |  |  | 2.5 | 5 |  |  |  | 3.86 | 5
| Regular Cadence |  |  | 3.375 | 5 |  |  |  | 4 | 5
| Adjusting Behaviour |  |  | 3.75 | 5 |  |  |  | 4.29 | 5
| Competency and Enjoying Work | 34% |  | 4.04 | 5 | 27.47% | 34% |  | 4.26 | 5 | 28.97%
| Great Team |  |  | 4 | 5 |  |  |  | 4.57 | 5
| Moral of the team |  |  | 3.5 | 5 |  |  |  | 4.29 | 5
| Helpfulness of team to each other |  |  | 4.75 | 5 |  |  |  | 4.71 | 5
| Ability to solve impediments |  |  | 4.25 | 5 |  |  |  | 4.14 | 5
| Team Proactiveness |  |  | 3.375 | 5 |  |  |  | 3.71 | 5
| Team's ability to deliver the commitments |  |  | 4.375 | 5 |  |  |  | 4.14 | 5
Benchmark | Productivity, Quality | 0% |  |  |  | 0% | 0% |  |  |  | 0%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5% | 5% | 0.5 | 100% |  | 5%
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Test Coverage | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5% | 5% | 100% | 100% |  | 5%
1 | Number of Product Demos | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
1 | Issues in the issue log | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5% | 5% | 25 | 100% |  | 5%
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5% | 5% | 1 | 100% |  | 5%
Improvement Identified
Estimation the work and negotiate the timeline and resources with customer
Conduct team sessions twice a week for 1 hour each for improving technical know how about customer business.
Understand sprint planning and perform sprint planning
Daily standup meeting
Best Practices
Daily call with customer
Continuous demo of the work performed to the customer
Stop Doing
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## Score-Summary
Project Id | Sprint St Date | Sprint End Date | Year Wk# | Project Wk# | Sprint# | Values | Principle | Enjoying Work | Score | Duration | Resources
KE.DWBI.1 | 2015-11-02 | 2015-11-06 | 2015-45 | 16 | Sprint01 | 3.63 | 3.34 | 4.04 | 73% | 5 | 8
KE.DWBI.1 | 2015-11-10 | 2015-11-23 | 2015-46 | 17 | Sprint02 | 4.29 | 4.09 | 4.26 | 84% | 10 | 8
Formulas:
Sprint End Date = [Sprint St Date]+[Duration]-1
Year Wk# = YEAR([Sprint St Date])&"-"&WEEKNUM([Sprint St Date])

## Lessons-Log
Team Learning Register
Date | Project# | Soruces | Type | Particular | Actionee | Date
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Estimation the work and negotiate the timeline and resources with customer | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Conduct team sessions twice a week for 1 hour each for improving technical know how about customer business. | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Understand sprint planning and perform sprint planning | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Improvement | Daily standup meeting | Team
2015-11-24 | KE.DWBI.1 | Retrospective | Best Practices | Daily call with customer
2015-11-24 | KE.DWBI.1 | Retrospective | Best Practices | Continuous demo of the work performed to the customer