## Sprint-Master
Sprint# | Week of Year | Start Date | End Date | Resources | Duration | Available Hours | Planned Hours | Actual Hours | Velocity | Remarks | Goal
Sprint01 | 2015-44 | 2015-10-26 | 2015-10-30 | 7 | 5
Sprint02 | 2015-45 | 2015-11-02 | 2015-11-06 |  | 5
Sprint03 | 2015-46 | 2015-11-09 | 2015-11-13 |  | 5
Sprint04 | 2015-47 | 2015-11-16 | 2015-11-20 |  | 5
Sprint05 | 2015-48 | 2015-11-23 | 2015-11-27 | 1 | 5
Sprint06 | 1900-00 |  |  |  | 5
Sprint07 | 1900-00 |  |  |  | 5
Sprint08 | 1900-00 |  |  |  | 5
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+3

## Resources
Week of Year | 2015-48
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
F15600 | Sanjana Babu | QA | SB | 1
F16453 | Ashok S | Dev | AS | 1
F16707 | Rajesh Kanna P | Dev | RK | 0.2
F0101 | Seshan T R | SM | STR | 1
Grand Total |  |  |  | 3.2

## PRA
Update this Every Weekend | [8 empty] | Project Coordinator Must Update this Sheet on Every Friday
Projet Resource Assignment | [8 empty] | Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role | If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15435 | 1 | Sathish V | SV | QA
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15856 | 1 | Deepika Ranganathan | DR | QA
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16453 | 1 | Ashok S | AS | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16305 | 1 | Dilip Prasad J | DP | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16039 | 1 | Karthikeyan V | KV | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16707 | 1 | Rajeshkanna P | RK | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F13676 | 0.2 | Ravindra Kumar Tiwary | RKT | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F0101 | 1 | Seshan T R | STR | SM
KE.MP.001 | 2015-48 | Sprint05 | 17 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev

## Project Log
Source | Type | Identification Date | Impediments/ Action/ Event/ Problem | Actionee | Verifier | Status | Due Date | Remarks

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Priority | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Nivedha | Ram | Roshan | Karthikeyan | Sathish | Shreya | Ravindra | TFS-ID | Related US-ID | Remarks1 | Remarks2
US.GQ.SC.01 | Subsidy Calculator (Get Quote Page) | 40 |  | Sprint2 |  | Web User | Calculate and display subsidy amount based on applicant data and family data | User should enter zip code and family income, age and tobacco use status | subsidy amount should be displayed as per connecture based on provided data. | [9 empty] | 40
Note on G2: Author: The primary user or stakeholder for the story
Note on H2: Author: The goal that the actor is trying to achieve in the story
Note on I2: Author: The actions performed by the actor.
Note on J2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
|  |  |  | Auto Calculation | [6 empty] | Development | [6 empty] | QA |  |  | Acceptance Testing
|  |  |  | No Entry |  | Current Wk# | 2015-48 |  |  | WIP | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProjectId | Week of Year | Sprint# | # | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Type | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO
KE.MP.001 | 2015-48 | Sprint05 | 1 | US.GQ.SC.01 | Subsidy Calculator (Get Quote Page) | 40 | Moved | 48 | 46 | Name |  | RKT | RKT | RKT | RKT | RKT |  | SV | SV | SV |  | RKT
KE.MP.001 | 2015-48 | [8 empty] | Status | NR | Done | WIP | Done | Done | Done | NR | NS | NS | NS | NR | NS
KE.MP.001 | 2015-48 | [8 empty] | Planned |  | 20 | 8 | 8 | 4 | 8
KE.MP.001 | 2015-48 | [8 empty] | Actual |  | 20 | 6 | 8 | 4 | 8
Note on K3: WIP Limit Status ==>>
Note on K6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes