## Sprint-Master
Sprint# | Week of Year | Start Date | End Date | Resources | Duration | Available Hours | Actual Hours | Remarks | Goal
Sprint01 | 2015-44 | 2015-10-26 | 2015-10-30 | 7 | 5
Sprint02 | 2015-45 | 2015-11-02 | 2015-11-06 |  | 5
Sprint03 | 2015-46 | 2015-11-09 | 2015-11-13 |  | 5
Sprint04 | 2015-47 | 2015-11-16 | 2015-11-20 |  | 5
Sprint05 | 2015-48 | 2015-11-23 | 2015-11-27 | 1 | 5
Sprint06 | 2015-49 | 2015-11-30 | 2015-12-04 |  | 5
Sprint07 | 2015-50 | 2015-12-07 | 2015-12-11 |  | 5
Sprint08 | 2015-51 | 2015-12-14 | 2015-12-18 |  | 5
Formulas:
Week of Year = YEAR([Start Date])&"-"&RIGHT("0"&WEEKNUM([Start Date]),2)
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+3

## Resources
Week of Year | (All)
Sum of Present
Emp ID# | Emp Name | Scrum Role | Initial | Total
F0101 | Seshan T R | SM | STR | 1
F13676 | Ravindra Kumar Tiwary | Dev | RKT | 0.2
F15435 | Sathish V | QA | SV | 1
F15856 | Deepika Ranganathan | QA | DR | 1
F16039 | Karthikeyan V | Dev | KV | 1
F16305 | Dilip Prasad J | Dev | DP | 1
F16453 | Ashok S | Dev | AS | 1
F16707 | Rajesh Kanna P | Dev | RK | 1
Grand Total |  |  |  | 7.2

## PRA
Update this Every Weekend
Projet Resource Assignment
Project ID | Week of Year | Sprint# | Project Wk# | Emp ID# | Present | Emp Name | Initial | Scrum Role
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15435 | 1 | Sathish V | SV | QA
KE.MP.001 | 2015-44 | Sprint01 | 16 | F15856 | 1 | Deepika Ranganathan | DR | QA
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16453 | 1 | Ashok S | AS | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16305 | 1 | Dilip Prasad J | DP | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16039 | 1 | Karthikeyan V | KV | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F16707 | 1 | Rajeshkanna P | RK | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F13676 | 0.2 | Ravindra Kumar Tiwary | RKT | Dev
KE.MP.001 | 2015-44 | Sprint01 | 16 | F0101 | 1 | Seshan T R | STR | SM
KE.MP.001 | 2015-48 | Sprint05 | 17 | F13676 | 1 | Ravindra Kumar Tiwary | RKT | Dev
Note on F3: Enter 1, .8, .6, .4, .2 for 5, 4, 3, 2, 1 days work respectably in the "Present" column If team member was working on more than 1 projects in any week then ensure total of a week in all project do not exceed 1

## ProductBacklog
Estimation
Story ID | Story Name | Story Points | Sprint Plan | Status | As a... (Actor) | Goal | When I... (Action) | Then... (Acceptance Criterion) | Remarks | Feedback Required from PO | Naresh | Karthikeyan | Sathish | Shreya | Ravindra | Status
US.GQ.SC.01 | Subsidy Calculator |  | Sprint2 |  | Web User | Calculate and display subsidy amount based on applicant data and family data | User should enter zip code and family income, age and tobacco use status | subsidy amount should be displayed as per connecture based on provided data. | [6 empty] | 40 | Not Discussed
Note on H2: Author: The primary user or stakeholder for the story
Note on I2: Author: The goal that the actor is trying to achieve in the story
Note on J2: Author: The actions performed by the actor.
Note on K2: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.

## SB-Sprints
Scrum Board
|  |  | Auto Calculation |  |  |  | Efforts |  |  | Development | [6 empty] | QA |  |  | Acceptance Testing
|  |  | No Entry |  |  |  | 16 | 16 | WIP | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# | Sprint# | Week of Year | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Type | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO
1 | Sprint01 | 2015-47 | US.GQ.SC.01 | Subsidy Calculator | 0 | WIP | 16 | 16 | Name |  | KV, AS | KV |  |  |  | KV |  |  | DR | PD | DP
|  | 2015-47 | [6 empty] | Status | NS | WIP |  | NA | NA | NA | Done | NR | NR | NR | NR | NR
|  | 2015-47 | [6 empty] | Planned |  | 8 | 6 |  |  |  | 2
|  | 2015-47 | [6 empty] | Actual |  | 8 | 6 |  |  |  | 2
Note on J3: WIP Limit Status ==>>
Note on J6: NS- Not Started WIP- Work in Progress NA- Not Applicable NR- Not Required

## Master
# | Sprint# | Week of Year | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO | Dev Team Status | Completed Complexity | Delivered Complexity
1 | Sprint01 | 2015-47 | US.GQ.SC.01 | Subsidy Calculator | 0 | WIP | 16 | 16 | Actual | 8 | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | NR | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## M
3 | <== Actual Effort Rows
# | # | Sprint# | Week of Year | User Story-ID | User Stories Description | Complexity | US Status | Planned | Acutal | Unit Test Code | Coding | Developed & Unit Tested | UI Developed | UI Integration | Web Service Integration | DB Integration | QA Test Case | Integration Testing | Functional Testing | Acceptance Test Case | Demoed to PO | Completed Complexity
64 | A | B | C | D | E | F | G | H | I | J | L | M | N | O | P | Q | R | S | T | U | V | T
Col # in Scrum Board | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 20
5 | ='SB-Sprints'!A5 | ='SB-Sprints'!B5 | ='SB-Sprints'!C5 | ='SB-Sprints'!D5 | ='SB-Sprints'!E5 | ='SB-Sprints'!F5 | ='SB-Sprints'!G5 | ='SB-Sprints'!H5 | ='SB-Sprints'!I5 | ='SB-Sprints'!J8 | ='SB-Sprints'!L8 | ='SB-Sprints'!M8 | ='SB-Sprints'!N8 | ='SB-Sprints'!O8 | ='SB-Sprints'!P8 | ='SB-Sprints'!Q8 | ='SB-Sprints'!R8 | ='SB-Sprints'!S8 | ='SB-Sprints'!T8 | ='SB-Sprints'!U8 | ='SB-Sprints'!V8 | ='SB-Sprints'!T6
9 | ='SB-Sprints'!A9 | ='SB-Sprints'!B9 | ='SB-Sprints'!C9 | ='SB-Sprints'!D9 | ='SB-Sprints'!E9 | ='SB-Sprints'!F9 | ='SB-Sprints'!G9 | ='SB-Sprints'!H9 | ='SB-Sprints'!I9 | ='SB-Sprints'!J12 | ='SB-Sprints'!L12 | ='SB-Sprints'!M12 | ='SB-Sprints'!N12 | ='SB-Sprints'!O12 | ='SB-Sprints'!P12 | ='SB-Sprints'!Q12 | ='SB-Sprints'!R12 | ='SB-Sprints'!S12 | ='SB-Sprints'!T12 | ='SB-Sprints'!U12 | ='SB-Sprints'!V12 | ='SB-Sprints'!T10
13 | ='SB-Sprints'!A13 | ='SB-Sprints'!B13 | ='SB-Sprints'!C13 | ='SB-Sprints'!D13 | ='SB-Sprints'!E13 | ='SB-Sprints'!F13 | ='SB-Sprints'!G13 | ='SB-Sprints'!H13 | ='SB-Sprints'!I13 | ='SB-Sprints'!J16 | ='SB-Sprints'!L16 | ='SB-Sprints'!M16 | ='SB-Sprints'!N16 | ='SB-Sprints'!O16 | ='SB-Sprints'!P16 | ='SB-Sprints'!Q16 | ='SB-Sprints'!R16 | ='SB-Sprints'!S16 | ='SB-Sprints'!T16 | ='SB-Sprints'!U16 | ='SB-Sprints'!V16 | ='SB-Sprints'!T14
17 | ='SB-Sprints'!A17 | ='SB-Sprints'!B17 | ='SB-Sprints'!C17 | ='SB-Sprints'!D17 | ='SB-Sprints'!E17 | ='SB-Sprints'!F17 | ='SB-Sprints'!G17 | ='SB-Sprints'!H17 | ='SB-Sprints'!I17 | ='SB-Sprints'!J20 | ='SB-Sprints'!L20 | ='SB-Sprints'!M20 | ='SB-Sprints'!N20 | ='SB-Sprints'!O20 | ='SB-Sprints'!P20 | ='SB-Sprints'!Q20 | ='SB-Sprints'!R20 | ='SB-Sprints'!S20 | ='SB-Sprints'!T20 | ='SB-Sprints'!U20 | ='SB-Sprints'!V20 | ='SB-Sprints'!T18

## DoD
US Definition of Done
US Status | Yes
Planned | Yes
Acutal | Yes
Type | Yes
Unit Test Code | Yes
Coding | Yes
Developed & Unit Tested | Yes
UI Developed | No
UI Integration | Yes
Web Service Integration | Yes
DB Integration | Yes
QA Test Case | Yes
Integration Testing | Yes
Functional Testing | Yes
Acceptance Test Case | Yes
Demoed to PO | Yes