## Objectives
Code | Objective
TB | Team Binding
PF | Project Focussed
RP | Retention of Performers
AEL | Auto Expulsion of Laggers
NCCPQ | No competion at the cost of Product Quality
QD | Quality Delivery
TD | Timely Delivery
B4O | Binding for the Organization
DUPL | Discourage unplanned off from work
VCC | Value creation for Customer
VCO | Value creation for Organization
TP | Team Play
AT | Agility in Team
HTP | High Team Productivity
TEW | Team Enjoy Working

## Score
Update this Every Weekend After Retrospective
|  |  | Project Code | KE.MP.001 | Final Score | 72.5%
|  |  | Sprint # | 1 | Wk#-> | 44
|  |  | Sprint Start Date | 2015-10-26 | Sprint End Date | 2015-10-30
|  |  | Sprint Duration (Days) | 5 | No of Resources | 7
|  |  |  | 100% | 0%
| Weightage/Gross Total | Weightage | Calculation | Teams's Rating | Customer's Rating | Total
| Team Living Agile Values | 33% |  | 3.84 | 5 | 25.34%
| Team is Focussed |  |  | 4.57 | 5
| Team is Committed to Sprint Goal |  |  | 4.85 | 5
| Team has Courage to take risk and make decisions |  |  | 3.5 | 5
| Close Communications |  |  | 3.21 | 5
| Team is Respect practices, other values, other people's value |  |  | 2.92 | 5
| Team is living opennes/transparency value |  |  | 4 | 5
| Team Living Agile Principles | 33% |  | 3.22 | 5 | 21.25%
| Continuous Value Delivery |  |  | 3.5 | 5
| Welcome Change |  |  | 3.5 | 5
| Deliver Frequently |  |  | 4.28 | 5
| Scrum Team Working Together |  |  | 3.28 | 5
| Team members are Highly Motivated |  |  | 3.78 | 5
| Sustainable Pace |  |  | 1 | 5
| Technical Excellence |  |  | 3.4 | 5
| Architecutre is Evolving |  |  | 2.6 | 5
| Regular Cadence |  |  | 3 | 5
| Adjusting Behaviour |  |  | 3.85 | 5
| Competency and Enjoying Work | 34% |  | 3.81 | 5 | 25.91%
| Great Team |  |  | 3 | 5
| Moral of the team |  |  | 2.92 | 5
| Helpfulness of team to each other |  |  | 4.35 | 5
| Ability to solve impediments |  |  | 4.28 | 5
| Team Proactiveness |  |  | 4 | 5
| Team's ability to deliver the commitments |  |  | 4.28 | 5
Benchmark | Productivity, Quality | 0% |  |  |  | 0%
0.5 | Functional Point Written by a every team | 5% | 0.5 | 100% |  | 5%
100% | % UAT test cases passed | 5% | 100% | 100% |  | 5%
100% | Test Coverage | 5% | 100% | 100% |  | 5%
100% | Functional Point Test Coverage | 5% | 100% | 100% |  | 5%
100% | Value Delivered (Value Points) | 5% | 100% | 100% |  | 5%
1 | Number of Product Demos | 5% | 1 | 100% |  | 5%
1 | No of defect leak to customer | 5% | 1 | 100% |  | 5%
1 | No of Defects Leaked to QA | 5% | 1 | 100% |  | 5%
1 | Issues in the issue log | 5% | 1 | 100% |  | 5%
25 | Time spent on rework (Hours) | 5% | 25 | 100% |  | 5%
1 | Team's unplanned leaves (Days) | 5% | 1 | 100% |  | 5%
Note on B41: Defect means system crashing/ improper validation, integration issue, UI alignment, navigation. Defect does not missing functionality. -Hari Thapliyal

## Score-Summary
Project Id | Sprint St Date | Sprint End Date | Year Wk# | Project Wk# | Sprint# | Values | Principle | Enjoying Work | Score | Duration | Resources
KE.MP.001 | 2015-10-26 | 2015-10-30 | 2015-44 | 16 | Sprint01 | 3.84 | 3.22 | 3.81 | 73% | 5 | 7
Formulas:
Year Wk# = YEAR([Sprint St Date])&"-"&WEEKNUM([Sprint St Date])

## Lessons-Log
Team Learning Register
Date | ProjectID | Soruces | Type | Particular | Actionee | Date
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Tight Deadlines
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Tough Calls
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of sprint process
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Long working hours (weekdays)
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No Clear deployment plan communication for Prod Environment code push
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Re-open items again
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Weekend Work
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Security testing could have been done on Tuesday & Wednesday
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Last minute code change for security fixes
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of tools to test security fixes inn test environment
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Lack of awareness for secure application development
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No clear requirements for sprints
2015-11-02 | KE.MP.001 | Retrospective | Challenges | No Plans for sprint.
2015-11-02 | KE.MP.001 | Retrospective | Challenges | Product owner’s responsibility
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Need a deployment plan (timings, technical docs)
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Developers should do integration testing in the dev environment
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Developers should write unit test cases
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Discussed risks in implementing functionality with product owner as and when needed
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Security testing has to be done as a regular activity of sprint
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Every sprint must have to be started with sprint planning
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Deployment checklist has to be created and deployment has to be done on rotational basis following same procedures.
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Prepare deployment checklist – Team (11/03/2015) | Dev. Team | 2015-11-04
2015-11-02 | KE.MP.001 | Retrospective | Improvement | Start Integration testing (Functional Flow) | Dev. Team | 2015-11-04