## Slide 1: Engineering to Scale Height
Project Management Backbone Processes

## Slide 2: Perceptive Learning Consultants
Recommendations of PMO Framework is based on Industry Neutral Project Management Best Practices from
  PMBOK v 5 (PMI),
  PRINCE2 2009 (OGC) and
  Agile Project Management Practices

## Slide 3: Agenda
Roles & Responsibilities
PMO Skelton Processes
Management by Exceptions
Project Organization Chart
Next Steps

## Slide 4: PMO Responsibilities
PMO is a function with organization. Like any other function this has a Head of Function. PMO Responsibilities should be rendered by PMO Head and his team of project managers to the Assigned Project Manager or to the Organization.

## Slide 5: PMO Responsibilities
Before Initiation
  Competency building of Project Managers
  Help organization in evaluating new business opportunities
  Creating knowledge infrastructure for Project Management
Initiation of Phase/Project
  Internal Project Sponsoring (Project Charter)
  Allocating a dedicated and trained project manager
  Identify & evaluate project inherent risks
  Refer to lessons learned from previous projects
  Ensure business case and feasibility study has been done else feasibility study is the first Phase of the project

## Slide 6: PMO Responsibilities
Planning of Phase/Project
  Helping project manager in making a project plan of execution and governance.
  Approving and allocating resources for project
  Negotiate with functional heads for availability of required project resources
  Reviewing/approving project plan
  Prepare project management infrastructure (templates, checklist, forms, guidelines, reporting systems)
  Help project manager in selecting a project management approach
  Setup appraisal system

## Slide 7: PMO Responsibilities
Execution of Phase/Project
  Provide Infrastructure to Project Manager
  If required get resources from market for a project
  Mentoring and Coaching Project Manager
  Maintain Project Records and permission for all projects
  Maintain Organization Process Assets
  Human Resource management at organization level
  Inventory Management at organization level

## Slide 8: PMO Responsibilities
Governance of Phase/Project
  Review phase/project status/progress with project manager
  Prepare project dashboard for entire organization
  Review the status with CEO and make go/no-go decision for future work
  Change Approval within threshold limits Or Seek approval from CEO.
  Perform Project Quality and Configuration Audit
  Perform Project Risk Audit
  Organizational Level Project Risk Profiling
  Coordination with account, supply-chain, quality team about payment, purchase quality, material availability

## Slide 9: PMO Head Responsibilities
Head of the PMO Ensure that PMO Responsibilities are taken care with the help of his team of Project Managers.
If PMO head is doing some project then
  Another person should sponsor his projects
  Another person should review and approve his project plans
  Another person should Audit his projects
  He can represent his projects before CEO
Ideally this person should be with authority and respect within the organization. And he should be kept away from doing projects.

## Slide 10: Project Manager’s Responsibilities
Conduct project Kickoff
Prepare/Update project plan
Get approval from project board and baseline project plan
Manage project within allowed thresholds
Brief project progress to project board on periodic basis
Ensure vendors are delivering as per contract
Team motivation
Process compliance
Deliver project product as per specification
Assessment of Change Request within threshold limit OR Seek Approval from Project Board
Maintain Project Documents
Maintain project records
Appraise human resources working on project
Get Project Sign off
Ideally this person should be BFL senior employee trained on PM frameworks.

## Slide 11: Senior User Responsibilities
Provide customer quality expectations and define acceptance criteria
Ensure project’s outcome is useful
Resolve user requirements and priority conflicts
Ensure user experts required are available (if needed)
Brief and advise users on requirement decisions
Provide user view on follow-on action recommendations
Project Assurance from user perspective.
Ideally a Representative from BFL’s client side

## Slide 12: Senior Supplier Responsibilities
Assess and confirm viability of the project approach
Ensure design is realistic
Advise on the selection of design, development and acceptance methods
Ensure supplier resources are available
Safeguarding complete solutions and make decision on escalated issues
Resolve supplier requirements and priority conflicts
Brief non-technical management on supplier aspects
Ensure quality procedures are used correctly
Project Assurance from supplier perspective
Ideally from BFL Design Team or major vendor side

## Slide 13: Project Planning
Scope
Time
Cost
Requirement
Understanding
Solutioning
Scope Baselining
Activity Identification & Sequencing
Estimate
Resource & Duration
Schedule Development
Activity Cost
Estimation
Budgeting with Consolidated Cost
Negotiate Scope, Time, Cost, Quality
Add all other cost
Baseline Scope, Schedule, Cost, Quality Expectations
Quality
Project & Product Quality Planning
Cost of Quality
P2
P5
P6
P7
P8
P9
P10
P11
P24
P3
P4
Configuration Management
Integration
P1

## Slide 14: Project Planning
Risk
Risk Identification
Risk Response Planning
Cost of Risk Management
Human Resource
HR & Staff Management Planning
Cost/Schedule of Training/Hiring/ Appraisal etc.
Procurement
Procurement Planning
Cost/Schedule of Contracting P/S/R
Communication
Communication Planning & Technology
Cost of Communication
Stakeholder
Stakeholder Management Planning
Cost of Stakeholder Engagement
Consolidate All Costs / Scheduled Activities
P12
P13
P14
P15
P16
P17
P18
P19
P20
P21
P22
P23
P24

## Slide 15: Project Execution
Human Resources
Procurement
Communication
Stakeholder
Contracting
Resource Acquisition
Team Capability Building
Team & Work Management
Project Planned/Ad-hoc Communications
Routine Stakeholder Engagements
Quality
Quality/Configuration Audits
Integration
Work Authorization
Work Tracking/Coordination/Communication
E1
E2
E3
E4
E5
E6
E7
E8

## Slide 16: Project Governance : Project Level
Risk
Procurement
Communication
Contract P/S/R Management
Risk Reassessment
Risk Audits
Reassess Communication/
Engagement Needs
Quality
Product Testing by QA Team
Integration
Integrated Change Control
Work Monitoring/Controlling/Coordination/Communication
Report Preparation
Product Testing by Customer
Scope, Time, Cost
CST Variance Management
Quality Variance Management
G1
G2
G3
G4
G5
G6
G7
G8
G9
G10

## Slide 17: Project Governance : PMO Level
PMO Review Project Progress/ Status with PM
Addressing Impediments & Taking Decisions
Authorize Next Phase/ Project
Approve (Revised) Baseline
Share Lessons Learned with/from Other Projects
Org Level Project Metrics
PMO Review Project Progress/ Status with CEO
Stakeholder Engagement
Risk
Procurement
Stakeholder / Communication
Quality
Integration
G1
Org Level Risk Management
Org Level Vendor & Inventory Control
G2
G3
G4
G5
G6
G7
G8
G9
G10

## Slide 18: Project Initiation
Prepare Project Charter
Identify Stakeholders
Risk
Integration
Stakeholders
I1
I2

## Slide 19: Project Closure
Each Vendor Contract Closing
Customer Sign Off
Phase or Project Closure
Procurement
Integration
C1
C2
C3

## Slide 20: Umbrella Processes
Communication & Stakeholder Engagement
Project Quality & Product Quality
Configuration Management

## Slide 21: Management by Exceptions
Project Board
CEO
Project Board
Project Manager
Team Leaders/ Vendors
Project Level Thresholds of S, T, C, Q
Phase Level Thresholds of S, T, C, Q
Workpackage Level Thresholds of S, T, C, Q
PMO Head
Senior User
Senior Supplier
S, T, C, Q: Scope, Time, Cost, Quality

## Slide 22: Project Organization Chart
CEO
PMO Head
Project Manager
Project Manager
Functional/ Operation Managers
Functional/ Technical Experts
Functional/ Technical Experts
Functional/ Operation Managers

## Slide 23: PMO & Departmental Services in P.L.C.
Directive-PMO
Contracting Experts
Design Experts
Supply Chain Experts
Manufacturing Experts
Erection & Commissioning Experts
Product Component Testing
Site Testing
1
2
3
4
6
5
7
Stage 1:
Contracts
Stage 2:
Design
Stage 3:
Supply Chain
Stage 4:
Manufacturing
Stage 5:
Erection & Commissioning
Project
Phases
Quality Experts

## Slide 24: Important Practices
Daily Standup
Sprint Planning
Retrospectives
Project Kanban Board

## Slide 25: Optimizing Knowledge Inputs and Actions
Expert Judgment (EJ)
Part time.
Involved
Provides Input/ share perspective
Typical from outside of the organization or senior people
Knowledge Driven
Project Manager seeks EJ input based on the need
Project Team Member (PTM)
Full time
Committed
Chose options and Perform actions
Typical from within the organization.
Doers./ Action Driven
Project Manager expects PTM to produce project deliverables

## Slide 26: Next Steps
Project Management Workshops to all Managers/PM/Departmental Heads– 10 Days
??
Procure/Install Automation Tools/ Automate processes as much possible
Processes Awareness/ Training (10 Days)
Training on Leadership / Interpersonal Skills (4 Days)
Map/Define PM processes to the implementation details (15 Days)
Phase 1:
Defining Framework & fine tuning to BFL
Phase 2:
Phase 3
Finalize a tool for Automation
Phase 4
Periodic Audit/Review of Implementation
Support

## Slide 27: A comparison of Sectors that Report Delivery on Time, Budget, Scope

## Slide 28: A comparison of Sectors that Report Delivery on Time, Budget, Scope

## Slide 29: Project Team