## MilestoneLists
| Phases | Milestones
1 | StartUp | Receipt Advance
2 | Kickoff | Project Kick-off
3 | Planning & Design | Prepare Project Approach with Design, Manu, Proc, Logistic, Finance Department. Include project review plan.
4 |  | Prepare/Approve Project Budget (cost, time)
5 |  | Prepare/Approval (Drawing SLD/SA) from customer
6 |  | Prepare Detail Procurement, Manufacturing, Logistic & E&C Plan
7 |  | Prepare Detail Design and release TPS/BOM
8 |  | Vendor Finalization (proc, manu) & PO issuance
9 | Manufacturing | Manufactruing clearance
10 |  | Finished Product Inspection by Customer/QA
11 |  | Payment Collection from Customer
12 |  | Vendor Finalzation for Logistic
13 | Dispatch | Material Dispatch to site & stored at customer site
14 | Erection | Erection & Commissioning
15 | Closure | Project Closure

## Process List
Process ID | Process Name | Level | Input From | Output To
I01 | Prepare Project Charter
I02 | Identify Stakeholders
P01 | Configuration Management | PMO | All Departments
P02 | Requirment Understanding
P03 | Solutioning
P04 | Scope Baselining
P05 | Actvitity Identification & Sequencing
P06 | Estimate Actvity Resource & Durations
P07 | Schedule Development
P08 | Activity Cost Etimation
P09 | Budgeting with consolidated cost
P10 | Project & Product Quality Planning
P11 | Cost of Quality
P12 | Risk Identification
P13 | Risk Response Planning
P14 | Cost of Risk Management
P15 | HR& Staff Management Planning
P16 | Cost of Training/Hiring/Appraisal etc.
P17 | Procurement Planning
P18 | Cost/Schedule of Contracting P/S/R
P19 | Communication Planning & Tech
P20 | Cost of Communication
P21 | Stakeholder Management Plan
P22 | Cost of Stakeholder Engagement
P23 | Consolidate all costs/schedule of activities
P24 | Negotiate cost/schedule/quality/scope- Baseline Project
E01 | Work Authorization
E02 | Quality and Config Audit
E03 | Resource Acquition
E04 | Team Capablity Building
E05 | Team & Work Management
E06 | Contracting
E07 | Project Planned/Ad-hoc Communications
E08 | Routine Stakeholder Engagement
G01 | Integrated Change Control
G02 | Report Prepration
G03 | Quality Variance Management
G04 | Product Testing by QA
G05 | Product Testing by Customer
G06 | CST Variance Management
G07 | Risk Reassessment
G08 | Risk Audit
G09 | Contract P/S/R Management
G10 | Reassess configuration /engagement need
PMO-G01 | PMO Review Project Progress with PM
PMO-G02 | PMO Review Project Progress with CEO
PMO-G03 | Approve Revised Baselines
PMO-G04 | Addressing Impediments & Taking Decisions
PMO-G05 | Authorize Next Phase/Project
PMO-G06 | Share Lessons Learned with Org /Other projects
PMO-G07 | Manage Org Level Project Metrics
PMO-G08 | Org Level Risk Management
PMO-G09 | Org Level Vendor & Inventory Management
PMO-G10 | Stakehodler Engagemetn
C01 | Each Vendor Contract Closing
C02 | Customer Sign off
C03 | Phase or Project Closure
A01 | Daily Standup
A02 | Sprint Planning
A03 | Retrospective
A04 | Project Kanbanboard

## Mapping
[5 empty] | 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 7 | 7 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16
|  |  |  | Phases | StartUp | Kickoff |  | Planning & Design | 10: Manufacturing; 14: Dispatch; 15: Erection; 16: Closure
Umbrella Process | Org Level Process | Process Name | # Occurance | Process ID Milestones | Receipt Advance | Project Kick-off with Maketting | Project Kick-off with Team | Project Setup | Prepare Project Approach with Design, Manu, Proc, Logistic, Finance Department. Include project review plan. | Prepare/Approve Project Budget (cost, time) | Prepare/Approval (Drawing SLD/SA) from customer | Prepare Detail Procurement Plan | Prepare Detail Manufacturing Plan | Prepare Detail Logistic Plan | Prepare Detail E&C Plan | Prepare Detail Design and release TPS/BOM | Vendor Finalization (proc, manu) & PO issuance | Manufactruing clearance | Finished Product Inspection by Customer/QA | Vendor Finalzation for Logistic | Material Dispatch to site & stored at customer site | Erection & Commissioning | Project Closure
|  | # Occrance |  |  | 0 | 3 |  | 5 | 28 | 18 | 19 | 22 | 32 | 32 | 32 | 19 | 19 | 15 | 16 | 18 | 19 | 19 | 4
|  | Prepare Project Charter | 1 | I01 |  | x
|  | Identify Stakeholders | 3 | I02 |  | x | bar: 4 to 16
| Yes | Configuration Management | 1 | P01 |  |  |  | x
| Yes | Time & Cost Management Plan | 1 | P25 | bar: 4 to 16
|  | Requirment Understanding | 3 | P02 |  |  | x | bar: 4 to 16
|  | Solutioning | 3 | P03 | bar: 4 to 16
|  | Scope Baselining | 4 | P04 |  |  | x | bar: 4 to 16
|  | Actvitity Identification & Sequencing | 6 | P05 |  |  | x | bar: 4 to 16
|  | Estimate Actvity Resource & Durations | 4 | P06 | bar: 4 to 16
|  | Schedule Development | 7 | P07 |  |  | x | bar: 4 to 16
|  | Activity Cost Etimation | 5 | P08 | bar: 4 to 16
|  | Budgeting with consolidated cost | 6 | P09 |  |  | x | bar: 4 to 16
|  | Project & Product Quality Planning | 4 | P10 | bar: 4 to 16
|  | Cost of Quality | 6 | P11 | bar: 4 to 16
Yes |  | Risk Identification | 17 | P12 |  | x | x | bar: 4 to 16
Yes |  | Risk Response Planning | 3 | P13 |  |  | x | bar: 4 to 16
|  | Cost of Risk Management | 5 | P14 | bar: 4 to 16
| Yes | HR& Staff Management Planning | 2 | P15 |  |  |  | x | bar: 4 to 16
| Yes | Cost of Training/Hiring/Appraisal etc. | 2 | P16 |  |  |  | x | bar: 4 to 16
|  | Procurement Planning | 6 | P17 |  |  | x | bar: 4 to 16
|  | Cost/Schedule of Contracting P/S/R | 5 | P18 | bar: 4 to 16
|  | Communication Planning & Tech | 4 | P19 | bar: 4 to 16
| Yes | Cost of Communication | 3 | P20 | bar: 4 to 16
|  | Stakeholder Management Plan | 4 | P21 | bar: 4 to 16
|  | Cost of Stakeholder Engagement | 4 | P22 | bar: 4 to 16
|  | Consolidate all costs/schedule of activities | 5 | P23 | bar: 4 to 16
|  | Negotiate cost/schedule/quality/scope- Baseline Project | 5 | P24 | bar: 4 to 16
Yes |  | Work Authorization | 3 | E01 | bar: 4 to 16
Yes |  | Quality and Config Audit | 14 | E02 | bar: 4 to 16
| Yes | Resource Acquition | 1 | E03 |  |  |  | x
| Yes | Team Capablity Building | 1 | E04 |  |  |  | x
Yes |  | Team & Work Management | 10 | E05 | bar: 4 to 16
|  | Contracting | 3 | E06 | bar: 4 to 16
Yes |  | Project Planned/Ad-hoc Communications | 13 | E07 | bar: 4 to 16
Yes |  | Routine Stakeholder Engagement | 12 | E08 | bar: 4 to 16
Yes |  | Integrated Change Control | 13 | G01 | bar: 4 to 16
Yes |  | Report Prepration | 13 | G02 | bar: 4 to 16
Yes |  | Quality Variance Management | 13 | G03 | bar: 4 to 16
Yes |  | WorkProduct/ Product Review/Testing by QA | 9 | G04 | bar: 4 to 16
|  | Product Testing by Customer | 1 | G05 | bar: 4 to 16
Yes |  | CST Variance Management | 10 | G06 | bar: 4 to 16
Yes |  | Risk Reassessment | 14 | G07 | bar: 4 to 16
Yes |  | Risk Audit | 4 | G08 | bar: 4 to 16
|  | Contract P/S/R Management | 2 | G09 | bar: 4 to 16
Yes |  | Reassess conmmunication /engagement need | 14 | G10 | bar: 4 to 16
|  | Each Vendor Contract Closing | 1 | C01 | bar: 4 to 16
|  | Customer Sign off | 1 | C02 | bar: 4 to 16
|  | Phase or Project Closure | 1 | C03 | bar: 4 to 16
Yes |  | Daily Standup | 14 | A01 | bar: 4 to 16
Yes |  | Sprint Planning | 14 | A02 | bar: 4 to 16
Yes |  | Retrospective | 14 | A03 | bar: 4 to 16
Yes |  | Project Kanbanboard | 14 | A04 | bar: 4 to 16
Yes |  | PMO Review Project Progress with PM | 0 | PMO-G01
Yes |  | PMO Review Project Progress with CEO | 0 | PMO-G02
Yes |  | Approve Revised Baselines | 0 | PMO-G03
Yes |  | Addressing Impediments & Taking Decisions | 14 | PMO-G04 | bar: 4 to 16
|  | Authorize Next Phase/Project | 4 | PMO-G05 | bar: 4 to 16
Yes |  | Share Lessons Learned with Org /Other projects | 5 | PMO-G06 | bar: 4 to 16
Yes |  | Manage Org Level Project Metrics | 0 | PMO-G07
Yes |  | Org Level Risk Management | 0 | PMO-G08
Yes |  | Org Level Vendor & Inventory Management | 0 | PMO-G09
Yes |  | Stakehodler Engagement | 0 | PMO-G10
Note on H3: Highlevel Info download from PM to Core Team so that they can provide Plan of the Planning.
Note on J3: All the Processes followed here are Top-down approach and at Higher Level
Note on P3: All the Processes followed here are bottom-up approach and at Detail Level
Note on C8: New Process

## Sheet5
[5 empty] | 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  |  |  | Phases | StartUp | Kickoff |  | Planning & Design | 13: Dispatch; 14: Erection & Commissioning; 16: Closure
Umbrella Process | Org Level Process | Process Name | # Occurance | Process ID Stages | Receipt Advance | Project Kick-off with Maketting | Project Kick-off with Team | Project Setup | Prepare Overall Project Approach | Prepare/Approve Project Budget (cost, time) | Drawing Prepare/Approval | Prepare Detail Procurement Plan | Prepare Detail Manufacturing Plan | Prepare Detail Logistic Plan | Prepare Detail E&C Plan | Governance Plan | Finished Product Inspection by Customer/QA | Material Dispatch to site & stored at customer site | Erection | Commissioning | Project Closure
x | x | # Occrance |  |  | 0 | 3 |  | 5 | 28 | 18 | 19 | 25 | 30 | 31 | 30 | 6 | 9 | 19 | 19 |  | 4
|  | Prepare Project Charter | 1 | I01 |  | x
|  | Identify Stakeholders | 1 | I02 |  | x
| Yes | Configuration Management | 1 | P01 |  |  |  | x
| Yes | Scope, Time & Cost Management Plan | 2 | P25 | bar: 4 to 16
|  | Requirment Understanding | 3 | P02 |  |  | x | bar: 4 to 16
|  | Solutioning | 2 | P03 | bar: 4 to 16
|  | Scope Baselining | 3 | P04 |  |  | x | bar: 4 to 16
|  | Actvitity Identification & Sequencing | 6 | P05 |  |  | x | bar: 4 to 16
|  | Estimate Actvity Resource & Durations | 4 | P06 | bar: 4 to 16
|  | Schedule Development | 7 | P07 |  |  | x | bar: 4 to 16
|  | Activity Cost Etimation | 5 | P08 | bar: 4 to 16
|  | Budgeting with consolidated cost | 6 | P09 |  |  | x | bar: 4 to 16
|  | Project & Product Quality Planning | 5 | P10 | bar: 4 to 16
|  | Cost of Quality | 6 | P11 | bar: 4 to 16
Yes |  | Risk Identification | 14 | P12 |  | x | x | bar: 4 to 16
Yes |  | Risk Response Planning | 4 | P13 |  |  | x | bar: 4 to 16
|  | Cost of Risk Management | 5 | P14 | bar: 4 to 16
| Yes | HR& Staff Management Planning | 2 | P15 |  |  |  | x | bar: 4 to 16
| Yes | Cost of Training/Hiring/Appraisal etc. | 2 | P16 |  |  |  | x | bar: 4 to 16
|  | Procurement Planning | 7 | P17 |  |  | x | bar: 4 to 16
|  | Cost/Schedule of Contracting P/S/R | 5 | P18 | bar: 4 to 16
|  | Communication Planning & Tech | 5 | P19 | bar: 4 to 16
| Yes | Cost of Communication | 0 | P20
|  | Stakeholder Management Plan | 5 | P21 | bar: 4 to 16
|  | Cost of Stakeholder Engagement | 4 | P22 | bar: 4 to 16
|  | Consolidate all costs/schedule of activities | 5 | P23 | bar: 4 to 16
|  | Negotiate cost/schedule/quality/scope- Baseline Project | 5 | P24 | bar: 4 to 16
Yes |  | Work Authorization | 3 | E01 | bar: 4 to 16
Yes |  | Quality and Config Audit | 12 | E02 | bar: 4 to 16
| Yes | Resource Acquition | 1 | E03 |  |  |  | x
| Yes | Team Capablity Building | 1 | E04 |  |  |  | x
Yes |  | Team & Work Management | 8 | E05 | bar: 4 to 16
|  | Contracting | 2 | E06 | bar: 4 to 16
Yes |  | Project Planned/Ad-hoc Communications | 9 | E07 | bar: 4 to 16
Yes |  | Routine Stakeholder Engagement | 9 | E08 | bar: 4 to 16
Yes |  | Integrated Change Control | 9 | G01 | bar: 4 to 16
Yes |  | Report Prepration | 9 | G02 | bar: 4 to 16
Yes |  | Quality Variance Management | 9 | G03 | bar: 4 to 16
Yes |  | WorkProduct/ Product Review/Testing by QA | 3 | G04 | bar: 4 to 16
|  | Product Testing by Customer | 1 | G05 | bar: 4 to 16
Yes |  | CST Variance Management | 8 | G06 | bar: 4 to 16
Yes |  | Risk Reassessment | 11 | G07 | bar: 4 to 16
Yes |  | Risk Audit | 3 | G08 | bar: 4 to 16
|  | Contract P/S/R Management | 2 | G09 | bar: 4 to 16
Yes |  | Reassess conmmunication /engagement need | 10 | G10 | bar: 4 to 16
|  | Each Vendor Contract Closing | 1 | C01 | bar: 4 to 16
|  | Customer Sign off | 1 | C02 | bar: 4 to 16
|  | Phase or Project Closure | 1 | C03 | bar: 4 to 16
Yes |  | Daily Standup | 11 | A01 | bar: 4 to 16
Yes |  | Sprint Planning | 11 | A02 | bar: 4 to 16
Yes |  | Retrospective | 11 | A03 | bar: 4 to 16
Yes |  | Project Kanbanboard | 11 | A04 | bar: 4 to 16
Yes |  | PMO Review Project Progress with PM | 0 | PMO-G01
Yes |  | PMO Review Project Progress with CEO | 0 | PMO-G02
Yes |  | Approve Revised Baselines | 0 | PMO-G03
Yes |  | Addressing Impediments & Taking Decisions | 11 | PMO-G04 | bar: 4 to 16
|  | Authorize Next Phase/Project | 2 | PMO-G05 | bar: 4 to 16
Yes |  | Share Lessons Learned with Org /Other projects | 5 | PMO-G06 | bar: 4 to 16
Yes |  | Manage Org Level Project Metrics | 0 | PMO-G07
Yes |  | Org Level Risk Management | 0 | PMO-G08
Yes |  | Org Level Vendor & Inventory Management | 0 | PMO-G09
Yes |  | Stakehodler Engagement | 0 | PMO-G10
Note on H3: Highlevel Info download from PM to Core Team so that they can provide Plan of the Planning.
Note on J3: All the Processes followed here are Top-down approach and at Higher Level
Note on M3: Bottom-up approach and at Detail Level
Note on N3: Bottom-up approach and at Detail Level
Note on O3: Bottom-up approach and at Detail Level
Note on P3: Bottom-up approach and at Detail Level
Note on C8: New Process