## MilestoneLists
| Phases | Milestones
1 | StartUp | Receipt Advance
2 | Kickoff | Project Kick-off
3 | Planning & Design | Prepare Project Approach with Design, Manu, Proc, Logistic, Finance Department. Include project review plan.
4 |  | Prepare/Approve Project Budget (cost, time)
5 |  | Prepare/Approval (Drawing SLD/SA) from customer
6 |  | Prepare Detail Procurement, Manufacturing, Logistic & E&C Plan
7 |  | Prepare Detail Design and release TPS/BOM
8 |  | Vendor Finalization (proc, manu) & PO issuance
9 | Manufacturing | Manufactruing clearance
10 |  | Finished Product Inspection by Customer/QA
11 |  | Payment Collection from Customer
12 |  | Vendor Finalzation for Logistic
13 | Dispatch | Material Dispatch to site & stored at customer site
14 | Erection | Erection & Commissioning
15 | Closure | Project Closure

## Process List
Process ID | Process Name | Level | Input From | Output To
I01 | Prepare Project Charter
I02 | Identify Stakeholders
P01 | Configuration Management | PMO | All Departments
P02 | Requirment Understanding
P03 | Solutioning
P04 | Scope Baselining
P05 | Actvitity Identification & Sequencing
P06 | Estimate Actvity Resource & Durations
P07 | Schedule Development
P08 | Activity Cost Etimation
P09 | Budgeting with consolidated cost
P10 | Project & Product Quality Planning
P11 | Cost of Quality
P12 | Risk Identification
P13 | Risk Response Planning
P14 | Cost of Risk Management
P15 | HR& Staff Management Planning
P16 | Cost of Training/Hiring/Appraisal etc.
P17 | Procurement Planning
P18 | Cost/Schedule of Contracting P/S/R
P19 | Communication Planning & Tech
P20 | Cost of Communication
P21 | Stakeholder Management Plan
P22 | Cost of Stakeholder Engagement
P23 | Consolidate all costs/schedule of activities
P24 | Negotiate cost/schedule/quality/scope- Baseline Project
E01 | Work Authorization
E02 | Quality and Config Audit
E03 | Resource Acquition
E04 | Team Capablity Building
E05 | Team & Work Management
E06 | Contracting
E07 | Project Planned/Ad-hoc Communications
E08 | Routine Stakeholder Engagement
G01 | Integrated Change Control
G02 | Report Prepration
G03 | Quality Variance Management
G04 | Product Testing by QA
G05 | Product Testing by Customer
G06 | CST Variance Management
G07 | Risk Reassessment
G08 | Risk Audit
G09 | Contract P/S/R Management
G10 | Reassess configuration /engagement need
PMO-G01 | PMO Review Project Progress with PM
PMO-G02 | PMO Review Project Progress with CEO
PMO-G03 | Approve Revised Baselines
PMO-G04 | Addressing Impediments & Taking Decisions
PMO-G05 | Authorize Next Phase/Project
PMO-G06 | Share Lessons Learned with Org /Other projects
PMO-G07 | Manage Org Level Project Metrics
PMO-G08 | Org Level Risk Management
PMO-G09 | Org Level Vendor & Inventory Management
PMO-G10 | Stakehodler Engagemetn
C01 | Each Vendor Contract Closing
C02 | Customer Sign off
C03 | Phase or Project Closure
A01 | Daily Standup
A02 | Sprint Planning
A03 | Retrospective
A04 | Project Kanbanboard

## Mapping
[5 empty] | 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  |  |  | Phases | StartUp | Kickoff |  | Planning & Design | 13: Dispatch; 14: Erection & Commissioning; 16: Closure
Umbrella Process | Org Level Process | Process Name | # Occurance | Process ID Stages | Receipt Advance | Project Kick-off with Maketting | Project Kick-off with Team | Project Setup | Prepare Overall Project Approach | Prepare/Approve Project Budget (cost, time) | Drawing Prepare/Approval | Prepare Detail Procurement Plan | Prepare Detail Manufacturing Plan | Prepare Detail Logistic Plan | Prepare Detail E&C Plan | Governance Plan | Finished Product Inspection by Customer/QA | Material Dispatch to site & stored at customer site | Erection | Commissioning | Project Closure
x | x | # Occrance |  |  | 0 | 3 |  | 5 | 28 | 18 | 19 | 25 | 30 | 31 | 30 | 6 | 9 | 19 | 19 |  | 4
|  | Prepare Project Charter | 1 | I01 |  | x
|  | Identify Stakeholders | 1 | I02 |  | x
| Yes | Configuration Management | 1 | P01 |  |  |  | x
| Yes | Scope, Time & Cost Management Plan | 2 | P25 | bar: 4 to 16
|  | Requirment Understanding | 3 | P02 |  |  | x | bar: 4 to 16
|  | Solutioning | 2 | P03 | bar: 4 to 16
|  | Scope Baselining | 3 | P04 |  |  | x | bar: 4 to 16
|  | Actvitity Identification & Sequencing | 6 | P05 |  |  | x | bar: 4 to 16
|  | Estimate Actvity Resource & Durations | 4 | P06 | bar: 4 to 16
|  | Schedule Development | 7 | P07 |  |  | x | bar: 4 to 16
|  | Activity Cost Etimation | 5 | P08 | bar: 4 to 16
|  | Budgeting with consolidated cost | 6 | P09 |  |  | x | bar: 4 to 16
|  | Project & Product Quality Planning | 5 | P10 | bar: 4 to 16
|  | Cost of Quality | 6 | P11 | bar: 4 to 16
Yes |  | Risk Identification | 14 | P12 |  | x | x | bar: 4 to 16
Yes |  | Risk Response Planning | 4 | P13 |  |  | x | bar: 4 to 16
|  | Cost of Risk Management | 5 | P14 | bar: 4 to 16
| Yes | HR& Staff Management Planning | 2 | P15 |  |  |  | x | bar: 4 to 16
| Yes | Cost of Training/Hiring/Appraisal etc. | 2 | P16 |  |  |  | x | bar: 4 to 16
|  | Procurement Planning | 7 | P17 |  |  | x | bar: 4 to 16
|  | Cost/Schedule of Contracting P/S/R | 5 | P18 | bar: 4 to 16
|  | Communication Planning & Tech | 5 | P19 | bar: 4 to 16
| Yes | Cost of Communication | 0 | P20
|  | Stakeholder Management Plan | 5 | P21 | bar: 4 to 16
|  | Cost of Stakeholder Engagement | 4 | P22 | bar: 4 to 16
|  | Consolidate all costs/schedule of activities | 5 | P23 | bar: 4 to 16
|  | Negotiate cost/schedule/quality/scope- Baseline Project | 5 | P24 | bar: 4 to 16
Yes |  | Work Authorization | 3 | E01 | bar: 4 to 16
Yes |  | Quality and Config Audit | 12 | E02 | bar: 4 to 16
| Yes | Resource Acquition | 1 | E03 |  |  |  | x
| Yes | Team Capablity Building | 1 | E04 |  |  |  | x
Yes |  | Team & Work Management | 8 | E05 | bar: 4 to 16
|  | Contracting | 2 | E06 | bar: 4 to 16
Yes |  | Project Planned/Ad-hoc Communications | 9 | E07 | bar: 4 to 16
Yes |  | Routine Stakeholder Engagement | 9 | E08 | bar: 4 to 16
Yes |  | Integrated Change Control | 9 | G01 | bar: 4 to 16
Yes |  | Report Prepration | 9 | G02 | bar: 4 to 16
Yes |  | Quality Variance Management | 9 | G03 | bar: 4 to 16
Yes |  | WorkProduct/ Product Review/Testing by QA | 3 | G04 | bar: 4 to 16
|  | Product Testing by Customer | 1 | G05 | bar: 4 to 16
Yes |  | CST Variance Management | 8 | G06 | bar: 4 to 16
Yes |  | Risk Reassessment | 11 | G07 | bar: 4 to 16
Yes |  | Risk Audit | 3 | G08 | bar: 4 to 16
|  | Contract P/S/R Management | 2 | G09 | bar: 4 to 16
Yes |  | Reassess conmmunication /engagement need | 10 | G10 | bar: 4 to 16
|  | Each Vendor Contract Closing | 1 | C01 | bar: 4 to 16
|  | Customer Sign off | 1 | C02 | bar: 4 to 16
|  | Phase or Project Closure | 1 | C03 | bar: 4 to 16
Yes |  | Daily Standup | 11 | A01 | bar: 4 to 16
Yes |  | Sprint Planning | 11 | A02 | bar: 4 to 16
Yes |  | Retrospective | 11 | A03 | bar: 4 to 16
Yes |  | Project Kanbanboard | 11 | A04 | bar: 4 to 16
Yes |  | PMO Review Project Progress with PM | 0 | PMO-G01
Yes |  | PMO Review Project Progress with CEO | 0 | PMO-G02
Yes |  | Approve Revised Baselines | 0 | PMO-G03
Yes |  | Addressing Impediments & Taking Decisions | 11 | PMO-G04 | bar: 4 to 16
|  | Authorize Next Phase/Project | 2 | PMO-G05 | bar: 4 to 16
Yes |  | Share Lessons Learned with Org /Other projects | 5 | PMO-G06 | bar: 4 to 16
Yes |  | Manage Org Level Project Metrics | 0 | PMO-G07
Yes |  | Org Level Risk Management | 0 | PMO-G08
Yes |  | Org Level Vendor & Inventory Management | 0 | PMO-G09
Yes |  | Stakehodler Engagement | 0 | PMO-G10
Note on H3: Highlevel Info download from PM to Core Team so that they can provide Plan of the Planning.
Note on J3: All the Processes followed here are Top-down approach and at Higher Level
Note on M3: Bottom-up approach and at Detail Level
Note on N3: Bottom-up approach and at Detail Level
Note on O3: Bottom-up approach and at Detail Level
Note on P3: Bottom-up approach and at Detail Level
Note on C8: New Process

## Sheet1
| Horst-Details | Horst Summary | Dinesh & Kumar |  | Hari Thapliyal
Work Type | Stage Name | Stage Name | Stage Name | Understanding | Stage Name | Remarks | Questions?
| 1. Receipt of advance from customer | Project starts with the advance received from customer (1) | 1. Receipt of Advance from customer | Ok | Receipt Advance
Initiation | 2. Confirmed taking over by Project Management (detailed briefing from Marketing, confirmation of Project Baseline, understanding of Scope, Timeline, Cost, Risk) | PMO takes over the project/contract from Marketing during a detailed briefing (2) | 2. Project Kick-off –Project / contract details briefing from marketing to execution team. | Ok | Project Kick-off with Marketing
Planning | 3. Draft of Project Framework by PMO (Project Team, Schedule, Budget, Risk Assessment, Risk Containment, Quality Plan) | All functions prepare their work schedule according to the contractual obligations (3a-e) and |  | Ok | Project Kick-off with Team & Department Level Plan
Plan-Design | a. Design Kick-off – MSD & ESD with PMO for understanding and clarifying the technical aspects of the project. Confirmed Project Scope of supply by MSD and ESD, confirmed time line for drawing availability |  | 3. Design Kick-off – MSD & ESD with Marketing for understanding and clarifying the technicalaspects of the project. | Ok | Design HLP
Plan-Manuf. | b. Manufacturing Kick-off – MSD, E&C, QA with Manufacturing for understanding and clarifying the technical aspects of the project and on schedule of release of documents for procurement and production. |  | 4. Manufacturing Kick-off – MSD, E&C, QAwith Manufacturing for understanding and clarifying the technical aspects of the project and on schedule of release of documents for procurement and production. | Ok | Manufacturing HLP
Plan-Proc | c. Procurement Kick-off - list of suppliers (as per contract). Delivery schedule prepared as per project schedule plan and scope of supply |  |  | Ok | Procurement HLP
Plan-Logs. | d. Logistic plan and strategy (point-to-point) |  |  | Ok | Logistic HLP
Plan-Fin. | e. Finance Kick off – On commercial terms of the contract & risk mitigation plan. Preparation of Billing Break-up |  | 5. Finance Kick off – On commercial terms of the contract & risk mitigation plan. | Ok | Finance HLP
Plan-Design |  |  | 6. Release of Project Scope of supply by MSD and ESD | Ok
Plan-Proc |  |  | 7. Preparation of Billing Break-up | Ok
Plan-Proc |  |  | 8. Procurement to prepare the list of suppliers as per contract, commercial terms &conditions. Delivery schedule and logistic plan prepared as per project schedule plan. | Ok
Plan-Design |  |  | 9. Release of Design Document Schedule for customer submission by MSD and ESD | Ok
Planning |  |  |  |  | Project Setup
Plan-PM | 4. Project Planning – Final Budget for approval (Confirmed time line, Cost, Risk, Quality) PMO/HOD/COO signoff | provide this input to the PMO in order to prepare the project plan for sign off by PMO/COO (4) | 10. Project schedule plan – inputs from Design, Mfg., Procurement & E&C | Ok | Consolidate & Prepare Detail Project Plan
Plan-PM | a. Project Budget preparation including execution strategy, contract summary, confirmed dates (Gantt chart) |  |  | Ok
Plan-PM | 5. Approved project plan |  | 11. Project Budget preparation including execution strategy, contract summary, need dates ( Gantt chart) including HOD/COO signoff | Ok | Approve Project Budget (cost, time)
Plan-PM | a. Internal (Budget Approval by MD) | The Sign Off by PMO/COO (4) is the prerequisite for approval by MD (5a) | 12. Budget Approval by MD | Ok
Plan-PM | b. External (customer) | After Approval by MD (5a) PMO communicates and agrees the Project Plan with the customer (5b) |  | Ok
Plan-Design | 6. Drawing approval |  |  | Ok | Prepare/Approve Detail Drawing
Plan-Design | a. Preliminary Internal review |  |  | Ok
Plan-Design | b. Approval by customer |  | 13. Release of Preliminary drawings (SLD & S.A) and QAP for customer approval | Ok
Plan-Design |  |  | 14. Receipt of Customer Approval on Preliminary drawings (SLD & S.A) and QAP | Ok
Plan-PM | 11. Project review meetings, reporting | PMO follows up on adherence according to the Project Plan and documents progress (11) |  | Ok | Governance Plan
Plan-PM | a. Communication strategy |  |  | Ok
Plan-PM | b. Time schedule |  |  | Ok
Plan-PM | c. Cost |  |  | Ok
Plan-PM | d. Risk |  |  | Ok
Plan-PM | e. Quality (NCR management) |  |  | Ok
Plan-PM | f. Claim management |  |  | Ok
Proc. | 7. Confirmed Procurement Plan (Time, Cost, Quality) | On the basis of the Project Plan (5) the Functional Team Member starts to perform their work (processes, work flow) according to the Input their function have provided as basis for the Project Plan (7, 8, 9, 10) |  | Ok | Procurement Work
Exec-Proc | a. Approved list of qualified supplier rating (global and local) |  |  | Ok | Approved Supplier Rating List
Exec-Proc | b. Release of TPS/BOM from design to procurement |  | 15. Release of TPS/BOM from design to procurement | Ok | TPS/BOM to Procurment | Optional
Exec-Proc | c. Request for quotation |  | 16. Request For Quotation | Ok | RFQ
Exec-Proc | d. Release of PO |  | 17. Release of PO | Ok | Release PO
M&C-Proc | e. Review and approval of designs received from suppliers |  | 18. Review and approval of designs received from suppliers | Ok | Review and Approval of Supplier Designs
M&C-Proc |  |  | 19. Receipt of Project Milestone payments | Ok
Exec-Proc | f. Issuance of Manufacturing clearance to suppliers |  | 20. Issuance of Manufacturing clearance to suppliers | Ok | Manufacturing Clearance
M&C-Proc | g. Expediting (procurement team member follow up on confirmed delivery dates, quantity, quality, cost) |  | 21. Inspection of Goods | Ok | Procurement Followup
Exec-Proc |  |  | 22. Payment Collection from customer towards dispatch ( depends on agreed terms – LC/ RTGS) | Ok
Manuf. | 8. Confirmed Manufacturing Plan (Time, Cost, Quality) |  |  | Ok | Prepare Detail Manufacturing Plan
Exec-Design | a. Release of TPS/BOM from design to manufacturing |  |  | Ok | TPS/BOM to Manufacturing
Plan-Manuf | b. Manufacturing plan |  |  | Ok | Manufacturing Plan
M&C-Manuf | c. Expediting (manufacturing team member follow up on confirmed delivery dates, quantity, quality, cost) |  |  | ?? | Manufacturing Followup |  | Is it same as followup?
Logs. | 9. Confirmed Logistics Plan (Time, Cost, Quality) |  |  | Ok | Prepare Detail Logistic Plan
Exec-Logs. | a. Selection of logistics partner (FOB, CIF) |  |  | Ok | Select Logistic Partners
Exec-Logs. | b. Selection of local logistic partner (clearance from customs, transportation to site, storage) |  |  | Ok | Select Local Logistic Partners
Plan-Logs. | c. Preparation of logistic planning |  |  | Ok | Prepare Logistic Plan
M&C-Logs. | d. Expediting (logistics team member follow up on confirmed logistics plan) |  |  | ?? | Logistic Followup |  | Is it same as followup?
E&C. | 10. Confirmed Erection and commissioning Plan (Time, Cost, Quality) |  |  | Ok | Prepare Detail E&C Plan
Plan-E&C | a. Time schedule |  |  | Ok | Prepare E&C Schedule
Plan-E&C | b. Manpower plan |  |  | Ok | Prepare E&C Manpower Plan
Plan-E&C | c. Erection manuals |  |  | ?? | Prepare Erection Manual |  | For what purpose is this manual?
Manuf | 12. Inspection of Goods, clearance by customer | Contractual hold points are observed during execution (12) |  | Ok | Finished Product Inspection by Customer/QA
M&C-Manuf | a. Payment Collection from customer towards dispatch ( depends on agreed terms – LC/ RTGS) |  |  | Ok | Payment Collection from Customer
Dispatch | 13. Dispatch | Dispatch will performed as per the execution strategy (13) | 23. Dispatch | Ok | Material Dispatch to site & stored at customer site
Exec-Dispatch | a. Receipt of materials |  | 24. Receipt of materials in good condition at CFS/Site | Ok | Material Receipt by Customer
Exec-Dispatch | b. Formal taking over by customer |  |  | ?? | Formal inspection by customer |  | Does customer do inspection here?
Exec-Dispatch | c. Storage & Security requirements (definition and check-up) |  | 25. Storage & Security requirements | Ok | Material Storage & Security Plan |  | Do you prepare Storage & Security plan? Where?
Erec. | 14. Erection execution (hold points reached and accepted) and Pre Commissioning acceptance | Erection execution (or supervision) will be performed (14) by E&C according to the plan provided under (10) | 26. Erection and commissioning activities | Ok | Erection
Exec-Erec |  |  | 27. Proving of Machines under available hydrological parameters | Ok
Comm. | 15. Commissioning | Commissioning will be performed (15) by E&C as provided under (10) |  | Ok | Commissioning
M&C-Comm | a. Documentation of closure of all project related NCRs |  |  | Ok | Doc NCR Status |  | NCR meas Non-compliance?
M&C-Comm | b. Documentation of unit performance |  |  | Ok | Document Unit Performance
Exec-Comm. | c. Creation of punch list, (provisional taking over) |  | 28. Creation and compliance of punch points | Ok | Create Punch List
Closing | 16. Project Closure activities external (final taking over) | PMO will perform formal project closure (16) | 29. Project Closure activities including handover formalities, reconciliation, claim settlement and receipt of retention. | Ok | Project Closure
Closing | a. handover formalities, |  |  | Ok
Closing | b. reconciliation, |  |  | Ok
Closing | c. Closing of punch points |  |  | Ok
Closing | d. Claim settlement and receipt of retention. |  |  | Ok
Closing | 17. Project Closure activities internal (lessons learned) | PMO will ensure the documentation and implementation of lessons learned (17) |  | Ok
Note on F5: Highlevel Info download from PM to Core Team so that they can provide Plan of the Planning.
Note on F16: All the Processes followed here are Top-down approach and at Higher Level
Note on B25: Sequence Changed

## Sheet2
1 | Receipt Advance
2 | Project Kick-off with Marketing
3 | Project Kick-off with Team & Department Level Plan
4 | Design HLP
5 | Manufacturing HLP
6 | Procurement HLP
7 | Logistic HLP
8 | Finance HLP
13 | Project Setup
14 | Consolidate & Prepare Detail Project Plan
16 | Approve Project Budget (cost, time)
19 | Prepare/Approve Detail Drawing
23 | Governance Plan
30 | Procurement Work
31 | Approved Supplier Rating List
32 | TPS/BOM to Procurment
33 | RFQ
34 | Release PO
35 | Review and Approval of Supplier Designs
37 | Manufacturing Clearance
38 | Procurement Followup
40 | Prepare Detail Manufacturing Plan
41 | TPS/BOM to Manufacturing
42 | Manufacturing Plan
43 | Manufacturing Followup
44 | Prepare Detail Logistic Plan
45 | Select Logistic Partners
46 | Select Local Logistic Partners
47 | Prepare Logistic Plan
48 | Logistic Followup
49 | Prepare Detail E&C Plan
50 | Prepare E&C Schedule
51 | Prepare E&C Manpower Plan
52 | Prepare Erection Manual
53 | Finished Product Inspection by Customer/QA
54 | Payment Collection from Customer
55 | Material Dispatch to site & stored at customer site
56 | Material Receipt by Customer
57 | Formal inspection by customer
58 | Material Storage & Security Plan
59 | Erection
61 | Commissioning
62 | Doc NCR Status
63 | Document Unit Performance
64 | Create Punch List
65 | Project Closure
Note on B3: Highlevel Info download from PM to Core Team so that they can provide Plan of the Planning.
Note on B10: All the Processes followed here are Top-down approach and at Higher Level