## MilestoneLists
| Phases | Milestones
1 | StartUp | Receipt Advance | Receipt Advance
2 | Kickoff | Project Kick-off | Project Kick-off with Marketing
3 | Planning & Design | Prepare Project Approach with Design, Manu, Proc, Logistic, Finance Department. Include project review plan. | Project Kick-off with Team & Department Level Plan
Project Setup
Consolidate & Prepare Detail Project Plan
4 |  | Prepare/Approve Project Budget (cost, time) | Approve Project Budget (cost, time)
5 |  | Prepare/Approval (Drawing SLD/SA) from customer | Prepare/Approve Detail Drawing
Governance Plan
6 |  | Prepare Detail Procurement, Manufacturing, Logistic & E&C Plan | Procurement Work
7 |  | Prepare Detail Design and release TPS/BOM | Prepare Detail Manufacturing Plan
8 |  | Vendor Finalization (proc, manu) & PO issuance | Prepare Detail Logistic Plan
9 | Manufacturing | Manufactruing clearance | Prepare Detail E&C Plan
10 |  | Finished Product Inspection by Customer/QA | Finished Product Inspection by Customer/QA
11 |  | Payment Collection from Customer | Material Dispatch to site & stored at customer site
12 |  | Vendor Finalzation for Logistic | Erection
13 | Dispatch | Material Dispatch to site & stored at customer site | Commissioning
14 | Erection | Erection & Commissioning | Project Closure
15 | Closure | Project Closure

## Process List
Process ID | Process Name | Level | Input From | Output To
I01 | Prepare Project Charter
I02 | Identify Stakeholders
P01 | Configuration Management | PMO | All Departments
P02 | Requirment Understanding
P03 | Solutioning
P04 | Scope Baselining
P05 | Actvitity Identification & Sequencing
P06 | Estimate Actvity Resource & Durations
P07 | Schedule Development
P08 | Activity Cost Etimation
P09 | Budgeting with consolidated cost
P10 | Project & Product Quality Planning
P11 | Cost of Quality
P12 | Risk Identification
P13 | Risk Response Planning
P14 | Cost of Risk Management
P15 | HR& Staff Management Planning
P16 | Cost of Training/Hiring/Appraisal etc.
P17 | Procurement Planning
P18 | Cost/Schedule of Contracting P/S/R
P19 | Communication Planning & Tech
P20 | Cost of Communication
P21 | Stakeholder Management Plan
P22 | Cost of Stakeholder Engagement
P23 | Consolidate all costs/schedule of activities
P24 | Negotiate cost/schedule/quality/scope- Baseline Project
E01 | Work Authorization
E02 | Quality and Config Audit
E03 | Resource Acquition
E04 | Team Capablity Building
E05 | Team & Work Management
E06 | Contracting
E07 | Project Planned/Ad-hoc Communications
E08 | Routine Stakeholder Engagement
G01 | Integrated Change Control
G02 | Report Prepration
G03 | Quality Variance Management
G04 | Product Testing by QA
G05 | Product Testing by Customer
G06 | CST Variance Management
G07 | Risk Reassessment
G08 | Risk Audit
G09 | Contract P/S/R Management
G10 | Reassess configuration /engagement need
PMO-G01 | PMO Review Project Progress with PM
PMO-G02 | PMO Review Project Progress with CEO
PMO-G03 | Approve Revised Baselines
PMO-G04 | Addressing Impediments & Taking Decisions
PMO-G05 | Authorize Next Phase/Project
PMO-G06 | Share Lessons Learned with Org /Other projects
PMO-G07 | Manage Org Level Project Metrics
PMO-G08 | Org Level Risk Management
PMO-G09 | Org Level Vendor & Inventory Management
PMO-G10 | Stakehodler Engagemetn
C01 | Each Vendor Contract Closing
C02 | Customer Sign off
C03 | Phase or Project Closure
A01 | Daily Standup
A02 | Sprint Planning
A03 | Retrospective
A04 | Project Kanbanboard

## WIP
| Horst-Details | Horst Summary | Dinesh & Kumar |  | Hari Thapliyal
Work Type | Stage Name | Stage Name | Stage Name | Understanding | Stage Name | Remarks | Questions?
| 1. Receipt of advance from customer | Project starts with the advance received from customer (1) | 1. Receipt of Advance from customer | Ok | Receipt Advance
Initiation | 2. Confirmed taking over by Project Management (detailed briefing from Marketing, confirmation of Project Baseline, understanding of Scope, Timeline, Cost, Risk) | PMO takes over the project/contract from Marketing during a detailed briefing (2) | 2. Project Kick-off –Project / contract details briefing from marketing to execution team. | Ok | Project Kick-off with Marketing
Planning | 3. Draft of Project Framework by PMO (Project Team, Schedule, Budget, Risk Assessment, Risk Containment, Quality Plan) | All functions prepare their work schedule according to the contractual obligations (3a-e) and |  | Ok | Project Kick-off with Team & Department Level Plan
Plan-Design | a. Design Kick-off – MSD & ESD with PMO for understanding and clarifying the technical aspects of the project. Confirmed Project Scope of supply by MSD and ESD, confirmed time line for drawing availability |  | 3. Design Kick-off – MSD & ESD with Marketing for understanding and clarifying the technicalaspects of the project. | Ok | Design HLP
Plan-Manuf. | b. Manufacturing Kick-off – MSD, E&C, QA with Manufacturing for understanding and clarifying the technical aspects of the project and on schedule of release of documents for procurement and production. |  | 4. Manufacturing Kick-off – MSD, E&C, QAwith Manufacturing for understanding and clarifying the technical aspects of the project and on schedule of release of documents for procurement and production. | Ok | Manufacturing HLP
Plan-Proc | c. Procurement Kick-off - list of suppliers (as per contract). Delivery schedule prepared as per project schedule plan and scope of supply |  |  | Ok | Procurement HLP
Plan-Logs. | d. Logistic plan and strategy (point-to-point) |  |  | Ok | Logistic HLP
Plan-Fin. | e. Finance Kick off – On commercial terms of the contract & risk mitigation plan. Preparation of Billing Break-up |  | 5. Finance Kick off – On commercial terms of the contract & risk mitigation plan. | Ok | Finance HLP
Plan-Design |  |  | 6. Release of Project Scope of supply by MSD and ESD | Ok
Plan-Proc |  |  | 7. Preparation of Billing Break-up | Ok
Plan-Proc |  |  | 8. Procurement to prepare the list of suppliers as per contract, commercial terms &conditions. Delivery schedule and logistic plan prepared as per project schedule plan. | Ok
Plan-Design |  |  | 9. Release of Design Document Schedule for customer submission by MSD and ESD | Ok
Planning |  |  |  |  | Project Setup
Plan-PM | 4. Project Planning – Final Budget for approval (Confirmed time line, Cost, Risk, Quality) PMO/HOD/COO signoff | provide this input to the PMO in order to prepare the project plan for sign off by PMO/COO (4) | 10. Project schedule plan – inputs from Design, Mfg., Procurement & E&C | Ok | Consolidate & Prepare Detail Project Plan
Plan-PM | a. Project Budget preparation including execution strategy, contract summary, confirmed dates (Gantt chart) |  |  | Ok
Plan-PM | 5. Approved project plan |  | 11. Project Budget preparation including execution strategy, contract summary, need dates ( Gantt chart) including HOD/COO signoff | Ok | Approve Project Budget (cost, time)
Plan-PM | a. Internal (Budget Approval by MD) | The Sign Off by PMO/COO (4) is the prerequisite for approval by MD (5a) | 12. Budget Approval by MD | Ok
Plan-PM | b. External (customer) | After Approval by MD (5a) PMO communicates and agrees the Project Plan with the customer (5b) |  | Ok
Plan-Design | 6. Drawing approval |  |  | Ok | Prepare/Approve Detail Drawing
Plan-Design | a. Preliminary Internal review |  |  | Ok
Plan-Design | b. Approval by customer |  | 13. Release of Preliminary drawings (SLD & S.A) and QAP for customer approval | Ok
Plan-Design |  |  | 14. Receipt of Customer Approval on Preliminary drawings (SLD & S.A) and QAP | Ok
Plan-PM | 11. Project review meetings, reporting | PMO follows up on adherence according to the Project Plan and documents progress (11) |  | Ok | Governance Plan
Plan-PM | a. Communication strategy |  |  | Ok
Plan-PM | b. Time schedule |  |  | Ok
Plan-PM | c. Cost |  |  | Ok
Plan-PM | d. Risk |  |  | Ok
Plan-PM | e. Quality (NCR management) |  |  | Ok
Plan-PM | f. Claim management |  |  | Ok
Proc. | 7. Confirmed Procurement Plan (Time, Cost, Quality) | On the basis of the Project Plan (5) the Functional Team Member starts to perform their work (processes, work flow) according to the Input their function have provided as basis for the Project Plan (7, 8, 9, 10) |  | Ok | Procurement Work
Exec-Proc | a. Approved list of qualified supplier rating (global and local) |  |  | Ok | Approved Supplier Rating List
Exec-Proc | b. Release of TPS/BOM from design to procurement |  | 15. Release of TPS/BOM from design to procurement | Ok | TPS/BOM to Procurment | Optional
Exec-Proc | c. Request for quotation |  | 16. Request For Quotation | Ok | RFQ
Exec-Proc | d. Release of PO |  | 17. Release of PO | Ok | Release PO
M&C-Proc | e. Review and approval of designs received from suppliers |  | 18. Review and approval of designs received from suppliers | Ok | Review and Approval of Supplier Designs
M&C-Proc |  |  | 19. Receipt of Project Milestone payments | Ok
M&C-Proc | f. Issuance of Manufacturing clearance to suppliers |  | 20. Issuance of Manufacturing clearance to suppliers | Ok | Manufacturing Clearance
M&C-Proc | g. Expediting (procurement team member follow up on confirmed delivery dates, quantity, quality, cost) |  | 21. Inspection of Goods | Ok | Procurement Followup
Exec-Proc |  |  | 22. Payment Collection from customer towards dispatch ( depends on agreed terms – LC/ RTGS) | Ok
Manuf. | 8. Confirmed Manufacturing Plan (Time, Cost, Quality) |  |  | Ok | Prepare Detail Manufacturing Plan
Exec-Design | a. Release of TPS/BOM from design to manufacturing |  |  | Ok | TPS/BOM to Manufacturing
Plan-Manuf | b. Manufacturing plan |  |  | Ok | Manufacturing Plan
M&C-Manuf | c. Expediting (manufacturing team member follow up on confirmed delivery dates, quantity, quality, cost) |  |  | ?? | Manufacturing Followup |  | Is it same as followup?
Logs. | 9. Confirmed Logistics Plan (Time, Cost, Quality) |  |  | Ok | Prepare Detail Logistic Plan
Plan-Logs. | a. Selection of logistics partner (FOB, CIF) |  |  | Ok | Select Logistic Partners
Plan-Logs. | b. Selection of local logistic partner (clearance from customs, transportation to site, storage) |  |  | Ok | Select Local Logistic Partners
Plan-Logs. | c. Preparation of logistic planning |  |  | Ok | Prepare Logistic Plan
M&C-Logs. | d. Expediting (logistics team member follow up on confirmed logistics plan) |  |  | ?? | Logistic Followup |  | Is it same as followup?
E&C. | 10. Confirmed Erection and commissioning Plan (Time, Cost, Quality) |  |  | Ok | Prepare Detail E&C Plan
Plan-E&C | a. Time schedule |  |  | Ok | Prepare E&C Schedule
Plan-E&C | b. Manpower plan |  |  | Ok | Prepare E&C Manpower Plan
Plan-E&C | c. Erection manuals |  |  | ?? | Prepare Erection Manual |  | For what purpose is this manual?
Manuf | 12. Inspection of Goods, clearance by customer | Contractual hold points are observed during execution (12) |  | Ok | Finished Product Inspection by Customer/QA
M&C-Manuf | a. Payment Collection from customer towards dispatch ( depends on agreed terms – LC/ RTGS) |  |  | Ok | Payment Collection from Customer
Dispatch | 13. Dispatch | Dispatch will performed as per the execution strategy (13) | 23. Dispatch | Ok | Material Dispatch to site & stored at customer site
Exec-Dispatch | a. Receipt of materials |  | 24. Receipt of materials in good condition at CFS/Site | Ok | Material Receipt by Customer
Exec-Dispatch | b. Formal taking over by customer |  |  | ?? | Formal inspection by customer |  | Does customer do inspection here?
Exec-Dispatch | c. Storage & Security requirements (definition and check-up) |  | 25. Storage & Security requirements | Ok | Material Storage & Security Plan |  | Do you prepare Storage & Security plan? Where? | Standard plan at org level
Erection | 14. Erection execution (hold points reached and accepted) and Pre Commissioning acceptance | Erection execution (or supervision) will be performed (14) by E&C according to the plan provided under (10) | 26. Erection and commissioning activities | Ok | Erection
Exec-Erec |  |  | 27. Proving of Machines under available hydrological parameters | Ok
Comm. | 15. Commissioning | Commissioning will be performed (15) by E&C as provided under (10) |  | Ok | Commissioning
M&C-Comm | a. Documentation of closure of all project related NCRs |  |  | Ok | Doc NCR Status |  | NCR meas Non-conformance?
M&C-Comm | b. Documentation of unit performance |  |  | Ok | Document Unit Performance
Exec-Comm. | c. Creation of punch list, (provisional taking over) |  | 28. Creation and compliance of punch points | Ok | Create Punch List
Closing | 16. Project Closure activities external (final taking over) | PMO will perform formal project closure (16) | 29. Project Closure activities including handover formalities, reconciliation, claim settlement and receipt of retention. | Ok | Project Closure
Closing | a. handover formalities, |  |  | Ok
Closing | b. reconciliation, |  |  | Ok
Closing | c. Closing of punch points |  |  | Ok
Closing | d. Claim settlement and receipt of retention. |  |  | Ok
Closing | 17. Project Closure activities internal (lessons learned) | PMO will ensure the documentation and implementation of lessons learned (17) |  | Ok
Note on F5: Highlevel Info download from PM to Core Team so that they can provide Plan of the Planning.
Note on F16: All the Processes followed here are Top-down approach and at Higher Level
Note on B25: Sequence Changed

## Mapping
[6 empty] | Work Type |  | Initiation | Plan-Overall | Plan-Design | Plan-Manuf. | Plan-Proc | Plan-Logs. | Plan-Fin. | Plan-Overall | Plan-PM | Plan-PM | Plan-PM | Plan-Overall | Proc. | Proc. | Exec-Design | Exec-Proc | Exec-Proc | Exec-Proc | M&C-Proc | M&C-Proc | Manf. | Exec-Design | Plan-Manuf | M&C-Manuf | Logs. | Plan-Logs. | Plan-Logs. | Plan-Logs. | M&C-Logs. | E&C. | Plan-E&C | Plan-E&C | Plan-E&C | Manf. | M&C-Manuf | Dispatch | Exec-Dispatch | Exec-Dispatch | Exec-Dispatch | Erection | Comm. | M&C-Comm | M&C-Comm | Exec-Comm. | Closing
[7 empty] | 1 | 2 | 3 | 3.a. | 3.b. | 3.c. | 3.d. | 3.e. |  | 4 | 5 | 6 | 11 | 7 | 7.a. | 7.b. | 7.c. | 7.d. | 7.e. | 7.f. | 7.g. | 8 | 8.a. | 8.b. | 8.c. | 9 | 9.a. | 9.b. | 9.c. | 9.d. | 10 | 10.a. | 10.b. | 10.c. | 12 | 12.A. | 13 | 13.a | 13.b | 13.c | 14 | 15 | 15.a | 15.b | 15.c | 16
Umbrella Process | Org Level Process | Process Type | Process Name | Definition | # Occurance | Process ID Stages | Receipt Advance | Project Kick-off with Marketing | Project Kick-off with Team & Department Level Plan | Design HLP | Manufacturing HLP | Procurement HLP | Logistic HLP | Finance HLP | Project Setup | Consolidate & Prepare Detail Project Plan | Approve Project Budget (cost, time) | Prepare/Approve Detail Drawing | Governance Plan | Procurement Work | Approved Supplier Rating List | TPS/BOM to Procurment | RFQ | Release PO | Review and Approval of Supplier Designs | Manufacturing Clearance | Procurement Followup | Manufacturing Work | TPS/BOM to Manufacturing | Manufacturing Plan | Manufacturing Followup | Prepare Detail Logistic Plan | Select Logistic Partners | Select Local Logistic Partners | Prepare Logistic Plan | Logistic Followup | Prepare Detail E&C Plan | Prepare E&C Schedule | Prepare E&C Manpower Plan | Prepare Erection Manual | Finished Product Inspection by Customer/QA | Payment Collection from Customer | Material Dispatch to site & stored at customer site | Material Receipt by Customer | Formal inspection by customer | Material Storage & Security Plan | Erection | Commissioning | Doc NCR Status | Document Unit Performance | Create Punch List | Project Closure
x | x |  | # Occrance |  |  |  | 0 | 3 | 24 | 0 | 0 | 0 | 0 | 0 | 5 | 31 | 13 | 17 | 6 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 28 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 23 | 6 | 0 | 0 | 25 | 0 | 20 | 0 | 0 | 0 | 29 | 24 | 0 | 0 | 0 | 10
|  | I | Prepare Project Charter | Write project summary in a 2 page template, assign PM and initial team to project and empower project manager to make a plan. After the plan is approved PM is empowered to use project resoures for the project. | 1 | I01 |  | x
|  | I | Identify Stakeholders | List all the stakeholders and their characterstics in a defined template | 1 | I02 |  | x
| Yes | P | Configuration Management & Work Authorization System | Define a system to manage all kind of document. A system to authorize any work to project team, contractor etc. | 1 | P01 | [8 empty] | x
| Yes | P | Scope, Time & Cost Management Plan | Define how scope, time, cost will be understood, estimated, planned, controlled, negotiated. | 4 | P25 |  |  | x | [6 empty] | x |  |  | x | [18 empty] | x
|  | P | Requirment Understanding | Prepare detail requirment documents. | 3 | P02 |  |  | x | [6 empty] | x |  | x
|  | P | Solutioning | Prepare drawing all kind of drawing and designs. | 3 | P03 |  |  | x | [6 empty] | x |  | x
|  | P | Scope Baselining | Prepare WBS & WBS dictionary and baseline scope along with detail requirements and drawings. | 3 | P04 |  |  | x | [6 empty] | x |  | x
|  | P | Actvitity Identification & Sequencing | List all acitivities their types and dependencies. | 8 | P05 |  |  | x | [6 empty] | x |  | x | [9 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x | [5 empty] | x
|  | P | Estimate Actvity Resource & Durations | Estimate resources and duration of every activity | 8 | P06 |  |  | x | [6 empty] | x |  | x | [9 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x | [5 empty] | x
|  | P | Schedule Development | Identify critical path and finalize the schedule as per the contractual constraint | 9 | P07 |  |  | x | [6 empty] | x | x | x | [9 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x | [5 empty] | x
|  | P | Activity Cost Etimation | Estimate cost of every deliverables and activity | 7 | P08 |  |  | x | [6 empty] | x | [11 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x | [5 empty] | x
|  | P | Budgeting with consolidated cost | Prepare a budget and funding requirments. Set up change budget also. | 7 | P09 |  |  | x | [6 empty] | x | x | [10 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x
|  | P | Project & Product Quality Planning | Prepare Quality review, testing, audit, process improvement plan. Identify quality metrices. Create quality checklist for review etc. | 11 | P10 |  |  | x | [6 empty] | x |  |  |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x | x |  |  | x | [5 empty] | x | x |  |  |  | x
|  | P | Cost of Quality | Determine cost of quality activities | 12 | P11 |  |  | x | [6 empty] | x |  | x | x | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x | [5 empty] | x | x |  |  |  | x
Yes |  | P | Risk Identification | Idenitfy all the possible risk. | 14 | P12 |  | x | x | [6 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | P | Risk Response Planning | Prepare response reponse approach for all the prioritized risk | 9 | P13 |  |  | x | [6 empty] | x | x | x | x | [8 empty] | x |  |  |  | x |  |  |  |  | x | x
|  | P | Cost of Risk Management | Determine cost of risk management activitie. Setup risk budget. | 9 | P14 |  |  | x | [6 empty] | x |  |  |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x | [5 empty] | x | x
| Yes | P | HR& Staff Management Planning | Prepare RACI chart, training need, reporting chart, appraisal plan. | 3 | P15 |  |  | x | [5 empty] | x | x
| Yes | P | Cost of Training/Hiring/Appraisal etc. | Determine cost of training, new hire, team building activities. | 3 | P16 |  |  | x | [5 empty] | x | x
|  | P | Procurement Planning | Prepare all possible document required to start procurement. | 5 | P17 |  |  | x | [6 empty] | x |  |  | x | [8 empty] | x | [9 empty] | x
|  | P | Cost/Schedule of Contracting P/S/R | Prepare procurment schedule, audit plan, verfication plan, producement cost summary doc. | 6 | P18 |  |  | x | [6 empty] | x | x | [10 empty] | x |  |  |  | x |  |  |  |  | x
|  | P | Communication Planning & Tech | Prepare all communication format, review format, review group, frequnecy of communication. | 8 | P19 |  |  | x | [6 empty] | x |  |  | x | [8 empty] | x |  |  |  | x |  |  |  |  | x | x |  |  | x
| Yes | P | Cost of Communication | Determine cost of communication. | 2 | P20 |  |  | x | [6 empty] | x
|  | P | Stakeholder Management Plan | Prepare a plan to engage key stakeholders. | 6 | P21 |  |  | x | [6 empty] | x |  |  | x | [8 empty] | x |  |  |  | x | [5 empty] | x
|  | P | Cost of Stakeholder Engagement | Determine cost of stakeholder engagement | 2 | P22 |  |  | x | [6 empty] | x
|  | P | Consolidate all costs/schedule of activities | Consolidate all the cost together under various headings. Consolidate all the timelines. | 6 | P23 |  |  | x | [6 empty] | x |  |  |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x
|  | P | Negotiate cost/schedule/quality/scope- Baseline Project | Negotiate and finalized the cost, time, scope and quality. | 7 | P24 |  |  | x | [6 empty] | x | x |  |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x
Yes |  | E | Work Authorization | Authorize work as and when milestone reaches. | 5 | E01 | [13 empty] | x | [20 empty] | x |  | x |  |  |  | x | x
Yes |  | E | Quality and Config Audit | Perform quality audit and configuraiton audit. | 5 | E02 | [13 empty] | x | [20 empty] | x |  | x |  |  |  | x | x
| Yes | E | Resource Acquition | Get resources on project, negotiate their KRA and define ground rule | 1 | E03 | [8 empty] | x
| Yes | E | Team Capablity Building | Training, team building actvities | 1 | E04 | [8 empty] | x
Yes |  | E | Team & Work Management | Conflict management and people issue resolution | 5 | E05 | [13 empty] | x | [20 empty] | x |  | x |  |  |  | x | x
|  | E | Contracting | Procurment contract work/material management. | 9 | E06 | [13 empty] | x | x | x | x | x |  |  |  | x | [14 empty] | x |  |  |  | x | x
Yes |  | E | Project Planned/Ad-hoc Communications | Send out communications to stakeholders. | 5 | E07 | [13 empty] | x | [20 empty] | x |  | x |  |  |  | x | x
Yes |  | E | Routine Stakeholder Engagement | Engage stakehoders as per the plan | 5 | E08 | [13 empty] | x | [20 empty] | x |  | x |  |  |  | x | x
Yes |  | MC | Integrated Change Control | Manage change request from central system. | 10 | G01 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x | [5 empty] | x |  |  |  | x | x
Yes |  | MC | Report Prepration | Prepare reports at the defined frequency in the format decided | 11 | G02 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x
Yes |  | MC | Quality Variance Management | Quality (defect, utiliztion, productivity, safety, security) variance analysis | 4 | G03 | [34 empty] | x |  | x |  |  |  | x | x
Yes |  | MC | Product Testing by QA | Internal review of the product. | 3 | G04 | [34 empty] | x | [5 empty] | x | x
|  | MC | Product Testing by Customer | Customer review of the product | 3 | G05 | [34 empty] | x | [5 empty] | x | x
Yes |  | MC | CST Variance Management | Cost, Scope, Time variance analysis and management. | 9 | G06 | [13 empty] | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | MC | Risk Reassessment | Periodic risk re-evaluation | 11 | G07 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x
Yes |  | MC | Risk Audit | Periodic risk audit by external to project person | 3 | G08 | [36 empty] | x |  |  |  | x | x
|  | MC | Contract P/S/R Management | Procurment product/work validation. Payment mgmt, claim settlement | 8 | G09 | [13 empty] | x |  |  |  |  | x | x | x | x | [14 empty] | x |  |  |  | x | x
Yes |  | MC | Reassess conmmunication /engagement need | Communication Reassessment | 8 | G10 | [11 empty] | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x | [5 empty] | x |  |  |  | x | x
|  | C | Each Vendor Contract Closing | Document lessons learned of each contracting. Inform PMO, Departments, team, finance etc about the procurement contract colosure | 4 | C01 | [13 empty] | x | [7 empty] | x | [14 empty] | x |  |  |  | x
|  | C | Customer Sign off | Customer singoff | 1 | C02 | [45 empty] | x
|  | C | Phase or Project Closure | Document lessons learned from the project. Archive documents. Inform all staekholders about project closure | 1 | C03 | [45 empty] | x
Yes |  | P | Daily Standup | Project team meets daily for 10 min to share progress and the plan of the day | 12 | A01 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | P | Sprint Planning | Project team meets every 2 week for 1 hours and prepare a plan of next 2 days. | 12 | A02 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | C | Retrospective | Project team meets at the end of every milestone/ 2week and review their lesson learned and improve their processes. | 12 | A03 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | E | Project Kanbanboard | Project team update the kanban board on daily basis | 12 | A04 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | MC | PMO Review Project Progress with PM |  | 12 | PMO-G01 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | MC | PMO Review Project Progress with CEO |  | 4 | PMO-G02 | [34 empty] | x |  | x |  |  |  | x | x
Yes |  | MC | Approve Revised Baselines |  | 12 | PMO-G03 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | MC | Addressing Impediments & Taking Decisions |  | 12 | PMO-G04 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
|  | MC | Authorize Next Phase/Project |  | 5 | PMO-G05 | [13 empty] | x | [7 empty] | x | [14 empty] | x |  |  |  | x | x
Yes |  | MC | Share Lessons Learned with Org /Other projects |  | 12 | PMO-G06 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | MC | Manage Org Level Project Metrics |  | 8 | PMO-G07 | [13 empty] | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x
Yes |  | MC | Org Level Risk Management |  | 8 | PMO-G08 | [13 empty] | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x
Yes |  | MC | Org Level Vendor & Inventory Management |  | 6 | PMO-G09 | [13 empty] | x | [20 empty] | x |  | x |  |  |  | x | x |  |  |  | x
Yes |  | MC | Stakehodler Engagement |  | 12 | PMO-G10 | [9 empty] | x | x | x |  | x | [7 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  | x |  |  |  | x | x |  |  |  | x
Note on D8: New Process