## BOM
Req Sl No | Job | Task Number | Req Date | Req Approved Date | Need By | Req No | Material Code | Code | Width | Length | Qty | Note To Supplier | Req Uom | Req Qty | Po No | Po Qty | Po Date | Po Approved Date | Mrin No | Grn Date | Vendor Dc No | Vendor Dc Date | Rec Qty | Acc Qty | Rej Qty | Dev Qty | Supplier Code | Supplier Name | Supplier Site | Status | Department | Po Due Date | Closed Reason | Closed Status | Eta@Team | Store Stock | Material Description | Null
1 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/001 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 19.15MM | -
2 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/002 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 31.85MM | -
3 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/003 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 44.55MM | -
4 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/004 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 57.25MM | -
5 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/005 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 69.95MM | -
6 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/006 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 82.65MM | -
7 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/007 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 95.35MM | -
8 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/008 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 108.05MM | -
9 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/009 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 120.75MM | -
10 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/010 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 133.45MM | -
11 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/011 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 146.15MM | -
12 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/012 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 158.85MM | -
13 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/013 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 171.55MM | -
14 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/014 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 184.25MM | -
15 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/015 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 196.95MM | -
16 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/016 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 209.65MM | -
17 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/017 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 222.35MM | -
18 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/018 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 235.05MM | -
19 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/019 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 247.75MM | -
20 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/020 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 20 | 771718000000 | 20 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 260.45MM | -
23 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/021 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 273.15MM | -
24 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/022 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 20 | 771718000000 | 20 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 285.85MM | -
25 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/023 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 20 | 771718000000 | 20 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 298.55MM | -
26 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/024 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 16 | 771718000000 | 16 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 311.25MM | -
27 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/025 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 16 | 771718000000 | 16 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 323.95MM | -
28 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/026 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 12 | 771718000000 | 12 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 336.85MM | -
29 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09AF/027 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209A&F-UT-001 SH.1 OF 1 REV.0) | Nos | 10 | 771718000000 | 10 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 19.05MM O/D X 2.11MM W/T(MIN.) ST LG- 6005MM:RADIUS- 349.35MM | -
1 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/001 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 40 | 771718000000 | 40 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 28.6MM | -
2 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/002 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 48 | 771718000000 | 48 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 54.0MM | -
3 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/003 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 48 | 771718000000 | 48 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 79.4MM | -
4 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/004 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 48 | 771718000000 | 48 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 104.8MM | -
5 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/005 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 44 | 771718000000 | 44 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 130.2MM | -
6 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/006 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 44 | 771718000000 | 44 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 155.6MM | -
7 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/007 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 40 | 771718000000 | 40 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 181.0MM | -
8 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/008 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 36 | 771718000000 | 36 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 206.4MM | -
9 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/009 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 231.8MM | -
10 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09BG/010 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-4209-B&G-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-4005MM RADIUS- 257.2MM | -
1 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/001 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 47.65MM | -
2 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/002 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 67.5MM | -
3 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/003 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 87.34MM | -
4 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/004 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 107.19MM | -
5 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/005 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 127.03MM | -
7 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/006 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 146.88MM | -
8 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/007 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 166.72MM | -
9 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/008 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 186.57MM | -
10 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/009 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 206.41MM | -
11 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/010 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 226.26MM | -
12 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/011 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 246.1MM | -
13 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/012 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 265.95MM | -
14 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/013 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 285.79MM | -
15 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/014 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 305.64MM | -
16 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/015 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 325.48MM | -
17 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/016 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 345.33MM | -
18 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/017 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 365.17MM | -
19 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/018 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 385.02MM | -
20 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/019 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 404.86MM | -
21 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/020 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 424.71MM | -
22 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/021 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 444.55MM | -
23 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/022 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 28 | 771718000000 | 28 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 464.4MM | -
24 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/023 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 26 | 771718000000 | 26 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 484.24MM | -
25 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/024 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 504.09MM | -
26 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/025 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 523.93MM | -
27 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/026 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 543.78MM | -
28 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/027 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 563.62MM | -
29 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/028 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 24 | 771718000000 | 24 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 583.47MM | -
30 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/029 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 22 | 771718000000 | 22 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 603.31MM | -
32 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/030 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 20 | 771718000000 | 20 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 623.16MM | -
33 | 4209 | 1.4 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/UT/09CH/031 | AS | - | - | - | TDC NO : TEAM/4209/01 REV.0 (AS PER SKETCH NO : TEAM-HX-4209C&H-UT-001 SH.1 OF 1 REV.0) | Nos | 16 | 771718000000 | 16 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 GR.T11 LOW ALLOY STEEL SEAMLESS 'U' TUBE 31.75MM O/D X 2.77MM W/T(MIN.) ST LG- 3005MM:RADIUS- 643MM | -
1 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/001 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 18 | 771718000000 | 18 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 28.6MM | -
2 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/002 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 16 | 771718000000 | 16 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 46.6MM | -
3 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/003 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 18 | 771718000000 | 18 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 64.5MM | -
4 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/004 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 16 | 771718000000 | 16 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 84.5MM | -
5 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/005 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 18 | 771718000000 | 18 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 100.4MM | -
6 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/006 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 16 | 771718000000 | 16 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 118.4MM | -
7 | 4209 | 1.5 | 2017-10-28 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/UT/09RS/007 | CS | - | - | - | TDC NO : TEAM/4209/02 REV.0 (AS PER SKETCH NO : TEAM-HX-4209R&S-UT-001 SH.1 OF 1 REV.0) | Nos | 12 | 771718000000 | 12 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA 179 CARBON STEEL SEAMLESS U-TUBE OD19.05MMX2.11T(MIN) ST.LG-3005MM RADIUS- 136.4MM | -
1 | 4209 | 1.4 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/TS/0T11/218 | AS | - | 6000 MM | 20 NOS | ASME EDITION 2015 (FOR JOB NO : 4209A&F) | RMT | 120 | 771718000000 | 120 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 T11 LOW ALLOY STEEL SEAMLESS TUBE OD 21.8 MM X 2.65(AVG) W.THK | -
2 | 4209 | 1.4 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/TS/0T11/218 | AS | - | 6000 MM | 23 NOS | ASME EDITION 2015 (FOR JOB NO : 4209C&H) | RMT | 138 | 771718000000 | 138 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 T11 LOW ALLOY STEEL SEAMLESS TUBE OD 21.8 MM X 2.65(AVG) W.THK | -
3 | 4209 | 1.18 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2334/254 | CS | - | 2505(+1/-0)MM | 408 NOS | TDC NO : TEAM/4209/05 REV.0 (FOR JOB NO : 4209D&I) | RMT | 1022.04 | 771718000000 | 1022.04 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA334 GR.6 CARBON STEEL SEAMLESS TUBE 25.4MM OD X 2.77MM W/THK(MIN) | -
4 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 6005(+1/-0)MM | 138 NOS | TDC NO : TEAM/4209/03 REV.0 (FOR JOB NO : 4209E&J) | RMT | 828.69 | 771718000000 | 6647.54 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
5 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 2005(+1/-0)MM | 508 NOS | TDC NO : TEAM/4209/04 REV.0 (FOR JOB NO : 4209K&L) | RMT | 1018.54 | 771718000000 | 1018.54 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
6 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 3005(+1/-0)MM | 608 NOS | TDC NO : TEAM/4209/04 REV.0 (FOR JOB NO : 4209M) | RMT | 1827.04 | 771718000000 | 1827.04 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
7 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 4005(+1/-0)MM | 478 NOS | TDC NO : TEAM/4209/03 REV.0 (FOR JOB NO : 4209N) | RMT | 1906.38 | 771718000000 | 1914.39 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
8 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 2505(+1/-0)MM | 1012 NOS | TDC NO : TEAM/4209/04 REV.0 (FOR JOB NO : 4209O&P) | RMT | 2535.06 | 771718000000 | 2535.06 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
9 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 2305(+1/-0)MM | 504 NOS | TDC NO : TEAM/4209/04 REV.0 (FOR JOB NO : 4209Q) | RMT | 1161.72 | 771718000000 | 1161.72 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
11 | 4209 | 1.5 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2119/019 | CS | - | 2000 MM | 1 NO | TDC NO : TEAM/4209/04 REV.0 (For Mockup Purpose) | RMT | 2 | 771718000000 | 2 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | SA179 CARBON STEEL SEAMLESS TUBE 19.05MM OD X 2.11MM W/THK (MIN) | -
12 | 4209 | 1.18 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | CS/TS/2334/254 | CS | - | 2000 MM | 1 NO | TDC NO : TEAM/4209/05 REV.0 (For Mockup Purpose) | RMT | 2 | 771718000000 | 2 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA334 GR.6 CARBON STEEL SEAMLESS TUBE 25.4MM OD X 2.77MM W/THK(MIN) | -
13 | 4209 | 1.4 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/TS/0T11/195 | AS | - | 2000 MM | 1 NO | TDC NO : TEAM/4209/01 REV.0 (For Mockup Purpose) | RMT | 2 | 771718000000 | 2 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 T11 LOW ALLOY STEEL SEAMLESS TUBE OD 19.05 MM X 2.11(MIN) W.THK | -
14 | 4209 | 1.4 | 2017-11-02 | 2017-11-03 | 2018-03-30 | 771719000000 | AS/TS/0T11/277 | AS | - | 2000 MM | 1 NO | TDC NO : TEAM/4209/01 REV.0 (For Mockup Purpose) | RMT | 2 | 771718000000 | 2 | 2017-12-16 | 2018-01-06 | - | - | - | - | - | - | - | - | 337088 | CHANGSHU SEAMLESS STEEL TUBE CO LTD | CHINA | PO Approved: Pending for Receiving | PPC | 2018-04-17 | - | OPEN | 2018-05-15 | - | ASME SA 213 T11 LOW ALLOY STEEL SEAMLESS TUBE OD 31.75 MM X 2.77(MIN) W.THK | -
1 | 4209 | 1.11 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/0TS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE OD 966MM X 130MM THK AS PER SKETCH NO: TEAM-HX-4209A&F-TS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/07 [ TUBE SHEET ] | -
2 | 4209 | 1.11 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/SFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE OD 966MM X ID 775MM X 45MM HUB X 110MM THK AS PER SKETCH NO: TEAM-HX-4209A&F-SFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/07 [ SHELL FLANGE ] | -
3 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/CFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE OD 966MM X ID 775MM X 45MM HUB X 110MM THK AS PER SKETCH NO: TEAM-HX-4209A&F-CFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/07A [ CHANNEL FLANGE ] | -
4 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09BG/0TS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 836MM X 110MM THK AS PER SKETCH NO: TEAM-HX-4209B&G-TS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ TUBE SHEET ] | -
5 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09BG/CFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 836MM X ID 650MM X 32MM HUB X 91MM THK AS PER SKETCH NO: TEAM-HX-4209B&G-CFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ CHANNEL FLANGE ] | -
6 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09BG/SFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 836MM X ID 650MM X 32MM HUB X 95MM THK AS PER SKETCH NO: TEAM-HX-4209B&G-SFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ SHELL FLANGE ] | -
8 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/LTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 604MM X 75MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209O-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ LHS TUBE SHEET ] | -
9 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/RTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 604MM X 75MM X 25MM LIP THK AS PER SKETCH NO: TEAM-HX-4209O-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ RHS TUBE SHEET ] | -
10 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/LCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 604MM X ID 440MM X 25MM HUB X 70MM THK AS PER SKETCH NO: TEAM-HX-4209O-LCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
11 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/RCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 604MM X ID 440MM X 25MM HUB X 70MM THK AS PER SKETCH NO: TEAM-HX-4209O-RCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
12 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/RTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 704MM X 75MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209Q-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ RHS TUBE SHEET ] | -
13 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/LTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 704MM X 75MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209Q-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ LHS TUBE SHEET ] | -
14 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/LCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 704MM X ID 540MM X 32MM HUB X 70MM THK AS PER SKETCH NO: TEAM-HX-4209Q-LCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
15 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/RCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 704MM X ID 540MM X 32MM HUB X 70MM THK AS PER SKETCH NO: TEAM-HX-4209Q-RCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
16 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09RS/0TS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 530MM X 60MM THK AS PER SKETCH NO: TEAM-HX-4209R&S-TS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ TUBE SHEET ] | -
17 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09RS/SFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 530MM X ID 387.3MM X 25MM HUB X 60MM THK AS PER SKETCH NO: TEAM-HX-4209R&S-SFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ SHELL FLANGE ] | -
18 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09RS/CFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 530MM X ID 387.3MM X 25MM HUB X 60MM THK AS PER SKETCH NO: TEAM-HX-4209R&S-CFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ CHANNEL FLANGE ] | -
19 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/RCF | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 522MM X ID 380MM X 25MM HUB X 65MM THK AS PER SKETCH NO: TEAM-HX-4209K&L-RCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
20 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/LCF | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 522MM X ID 380MM X 25MM HUB X 65MM THK AS PER SKETCH NO: TEAM-HX-4209K&L-LCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
23 | 4209 | 1.11 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/0TS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 LOW ALLOY STEEL FORGING OD 1772MM X 260MM THK AS PER SKETCH NO: TEAM-HX-4209C&H-TS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/07 [ TUBE SHEET ] | -
24 | 4209 | 1.11 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/SFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE OD 1772MM X ID 1450MM X 75MM HUB X 165MM THK AS PER SKETCH NO: TEAM-HX-4209C&H-SFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/07A [ SHELL FLANGE ] | -
25 | 4209 | 1.11 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/CFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE OD 1772MM X ID 1450MM X 80MM HUB X 178MM THK AS PER SKETCH NO: TEAM-HX-4209C&H-CFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/07 [ CHANNEL FLANGE ] | -
26 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09DI/RTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 350 LF.2 CL.1 CARBON STEEL FORGING OD 786MM X 85MM THK AS PER SKETCH NO: TEAM-HX-4209D&I-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/10 [ RHS TUBE SHEET ] | -
27 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09DI/LTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 350 LF.2 CL.1 CARBON STEEL FORGING OD 786MM X 85MM THK AS PER SKETCH NO: TEAM-HX-4209D&I-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/10 [ LHS TUBE SHEET ] | -
28 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09DI/LFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 350 LF.2 CL.1 CARBON STEEL FORGED FLANGE OD 786MM X ID 600MM X 32MM HUB X 90MM THK AS PER SKETCH NO: TEAM-HX-4209D&I-LFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/10 [ LHS CHANNEL FLANGE ] | -
29 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09DI/RFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | - | - | - | OPEN | - | - | ASME SA 350 LF.2 CL.1 CARBON STEEL FORGED FLANGE OD 786MM X ID 600MM X 32MM HUB X 90MM THK AS PER SKETCH NO: TEAM-HX-4209D&I-RFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/10 [ RHS CHANNEL FLANGE ] | -
30 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/RTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 748MM X 100MM THK X 30MM LIP AS PER SKETCH NO: TEAM-HX-4209M-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ RHS TUBE SHEET ] | -
31 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/LCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 748MM X ID 575MM X 32MM HUB X 80MM THK AS PER SKETCH NO: TEAM-HX-4209M-LCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
32 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/RCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 748MM X ID 575MM X 32MM HUB X 80MM THK AS PER SKETCH NO: TEAM-HX-4209M-RCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
33 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209N/RTS | FL | - | - | - | - | Nos | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 936MM X 55MM THK AS PER SKETCH NO: TEAM-HX-4209N-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS TUBE SHEET ] | -
34 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209N/LTS | FL | - | - | - | - | Nos | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 936MM X 55MM THK AS PER SKETCH NO: TEAM-HX-4209N-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS TUBE SHEET ] | -
35 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209N/LFG | FL | - | - | - | - | Nos | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 936MM X ID 790MM X 32MM HUB X 75MM THK AS PER SKETCH NO: TEAM-HX-4209N-LFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
36 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209N/RFG | FL | - | - | - | - | Nos | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 936MM X ID 790MM X 32MM HUB X 75MM THK AS PER SKETCH NO: TEAM-HX-4209N-RFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
37 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209P/RTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 836MM X 65MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209P-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ RHS TUBE SHEET ] | -
38 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209P/LTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 836MM X 65MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209P-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ LHS TUBE SHEET ] | -
39 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209P/LCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 836MM X ID 675MM X 32MM HUB X 80MM THK AS PER SKETCH NO: TEAM-HX-4209P-LCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
40 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209P/RCF | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 836MM X ID 675MM X 32MM HUB X 80MM THK AS PER SKETCH NO: TEAM-HX-4209P-RCFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
41 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/LTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 748MM X 100MM THK X 30MM LIP AS PER SKETCH NO: TEAM-HX-4209M-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ LHS TUBE SHEET ] | -
42 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09EJ/LFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 398MM X ID 257.4MM X 25MM HUB X 45MM THK AS PER SKETCH NO: TEAM-HX-4209E&J-LFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS CHANNEL FLANGE ] | -
43 | 4209 | 1.1 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09EJ/RFG | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGED FLANGE OD 398MM X ID 257.4MM X 25MM HUB X 45MM THK AS PER SKETCH NO: TEAM-HX-4209E&J-RFG-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS CHANNEL FLANGE ] | -
44 | 4209 | 1.7 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09EJ/RTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 398MM X 50MM THK AS PER SKETCH NO: TEAM-HX-4209E&J-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ RHS TUBE SHEET ] | -
45 | 4209 | 1.7 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09EJ/LTS | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 398MM X 50MM THK AS PER SKETCH NO: TEAM-HX-4209E&J-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09 [ LHS TUBE SHEET ] | -
46 | 4209 | 1.7 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/LTS | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 522MM X 70MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209K&L-LTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ LHS TUBE SHEET ] | -
47 | 4209 | 1.7 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/RTS | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING OD 522MM X 70MM THK X 25MM LIP AS PER SKETCH NO: TEAM-HX-4209K&L-RTS-001 SH 1 OF 1 REV.0 & TDC NO: TEAM/4209/09B [ RHS TUBE SHEET ] | -
48 | 4209 | 1.8 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/4209/MO1 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 336 F11 CL.2 STEEL FORGING 40MM THK X 300 MM X 300 MM AS PER TDC NO: TEAM/4209/07 [FOR MOCKUP PURPOSE] | -
49 | 4209 | 1.7 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/4209/MO2 | FL | - | - | - | - | Nos | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 350 LF.2 CL.1 CARBON STEEL FORGING 40MM THK X 300 MM X 300 MM AS PER TDC NO: TEAM/4209/10 [FOR MOCKUP PURPOSE] | -
50 | 4209 | 1.7 | 2017-11-28 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/4209/MO3 | FL | - | - | - | - | Nos | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 266 GR.4 CARBON STEEL FORGING 40MM THK X 300 MM X 300 MM AS PER TDC NO: TEAM/4209/09A [FOR MOCKUP PURPOSE] | -
1 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/L01 | FL | - | - | - | - | Nos | 20 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL2 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 300 - 15.875 MM THK X 184 MM LG (NOZZLE N13-N22) (AS PER SKETCH NO: TEAM-HX-4209A&F-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06 REV.0 | -
2 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/L02 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL2 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 300 - 16.67 MM THK X 186 MM LG (NOZZLE D2&V2) (AS PER SKETCH NO: TEAM-HX-4209A&F-LWNFG-002 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06 REV.0 | -
3 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/L03 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL2 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 600 - 15.875 MM THK X 210 MM LG (NOZZLE N24) (AS PER SKETCH NO: TEAM-HX-4209A&F-LWNFG-003 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/6B REV.0 | -
4 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/L04 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL2 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 600 - 16.67 MM THK X 213 MM LG (NOZZLE V1) (AS PER SKETCH NO: TEAM-HX-4209A&F-LWNFG-004 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/6B REV.0 | -
5 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/L01 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 300 - 16.67 MM THK X 182 MM LG (NOZZLE D2&V2) (AS PER SKETCH NO: TEAM-HX-4209O-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
6 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/L02 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 300 - 15.875 MM THK X 179 MM LG (NOZZLE N7&N8) (AS PER SKETCH NO: TEAM-HX-4209O-LWNFG-002 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
7 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/L01 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 300 - 16.67 MM THK X 186 MM LG (NOZZLE D2&V2) (AS PER SKETCH NO: TEAM-HX-4209Q-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
8 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/L02 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 300 - 15.875 MM THK X 184 MM LG (NOZZLE N7&N8) (AS PER SKETCH NO: TEAM-HX-4209Q-LWNFG-002 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
9 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/L01 | FL | - | - | - | - | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 600 - 16.67 MM THK X 260 MM LG (NOZZLE D2&V2) (AS PER SKETCH NO: TEAM-HX-4209K&L-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
10 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/L02 | FL | - | - | - | - | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 600 - 15.875 MM THK X 270 MM LG (NOZZLE N7&N8) (AS PER SKETCH NO: TEAM-HX-4209K&L-LWNFG-002 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
11 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/L01 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL1 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 600 - 15.875 MM THK X 179 MM LG (NOZZLE N5) (AS PER SKETCH NO: TEAM-HX-4209C&H-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06C REV.0 | -
12 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/L02 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL1 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 600 - 15.875 MM THK X 211 MM LG (NOZZLE N6) (AS PER SKETCH NO: TEAM-HX-4209C&H-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06C REV.0 | -
13 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/L03 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL1 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 300 - 15.875 MM THK X 163 MM LG (NOZZLE N7&N8) (AS PER SKETCH NO: TEAM-HX-4209C&H-LWNFG-002 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06A REV.0 | -
14 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/L04 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL1 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 600 - 16.67 MM THK X 266 MM LG (NOZZLE V2&D2) (AS PER SKETCH NO: TEAM-HX-4209C&H-LWNFG-003 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06C REV.0 | -
15 | 4209 | 1.15 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/L05 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA182 F11 CL1 - LOW ALLOY STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 300 - 16.67 MM THK X 164 MM LG (NOZZLE V1&D1) (AS PER SKETCH NO: TEAM-HX-4209C&H-LWNFG-004 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/06A REV.0 | -
16 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/L01 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN50 LWNRF CL 300 - 16.67 MM THK X 183 MM LG (NOZZLE D2&V2) (AS PER SKETCH NO: TEAM-HX-4209M-LWNFG-001 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
17 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/L02 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 - CARBON STEEL - FORGED FLANGE ASME B16.5 DN40 LWNRF CL 300 - 15.875 MM THK X 181 MM LG (NOZZLE N7&N8) (AS PER SKETCH NO: TEAM-HX-4209M-LWNFG-002 SH 1 OF 1 REV.0) & TDC NO: TEAM/4209/08A REV.0 | -
18 | 4209 | 1.14 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/S01 | FL | - | - | - | - | Nos | 20 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA336 F11 CL2 LOW ALLOY STEEL-SELF REINFORCED NOZZLE(A2-A6,B2-B6)-DN 300 x 12MM THK X WITH LIP OD 536.26 MM X ID 300 MM X 16 MM LIP THK X OVERALL LENGTH 464 MM(AS PER SKETCH:TEAM-HX-4209A&F-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/07 REV.0 | -
19 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209O/S01 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 200 X 12MM THK X WITH LIP OD 377.6 MM X ID 195 MM X 14 MM LIP THK X OVERALL LENGTH 357 MM(AS PER SKETCH:TEAM-HX-4209O-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/08A REV.0 | -
20 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209Q/S01 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 300 X 12 MM THK X WITH LIP OD 482.2 MM X ID 300 MM X 10 MM LIP THK X OVERALL LENGTH 355.73 MM(AS PER SKETCH:TEAM-HX-4209Q-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/08A REV.0 | -
21 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09KL/S01 | FL | - | - | - | - | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 80 X 11.13MM THK X WITH LIP OD 213 MM X ID 66.64 MM X 12 MM LIP THK X OVERALL LENGTH 248 MM(AS PER SKETCH:TEAM-HX-4209K&L-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/08A REV.0 | -
22 | 4209 | 1.14 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/S03 | FL | - | - | - | - | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA336 F11 CL2 LOW ALLOY STEEL-SELF REINFORCED NOZZLE(CYL.CHANNEL)-DN 500 X 14MM THK X LIP OD 797.6 MM X ID 480 MM X 26 MM LIP THK X OVERALL LENGTH 573 MM(AS PER SKETCH:TEAM-HX-4209C&H-SRN-003 SH 1 OF 1 REV.0)& TDC:TEAM/4209/07 REV.0 | -
23 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/S01 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 250 X 12MM THK X WITH LIP OD 459.2 MM X ID 249 MM X 16 MM LIP THK X OVERALL LENGTH 378 MM(AS PER SKETCH:TEAM-HX-4209M-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/08A REV.0 | -
24 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209M/S02 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 200 X 12MM THK X WITH LIP OD 385.3 MM X ID 195 MM X 16 MM LIP THK X OVERALL LENGTH 335 MM(AS PER SKETCH:TEAM-HX-4209M-SRN-002 SH 1 OF 1 REV.0)& TDC:TEAM/4209/08A REV.0 | -
25 | 4209 | 1.13 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/209P/S01 | FL | - | - | - | HOLD FOR PROCUREMENT [ISSUED ONLY FOR ENQUIRY PURPOSE] | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 400 X 14MM THK X WITH LIP OD 600.3 MM X ID 378 MM X 10 MM LIP THK X OVERALL LENGTH 407.9 MM(AS PER SKETCH:TEAM-HX-4209P-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/08A REV.0 | -
26 | 4209 | 1.14 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/S02 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA336 F11 CL2 LOW ALLOY STEEL-SELF REINFORCED NOZZLE(A1)-DN 150 WITH OD 220 MM X ID 148 MM X 36 MM THK X OVERALL LENGTH 269.5 MM(AS PER SKETCH:TEAM-HX-4209A&F-SRN-002 SH 1 OF 1 REV.0)& TDC:TEAM/4209/07A REV.0 | -
27 | 4209 | 1.14 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09AF/S03 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | - | - | - | OPEN | - | - | SA336 F11 CL2 LOW ALLOY STEEL-SELF REINFORCED NOZZLE(B1)-DN 250 WITH OD 365 MM X ID 249 MM X 58 MM THK X OVERALL LENGTH 329.5 MM(AS PER SKETCH:TEAM-HX-4209A&F-SRN-003 SH 1 OF 1 REV.0)& TDC:TEAM/4209/07A REV.0 | -
28 | 4209 | 1.14 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/S01 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA336 F11 CL2 LOW ALLOY STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 200 WITH OD 285 MM X ID 195 MM X 45 MM THK X OVERALL LENGTH 359 MM(AS PER SKETCH:TEAM-HX-4209C&H-SRN-001 SH 1 OF 1 REV.0)& TDC:TEAM/4209/07A REV.0 | -
29 | 4209 | 1.14 | 2017-12-07 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/NS/09CH/S02 | FL | - | - | - | - | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA336 F11 CL2 LOW ALLOY STEEL-SELF REINFORCED NOZZLE(CYLINDRICAL SHELL)-DN 250 WITH OD 360 MM X ID 249 MM X 55.5 MM THK X OVERALL LENGTH 399 MM(AS PER SKETCH:TEAM-HX-4209C&H-SRN-002 SH 1 OF 1 REV.0)& TDC:TEAM/4209/07A REV.0 | -
1 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0150/040 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 22 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 40 BLRF 150# | -
2 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0300/040 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 30 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 40 X BLRF X CL.300 | -
3 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0600/040 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 40 X BLRF X CL.600 | -
4 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H150/040 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 21 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 40 WNRF SCH160 CL.150 | -
5 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H300/040 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 29 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 40 X WNRF X SCH160 X CL.300 | -
6 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H600/040 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 40 WNRF SCH160 CL.600 | -
7 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0150/050 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 18 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME B16.5 SA 105 CARBON STEEL BLIND FLANGE DN 50 BLRF CL.150 | -
8 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0300/050 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 60 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 50 BLRF CL.300 | -
9 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0600/050 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 50 BLRF CL.600 | -
10 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H150/050 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 21 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA105 CARBON STEEL FORGED FLANGE DN 50 WNRF SCH160 CL.150 AS PER ASME B16.5 | -
11 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H300/050 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 58 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN50 WNRF SCH160 CL.300 | -
12 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H600/050 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN50 WNRF SCH160 CL.600 | -
13 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H150/080 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA105 CARBON STEEL FORGED FLANGE ASME DN80 WNRF SCH160 CL.150 AS PER ASME B16.5 | -
14 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H300/080 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN80 WNRF SCH160 CL.300 | -
15 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/G300/100 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 100 WNRF SCH 120 CL.300 | -
16 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/F150/150 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 6 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN150 WNRF SCH80 CL.150 | -
17 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/F300/150 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 21 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN150 WNRF SCH80 CL.300 | -
18 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/F600/200 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 WNRF DN200 SCH80 600# | -
19 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0300/040 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 22 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 40 X BLRF X CL.300 | -
20 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0600/040 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 40 X BLRF X CL.600 | -
21 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H300/040 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 40 X WNRF X SCH160 X CL.300 | -
22 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/1230/300 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 300 WNRF 12THK CL.300 | -
23 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/1430/400 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 400 WNRF 14THK CL.300 | -
24 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0300/050 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 18 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 50 BLRF CL.300 | -
25 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/30/0600/050 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL BLIND FLANGE ASME B16.5 DN 50 BLRF CL.600 | -
26 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H300/050 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 DN50 WNRF SCH160 CL.300 | -
27 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/G150/100 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE 100 NB WNRF SCH 120 CL.150 | -
28 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/F600/150 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 WNRF DN 150 SCH80 600# | -
29 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/1230/250 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 250 WNRF 12THK CL.300 | -
30 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/1230/200 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 6 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 200 WNRF 12THK CL.300 | -
31 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/CS/0300/040 | FL | - | - | - | TDC NO : TEAM/4209/10 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 350 GR.LF2 CL.1 CARBON STEEL FORGED FLANGE ASME B16.5 40NB X BLRF X CL.300 | -
32 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/H6/I300/040 | FL | - | - | - | TDC NO : TEAM/4209/10 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME B16.5 SA 350 LF2 CARBON STEEL FORGED FLANGE DN40 WNRF SCH.160 CL.300 | -
33 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/CS/0300/050 | FL | - | - | - | TDC NO : TEAM/4209/10 REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 350 GR.LF2 CL.1 CARBON STEEL FORGED FLANGE ASME B16.5 50NB X BLRF X CL.300 | -
34 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/H6/I300/050 | FL | - | - | - | TDC NO : TEAM/4209/10 REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME B16.5 SA 350 LF2 CL.1 CARBON STEEL FORGED FLANGE DN50 WNRF SCH.160 CL.300 | -
35 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/G300/040 | FL | - | - | - | TDC NO : TEAM/4209/06 REV.0 | Nos | 22 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 F11 CL.2 LOW ALLOY BLIND FLANGE 40NB BLRF 300 #. | -
36 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/G300/050 | FL | - | - | - | TDC NO : TEAM/4209/06 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 GR.F11 CL.2 LOW ALLOY STEEL BLIND FLANGE DN 50 X BLRF X CL.300 | -
37 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/49/1230/300 | FL | - | - | - | TDC NO : TEAM/4209/06 REV.0 | Nos | 21 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 GR.F11 CL.2 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 300 WNRF 12THK CL.300 | -
38 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/G600/040 | FL | - | - | - | TDC NO : TEAM/4209/06B REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 F11 CL.2 LOW ALLOY BLIND FLANGE ASME B16.5 DN 40 BLRF CL.600 | -
39 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/49/WN01/250 | FL | - | - | - | TDC NO : TEAM/4209/06B REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 250 X 12THK X WNRF X CL.600 | -
40 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/G600/050 | FL | - | - | - | TDC NO : TEAM/4209/06B REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 F11 CL.2 LOW ALLOY BLIND FLANGE ASME B16.5 DN 50 BLRF CL.600 | -
41 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/49/WN01/150 | FL | - | - | - | TDC NO : TEAM/4209/06B REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 F11 CL.2 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 150 X 10THK X WNRF X CL.600 | -
42 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/H600/080 | FL | - | - | - | TDC NO : TEAM/4209/08A REV.0 | Nos | 8 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA105 CARBON STEEL FORGED FLANGE ASME B16.5 WNRF DN80 . SCH160 600# | -
44 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/26/1230/150 | FL | - | - | - | TDC NO : TEAM/4209/08 REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED FLANGE ASME B16.5 DN 300 WNRF 12THK CL.150 | -
45 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/L300/040 | FL | - | - | - | TDC NO : TEAM/4209/06A REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 F11 CL.1 LOW ALLOY BLIND FLANGE 40NB BLRF 300 #. | -
46 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/L300/050 | FL | - | - | - | TDC NO : TEAM/4209/06A REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 Gr .F11 CL.1 - LOW ALLOY FORGED FLANGE - DN 50 X BLRFX 300# | -
47 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/49/WN02/500 | FL | - | - | - | TDC NO : TEAM/4209/06A REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 F11 CL.1 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 500 X 14THK X WNRF X CL.300 | -
48 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/L600/040 | FL | - | - | - | TDC NO : TEAM/4209/06C REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 F11 CL.1 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 40 X BLRF X CL.600 | -
49 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/49/WN02/250 | FL | - | - | - | TDC NO : TEAM/4209/06C REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 F11 CL.1 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 250 X 12THK X WNRF X CL.600 | -
50 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/A6/L600/050 | FL | - | - | - | TDC NO : TEAM/4209/06C REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 Gr .F11 CL.1 - LOW ALLOY FORGED FLANGE - DN 50 X BLRFX 600# | -
51 | 4209 | 1.15 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/49/WN02/200 | FL | - | - | - | TDC NO : TEAM/4209/06C REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 182 F11 CL.1 LOW ALLOY STEEL FORGED FLANGE ASME B16.5 DN 200 X 12THK X WNRF X CL.600 | -
52 | 4209 | 1.13 | 2017-12-14 | 2017-12-16 | 2018-03-15 | 771719000000 | FL/H6/G300/100 | FL | - | - | - | TDC NO : TEAM/4209/010 REV.0 | Nos | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME B16.5 SA 350 LF2 CL.1 CARBON STEEL FORGED FLANGE DN100 WNRF SCH120 CL.300 | -
1 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/006 | CS | 2500 MM | 1250 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 147 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 6mmTHK. | -
2 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/008 | CS | 2500 MM | 6000 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 942 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 8mmTHK. | -
3 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/010 | CS | 2500 MM | 9000 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 1766 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 10mmTHK. | -
4 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/012 | CS | 1850 MM | 5700 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 993 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 12MM THK | -
5 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/014 | CS | 2500 MM | 12000 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 3297 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 14 mmTHK | -
6 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/014 | CS | 2500 MM | 4500 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 1236 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 14 mmTHK | -
7 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/016 | CS | 2500 MM | 6000 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 1884 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 16 mmTHK. | -
8 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/018 | CS | 2500 MM | 4500 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 1590 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 18mmTHK. | -
9 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/020 | CS | 2500 MM | 3000 MM | 1 NO | TDC No:TEAM/4209/14 REV.0 | Kg | 1178 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 20 mmTHK | -
10 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/006 | CS | 2500 MM | 4000 MM | 1 NO | TDC No:TEAM/4209/15 REV.0 | Kg | 471 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 6mmTHK. | -
11 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/008 | CS | 2500 MM | 12000 MM | 2 NOS | TDC No:TEAM/4209/15 REV.0 | Kg | 3768 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 8mmTHK. | -
12 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/010 | CS | 2500 MM | 10000 MM | 1 NO | TDC No:TEAM/4209/15 REV.0 | Kg | 1963 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 10mmTHK. | -
13 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/012 | CS | 2500 MM | 12000 MM | 1 NO | TDC No:TEAM/4209/15 REV.0 | Kg | 2826 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 12MM THK | -
14 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/012 | CS | 2500 MM | 3000 MM | 1 NO | TDC No:TEAM/4209/15 REV.0 | Kg | 707 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 12MM THK | -
15 | 4209 | 1.1 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | CS/PL/5166/014 | CS | 2500 MM | 10000 MM | 1 NO | TDC No:TEAM/4209/15 REV.0 | Kg | 2748 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 516 GR 60 CARBON STEEL PLATE 14 mmTHK | -
16 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/006 | AS | 1250 MM | 1250 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 74 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 6.0MM THK. | -
17 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/008 | AS | 2000 MM | 12000 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 1507 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 8.0MM THK. | -
18 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/012 | AS | 2500 MM | 1500 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 354 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 12MM THK. | -
19 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/014 | AS | 2500 MM | 5000 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 1374 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 14.0MM THK. | -
20 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/016 | AS | 2500 MM | 12000 MM | 3 NOS | TDC No:TEAM/4209/13 REV.0 | Kg | 11304 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 16.0MM THK. | -
21 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/018 | AS | 2500 MM | 5500 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 1943 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 18.0MM THK. | -
22 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/020 | AS | 2500 MM | 5000 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 1963 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 20.0MM THK. | -
23 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/024 | AS | 1050 MM | 2100 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 415 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 24.0MM THK. | -
24 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/026 | AS | 2500 MM | 5000 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 2551 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 26.0MM THK. | -
25 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/030 | AS | 1250 MM | 1400 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 412 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 30.0MM THK. | -
26 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/032 | AS | 2500 MM | 7000 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 4396 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 32.0MM THK. | -
27 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/032 | AS | 2500 MM | 12000 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 7536 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 32.0MM THK. | -
28 | 4209 | 1.2 | 2018-01-03 | 2018-01-05 | 2018-03-26 | 771719000000 | AS/PL/1011/040 | AS | 1900 MM | 3800 MM | 1 NO | TDC No:TEAM/4209/13 REV.0 | Kg | 2267 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 387 GR.11 CL.1 LOW ALLOY STEEL PLATE 40.0MM THK. | -
1 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/1000/120 | CS | - | 1600 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 1.6 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA106 GR.B CARBON STEEL SEAMLESS PIPE DN100 X SCH.120 | -
2 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/1500/080 | CS | - | 6000 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 6 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 150 X SCH 80 | -
3 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/1500/080 | CS | - | 1600 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 1.6 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 150 X SCH 80 | -
5 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/2000/080 | CS | - | 1000 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 200 X SCH.80 | -
6 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/2500/030 | CS | - | 6000 MM | 2 NOS | TDC No:TEAM/4209/11 REV.0 | RMT | 12 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 250 X SCH.30 | -
7 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/2500/030 | CS | - | 2000 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 250 X SCH.30 | -
8 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/0040/160 | CS | - | 6000 MM | 2 NOS | TDC No:TEAM/4209/11 REV.0 | RMT | 12 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 40 x SCH.160 | -
9 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/0040/160 | CS | - | 1000 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 40 x SCH.160 | -
10 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/0500/160 | CS | - | 6000 MM | 3 NOS | TDC No:TEAM/4209/11 REV.0 | RMT | 18 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 50 X SCH 160 | -
12 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/0800/160 | CS | - | 4000 MM | 1 NO | TDC No:TEAM/4209/11 REV.0 | RMT | 4 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 80 x SCH160 | -
13 | 4209 | 1.18 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/36/0040/160 | CS | - | 1000 MM | 1 NO | TDC No:TEAM/4209/12 REV.0 | RMT | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 333 GR.6 CARBON STEEL SEAMLESS PIPE DN 40 X SCH 160 | -
14 | 4209 | 1.18 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/36/0100/120 | CS | - | 1300 MM | 1 NO | TDC No:TEAM/4209/12 REV.0 | RMT | 1.3 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 333 GR.6 CARBON STEEL SEAMLESS PIPE DN 100 X SCH 120 | -
15 | 4209 | 1.18 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/36/0050/160 | CS | - | 1600 MM | 1 NO | TDC No:TEAM/4209/12 REV.0 | RMT | 1.6 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 333 GR.6 CARBON STEEL SEAMLESS PIPE DN 50 X SCH 160 | -
16 | 4209 | 1.17 | 2018-01-08 | 2018-01-09 | 2018-03-26 | 771719000000 | CS/PS/4000/STD | CS | - | 6000 MM | 2 NOS | TDC No:TEAM/4209/11 REV.0 | RMT | 12 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 400 X SCH.STD | -
1 | 4209 | 1.3 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | MS/RD/2062/010 | MS | - | 6000 MM | 50 NOS | - | Kg | 185 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | IS 2062 GRA/B MS ROD 10 mm DIA | -
2 | 4209 | 1.3 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | MS/RD/2062/012 | MS | - | 3100 MM | 6 NOS | - | Kg | 17 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | IS2062 GR A/B MS ROD 12MM DIA | -
3 | 4209 | 1.3 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | MS/RD/1905/000 | MS | - | 6000 MM | 35 NOS | - | Kg | 470 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | IS 2062 GR.A/B MS ROD 19.05MM DIA | -
4 | 4209 | 1.1 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | CS/RD/0105/020 | CS | - | 200 MM | 1 NO | - | Kg | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 105 CARBON STEEL FORGED ROD 20.0 MM DIA. | -
5 | 4209 | 1.2 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | AS/RD/2011/025 | AS | - | 300 MM | 1 NO | - | Kg | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 F11 CL.2 LOW ALLOY STEEL FORGED ROD 25.0MM DIA. | -
6 | 4209 | 1.2 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | AS/RD/2011/035 | AS | - | 350 MM | 1 NO | - | Kg | 3 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 182 F11 CL.2 LOW ALLOY STEEL FORGED ROD 35.0MM DIA. | -
7 | 4209 | 1.2 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | AS/RD/0739/012 | AS | - | 6000 MM | 45 NOS | - | Kg | 240 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 739 B11 LOW ALLOY STEEL ROD 12MM DIA. | -
8 | 4209 | 1.2 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | AS/RD/0739/025 | AS | - | 4500 MM | 1 NO | - | Kg | 17 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | ASME SA 739 B11 LOW ALLOY STEEL ROD 25MM DIA. | -
9 | 4209 | 1.2 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | SS/RD/0304/012 | SS | - | 200 MM | 1 NO | - | Kg | 1 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 479 TP304 STAINLESS STEEL ROD 12 MM DIA | -
10 | 4209 | 1.2 | 2018-01-12 | 2018-01-12 | 2018-04-16 | 771719000000 | SS/RD/0304/020 | SS | - | 5000 MM | 1 NO | - | Kg | 13 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Approved | PPC | - | - | OPEN | - | - | SA 479 TP304 STAINLESS STEEL ROD 20 MM DIA | -
1 | 4209 | 1.13 | 2018-01-12 | - | 2018-03-26 | 771719000000 | FT/CS/RT54/160 | FT | - | - | - | TDC No:TEAM/4209/17 REV.0 | Nos | 2 | - | 0 | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | - | - | Requisition Incomplete | PPC | - | - | OPEN | - | - | SA 234 GR.WPB CARBON STEEL REDUCING TEE DN 50 X DN 40 X SCH.160 | -

## Naming
Product Code Part # | 1 | 2 | 3 | 4
Length | 2 | 2 | 4 | 3
Part Name | Material Grade | Part Short Code | ?? | ??
U Tube | AS, CS, TI, SS, MO, HA, IN | UT | Job no. Last 2 digits + Equipment # | Part number given by Design
Tube | AS, CS, TI, SS, MO, HA, IN | TS | 3 digits for thickness of tube. Last digit is ???? | OD of Tube
Plate | AS, CS, TI, SS, MO, HA, IN, MS | PL | Grade | Thinkness
Std. Flange | FL | Type of flange | Schedule & Class of Flange from Design | Size of Flange
Forging | FL | NS | Job# | Position of Forge in Equipment. As per the Design.
Pipe
Fastners
Gaskets
Rod
Boughtout
| AS | UT
| CS | TS
| FL | NS
| MS | 30
| SS | 26
| FT | CS
H6
A6
49
PL
PS
36
RD
Note on C7: Get the list from Nandakumar / Basanta

## Plan
Task | Duration | Work | Resource
ASME B16.5 SA 105 C
ASME B16.5 SA 350 L
ASME SA 182 F11 CL.
ASME SA 182 GR.F11
ASME SA 213 GR.T11
ASME SA 213 T11 LOW
ASME SA 266 GR.4 CA
ASME SA 336 F11 CL.
ASME SA 350 LF.2 CL
ASME SA 739 B11 LOW
ASME SA105 CARBON S
ASME SA334 GR.6 CAR
IS 2062 GR.A/B MS R
SA 105 CARBON STEEL
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 150 X SCH 80
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 200 X SCH.80
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 250 X SCH.30
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 40 x SCH.160
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 400 X SCH.STD
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 50 X SCH 160
SA 106 GR.B CARBON STEEL SEAMLESS PIPE DN 80 x SCH160
SA 179 CARBON STEEL
SA 182 F11 CL.1 LOW
SA 182 F11 CL.2 LOW
SA 182 Gr .F11 CL.1
SA 182 GR.F11 CL.2
SA 234 GR.WPB CARBO
SA 333 GR.6 CARBON STEEL SEAMLESS PIPE DN 100 X SCH 120
SA 333 GR.6 CARBON STEEL SEAMLESS PIPE DN 40 X SCH 160
SA 333 GR.6 CARBON STEEL SEAMLESS PIPE DN 50 X SCH 160
SA 350 GR.LF2 CL.1
SA 387 GR.11 CL.1 L
SA 479 TP304 STAINL
SA 516 GR 60 CARBON
SA105 CARBON STEEL
SA106 GR.B CARBON STEEL SEAMLESS PIPE DN100 X SCH.120
SA179 CARBON STEEL
SA182 F11 CL1 - LOW
SA182 F11 CL2 - LOW
SA336 F11 CL2 LOW A