## PoP
| Tag |  |  | Full Name | Qty | Name | Client Status | Status | Date | Time | Who
4220-133-EE | 1001 | A | A1 | 4220-133-EE-A1 | 2 | AB | Oked | Done
|  |  | A2 | 4220-133-EE-A2 | 2 | CD | Oked | Done
| 1003 | B | B | 4220-133-EE-B | 2 | AB | On Hold | Done
| 1004 | C | C | 4220-133-EE-C | 1 |  | On Hold
| 1006 | D | D | 4220-133-EE-D | 2 | AB | Oked | WIP | 2018-02-04 | 20:00 | SRK
| 1007 | E | E | 4220-133-EE-E | 2 | AB | On Hold
| 1008 | F | F | 4220-133-EE-F | 1 |  | Oked | WIP | 2018-02-05 | 20:00 | Nanda
| 1009 | G | G | 4220-133-EE-G | 1 |  | Oked | Not Started | 2018-02-07 | 17:00 | Nanda
| 1010 | H | H | 4220-133-EE-H | 1 |  | Oked | Not Started | 2018-02-06 | 17:00 | SRK
| 1011 | I | I1 | 4220-133-EE-I1 | 2 | AB | On Hold
|  |  | I2 | 4220-133-EE-I2 | 2 | CD | On Hold
| 1012 | J | J1 | 4220-133-EE-J1 | 2 | AB | Oked | Not Started | 2018-02-06 | 17:00 | SRK
|  |  | J2 | 4220-133-EE-J2 | 2 | CD | Oked | Not Started | 2018-02-07 | 17:00 | SRK
| 1013 | K | K | 4220-133-EE-K | 2 | AB | On Hold
| 1014 | L | L | 4220-133-EE-L | 1 |  | Oked | Not Started | 2018-02-07 | 17:00 | SRK
| 1015 | M | M | 4220-133-EE-M | 1 |  | On Hold
| 1011 | N | N | 4220-133-EE-N | 1 |  | Oked | Not Started | 2018-02-08 | 17:00 | SRK

## Legends
Do Not Enter Anything here
This is formula. Do not change this
You need to enter data here

## Template
[7 empty] | Thickness |  | Dimension |  |  | Qty |  | Work Volume |  | BMT |  | Duration
TaskID | Smry | TaskID | Tag Name (133-EE-1006-A) | Predecessor | Resources | Status | Thickness | UoM | Dim | UoM | Dimension | Qty | Qty UOM | Work Volume (WV) | WV UOM | BMT | BMT UOM | Work Duration | ST | Total Duration | Dur UOM
2 |  | 2 | Raw Material
3 |  | 3 | Shell Plate-Sa 516 Gr60
4 |  | 4 | Shell Girth Flange-Sa266 Gr4
5 |  | 5 | Channel Plate-Sa 516 Gr60
6 |  | 6 | Channel Girth Flange-Sa 266 Gr4
7 |  | 7 | Barrel Sheel Plate-Sa 516 Gr 60
8 |  | 8 | Barrel Girth Flange-Sa 266 Gr4
9 |  | 9 | Barrel Dish-Sa 516 Gr 60
10 |  | 10 | Tube Sheet-1-Sa 266 Gr4
11 |  | 11 | Tube Sheet -2-Sa 266 Gr4
12 |  | 12 | Floating Head Flg-Sa 266 Gr4
13 |  | 13 | Floating Head Dish-Sa 516 Gr60
14 |  | 14 | Backing Ring-Sa 266 Gr4
15 |  | 15 | Baffle Plate-Sa 516 Gr60
16 |  | 16 | Sealing Strip Plate-Sa 516 Gr60
17 |  | 17 | Sliding Strip Plate-Sa 516 Gr60
18 |  | 18 | Seal Rod-Sa 36
19 |  | 19 | Noz Srn-Sa 105
20 |  | 20 | Tube -Sa 179
21 |  | 21 | Spacer Tube-Sa 179
22 |  | 22 | Tie Rod-Sa 36
23 |  | 23 | Test Ring & Test Flg-Sa 266 Gr4
24 |  | 24 | Ms Rod For Handle Etc
25 |  | 25 | Ms Plate For Saddle
26 | Yes | 26 | Dish Forming - 24T*1700 Od | 9
|  | 27 | Bar Dish Blank Issuence |  | T |  | 12 |  |  |  |  | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Days
|  | 28 | Bar-Dish Blank Marking - 12 * 764 Od | 27 | F,H |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 0.74 | Dia-mtr | 0.1 | Hr/mtr | 0.074 | 1 | 1.07 | Hrs
|  | 29 | Bar-Dish Blank Marking Inspection | 28 | F,H |  | 12 |  |  |  |  | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 30 | Bar-Dish Blank Cutting | 29 | C,H |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 0.74 | Dia-mtr | 0.25 | RMT | 0.185 | 1 | 1.19 | Hrs
|  | 31 | Bar-Dish Forming | 30 | SC |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 10 | Day | 10 |  | 10 | Days
|  | 32 | Profile Insp | 31 | F,H |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 33 | Heat Treatment Preparation | 32 | SC |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 34 | Stress Releiving- Sub Cont | 33 | SC |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Days
|  | 35 | Removal Of Spiders | 34 | F,H |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 36 | Surface Preparation | 35 | G |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 | 1 | 2 | Days
|  | 37 | Inspection | 36 | F |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 38 | Tpi Inspection | 37 | F |  | 12 |  | 740 | mm | 740 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 39 | Sf Marking | 38 | F,H | enter | 12 |  | 2323 | mm | 2323 mm | 1 | Nos | 7.2989 | Rmt | 0.1 | RMT | 0.72989 | 1 | 1.73 | Hrs
|  | 40 | Sf Cutting | 39 | C,H |  | 12 |  | 2323 | mm | 2323 mm | 1 | Nos | 7.2989 | Rmt | 1 | RMT | 7.2989 | 1 | 8.3 | Hrs
|  | 41 | Sf Gridning & Ep | 40 | G |  | 12 |  | 2323 | mm | 2323 mm | 1 | Nos | 7.2989 | Rmt | 1 | RMT | 7.2989 |  | 7.3 | Hrs
42 | Yes | 42 | Tube Sheet
43 | Yes | 43 | Tube Sheet Machining 1 Off 2 | 10
|  | 44 | Inward Inspection |  |  | enter | 60 |  |  |  |  | 1 | Nos | 1 | Nos | 2 | Day | 2 |  | 2 | Days
|  | 45 | Tube Sheet M/C - 1/2 | 44 | SC |  | 60 |  |  |  |  | 1 | Nos | 1 | Nos | 5 | Day | 5 |  | 5 | Days
46 | Yes | 46 | Tube Sheet Drilling 1 Off 2 | 43
|  | 47 | Tube Sheet Drilling -1/2 |  | SC |  | 60 |  | 212 | Holes | 212 Holes | 1 | Nos | 12.72 | rmt | 0.66667 | Hr/mtr | 0.35333 |  | 0.35 | Days
|  | 48 | Exp Groove+Welding Groove -1/2 | 47 | SC |  | 60 |  | 212 | Holes | 212 Holes | 1 | Nos | 212 | Nos | 0.083333 | Hr/mtr | 0.73611 |  | 0.74 | Days
|  | 49 | Tie Rod, Pulling, Lifting Hole - 1/2 | 48 | SC |  | 60 |  |  |  |  | 1 | Set | 1 | Set | 1 | Day | 1 |  | 1 | Days
|  | 50 | Pass Partition Groove M/C -1/2 | 49 | SC |  | 60 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 51 | Cleaning ,Go/No Go Check -1/2 | 50 | F,H |  | 60 |  | 212 | Holes | 212 Holes | 1 | Nos | 212 | Nos | 0.05 | Hr/no | 10.6 |  | 10.6 | Hrs
|  | 52 | Final Inspection -1/2 | 51 | F,H
53 | Yes | 53 | Tube Sheet Machining 2 Off 2 | 10
|  | 54 | Inward Inspection |  |  |  | 60 |  | 691 | od | 691 od | 1 | Nos | 1 | Nos | 2 | Day | 2 |  | 2 | Days
|  | 55 | Tube Sheet M/C - 2/2 | 54 | SC |  | 60 |  | 691 | od | 691 od | 1 | Nos | 1 | Nos | 5 | Day | 5 |  | 5 | Days
56 | Yes | 56 | Tube Sheet Drilling 2 Off 2
|  | 57 | Tube Sheet Drilling -2/2 |  | SC |  | 60 |  | 212 | Holes | 212 Holes | 1 | Nos | 12.72 | rmt | 0.66667 | Hr/mtr | 0.35333 |  | 0.35 | Days
|  | 58 | Exp Groove+Welding Groove -2/2 | 57 | SC |  | 60 |  | 212 | Holes | 212 Holes | 1 | Nos | 212 | Nos | 0.083333 | Hr/mtr | 0.73611 |  | 0.74 | Days
|  | 59 | Tie Rod, Pulling, Lifting Hole - 2/2 | 58 | SC |  | 60 |  |  |  |  | 1 | Set | 1 | Set | 1 | Day | 1 |  | 1 | Days
|  | 60 | Pass Partition Groove M/C -2/2 | 59 | SC |  | 60 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 61 | Cleaning ,Go/No Go Check -2/2 | 60 | F,H |  | 60 |  | 212 | Holes | 212 Holes | 1 | Nos | 212 | Nos | 0.05 | Hr/no | 10.6 |  | 10.6 | Hrs
|  | 62 | Final Inspection -2/2 | 61 | F,H | [6 empty] | 1 |  | 1050 | Nos | 0.05 | RMT | 52.5 | 1 | 53.5 | Hrs
63 | Yes | 63 | Nozzle Fab | 19
64 | Yes | 64 | Sh Noz Pipe Marking | 3
|  | 65 | 26"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  |  | Nos | 0 | Nos | 1 |  | 0 | 1 | 1 | Hrs
|  | 66 | 2" Mp Con - 2 No | 65 | F,H |  | 2 | nb |  |  |  |  | Nos | 0 | Nos | 0.5 |  | 0 | 1 | 1 | Hrs
|  | 67 | Inspection Of Marking | 66 | F,H | [7 empty] | Nos | 0 | Nos | 0.5 |  | 0 | 1 | 1 | Hrs
68 | Yes | 68 | Sh Noz Pipe Cutting | 64
|  | 69 | 26"Nb Srn - 2 Nos |  | C,H |  | 26 | nb |  |  |  |  | Nos | 0 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 70 | 2" Mp Con - 2 No | 69 | C,H |  | 2 | nb |  |  |  |  | Nos | 0 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 71 | Inspection Of Marking | 70 | C,H | [7 empty] | Nos | 0 | Nos | 0 |  | 0 | 0 |  | Hrs
72 | Yes | 72 | Sh Noz Pipe Ep | 68
|  | 73 | 26"Nb Srn - 2 Nos |  | C,H |  | 26 | nb |  |  |  |  | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
|  | 74 | 2" Mp Con - 2 No | 73 | C,H |  | 2 | nb |  |  |  |  | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 75 | Inspection | 74 | C,H | [7 empty] | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
76 | Yes | 76 | Sh Noz+Flg Fiitup | 72
|  | 77 | 26"Nb Srn - 2 Nos |  | F[2],W,H |  | 26 | [5 empty] | Nos | 2 | Nos | 4 | hr | 8 | 1 | 9 | Hrs
|  | 78 | 2" Mp Con - 2 No | 77 | F[2],W,H |  | 2 | [5 empty] | Nos | 2 | Nos | 0 | hr | 0 | 1 | 1 | Hrs
|  | 79 | Inspection | 78 | F[2],W,H | [7 empty] | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
80 | Yes | 80 | Sh Noz Pipe+Flg Welding | 76
|  | 81 | 26"Nb Srn - 2 Nos |  | W,H |  | 18 | [5 empty] | Nos | #VALUE! | Nos | 6.12 | hr | #VALUE! | 1 | #VALUE! | Hrs
|  | 82 | 2" Mp Con - 2 No | 81 | W,H |  | 2 | [5 empty] | Nos | 0 | Nos |  | hr | 0 |  |  | Hrs
|  | 83 | Inspection | 82 | W,H | [7 empty] | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
84 | Yes | 84 | Sh Noz Pipe Profile Marking | 80
|  | 85 | 26"Nb Srn - 2 Nos |  | F,H |  | 26 | [5 empty] | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 86 | 2" Mp Con - 2 No | 85 | F,H |  | 2 | [5 empty] | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 87 | Inspection | 86 | F,H | [7 empty] | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
88 | Yes | 88 | Sh Nozzle Pipe Profile Cutting | 84
|  | 89 | 26"Nb Srn - 2 Nos |  | G,H |  | 26 | [5 empty] | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 90 | 2" Mp Con - 2 No | 89 | G,H |  | 2 | [5 empty] | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 91 | Inspection | 90 | G,H | [7 empty] | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
92 | Yes | 92 | Sh Nozzle Pipe Pr0File Ep | 88
|  | 93 | 26"Nb Srn - 2 Nos |  | G,H |  | 18 |  | 0 |  | 0 |  | Nos | 0 | Nos | 1 | hr | 0 | 1 | 1 | Hrs
|  | 94 | 2" Mp Con - 2 No | 93 | G,H |  | 18 |  | 0 |  | 0 |  | Nos | 0 | Nos | 0.5 | hr | 0 | 1 | 1 | Hrs
|  | 95 | Inspection | 94 | G,H | [7 empty] | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
96 | Yes | 96 | Ch Noz Pipe Marking | 92
|  | 97 | 16"Nb Srn - 2 Nos |  | F,H |  | 26 | nb | 0 |  | 0 |  | Nos | 0 | Nos | 1 |  | 0 | 1 | 1 | Hrs
|  | 98 | 2" Mp Con - 2 No | 97 | F,H |  | 2 | nb | 0 |  | 0 |  | Nos | 0 | Nos | 1 |  | 0 | 1 | 1 | Hrs
|  | 99 | Inspection | 98 | F,H | [7 empty] | Nos | 0 | Nos | 0.5 |  | 0 | 1 | 1 | Hrs
100 | Yes | 100 | Ch Noz Pipe Cutting | 96
|  | 101 | 16"Nb Srn - 2 Nos |  | C,H |  | 26 | nb |  |  |  |  | Nos | 0 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 102 | 2" Mp Con - 2 No | 101 | C,H |  | 2 | nb |  |  |  |  | Nos | 0 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 103 | Inspection | 102 | C,H | [7 empty] | Nos | 0 | Nos | 0 |  | 0 | 0 |  | Hrs
104 | Yes | 104 | Ch Noz Pipe Ep | 100
|  | 105 | 16"Nb Srn - 2 Nos |  | G,H |  | 26 | nb |  |  |  |  | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
|  | 106 | 2" Mp Con - 2 No | 105 | G,H |  | 2 | nb |  |  |  |  | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 107 | Inspection | 106 | G,H | [7 empty] | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
108 | Yes | 108 | Ch Noz+Flg Fit Up | 104
|  | 109 | 16"Nb Srn - 2 Nos |  | F[2],W,H |  | 26 | nb |  |  |  |  | Nos | 2 | Nos | 4 | hr | 8 | 1 | 9 | Hrs
|  | 110 | 2" Mp Con - 2 No | 109 | F[2],W,H |  | 2 | nb |  |  |  |  | Nos | 2 | Nos | 0 | hr | 0 | 1 | 1 | Hrs
|  | 111 | Inspection | 110 | F[2],W,H | [7 empty] | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
112 | Yes | 112 | Ch Noz Pipe+Flg Welding | 108
|  | 113 | 16"Nb Srn - 2 Nos |  | W,H |  | 18 | [5 empty] | Nos | #VALUE! | Nos | 6.12 | hr | #VALUE! | 1 | #VALUE! | Hrs
|  | 114 | 2" Mp Con - 2 No | 113 | W,H |  | 2 | nb |  |  |  |  | Nos | 0 | Nos |  | hr | 0 |  |  | Hrs
|  | 115 | Inspection | 114 | W,H | [7 empty] | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
116 | Yes | 116 | Ch Noz Pipe Profile Marking | 112
|  | 117 | 16"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  |  | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 118 | 2" Mp Con - 2 No | 117 | F,H |  | 2 | nb |  |  |  |  | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 119 | Inspection | 118 | F,H | [7 empty] | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
120 | Yes | 120 | Ch Nozzle Pipe Profile Cutting | 116
|  | 121 | 16"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  |  | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 122 | 2" Mp Con - 2 No | 121 | F,H |  | 2 | nb |  |  |  |  | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 123 | Inspection | 122 | F,H | [7 empty] | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
124 | Yes | 124 | Ch Nozzle Pipe Pr0File Ep | 120
|  | 125 | 16"Nb Srn - 2 Nos |  | G,H |  | 18 |  | 0 |  | 0 |  | Nos | 0 | Nos | 1 | hr | 0 | 1 | 1 | Hrs
|  | 126 | 2" Mp Con - 2 No | 125 | G,H |  | 18 |  | 0 |  | 0 |  | Nos | 0 | Nos | 0.5 | hr | 0 | 1 | 1 | Hrs
|  | 127 | Inspection | 126 | G,H | [7 empty] | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
128 | Yes | 128 | Saddle & Other
129 | Yes | 129 | Top Saddle Fabrrication | 128
|  | 130 | Plate Issuence | [8 empty] | 1 | Set | 1 | Set | 4 | Day | 4 | 0 | 4 | Days
|  | 131 | Base Marking | 130 | F,H |  | 16 |  |  |  |  | 1 | Set | #VALUE! | mtr | 0.25 | hr | #VALUE! | 1 | #VALUE! | Hrs
|  | 132 | Web Pl Marking | 131 | F,H |  | 12 |  |  |  |  | 1 | Set | #VALUE! | mtr | 0.25 | hr | #VALUE! | 1 | #VALUE! | Hrs
|  | 133 | Ribs Marking | 132 | F,H |  | 12 |  |  |  |  | 1 | Set | #VALUE! | mtr | 0.25 | hr | #VALUE! | 1 | #VALUE! | Hrs
134 | Yes | 134 | Top Sadlle Plate Cutting | 129
|  | 135 | Base Cutting |  | C,H |  | 16 |  | 0 |  | 0 | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs
|  | 136 | Web Pl Cutting | 135 | C,H |  | 12 |  | 0 |  | 0 | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs
|  | 137 | Ribs Cutting | 136 | C,H |  | 12 |  | 0 |  | 0 | 1 | Nos | 0 | mtr | 0.25 | hr | 0 | 1 | 1 | Hrs
|  | 138 | Grinnding Of Above | 137 | G[2] | [8 empty] | 0 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
139 | Yes | 139 | Saddle Fit Up & Welding | 134
|  | 140 | Base + Web Fit Up |  | F,H[2],W | [6 empty] | 1 | Set | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 141 | Base + Web Welding | 140 | W,H |  | 16 |  |  |  |  | 1 | Set | 4 | Nos | 2.8 | hr | 11.2 | 1 | 12.2 | Hrs
|  | 142 | Ribs+Web Fit Up | 141 | F,H[2],W | [6 empty] | 1 | Set | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 143 | Ribs+Web Welding | 142 | W[2],H[2] |  | 12 |  |  |  |  | 1 | Set | 24.8 | Nos | 1.6 | hr | 39.68 | 1 | 40.68 | Hrs
144 | Yes | 144 | Davit Pipe Fabrication | 139
|  | 145 | Pipe Transfere |  | H[4] | [6 empty] | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 146 | Pipe Marking - 6 Nos | 145 | F,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
|  | 147 | Support Pl Marking | 146 | F,H |  | 16 |  |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 148 | Gusset Pl Marking | 147 | F,H |  | 16 |  |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 149 | Base Hub Marking | 148 | F,H |  | 30 |  |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 150 | Pipe Cutting - 6 Nos | 149 | C,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
|  | 151 | Support Pl Cutting | 150 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 152 | Pipe Grinding - 6 Nos | 151 | F,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
|  | 153 | Support Pl Grinding-10 Nos | 152 | G | [6 empty] | 10 | Nos | 10 | Nos | 0.5 | Hr | 5 |  | 5 | Hrs
|  | 154 | Pivot Pl Grinding | 153 | G | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 155 | Pipe Fit Up-2 Nos | 154 | F,H,W | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 156 | Pipe Welding -2 Nos | 155 | W,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 157 | Pivot Pl Welding | 156 | W,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 158 | Support Pl Welding -4 Nos | 157 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
159 | Yes | 159 | Lifting Lug Pad | 144
|  | 160 | Plate Issuence | [8 empty] | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 161 | Lifting Lug Pad Marking | 160 | F,H |  | 16 |  |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 162 | Lifting Lug Pad Cutting | 161 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 163 | Lifting Lugs Pad Grinding | 162 | G,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
164 | Yes | 164 | Lifting Lug Preparation | 159
|  | 165 | Lifting Lugs Marking |  | F,H |  | 12 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 166 | Lifting Lugs Cutting | 165 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 167 | Lifting Lugs Grinding | 166 | G,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 168 | Lifting Lug Drilling | 167 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
169 | Yes | 169 | Channel Cover Handle Prepataion | 164
|  | 170 | Ch Cover Ring Forming |  | F,H | [6 empty] | 2 | Nos | 2 | Nos | 1 | Hr | 2 |  | 2 | Days
|  | 171 | Sliding Sling Forming | 170 | F,H | [6 empty] | 2 | Nos | 2 | Nos | 1 | Hr | 2 |  | 2 | Days
172 | Yes | 172 | Insulation Ring Prparation | 169
|  | 173 | Insulaion Ring Marking |  | F,H |  | 12 | [5 empty] | Nos | 0 | Nos | 4 | Hr | 0 |  | 0 | Hrs
|  | 174 | Insulaion Ring Cutting | 173 | C,H | [7 empty] | Nos | 0 | Nos | 4 | Hr | 0 |  | 0 | Hrs
|  | 175 | Insulaion Ring Hole Marking | 174 | F,H | [7 empty] | Nos | 0 | Nos | 2 | Hr | 0 |  | 0 | Hrs
|  | 176 | Insulaion Ring Hole Drilling | 175 | F,H | [7 empty] | Nos | 0 | Nos | 1 | Hr | 0 |  | 0 | Hrs
177 | Yes | 177 | Baffle & Tb Items Fab
178 | Yes | 178 | Baffle Preparation | 177
|  | 179 | Baffle Plate Transfer | [8 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
|  | 180 | Baffle Marking | 179 | F,H |  | 6 |  |  |  |  | 17 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Hrs
|  | 181 | Baffle Profile Cutting | 180 | C,H | [6 empty] | 17 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Hrs
182 | Yes | 182 | Baffle Bend Removal & Stacking
|  | 183 | Baffle Pl Bend Removal |  | F,H[2] | [6 empty] | 17 | Nos | 17 | Nos | 1 | Hr | 17 |  | 17 | Hrs
|  | 184 | Baffle Pl Stacking | 183 | F,H |  |  |  | 3 | budle | 3 bundle | 2 | Nos | 3 | Nos | 2 | Hr | 6 |  | 6 | Hrs
185 | Yes | 185 | Baffle Drilling | 182
|  | 186 | Baffle Drilling | 185 | SC |  | 6 |  |  |  |  | 2 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 | Days
187 | Yes | 187 | Baffle De Stacking & Chamfering | 185
|  | 188 | Baffle De Stacing |  | F,H | [6 empty] | 2 | Bunch | 4 | Bunch | 6 | Hrs | 24 |  | 24 | Hrs
|  | 189 | Baffle Chamfering | 188 | F | [6 empty] | 17 | Nos | 23544 | Holes | 0.01 |  | 235.44 |  | 235.44 | Days
190 | Yes | 190 | Baffle Stacking & Thro Hole Check | 187
|  | 191 | Stacking |  | F,H | [6 empty] | 2 | Nos | 2 | Nos | 0.25 | Hr | 0.5 |  | 0.5 | Hrs
|  | 192 | Baffle Hole Alingment | 191 | F,H | [6 empty] | 2 | Nos | 1 | Set | 1 | Hrs | 1 |  | 1 | Hrs
|  | 193 | Baffle Hole Re Drill | 192 | SC | [6 empty] | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
|  | 194 | Baffle Od Machining | 193 | SC | [6 empty] | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
|  | 195 | Baffle Cleaning | 194 | H[3] | [6 empty] | 2 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days
196 | Yes | 196 | Support Plate Marking | 190
|  | 197 | Support Plate Transfer | [8 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 198 | Support Marking | 197 | SC |  | 14 |  |  |  |  | 1 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days
|  | 199 | Support Profile Cutting | 198 | SC | [6 empty] | 1 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
200 | Yes | 200 | Support Plate Bend Removal | 196
|  | 201 | Support Pl Bend Removal |  | F,H[3] | [6 empty] | 1 | Nos | 1 | Nos | 2 | Hr | 2 |  | 2 | Hrs
|  | 202 | Support Pl Stacking | 201 | F,H | [7 empty] | Nos | 0 | Nos | 0.5 | Hr | 0 |  | 0 | Hrs
203 | Yes | 203 | Support Plate Drlinng | 200
|  | 204 | Support Drilling | 203 | SC |  | 14 | thk |  |  |  | 1 | Bunch | 1 | Set | 10 | Day | 10 |  | 10
205 | Yes | 205 | Sup Plate De Stacking & Chamfering | 203
|  | 206 | Support De Stacing |  | F,H | [7 empty] | Bunch | 1 | Bunch | 3 | Hrs | 3 |  | 3 | Hrs
|  | 207 | Support Hole Chamfering | 206 | F | [6 empty] | 1 | Plate | 2616 | Holes | 0.01 |  | 26.16 |  | 26.16
208 | Yes | 208 | Tie Rod Preparation | 22
|  | 209 | Tie Rod Matl Transfere | [8 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 210 | Rod Cutting | 209 | F,H | [6 empty] | 6 | Nos | 6 | Nos | 0.25 | Hr | 1.5 |  | 1.5 | Hrs
|  | 211 | Thread Machining. | 210 | L | [6 empty] | 6 | Nos | 6 | Nos | 0.45 | Hr | 2.7 |  | 2.7 | Hrs
|  | 212 | Joining | 211 | W,F,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
213 | Yes | 213 | Spacer Tube Preparation | 21
|  | 214 | Spacer Tube Transfere | [8 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
|  | 215 | Length Cutting 237Nos | 214 | F,H | [6 empty] | 72 | Nos | 72 | Nos | 0.1 | Hr | 7.2 |  | 7.2 | Hrs
|  | 216 | Lenngth Machining | 215 | L | [6 empty] | 72 | Nos | 72 | Nos | 0.1 | Hr | 7.2 |  | 7.2 | Hrs
|  | 217 | Cleaninng | 216 | H[3] | [6 empty] | 72 | Nos | 72 | Nos | 0.016667 | Hr | 1.2 |  | 1.2 | Hrs
218 | Yes | 218 | Sealing Strip Preparation | 16
|  | 219 | Sealing Strip Marking |  | F,H |  | 8 |  | 5757 | mm | 5757 mm | 2 | Nos | 11.514 | Mtr | 0.1 | Hr | 1.1514 |  | 1.15 | Hrs
|  | 220 | Sealing Strip Cutting | 219 | C,H |  | 40 |  | 5757 | mm | 5757 mm | 2 | Nos | 11.514 | Mtr | 0.25 | Hr | 2.8785 |  | 2.88 | Hrs
|  | 221 | Sealing Strip Bend Removal | 220 | F,H[2] |  | 40 |  | 5757 | mm | 5757 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
|  | 222 | Sealing Strip Grinding | 221 | G |  | 40 |  | 5757 | mm | 5757 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
|  | 223 | Sealing Strip Joining | 222 | W,F,H |  | 40 |  | 5757 | mm | 5757 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
|  | 224 | Sealing Strip Dress Up | 223 | G |  | 40 |  | 5757 | mm | 5757 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
225 | Yes | 225 | Sliding Strip Preparation | 17
|  | 226 | Sliding Strip Marking |  | F,H |  | 16 |  | 5757 | mm | 5757 mm | 2 | Nos | 11.514 | Mtr | 0.1 | Hr | 1.1514 |  | 1.15 | Hrs
|  | 227 | Sliding Strip Cutting | 226 | C,H |  | 16 |  | 5757 | mm | 5757 mm | 2 | Nos | 11.514 | Mtr | 0.25 | Hr | 2.8785 |  | 2.88 | Hrs
|  | 228 | Sliding Strip Bend Removal | 227 | F,H[2] |  | 16 |  | 5757 | mm | 5757 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
|  | 229 | Sliding Strip Grinding | 228 | G |  | 16 |  | 5757 | mm | 5757 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
|  | 230 | Sliding Strip Joining | 229 | W,F,H |  | 16 |  | 5757 | mm | 5757 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
|  | 231 | Sliding Strip Dress Up | 230 | G |  | 16 |  | 5757 | mm | 5757 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
232 | Yes | 232 | Seal Rod Preparation | 18
|  | 233 | Seal Rod Issuenece |  | T | [7 empty] | Set | 1 |  | 4 | Day | 4 |  | 4 | Days
|  | 234 | Seal Rod Marking | 233 | F,H |  | 25.4 | dia | 14 |  | 14 |  | Nos | 0 | Nos | 0.25 | Hr | 0 |  | 0 | Hrs
|  | 235 | Seal Rod Cutting | 234 | F,H |  | 25.4 | dia | 14 |  | 14 | 0 | Nos | 0 | Nos | 0.5 | Hr | 0 |  | 0 | Hrs
|  | 236 | Seal Rod Bend Removal | 235 | F,H[2] |  | 25.4 | dia | 14 |  | 14 | 0 | Nos | 0 | Nos | 1 | Hr | 0 |  | 0 | Hrs
237 | Yes | 237 | Shell Fabrication | 236
238 | Yes | 238 | Shell Marking & Cutting | 3
|  | 239 | Sh Plate Trnasfer |  | T | [6 empty] | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days
|  | 240 | Sh-Marking | 239 | F,H[2] |  | 12 |  | 5553 | mm | 5553 mm | 1 | Nos | 5.553 | mtr | 0.1 | hr | 0.5553 | 1 | 1.56 | Hrs
241 | Yes | 241 | Shell Plate Cutting | 238
|  | 242 | Sh-Cutting |  | C,H[2] |  | 12 |  | 5553 | mm | 5553 mm | 3 | Nos | 16.659 | mtr | 0.25 | hr | 4.1647 | 1 | 5.16 | Hrs
243 | Yes | 243 | Sh Pl Side Grinding | 241
|  | 244 | Sh Pl Side Bevel Cutting |  | F,H[3] |  | 12 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 245 | Sh Pl Side Bevel Cutting | 244 | F,H[3] |  | 12 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | 0.5 | hr | 1 | 1 | 2 | Hrs
|  | 246 | Sh Pl Side Bevel Cutting | 245 | F,H[3] |  | 12 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 247 | Sh Pl Side Bevel Cutting | 246 | F,H[3] |  |  |  |  | mm | mm | 1 | Nos | #VALUE! | mtr | #N/A | hr | #VALUE! |  |  | Hrs
248 | Yes | 248 | Shell Plate Edge Preparation | 243
|  | 249 | Sh-Bevel Grinding |  | G,H |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 250 | Sh-Bevel Grinding | 249 | G,H |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 251 | Sh-Bevel Grinding | 250 | G,H |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 252 | Sh-Bevel Grinding | 251 | G,H |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
253 | Yes | 253 | Shell Pre Bending | 248
|  | 254 | Sh-Pre Bend |  | F[2],H |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 255 | Sh-Pre Bend | 254 | F[2],H |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 256 | Sh-Pre Bend | 255 | F[2],H |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 257 | Sh-Pre Bend | 256 | F[2],H |  | 0 |  | 0 | mm | 0 mm | 0 | Nos | 0 | Nos | #N/A | hr | #N/A |  |  | Hrs
258 | Yes | 258 | Shell Pl Pre Bend Cut Off | 253
|  | 259 | Sh-Pre Bend Cut Off |  | F[2],H,C |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 260 | Sh-Pre Bend Cut Off | 259 | F[2],H,C |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 261 | Sh-Pre Bend Cut Off | 260 | F[2],H,C |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 262 | Sh-Pre Bend Cut Off | 261 | F[2],H,C |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 0 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
263 | Yes | 263 | Shell Plate Ls Ep | 258
|  | 264 | Sh-Pre Bend Ls Ep |  | F,H |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 265 | Sh-Pre Bend Ls Ep | 264 | F,H |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 266 | Sh-Pre Bend Ls Ep | 265 | F,H |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 267 | Sh-Pre Bend Ls Ep | 266 | F,H |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
268 | Yes | 268 | Shell Rolling | 263
|  | 269 | Sh-Rolling 1/4 |  | F[2],H |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 270 | Sh-Rolling | 269 | F[2],H |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 271 | Sh-Rolling | 270 | F[2],H |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 272 | Sh-Rolling | 271 | F[2],H |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
273 | Yes | 273 | Shell Cir Length & Ep Correction | 268 | [13 empty] | 0
|  | 274 | Sh-Ls Correction |  | F,H[2] |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 275 | Sh-Ls Correction | 274 | F,H[2] |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 276 | Sh-Ls Correction | 275 | F,H[2] |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 277 | Sh-Ls Correction | 276 | F,H[2] |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
278 | Yes | 278 | Shell Ls Seams Fit Up | 273 | [13 empty] | 0
|  | 279 | Sh-Ls Fit Up |  |  |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 280 | Sh-Ls Fit Up | 279 | F[2],H,W |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 281 | Sh-Ls Fit Up | 280 | F[2],H,W |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 282 | Sh-Ls Fit Up | 281 | F[2],H,W |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
283 | Yes | 283 | Sh Ls Welding Arrangement | 278
|  | 284 | Sh-Ls Weld Arrangement |  | F,H |  | 0 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 285 | Sh-Ls Weld Arrangement | 284 | F,H |  | 0 |  | 2000 | mm | 2000 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 286 | Sh-Ls Weld Arrangement | 285 | F,H |  | 0 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 287 | Sh-Ls Weld Arrangement | 286 | F,H |  | 0 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
288 | Yes | 288 | Shell Long Seam Outer Welding | 283
|  | 289 | Sh-Ls Welding- Top Side |  | W,H |  | 12 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
|  | 290 | Sh-Ls Welding- Top Side | 289 | W,H |  | 12 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | 2.5 | hr | 5 | 1 | 6 | Hrs
|  | 291 | Sh-Ls Welding- Top Side | 290 | W,H |  | 12 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | 2.5 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 292 | Sh-Ls Welding- Top Side | 291 | W,H |  | 12 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
293 | Yes | 293 | Sh Ls Back Chip | 288
|  | 294 | Sh-Ls Welding- Back Chip |  | G |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 295 | Sh-Ls Welding- Back Chip | 294 | G |  | 18 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | 1 | hr | 2 | 1 | 3 | Hrs
|  | 296 | Sh-Ls Welding- Back Chip | 295 | G |  | 18 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 297 | Sh-Ls Welding- Back Chip | 296 | G |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
298 | Yes | 298 | Sh Ls Inner Welding | 293
|  | 299 | Sh-Ls Inner Welding |  | W,H |  | 6 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
|  | 300 | Sh-Ls Inner Welding | 299 | W,H |  | 6 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | 0.9 | hr | 1.8 | 1 | 2.8 | Hrs
|  | 301 | Sh-Ls Inner Welding | 300 | W,H |  | 6 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | 0.9 | hr | 0.9 | 1 | 1.9 | Hrs
|  | 302 | Sh-Ls Inner Welding | 301 | W,H |  | 6 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 0.9 | hr | 0 | 1 | 1 | Hrs
303 | Yes | 303 | Sh Inner Ls Flush Grinding | 298
|  | 304 | Sh Inner Flush Grinding |  | G |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 305 | Sh Inner Flush Grinding | 304 | G |  | 18 |  | 2000 | mm | 2000 mm | 1 | Nos | 2 | mtr | 0.5 | hr | 1 | 1 | 2 | Hrs
|  | 306 | Sh Inner Flush Grinding | 305 | G |  | 18 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | mtr | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 307 | Sh Inner Flush Grinding | 306 | G |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs
308 | Yes | 308 | Sh Ls Radiography | 303
|  | 309 | Sh Ls Welding Rt |  | RT |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 310 | Sh Ls Welding Rt | 309 | RT |  | 18 |  | 2000 | mm | 2000 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 311 | Sh Ls Welding Rt | 310 | RT |  | 18 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 312 | Sh Ls Welding Rt | 311 | RT |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
313 | Yes | 313 | Shell Re Rolling | 308 | [13 empty] | 0
|  | 314 | Sh Re Rolling |  | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 315 | Sh Re Rolling | 314 | F[2],H |  | 18 |  | 2000 | mm | 2000 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 316 | Sh Re Rolling | 315 | F[2],H |  | 18 |  | 1000 | mm | 1000 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 317 | Sh Re Rolling | 316 | F[2],H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
318 | Yes | 318 | Sh Plate Cs Ep Correction | 313
|  | 319 | Sh Cir Ep Correction |  | F,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 320 | Sh Cir Ep Correction | 319 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 321 | Sh Cir Ep Correction | 320 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 322 | Sh Cir Ep Correction | 321 | F,H |  | 18 |  | 0 | mm id | 0 mm id | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
323 | Yes | 323 | Sh Cir Seam First Fit Up | 318
|  | 324 | Sh Cs Fit Up - [Ls1+Ls2] |  | F[2],H,W |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 325 | Sh Cs Tack Dp Check - [Ls1+Ls2] | 324 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
326 | Yes | 326 | Sh Cir Seam First Welding | 323
|  | 327 | Sh Cs Welding Transfere |  | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 328 | Sh Cs Welding Outer [Ls1+Ls2] | 327 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 329 | Sh Cs Welding Back Chip [Ls1+Ls2] | 328 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 330 | Sh Cs Inner Welding [Ls1+Ls2] | 329 | W,H |  | 6 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.9 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 331 | Sh Cs Flush Grinding [Ls1+Ls2] | 330 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
332 | Yes | 332 | Sh Cir Seam Second Fitup | 326
|  | 333 | Sh Cs Fit Up - [Ls2+Ls3] |  | F[2],H,W |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 334 | Sh Cs Tack Dp Check - [Ls2+Ls3] | 333 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
335 | Yes | 335 | Sh Cir Seam Second Welding | 332 | [13 empty] | 0
|  | 336 | Sh Cs Welding Transfere-[Ls2+Ls3] |  | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 337 | Sh Cs Welding Outer [Ls2+Ls3] | 336 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 338 | Sh Cs Welding Back Chip [Ls2+Ls3] | 337 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 339 | Sh Cs Inner Welding [Ls2+Ls3] | 338 | W,H |  | 6 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.9 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 340 | Sh Cs Flush Grinding [Ls2+Ls3] | 339 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
341 | Yes | 341 | Sh Cir Seam Iii Rd Fitup | 335
|  | 342 | Sh Cs Fit Up Cs3 |  | F[2],H,W |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 343 | Sh Cs Tack Dp Check Cs3 | 342 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
344 | Yes | 344 | Sh Cir Seam Third Welding | 341
|  | 345 | Sh Cs Welding Transfere Cs3 |  | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 346 | Sh Cs Welding Outer Cs3 | 345 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 347 | Sh Cs Welding Back Chip Cs3 | 346 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 348 | Sh Cs Inner Welding Cs3 | 347 | W,H |  | 6 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.9 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 349 | Sh Cs Flush Grinding Cs3 | 348 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
350 | Yes | 350 | Sh Final Length Correction | 344
|  | 351 | Sh Length Marking |  | F[2] |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 352 | Length Cutting | 351 | C,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
|  | 353 | Grinding & Ep | 352 | G,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
354 | Yes | 354 | Sh Cir Seam Flange 1 Fitup | 350
|  | 355 | Sh Cs Fit Up Flg Cs1 |  | F[2],H,W |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 356 | Sh Cs Tack Dp Check Flg Cs1 | 355 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
357 | Yes | 357 | Sh Cir Seam Flange 1 Welding | 354
|  | 358 | Sh Cs Welding Transfere |  | F,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 359 | Sh Cs Welding Outer Flg Cs1 | 358 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 360 | Sh Cs Welding Back Chip Flg Cs1 | 359 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 361 | Sh Cs Inner Welding Flg Cs1 | 360 | W,H |  | 6 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.9 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 362 | Sh Cs Flush Grinding Flg Cs1 | 361 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
363 | Yes | 363 | Sh Cs Fit Up Flg2 | 357
|  | 364 | Sh Cs Fit Up Flg 2 |  | F[2],H,W |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 365 | Sh Cs Tack Dp Check Flg2 | 364 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
366 | Yes | 366 | Sh Cs Welding Flg2 | 363
|  | 367 | Sh Cs Welding Transfere Flg2 |  | F,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 368 | Sh Cs Welding Outer Flg2 | 367 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 369 | Sh Cs Welding Back Chip Flg2 | 368 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 370 | Sh Cs Inner Welding Flg2 | 369 | W,H |  | 6 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 0.9 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 371 | Sh Cs Flush Grinding Flg2 | 370 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
372 | Yes | 372 | Nozzle Orientation Marking | 366
|  | 373 | Sh-Noz Orientaion Marking |  | F[2] |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 374 | Sh-Noz Marking-N2A1 | 373 | F[2] |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 375 | Sh-Noz Marking-N2A1 | 374 | F[2] |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
376 | Yes | 376 | Sh Nozzle Openning | 372
|  | 377 | 26"Nb Srn - 1 |  | C,H |  | 18 |  |  |  |  | 1 | Nos | #VALUE! | Mtr | 0.1 | hr | #VALUE! | 1 | #VALUE! | Hrs
|  | 378 | 26"Nb Srn - 1 | 377 | C,H |  | 18 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 0.1 | hr | 0 | 1 | 1 | Hrs
379 | Yes | 379 | Inspection | 376 | C,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
380 | Yes | 380 | Sh Nozzle Ep | 379
|  | 381 | 26"Nb Srn - 1 |  | G |  | 18 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 1 | hr | 0 | 1 | 1 | Hrs
|  | 382 | 26"Nb Srn - 1 | 381 | G |  | 18 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 1 | hr | 0 | 1 | 1 | Hrs
|  | 383 | Inspection | 382 | [7 empty] | 1 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
384 | Yes | 384 | Sh Nozzzle Fit Up | 380
|  | 385 | 26"Nb Srn - 1 |  | F[2],H,W | [6 empty] | 1 | Nos | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 386 | 26"Nb Srn - 1 | 385 | F[2],H,W | [6 empty] | 1 | Nos | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 387 | Dp Check | 386 | [7 empty] | 2 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
388 | Yes | 388 | Sh Nozzle Fit Up Inspection | 384
|  | 389 | 26"Nb Srn - 1 |  | F,H | [6 empty] | 1 | Nos | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
|  | 390 | 26"Nb Srn - 1 | 389 | F,H | [6 empty] | 1 | Nos | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
|  | 391 | Dp Check | 390 | F,H | [6 empty] | 2 | Nos | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
392 | Yes | 392 | Sh Nozzle Welding | 388
|  | 393 | Sh Noz Welding Arrangement |  | T | [6 empty] | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
|  | 394 | Sh-Noz Welding -N1A | 393 | W,H |  | 12 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
|  | 395 | Sh-Noz Welding-N2A1 | 394 | W,H |  | 12 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
|  | 396 | Sh-Noz Welding-N2A2 | 395 | W,H |  | 12 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
|  | 397 | Sh Noz Root Dp Check | 396 | F,H |  | 12 |  | 0 |  | 0 | 2 | Nos | 0 | Mtr | 1 | hr | 0 | 1 | 1 | Hrs
|  | 398 | Sh-Noz Inner Weld -N1A | 397 | H,W |  | 8 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs
|  | 399 | Sh-Noz Inner Weld-N2A1 | 398 | H,W |  | 8 |  | 0 |  | 0 | 1 | Nos | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs
|  | 400 | Sh-Noz Inner Weld-N2A2 | 399 | H,W |  | 8 |  | 0 |  | 0 | 0 | Nos | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs
|  | 401 | Sh Saddle Welding | 392
|  | 402 | Sh-Saddle Pad Fit Up |  | F[2],W,H |  | 12 |  | 649 | mm od | 649 mm od | 2 | Nos | 8.1566 | Nos | 0.5 | Hr | 4.0783 | 1 | 5.08 | Hrs
|  | 403 | Sh-Saddle Pad Welding | 402 | W[2],H[2] |  | 12 |  | 649 | mm od | 649 mm od | 2 | Mtr | 8.1566 | Mtr | 1.6 | Hr | 13.0506 | 1 | 14.05 | Hrs
|  | 404 | Sh-Saddle Matching | 403 | F[2],G[2] |  |  |  | 649 | mm od | 649 mm od | 2 | Nos | 2 | Nos | 8 | Hr | 16 | 1 | 17 | Hrs
|  | 405 | Sh-Saddle Fit Up | 404 | W,F[2],H |  |  |  | 649 | mm od | 649 mm od | 2 | Nos | 2 | Nos | 6 | Hr | 12 | 1 | 13 | Hrs
|  | 406 | Sh-Saddle Welding | 405 | W[2],H[2] |  | 12 |  | 11400 | rmt | 11400 rmt | 1 | Nos | 16.0348 | Mtr | 1.6 | Hr | 25.6557 | 1 | 26.66 | Hrs
|  | 407 | Sh-Saddle Dress Up | 406 | G[2] | [6 empty] | 1 | Nos | 1 | Nos | 8 | Hr | 8 | 1 | 9 | Hrs
408 | Yes | 408 | Sh Davit Arm Welding | 401
|  | 409 | Sh-Davit Arm Arm Match |  | F,G | [6 empty] | 1 | Nos | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
|  | 410 | Sh-Davit Arm Fit Up | 409 | F,H,W | [6 empty] | 1 | Nos | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
|  | 411 | Sh-Davit Arm Welding | 410 | W,H |  | 12 |  |  |  |  | 6 | mtr | 5.16 | Mtr | 1.6 | Hr | 8.256 | 1 | 9.26 | Hrs
412 | Yes | 412 | Sh Nde Clearence | 408
|  | 413 | Sh-Sh Nde Clearence | 412 | F,H |  | 12 |  | 5553 | lg | 5553 lg | 1 | Nos | 1 |  | 12 | Hr | 12 | 1 | 13 | Hrs
|  | 414 | Tpi Inspection | 413 | F,H |  | 12 |  | 5553 | lg | 5553 lg | 1 | Nos | 1 |  | 1 | Day | 1 |  | 1 | Days
415 | Yes | 415 | Channel Fabrication
416 | Yes | 416 | Channel Shell Ls Welding | 5
|  | 417 | Ch Plate Trnasfer | 416 | T | [6 empty] | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Days
|  | 418 | Ch-Marking | 417 | F,H[2] |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 0.1 | hr | 0.0512 | 1 | 1.05 | Hrs
|  | 419 | Ch-Cutting | 418 | C,H |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 0.25 | hr | 0.128 | 1 | 1.13 | Hrs
|  | 420 | Ch Pl Side Grinding | 419 | G |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 0.15 | hr | 0.0768 | 1 | 1.08 | Hrs
|  | 421 | Ch-Bevelling Cir Side | 420 | F,H[3] |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 0.5 | hr | 0.256 | 1 | 1.26 | Hrs
|  | 422 | Ch Ep Grinding | 421 | G |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 1 | hr | 0.512 | 1 | 1.51 | Hrs
423 | Yes | 423 | Channel Sh Rolling | 416
|  | 424 | Ch-Pre Bend |  | F[2],H |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
|  | 425 | Ch-Pre Bend Cut Off | 424 | F[2],C |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 1.024 | mtr | 0.3 | hr | 0.3072 | 1 | 1.31 | Hrs
|  | 426 | Ch Ls Beveling | 425 | F[2] |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 1.024 | mtr | 1 | hr | 1.024 | 1 | 2.02 | Hrs
|  | 427 | Ch-Rolling | 426 | F[2],H |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
428 | Yes | 428 | Ch Shell Ls Fit Up | 423
|  | 429 | Ch-Ls Correction |  | F[2] |  | 18 |  | 512 | mm | 512 mm | 1 | Nos | 1.024 | mtr | 1 | hr | 1.024 | 1 | 2.02 | Hrs
|  | 430 | Ch-Ls Fit Up | 429 | F[2],W,H |  | 18 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 1 | hr | 0.512 | 1 | 1.51 | Hrs
431 | Yes | 431 | Ch Shell Ls Welding | 428
|  | 432 | Ch-Ls Weld Arrangement |  | F,H[2] |  | 18 |  | 512 | mm | 512 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 433 | Ch-Ls Welding- Top Side | 432 | W,H |  | 12 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 2.5 | hr | 1.28 | 1 | 2.28 | Hrs
|  | 434 | Ch-Ls Welding- Back Chip | 433 | G,H |  | 18 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 1 | hr | 0.512 | 1 | 1.51 | Hrs
|  | 435 | Ch-Ls Inner Welding | 434 | W,H |  | 6 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 0.9 | hr | 0.4608 | 1 | 1.46 | Hrs
|  | 436 | Ch-Ls Innner Flush Grind | 435 | G |  | 6 |  | 512 | mm | 512 mm | 1 | Nos | 0.512 | mtr | 0.5 | hr | 0.256 | 1 | 1.26 | Hrs
|  | 437 | Ch Re Rolling | 436 | F[2],H |  | 18 |  | 512 | mm | 512 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
438 | Yes | 438 | Ch Ls Welding Radiography | 431
|  | 439 | Ch Ls Welding Rt |  | RT |  | 18 |  | 512 | mm | 512 mm | 1 | Nos | 1 | Nos | 1 | dya | 1 |  | 1 | Days
440 | Yes | 440 | Ch Cs Flg 1 Fit Up | 438
|  | 441 | Ch Cir Ep Correction |  | F[2] |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 3.9275 | mtr | 0.45 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 442 | Ch Cs Fit Up Flg1 | 441 | F[2],W,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 443 | Ch Cs Tack Dp Check Flg1 | 442 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | mtr | 4 | hr | 4 | 1 | 5 | Hrs
444 | Yes | 444 | Ch Cs Flg 1 Welding | 440
|  | 445 | Ch Cs Welding Transfere |  | F,H[2] |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 446 | Ch Cs Welding Outer Flg1 | 445 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 447 | Ch Cs Welding Back Chip Flg1 | 446 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 448 | Ch Cs Inner Welding Flg 1 | 447 | W,H |  | 8 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 1.36 | hr | 2.6707 | 1 | 3.67 | Hrs
|  | 449 | Ch Cs Flush Grinding Flg1 | 448 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
450 | Yes | 450 | Ch Cs Flg 2 Fit Up | 444
|  | 451 | Ch Length Cutting |  | C,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
|  | 452 | Ch Cir Ep Correction | 451 | F,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 453 | Ch Cs Fit Up Flg2 | 452 | F[2],W,H |  | 8 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 4 | hr | 7.855 | 1 | 8.86 | Hrs
|  | 454 | Ch Cs Tack Dp Check Flg1 | 453 | F |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
455 | Yes | 455 | Ch Cs Flg 2 Welding | 450
|  | 456 | Ch Cs Welding Transfere Flg2 |  | F,H[2] |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 457 | Ch Cs Welding Outer Flg2 | 456 | W,H |  | 12 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 2.5 | hr | 4.9094 | 1 | 5.91 | Hrs
|  | 458 | Ch Cs Welding Back Chip Flg2 | 457 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 1 | hr | 1.9638 | 1 | 2.96 | Hrs
|  | 459 | Ch Cs Inner Welding Flg2 | 458 | W,H |  | 6 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 0.9 | hr | 1.7674 | 1 | 2.77 | Hrs
|  | 460 | Ch Cs Flush Grinding Flg2 | 459 | G |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1.9638 | Mtr | 0.5 | hr | 0.98188 | 1 | 1.98 | Hrs
461 | Yes | 461 | Ch Cs Flg 1 & 2 Welding Rt | 455
|  | 462 | Ch Cs Welding Rt |  | RT |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | n | 1 | Day | 1 |  | 1 | Days
463 | Yes | 463 | Channel Noz Marking | 461
|  | 464 | Ch- Noz Ireientation Nkg |  | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 465 | Ch-Noz Marking- 16"Nb - 2 Nos | 464 | F,H |  | 18 |  | 625 | mm id | 625 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
466 | Yes | 466 | Ch Noz Opnning | 463
|  | 467 | Ch-Noz Openning-Top |  | C,H |  |  |  | 160 | NB | 160 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 468 | Ch-Noz Openning-Bot | 467 | C,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
469 | Yes | 469 | Ch Noz Open Ep | 466
|  | 470 | Ch-Noz Ep -N3A |  | G,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 471 | Ch-Noz Ep-N4A | 470 | G,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
472 | Yes | 472 | Ch Noz Fit Up | 469
|  | 473 | Ch-Noz Fit Up -N3A |  | F[2],W,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 474 | Ch-Noz Fit Up -N4A | 473 | F[2],W,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
475 | Yes | 475 | Ch Noz Fit Up Insp | 472
|  | 476 | Ch-Noz Inspn -N3A |  | F,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 477 | Ch-Noz Inspn-N4A | 476 | F,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
478 | Yes | 478 | Ch Noz Welding | 475
|  | 479 | Ch Noz Welding Arrangement |  | F,H[2] |  |  |  | 400 | NB | 400 NB | 2 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 480 | Ch-Noz Welding -N3A | 479 | W,H |  | 14 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs
|  | 481 | Ch-Noz Welding-N4A | 480 | W,H |  | 14 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs
|  | 482 | Ch Noz Root Dp Check | 481 | W,H |  | 14 |  | 407 | mm | 407 mm | 2 | Nos | 2 | Nos | 1 | hr | 2 | 1 | 3 | Hrs
|  | 483 | Ch-Noz Inner Weld -N3A | 482 | W,H |  | 6 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs
|  | 484 | Ch-Noz Inner Weld-N4A | 483 | W,H |  | 6 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs
|  | 485 | Rf Pad Fit Up & Nozzle Fit Up | 484 | W,H |  |  |  | 400 | NB | 400 NB | 2 | Nos | 2 | Set | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 486 | Rf Pad Fit Up Welding | 485 | G,H |  | 18 |  |  |  |  | 2 | Nos | 2.5538 | Mtr | 6.8 | hr | 17.366 | 1 | 18.37 | Hrs
|  | 487 | Noz Welding Flush Grind- 16"Nb | 486 | G |  |  |  | 407 | mm | 407 mm | 2 | NoS | 2.5538 | Nos | 0.15 | hr | 0.38307 | 1 | 1.38 | Hrs
488 | Yes | 488 | Channel Pp Plate Fit Up | 478
|  | 489 | Ch- Pp Plate Fit Up |  | F[2],H,W |  | 24 |  | 14465 |  | 14465 | 1 | Nos | 14.465 | Nos | 0.5 | hr | 7.2325 | 1 | 8.23 | Hrs
|  | 490 | Ch- Pp Plate Fit Up Insp | 489 | F,H |  | 24 |  | 1560 | id | 1560 id | 3 | Nos | 4 | Nos | 0.5 | hr | 2 | 1 | 3 | Hrs
491 | Yes | 491 | Ch Pp Plate Welding | 488
|  | 492 | Ch- Pp Plate Welding |  | W,H |  | 24 |  | 1480 |  | 1480 | 3 | Nos | 4.44 |  | 11.2 | hr | 49.728 | 1 | 50.73 | Hrs
|  | 493 | Ch- Pp Plate Face Grinding | 492 | G,H |  | 12 |  | 12310 | mm | 12310 mm | 1 | Nos | 12.31 | Nos | 1.6 | hr | 19.696 | 1 | 20.7 | Hrs
494 | Yes | 494 | Channel Davit Arm Welding | 491
|  | 495 | Ch-Davit Arm Arm Match |  | F,H |  | 18 |  | 1480 | lg | 1480 lg | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 496 | Ch-Davit Arm Fit Up | 495 | F,W,H |  | 18 |  | 1251 | lg | 1251 lg | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 497 | Ch-Davit Arm Welding | 496 | W,H |  | 12 |  | 6 |  | 6 | 1 | Nos | 6 | mtr | 1.6 | hr | 9.6 | 1 | 10.6 | Hrs
498 | Yes | 498 | Channel Nde & Pwht | 494
|  | 499 | Ch All Welding Dressup & Dp Check |  | G[2] |  | 18 |  | 1480 | lg | 1480 lg | 1 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 500 | Ch-Ch Nde Clearence | 499 | F |  | 18 |  | 1480 | lg | 1480 lg | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Hrs
501 | Yes | 501 | Barrel Fabrication
502 | Yes | 502 | Barrel Sh Plate Cutting & Ep | 7 | [7 empty] | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Hrs
|  | 503 | Barrel Plate Trnasfer |  | T |  | 18 |  | 373 | mm | 373 mm | 1 | Nos | 0.373 | mtr | 0.1 | Hr/mtr | 0.0373 | 1 | 1.04 | Hrs
|  | 504 | Barrel-Marking | 503 | F,H[2] |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 0.25 | Hr/mtr | 2.825 | 1 | 3.83 | Hrs
|  | 505 | Barrel-Cutting | 504 | C,H |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 0.15 | Hr/mtr | 1.695 | 1 | 2.7 | Hrs
|  | 506 | Barrel Pl Side Grinding | 505 | G |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 0.5 | Hr/mtr | 5.65 | 1 | 6.65 | Hrs
|  | 507 | Barrel-Bevelling Cir Side | 506 | F,H[3] |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs
|  | 508 | Ch Ep Grinding | 507 | G |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs
509 | Yes | 509 | Bar Shell Rolling | 502
|  | 510 | Barrel-Pre Bend |  | F[2],H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
|  | 511 | Barrel-Pre Bend Cut Off | 510 | F[2],C |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 3.328 | Nos | 0.3 | hr | 0.9984 | 1 | 2 | Hrs
|  | 512 | Barrel -Pre Ls Ep | 511 | F[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs
|  | 513 | Barrel-Rolling | 512 | F[2],H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
514 | Yes | 514 | Barrel Shell Ls Fit Up | 509
|  | 515 | Barrel-Ls Correction |  | F[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs
|  | 516 | Barrel-Ls Fit Up | 515 | F[2],W,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs
517 | Yes | 517 | Barrel Shell Ls Welding | 514
|  | 518 | Barrel-Ls Weld Arrangement |  | F,H[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 519 | Barrel-Ls Welding- Top Side | 518 | W,H |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 2.5 | hr | 4.16 | 1 | 5.16 | Hrs
|  | 520 | Barrel-Ls Welding- Back Chip | 519 | G,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs
|  | 521 | Barrel-Ls Inner Welding | 520 | W,H |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.9 | hr | 1.4976 | 1 | 2.5 | Hrs
|  | 522 | Barrel-Ls Innner Flush Grind | 521 | G |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.5 | hr | 0.832 | 1 | 1.83 | Hrs
|  | 523 | Barrel Re Rolling | 522 | F[2],H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
524 | Yes | 524 | Barrel Ls Welding Rt
|  | 525 | Bar Ls Welding Rt |  | RT |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
526 | Yes | 526 | Barrel Shell Cs Flg 1 Fit Up | 524
|  | 527 | Barrel Cir Ep Correction |  | F[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 528 | Barrel Cs Fit Up Flg1 | 527 | F[2],W,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Nos | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 529 | Barrel Cs Tack Dp Check Flg1 | 528 | F,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Nos | 0.25 | hr | 1.3071 | 1 | 2.31 | Hrs
530 | Yes | 530 | Barrel Sh Cs Flg 1 Welding | 526
|  | 531 | Barrel Cs Welding Transfere |  | F,H[2] |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 532 | Barrel Cs Welding Outer Flg1 | 531 | W,H |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs
|  | 533 | Barrel Cs Welding Back Chip Flg1 | 532 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 534 | Barrel Cs Inner Welding Flg 1 | 533 | W,H |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs
|  | 535 | Barrel Cs Flush Grinding Flg1 | 534 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs
536 | Yes | 536 | Barrel Cs Fit Up With Dish | 530 | [13 empty] | 0
|  | 537 | Barrel Length Cutting | 536 | C,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 538 | Barrel Ep | 537 | F,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 539 | Barrel Cs Fit Up Dish | 538 | F[2],W,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 4 | hr | 20.9132 | 1 | 21.91 | Hrs
|  | 540 | Barrel Cs Tack Dp Check Dish | 539 | F |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Nos | 3.5 | hr | 18.299 | 1 | 19.3 | Hrs
541 | Yes | 541 | Barrel Cs Welding With Dish | 536
|  | 542 | Barrel Cs Welding Transfere Dish |  | F,H[2] |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 543 | Barrel Cs Welding Outer Dish | 542 | W,H |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs
|  | 544 | Barrel Cs Welding Back Chip Dish | 543 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 545 | Barrel Cs Inner Welding Dish | 544 | W,H |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs
|  | 546 | Barrel Cs Flush Grinding Dish | 545 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs
547 | Yes | 547 | Barrel Cs Flg 1 & Dish Welding Rt | 541
|  | 548 | Barrel Cs Welding Rt |  | RT |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
549 | Yes | 549 | Barrel Noz Oreination Marking | 547
|  | 550 | Barrel- Noz Ireientation Nkg |  | F,H |  | 20 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 551 | Barrel-Noz Marking- 2 | 550 | F,H |  | 20 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
552 | Yes | 552 | Barrel Nozzle Oppening | 549
|  | 553 | Barrel-Noz Openning-40 Nb - Lwn |  | C,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 554 | Barrel-Noz Openning-40 Nb - Lwn | 553 | C,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
555 | Yes | 555 | Barrel Noz Edge Preparation | 552
|  | 556 | Barrel-Noz Openning-40 Nb - Lwn |  | G,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
|  | 557 | Barrel-Noz Openning-40 Nb - Lwn | 556 | G,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
558 | Yes | 558 | Barrel Nozzzle Fit Up | 555
|  | 559 | Barrel-Noz Fit Up -N5A |  | F[2],W,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 560 | Barrel-Noz Fit Up -N6A | 559 | F[2],W,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
561 | Yes | 561 | Barrel Noz Fit Up Inspection | 558
|  | 562 | Barrel-Noz Inspn -5A |  | INS |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 563 | Barrel-Noz Inspn-6A | 562 | INS |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
564 | Yes | 564 | Barrel Nozzle Welding | 561
|  | 565 | Barrel Noz Welding Arrangement |  | T |  | 40 | NB | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 566 | Barrel-Noz Welding -N5A | 565 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
|  | 567 | Barrel-Noz Welding-N6A | 566 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
|  | 568 | Barrel Noz Root Dp | 567 | F,H |  |  |  | 75 | mm | 75 mm | 2 | Nos | 2 |  | 0.5 | hr | 1 | 1 | 2 | Hrs
|  | 569 | Barrel-Noz Inner Welding -N5A | 568 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
|  | 570 | Barrel-Noz Inner Welding-N6A | 569 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
571 | Yes | 571 | Barrel Noz Inner Weld Flush Grind | 564
|  | 572 | Barrel All Welding Dressup & Dp |  | G[2] |  | 20 |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 573 | Barrel-Barrel Nde Clearence | 572 | F |  | STD |  | 40 | NB | 40 NB | 1 | NoS | 1 | Nos | 1 | Day | 1 |  | 1 | Hrs
574 | Yes | 574 | Fl Head Fabrication
575 | Yes | 575 | Flaoting Head Dish Forming | 13
|  | 576 | Fl Head Dish Pl Issue |  | T | [6 empty] | 1 | Nos | 1 |  | 4 | Day | 4 |  | 4 | Days
|  | 577 | Fl Head Pl Marking | 576 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.1 | hr | 0.62337 | 1 | 1.62 | Hrs
|  | 578 | Fl Head Pl Stamping | 577 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Hr | 1 | 1 | 2 | Hrs
|  | 579 | Fl Head Pl Cutting | 578 | C,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.25 | hr | 1.5584 | 1 | 2.56 | Hrs
|  | 580 | Fl Head Pl Grinding | 579 | G |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | mtr | 1 | hr | 6.2337 | 1 | 7.23 | Hrs
581 | Yes | 581 | Fl Head Formig | 575
|  | 582 | Fl Head Forming |  | SC |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 10 | Day | 10 |  | 10 | Days
|  | 583 | Fl Head Profile Check | 582 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
584 | Yes | 584 | Fl Head Cutting | 581
|  | 585 | Fl Head Marking |  | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 4 | Hr/No | 4 |  | 4 | Hrs
|  | 586 | Fl Head Cutting | 585 | C,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 0.1 | hr | 0.62337 | 2 | 2.62 | Hrs
587 | Yes | 587 | Fl Head Ep | 584
|  | 588 | Fl Head Grinding |  | G,H |  | 25 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs
589 | Yes | 589 | Fl Head Fit Up | 587,12
|  | 590 | Fl Head Fit Up |  | F[2],W,H |  | 25 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs
591 | Yes | 591 | Fl Head Welding | 589
|  | 592 | Fl Head Welding |  | W,H |  | 30 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 16.8 | hr | 104.7266 | 2 | 106.73 | Hrs
|  | 593 | Fl Head Pp Plate Fit Up | 592 | F[2],H,W |  | 16 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 594 | Fl Head Pp Pl Welding | 593 | W,H |  | 16 |  | 3000 | mm id | 3000 mm id | 1 | Nos | 3 | Mtr | 2.8 | hr | 8.4 | 2 | 10.4 | Hrs
|  | 595 | Fl Head Pp Pl Level Grinding | 594 | F,H |  | 16 |  | 3000 | mm id | 3000 mm id | 1 | Nos | 1 | Nos | 6 | hr | 6 | 1 | 7 | Hrs
|  | 596 | Fl Head Inspection | 595 | F |  | 16 |  | 3000 | mm id | 3000 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
597 | Yes | 597 | Fl Head Sr & Machining | 591
|  | 598 | Fl Head Sr |  | SC |  |  |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 3 | Day | 3 | 0 | 3 | Hrs
|  | 599 | Fl Head Final Machining | 598 | SC |  |  |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 4 | Day | 4 | 0 | 4 | Hrs
|  | 600 | Fl Head Hole Marking | 599 | F,H |  |  |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 0.5 | Day | 0.5 | 0 | 0.5 | Hrs
|  | 601 | Fl Head Hole Drilling | 600 | SC |  | 140 | mm | 1550 | mm id | 1550 mm id | 72 | Hole | 1 | Nos | 4 | Day | 4 | 0 | 4 | Hrs
|  | 602 | Fl Head Final Inspection | 601 | F,H |  | 140 | mm | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 | 0 | 1 | Hrs
603 | Yes | 603 | Tube Bundle Fabrication
604 | Yes | 604 | Tube Bundle Assy | 46,177
|  | 605 | Frame Set Up & Tube Sht Set Up |  | F[2],W |  | 145 |  | 1308 | tube | 1308 tube |  |  | 1 |  | 1.5 | Day | 1.5 | 0 | 1.5 | Hrs
|  | 606 | Skeliton Assy- 19 Baffle | 605 | F[2],H[3] |  |  |  | 19 | baffle | 19 baffle | 1 | Nos | 19 | Nos | 0.5 | hr | 9.5 | 1 | 10.5 | Hrs
607 | Yes | 607 | Tube Insert | 604,412
|  | 608 | Tube Insert |  | F,H[4] |  | 25.4 | dia | 7000 | lg | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
|  | 609 | Seal Rod Insert & Weld | 608 | F[2],W,H[2] |  | 25.4 | dia | 5134 | lg | 5134 lg | 14 | Nos | 14 | Nos | 0.5 | Hr/no | 7 | 1 | 8 | Hrs
|  | 610 | Tube Insert | 609 | F,H[4] |  | 25.4 | dia | 7000 | lg | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
611 | Yes | 611 | Sliding Strip Fit Up Welding | 607
|  | 612 | Sealing Strip Fit Up |  | F,H |  | 8 |  | 4592 | mm lg | 4592 mm lg | 2 | Nos | 2 | Nos | 3 | Hr/no | 6 | 1 | 7 | Hrs
|  | 613 | Sliding Strip Welding | 612 | W,H |  | 8 |  | 60 | joints | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
|  | 614 | Seal/Slid Trip Weld Grind | 613 | G |  | 1500 |  | 60 | joints | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
615 | Yes | 615 | Tube Bundle Insert | 611
|  | 616 | Tube Bundle Insert In Shell |  | F[3],H[8] |  |  |  | 7000 | lg | 7000 lg | 1 | Nos | 1 | Nos | 16 | Hr/no | 16 | 1 | 17 | Hrs
|  | 617 | Fl Head Tube Sht Fixing | 616,56 | F[2],H[4] |  | 145 | mm |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr/no | 4 | 1 | 5 | Hrs
|  | 618 | Test Flg & Gland Assy | 617 | F[3],H[6] |  | 165 | mm | 1490 |  | 1490 | 1 | Nos | 56 | Bolts | 0.16667 | hr | 9.3333 | 1 | 10.33 | Hrs
619 | Yes | 619 | Tube Expansion In Grooves | 615
|  | 620 | Tube Exp - St Side - 1 Stage |  | F,H[2] |  | 150 | mm | 1308 | nos | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.016667 | hr | 21.8 | 1 | 22.8 | Hrs
|  | 621 | Tube Exp - Fl Side - 1 Stage | 620 | F,H[2] |  | Servo |  | 1308 | nos | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.0083333 | hr | 10.9 | 1 | 11.9 | Hrs
|  | 622 | Tube Trimming Fl Side | 621 | F,H |  | Servo |  | 1308 | nos | 1308 nos | 1308 | Nos | 1308 | Trimm | 0.033333 | hr | 43.6 | 1 | 44.6 | Hrs
|  | 623 | Tube Exp Both Side - 4 Stage | 622 | F[2],H[2] |  | 150 | mm | 2616 | Roll | 2616 Roll | 2616 | Nos | 2616 | Rolling | 0.0083333 | hr | 21.8 | 1 | 22.8 | Hrs
624 | Yes | 624 | Tube Exp- Pnuematic Test | 619
|  | 625 | Tube Exp Pnuematic Test |  | F[2],H[2] | [6 empty] | 1 | Nos | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
|  | 626 | Pnuematic Test Tpi Witness | 625 | F,H | [6 empty] | 1 | Nos | 1 | Test | 1 | Day | 1 |  | 1 | Hrs
|  | 627 | Cleaning | 626 | F,H[3] | [6 empty] | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
628 | Yes | 628 | Tube Tube Sheet Welding- Ft Side | 624
|  | 629 | Tube Welding - St Side Root |  | TW,H |  | 2.77 |  | 25.4 | od | 25.4 od | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 630 | Tube Welding - St Side Root Dp | 629 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 631 | Tube Welding - St Side Final Weld | 630 | TW,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 632 | Tube Welding - St Side Final Dp | 631 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
633 | Yes | 633 | Tube To Tube Sheet Welding - Fl Head Side | 628
|  | 634 | Tube Welding - Flh Side Root |  | TW,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 635 | Tube Welding - Flh Side Root Dp | 634 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 636 | Tube Welding - Flh Side Final Weld | 635 | TW,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 637 | Tube Welding - Flh Side Final Dp | 636 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
638 | Yes | 638 | Shell Side Hydro | 633
|  | 639 | Shell Side Water Filling | [8 empty] | 1 | Nos | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
|  | 640 | Shell Side Hydro | 639 | F[2],H[2] |  |  |  | 6130 | lg | 6130 lg | 1 | Nos | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs
|  | 641 | Shell Side Tpi Witness | 640 | F[2] |  |  |  | 6130 | lg | 6130 lg | 1 | Nos | 1 | Test | 1 | Day | 1 | 0 | 1 | Hrs
|  | 642 | De Watering & Dismantle Of Gland | 641 | F[2],H[4] |  |  |  | 6130 | lg | 6130 lg | 1 | Nos | 1 | Test | 4 | hr | 4 | 0 | 4 | Hrs
643 | Yes | 643 | Dish Forming - 24T*1700 Od | 1263
|  | 644 | Bar Dish Blank Issuence |  | T |  | 24 |  | ID dish |  | ID dish | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Days
|  | 645 | Bar-Dish Blank Marking - 24 * 1670 | 644 | F,H |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 6.723 | Dia-mtr | 0.1 | Hr/mtr | 0.6723 | 1 | 1.67 | Hrs
|  | 646 | Bar-Dish Blank Marking Inspection | 645 | F,H |  | 24 |  |  |  |  | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 647 | Bar-Dish Blank Cutting | 646 | C,H |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 6.723 | Dia-mtr | 0.25 | RMT | 1.6807 | 1 | 2.68 | Hrs
|  | 648 | Bar-Dish Forming | 647 | SC |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 10 | Day | 10 |  | 10 | Days
|  | 649 | Profile Insp | 648 | F,H |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 650 | Heat Treatment Preparation | 649 | SC |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 651 | Stress Releiving- Sub Cont | 650 | SC |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Days
|  | 652 | Removal Of Spiders | 651 | F,H |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 653 | Surface Preparation | 652 | G |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 | 1 | 2 | Days
|  | 654 | Inspection | 653 | F |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 655 | Tpi Inspection | 654 | F |  | 24 |  | 6723 | mm | 6723 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 656 | Sf Marking | 655 | F,H | enter | 24 |  | 1692 | od | 1692 od | 1 | Nos | 5.3163 | Rmt | 0.1 | RMT | 0.53163 | 1 | 1.53 | Hrs
|  | 657 | Sf Cutting | 656 | C,H |  | 24 |  | 1692 | od | 1692 od | 1 | Nos | 5.3163 | Rmt | 1 | RMT | 5.3163 | 1 | 6.32 | Hrs
|  | 658 | Sf Gridning & Ep | 657 | G |  | 24 |  | 1692 | od | 1692 od | 1 | Nos | 5.3163 | Rmt | 1 | RMT | 5.3163 |  | 5.32 | Hrs
659 | Yes | 659 | Tube Sheet
660 | Yes | 660 | Tube Sheet Machining 1 Off 2 | 1264
|  | 661 | Inward Inspection |  |  | enter | 145 |  | 1692 | od | 1692 od | 1 | Nos | 1 | Nos | 2 | Day | 2 |  | 2 | Days
|  | 662 | Tube Sheet M/C - 1/2 | 661 | SC |  | 145 |  | 1692 | od | 1692 od | 1 | Nos | 1 | Nos | 5 | Day | 5 |  | 5 | Days
663 | Yes | 663 | Tube Sheet Drilling 1 Off 2 | 660
|  | 664 | Tube Sheet Drilling -1/2 |  | SC |  | 145 |  | 1308 | holes | 1308 holes | 1 | Nos | #VALUE! | rmt | 0.66667 | Hr/mtr | #VALUE! |  | #VALUE! | Days
|  | 665 | Exp Groove+Welding Groove -1/2 | 664 | SC |  | 145 |  | 1308 | holes | 1308 holes | 1 | Nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.54 | Days
|  | 666 | Tie Rod, Pulling, Lifting Hole - 1/2 | 665 | SC |  | 145 |  |  |  |  | 1 | Set | 1 | Set | 1 | Day | 1 |  | 1 | Days
|  | 667 | Pass Partition Groove M/C -1/2 | 666 | SC |  | 145 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 668 | Cleaning ,Go/No Go Check -1/2 | 667 | F,H |  | 145 |  | 1308 | holes | 1308 holes | 1 | Nos | 1308 | Nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs
|  | 669 | Final Inspection -1/2 | 668 | F,H
670 | Yes | 670 | Tube Sheet Machining 2 Off 2 | 1264
|  | 671 | Inward Inspection |  |  |  | 145 |  | 1670 | od | 1670 od | 1 | Nos | 1 | Nos | 2 | Day | 2 |  | 2 | Days
|  | 672 | Tube Sheet M/C - 2/2 | 671 | SC |  | 145 |  | 1548 | od | 1548 od | 1 | Nos | 1 | Nos | 5 | Day | 5 |  | 5 | Days
673 | Yes | 673 | Tube Sheet Drilling 2 Off 2
|  | 674 | Tube Sheet Drilling -2/2 |  | SC |  | 145 |  | 1308 | holes | 1308 holes | 1 | Nos | #VALUE! | rmt | 0.66667 | Hr/mtr | #VALUE! |  | #VALUE! | Days
|  | 675 | Exp Groove+Welding Groove -2/2 | 674 | SC |  | 145 |  | 1308 | holes | 1308 holes | 1 | Nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.54 | Days
|  | 676 | Tie Rod, Pulling, Lifting Hole - 2/2 | 675 | SC |  | 145 |  |  |  |  | 1 | Set | 1 | Set | 1 | Day | 1 |  | 1 | Days
|  | 677 | Pass Partition Groove M/C -2/2 | 676 | SC |  | 145 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 678 | Cleaning ,Go/No Go Check -2/2 | 677 | F,H |  | 145 |  | 1308 | holes | 1308 holes | 1 | Nos | 1308 | Nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs
|  | 679 | Final Inspection -2/2 | 678 | F,H | [6 empty] | 1 |  | 1050 | Nos | 0.05 | RMT | 52.5 | 1 | 53.5 | Hrs
680 | Yes | 680 | Nozzle Fab
681 | Yes | 681 | Sh Noz Pipe Marking | 1099
|  | 682 | 26"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 1 | Hr/no | 2 | 1 | 3 | Hrs
|  | 683 | 2" Mp Con - 2 No | 682 | F,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 1 | Hr/no | 2 | 1 | 3 | Hrs
|  | 684 | Inspection Of Marking | 683 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr/no | 2 | 1 | 3 | Hrs
685 | Yes | 685 | Sh Noz Pipe Cutting | 681
|  | 686 | 26"Nb Srn - 2 Nos |  | C,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 | Hr/no | 0 | 0 |  | Hrs
|  | 687 | 2" Mp Con - 2 No | 686 | C,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 | Hr/no | 0 | 0 |  | Hrs
|  | 688 | Inspection Of Marking | 687 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0 | Hr/no | 0 | 0 |  | Hrs
689 | Yes | 689 | Sh Noz Pipe Ep | 685
|  | 690 | 26"Nb Srn - 2 Nos |  | C,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
|  | 691 | 2" Mp Con - 2 No | 690 | C,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 692 | Inspection | 691 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
693 | Yes | 693 | Sh Noz+Flg Fiitup | 689
|  | 694 | 26"Nb Srn - 2 Nos |  | F[2],W,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 4 | hr | 8 | 1 | 9 | Hrs
|  | 695 | 2" Mp Con - 2 No | 694 | F[2],W,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 | hr | 0 | 1 | 1 | Hrs
|  | 696 | Inspection | 695 | F[2],W,H | [6 empty] | 4 | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
697 | Yes | 697 | Sh Noz Pipe+Flg Welding | 693
|  | 698 | 26"Nb Srn - 2 Nos |  | W,H |  | 18 |  | 3054 | mm | 3054 mm | 2 | Nos | 6.108 | Nos | 6.12 | hr | 37.381 | 1 | 38.38 | Hrs
|  | 699 | 2" Mp Con - 2 No | 698 | W,H |  | 2 | nb | 272 | mm | 272 mm | 2 | Nos | 0 | Nos |  | hr | 0 |  |  | Hrs
|  | 700 | Inspection | 699 | W,H | [6 empty] | 4 | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
701 | Yes | 701 | Sh Noz Pipe Profile Marking | 697
|  | 702 | 26"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  | 2 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 703 | 2" Mp Con - 2 No | 702 | F,H |  | 2 | nb |  |  |  | 2 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 704 | Inspection | 703 | F,H | [6 empty] | 4 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
705 | Yes | 705 | Sh Nozzle Pipe Profile Cutting | 701
|  | 706 | 26"Nb Srn - 2 Nos |  | G,H |  | 26 | nb |  |  |  | 2 | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 707 | 2" Mp Con - 2 No | 706 | G,H |  | 2 | nb |  |  |  | 2 | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 708 | Inspection | 707 | G,H | [6 empty] | 4 | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
709 | Yes | 709 | Sh Nozzle Pipe Pr0File Ep | 705
|  | 710 | 26"Nb Srn - 2 Nos |  | G,H |  | 18 |  | 3054 | mm | 3054 mm | 2 | Nos | 6.108 | Nos | 1 | hr | 6.108 | 1 | 7.11 | Hrs
|  | 711 | 2" Mp Con - 2 No | 710 | G,H |  | 18 |  | 272 | mm | 272 mm | 2 | Nos | 0.544 | Nos | 0.5 | hr | 0.272 | 1 | 1.27 | Hrs
|  | 712 | Inspection | 711 | G,H | [6 empty] | 4 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
713 | Yes | 713 | Ch Noz Pipe Marking | 709
|  | 714 | 16"Nb Srn - 2 Nos |  | F,H |  | 26 | nb | 3054 | mm | 3054 mm | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
|  | 715 | 2" Mp Con - 2 No | 714 | F,H |  | 2 | nb | 272 | mm | 272 mm | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
|  | 716 | Inspection | 715 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs
717 | Yes | 717 | Ch Noz Pipe Cutting | 713
|  | 718 | 16"Nb Srn - 2 Nos |  | C,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 719 | 2" Mp Con - 2 No | 718 | C,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 720 | Inspection | 719 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
721 | Yes | 721 | Ch Noz Pipe Ep | 717
|  | 722 | 16"Nb Srn - 2 Nos |  | G,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
|  | 723 | 2" Mp Con - 2 No | 722 | G,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
|  | 724 | Inspection | 723 | G,H | [6 empty] | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
725 | Yes | 725 | Ch Noz+Flg Fit Up | 721
|  | 726 | 16"Nb Srn - 2 Nos |  | F[2],W,H |  | 26 | nb |  |  |  | 2 | Nos | 2 | Nos | 4 | hr | 8 | 1 | 9 | Hrs
|  | 727 | 2" Mp Con - 2 No | 726 | F[2],W,H |  | 2 | nb |  |  |  | 2 | Nos | 2 | Nos | 0 | hr | 0 | 1 | 1 | Hrs
|  | 728 | Inspection | 727 | F[2],W,H | [6 empty] | 4 | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
729 | Yes | 729 | Ch Noz Pipe+Flg Welding | 725
|  | 730 | 16"Nb Srn - 2 Nos |  | W,H |  | 18 |  | 3054 | mm | 3054 mm | 2 | Nos | 6.108 | Nos | 6.12 | hr | 37.381 | 1 | 38.38 | Hrs
|  | 731 | 2" Mp Con - 2 No | 730 | W,H |  | 2 | nb | 272 | mm | 272 mm | 2 | Nos | 0 | Nos |  | hr | 0 |  |  | Hrs
|  | 732 | Inspection | 731 | W,H | [6 empty] | 4 | Nos | 4 | Nos | 0.25 | hr | 1 | 1 | 2 | Hrs
733 | Yes | 733 | Ch Noz Pipe Profile Marking | 729
|  | 734 | 16"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  | 2 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 735 | 2" Mp Con - 2 No | 734 | F,H |  | 2 | nb |  |  |  | 2 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 736 | Inspection | 735 | F,H | [6 empty] | 4 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
737 | Yes | 737 | Ch Nozzle Pipe Profile Cutting | 733
|  | 738 | 16"Nb Srn - 2 Nos |  | F,H |  | 26 | nb |  |  |  | 2 | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 739 | 2" Mp Con - 2 No | 738 | F,H |  | 2 | nb |  |  |  | 2 | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
|  | 740 | Inspection | 739 | F,H | [6 empty] | 4 | Nos | 0 | Nos |  | hr | 0 | 1 | 1 | Hrs
741 | Yes | 741 | Ch Nozzle Pipe Pr0File Ep | 737
|  | 742 | 16"Nb Srn - 2 Nos |  | G,H |  | 18 |  | 3054 | mm | 3054 mm | 2 | Nos | 6.108 | Nos | 1 | hr | 6.108 | 1 | 7.11 | Hrs
|  | 743 | 2" Mp Con - 2 No | 742 | G,H |  | 18 |  | 272 | mm | 272 mm | 2 | Nos | 0.544 | Nos | 0.5 | hr | 0.272 | 1 | 1.27 | Hrs
|  | 744 | Inspection | 743 | G,H | [6 empty] | 4 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
745 | Yes | 745 | Saddle & Other
746 | Yes | 746 | Top Saddle Fabrrication | 745
|  | 747 | Plate Issuence | [8 empty] | 1 | Set | 1 | Set | 4 | Day | 4 | 0 | 4 | Days
|  | 748 | Base Marking | 747 | F,H |  | 30/25 |  | 9 | rmt | 9 rmt | 1 | Set | 9 | mtr | 0.25 | hr | 2.25 | 1 | 3.25 | Hrs
|  | 749 | Web Pl Marking | 748 | F,H |  | 30/25 |  | 29 | rmt | 29 rmt | 1 | Set | 29 | mtr | 0.25 | hr | 7.25 | 1 | 8.25 | Hrs
|  | 750 | Ribs Marking | 749 | F,H |  | 25 |  | 10.5 | rmt | 10.5 rmt | 1 | Set | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.63 | Hrs
751 | Yes | 751 | Top Sadlle Plate Cutting | 746
|  | 752 | Base Cutting |  | C,H |  | 30/25 |  | 9 | rmt | 9 rmt | 1 | Nos | 9 | mtr | 0.5 | hr | 4.5 | 1 | 5.5 | Hrs
|  | 753 | Web Pl Cutting | 752 | C,H |  | 30/25 |  | 29 | rmt | 29 rmt | 1 | Nos | 29 | mtr | 0.5 | hr | 14.5 | 1 | 15.5 | Hrs
|  | 754 | Ribs Cutting | 753 | C,H |  | 25 |  | 10.5 | rmt | 10.5 rmt | 1 | Nos | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.63 | Hrs
|  | 755 | Grinnding Of Above | 754 | G[2] |  | 25 | [6 empty] | 48.5 | mtr | 0.15 | hr | 7.275 | 1 | 8.28 | Hrs
756 | Yes | 756 | Saddle Fit Up & Welding | 751
|  | 757 | Base + Web Fit Up |  | F,H[2],W | [6 empty] | 1 | Set | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 758 | Base + Web Welding | 757 | W,H |  | 18 |  |  |  |  | 1 | Set | 4 | Nos | 3.4 | hr | 13.6 | 1 | 14.6 | Hrs
|  | 759 | Ribs+Web Fit Up | 758 | F,H[2],W | [6 empty] | 1 | Set | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 760 | Ribs+Web Welding | 759 | W[2],H[2] |  | 18 |  |  |  |  | 1 | Set | 24.8 | Nos | 3.4 | hr | 84.32 | 1 | 85.32 | Hrs
761 | Yes | 761 | Davit Pipe Fabrication | 756
|  | 762 | Pipe Transfere |  | H[4] | [6 empty] | 1 | Set | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 763 | Pipe Marking - 6 Nos | 762 | F,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
|  | 764 | Support Pl Marking | 763 | F,H |  | 16 |  |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 765 | Gusset Pl Marking | 764 | F,H |  | 16 |  |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 766 | Base Hub Marking | 765 | F,H |  | 30 |  |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 767 | Pipe Cutting - 6 Nos | 766 | C,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
|  | 768 | Support Pl Cutting | 767 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 769 | Pipe Grinding - 6 Nos | 768 | F,H | [6 empty] | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
|  | 770 | Support Pl Grinding-10 Nos | 769 | G | [6 empty] | 10 | Nos | 10 | Nos | 0.5 | Hr | 5 |  | 5 | Hrs
|  | 771 | Pivot Pl Grinding | 770 | G | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 772 | Pipe Fit Up-2 Nos | 771 | F,H,W | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 773 | Pipe Welding -2 Nos | 772 | W,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 774 | Pivot Pl Welding | 773 | W,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
|  | 775 | Support Pl Welding -4 Nos | 774 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
776 | Yes | 776 | Lifting Lug Pad | 761
|  | 777 | Plate Issuence | [8 empty] | 1 | Set | 1 | Set | 4 | dAY | 4 |  | 4 | Days
|  | 778 | Lifting Lug Pad Marking | 777 | F,H |  | 18 |  |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 779 | Lifting Lug Pad Cutting | 778 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 780 | Lifting Lugs Pad Grinding | 779 | G,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
781 | Yes | 781 | Lifting Lug Preparation | 776
|  | 782 | Lifting Lugs Marking |  | F,H |  | 24 |  |  |  |  | 1 | Set | 1 | Set | 4 | dAY | 4 |  | 4 | Days
|  | 783 | Lifting Lugs Cutting | 782 | C,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 784 | Lifting Lugs Grinding | 783 | G,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
|  | 785 | Lifting Lug Drilling | 784 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
786 | Yes | 786 | Channel Cover Handle Prepataion | 781
|  | 787 | Ch Cover Ring Forming |  | F,H | [6 empty] | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days
|  | 788 | Sliding Sling Forming | 787 | F,H | [6 empty] | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days
789 | Yes | 789 | Insulation Ring Prparation | 786
|  | 790 | Insulaion Ring Marking |  | F,H |  | 12 |  |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs
|  | 791 | Insulaion Ring Cutting | 790 | C,H | [6 empty] | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs
|  | 792 | Insulaion Ring Hole Marking | 791 | F,H | [6 empty] | 1 | Nos | 1 | Nos | 2 | Hr | 2 |  | 2 | Hrs
|  | 793 | Insulaion Ring Hole Drilling | 792 | F,H | [6 empty] | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
794 | Yes | 794 | Baffle & Tb Items Fab
795 | Yes | 795 | Baffle Preparation | 794
|  | 796 | Baffle Plate Transfer | 795 | [7 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
|  | 797 | Baffle Marking | 796 | F,H |  | 14 |  |  |  |  | 19 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Hrs
|  | 798 | Baffle Profile Cutting | 797 | C,H | [6 empty] | 19 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Hrs
799 | Yes | 799 | Baffle Bend Removal & Stacking | 795
|  | 800 | Baffle Pl Bend Removal |  | F,H[2] | [6 empty] | 19 | Nos | 19 | Nos | 1 | Hr | 19 |  | 19 | Hrs
|  | 801 | Baffle Pl Stacking | 800 | F,H |  |  |  | 3 | budle | 3 budle | 3 | Nos | 3 | Nos | 2 | Hr | 6 |  | 6 | Hrs
802 | Yes | 802 | Baffle Drilling | 799
|  | 803 | Baffle Drilling |  | SC |  | 14 | thk |  |  |  | 3 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 | Days
804 | Yes | 804 | Baffle De Stacking & Chamfering | 802
|  | 805 | Baffle De Stacing |  | F,H | [6 empty] | 3 | Bunch | 4 | Bunch | 6 | Hrs | 24 |  | 24 | Hrs
|  | 806 | Baffle Chamfering | 805 | F | [6 empty] | 9 | Nos | 23544 | Holes | 0.01 |  | 235.44 |  | 235.44 | Days
807 | Yes | 807 | Baffle Stacking & Thro Hole Check | 804
|  | 808 | Stacking |  | F,H | [6 empty] | 3 | Nos | 3 | Nos | 0.25 | Hr | 0.75 |  | 0.75 | Hrs
|  | 809 | Baffle Hole Alingment | 808 | F,H | [6 empty] | 3 | Nos | 1 | Set | 1 | Hrs | 1 |  | 1 | Hrs
|  | 810 | Baffle Hole Re Drill | 809 | SC | [6 empty] | 3 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
|  | 811 | Baffle Od Machining | 810 | SC | [6 empty] | 3 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
|  | 812 | Baffle Cleaning | 811 | H[3] | [6 empty] | 3 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days
813 | Yes | 813 | Support Plate Marking | 807
|  | 814 | Support Plate Transfer | [8 empty] | 2 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 815 | Support Marking | 814 | SC |  | 20 |  |  |  |  | 2 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days
|  | 816 | Support Profile Cutting | 815 | SC | [6 empty] | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
817 | Yes | 817 | Support Plate Bend Removal | 813
|  | 818 | Support Pl Bend Removal |  | F,H[3] | [6 empty] | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
|  | 819 | Support Pl Stacking | 818 | F,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
820 | Yes | 820 | Support Plate Drlinng | 817
|  | 821 | Support Drilling | 820 | SC |  | 20 | thk |  |  |  | 1 | Bunch | 1 | Set | 10 | Day | 10 |  | 10
822 | Yes | 822 | Sup Plate De Stacking & Chamfering | 820
|  | 823 | Support De Stacing |  | F,H | [6 empty] | 1 | Bunch | 1 | Bunch | 3 | Hrs | 3 |  | 3 | Hrs
|  | 824 | Support Hole Chamfering | 823 | F | [6 empty] | 2 | Plate | 2616 | Holes | 0.01 |  | 26.16 |  | 26.16
825 | Yes | 825 | Tie Rod Preparation | 1276
|  | 826 | Tie Rod Matl Transfere | [8 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days
|  | 827 | Rod Cutting | 826 | F,H | [6 empty] | 22 | Nos | 22 | Nos | 0.25 | Hr | 5.5 |  | 5.5 | Hrs
|  | 828 | Thread Machining. | 827 | L | [6 empty] | 22 | Nos | 22 | Nos | 0.45 | Hr | 9.9 |  | 9.9 | Hrs
|  | 829 | Joining | 828 | W,F,H | [6 empty] | 22 | Nos | 22 | Nos | 0.5 | Hr | 11 |  | 11 | Hrs
830 | Yes | 830 | Spacer Tube Preparation | 1275
|  | 831 | Spacer Tube Transfere | [8 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
|  | 832 | Length Cutting 237Nos | 831 | F,H | [6 empty] | 414 | Nos | 414 | Nos | 0.1 | Hr | 41.4 |  | 41.4 | Hrs
|  | 833 | Lenngth Machining | 832 | L | [6 empty] | 414 | Nos | 414 | Nos | 0.1 | Hr | 41.4 |  | 41.4 | Hrs
|  | 834 | Cleaninng | 833 | H[3] | [6 empty] | 414 | Nos | 414 | Nos | 0.016667 | Hr | 6.9 |  | 6.9 | Hrs
835 | Yes | 835 | Sealing Strip Preparation | 1270
|  | 836 | Sealing Strip Marking |  | F,H |  | 8 |  | 9522 | mm | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.1 | Hr | 1.9044 |  | 1.9 | Hrs
|  | 837 | Sealing Strip Cutting | 836 | C,H |  | 25 |  | 9522 | mm | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.25 | Hr | 4.761 |  | 4.76 | Hrs
|  | 838 | Sealing Strip Bend Removal | 837 | F,H[2] |  | 25 |  | 9522 | mm | 9522 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
|  | 839 | Sealing Strip Grinding | 838 | G |  | 25 |  | 9522 | mm | 9522 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
|  | 840 | Sealing Strip Joining | 839 | W,F,H |  | 25 |  | 9522 | mm | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
|  | 841 | Sealing Strip Dress Up | 840 | G |  | 25 |  | 9522 | mm | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
842 | Yes | 842 | Sliding Strip Preparation | 1271
|  | 843 | Sliding Strip Marking |  | F,H |  | 8 |  | 13366 | mm | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.1 | Hr | 2.6732 |  | 2.67 | Hrs
|  | 844 | Sliding Strip Cutting | 843 | C,H |  | 8 |  | 13366 | mm | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.25 | Hr | 6.683 |  | 6.68 | Hrs
|  | 845 | Sliding Strip Bend Removal | 844 | F,H[2] |  | 8 |  | 13366 | mm | 13366 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
|  | 846 | Sliding Strip Grinding | 845 | G |  | 8 |  | 13366 | mm | 13366 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
|  | 847 | Sliding Strip Joining | 846 | W,F,H |  | 8 |  | 13366 | mm | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
|  | 848 | Sliding Strip Dress Up | 847 | G |  | 8 |  | 13366 | mm | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
849 | Yes | 849 | Seal Rod Preparation | 1272
|  | 850 | Seal Rod Issuenece |  | T | [6 empty] | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days
|  | 851 | Seal Rod Marking | 850 | F,H |  | 25.4 | dia | 14 |  | 14 | 14 | Nos | 14 | Nos | 0.25 | Hr | 3.5 |  | 3.5 | Hrs
|  | 852 | Seal Rod Cutting | 851 | F,H |  | 25.4 | dia | 14 |  | 14 | 14 | Nos | 14 | Nos | 0.5 | Hr | 7 |  | 7 | Hrs
|  | 853 | Seal Rod Bend Removal | 852 | F,H[2] |  | 25.4 | dia | 14 |  | 14 | 14 | Nos | 14 | Nos | 1 | Hr | 14 |  | 14 | Hrs
854 | Yes | 854 | Shell Fabrication
855 | Yes | 855 | Shell Marking & Cutting | 1099
|  | 856 | Sh Plate Trnasfer |  | T | [6 empty] | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days
|  | 857 | Sh-Marking | 856 | F,H[2] |  | 18 |  | 43000 | mm | 43000 mm | 1 | Nos | 43 | mtr | 0.1 | hr | 4.3 | 1 | 5.3 | Hrs
858 | Yes | 858 | Shell Plate Cutting | 855
|  | 859 | Sh-Cutting | 858 | C,H[2] |  | 18 |  | 43000 mm | mm | 43000 mm mm | 3 | Nos | 129 | mtr | 0.25 | hr | 32.25 | 1 | 33.25 | Hrs
860 | Yes | 860 | Sh Pl Side Grinding | 858
|  | 861 | Sh Pl Side Bevel Cutting | 860 | C,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 862 | Sh Pl Side Bevel Cutting | 861 | C,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 863 | Sh Pl Side Bevel Cutting | 862 | C,H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.63 | Hrs
|  | 864 | Sh Pl Side Bevel Cutting | 863 | C,H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 |  |  | Hrs
865 | Yes | 865 | Shell Plate Edge Preparation | 860
|  | 866 | Sh-Bevel Grinding |  | G,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 867 | Sh-Bevel Grinding | 866 | G,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 868 | Sh-Bevel Grinding | 867 | G,H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 869 | Sh-Bevel Grinding | 868 | G,H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
870 | Yes | 870 | Shell Pre Bending | 865
|  | 871 | Sh-Pre Bend |  | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 872 | Sh-Pre Bend | 871 | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 873 | Sh-Pre Bend | 872 | F[2],H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 874 | Sh-Pre Bend | 873 | F[2],H |  | 18 |  | 0 | mm | 0 mm | 0 | Nos | 0 | Nos | 0 | hr | 0 |  |  | Hrs
875 | Yes | 875 | Shell Pl Pre Bend Cut Off | 870
|  | 876 | Sh-Pre Bend Cut Off |  | F[2],H,C |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs
|  | 877 | Sh-Pre Bend Cut Off | 876 | F[2],H,C |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs
|  | 878 | Sh-Pre Bend Cut Off | 877 | F[2],H,C |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs
|  | 879 | Sh-Pre Bend Cut Off | 878 | F[2],H,C |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | Nos | 0.3 | hr | 0 | 1 | 1 | Hrs
880 | Yes | 880 | Shell Plate Ls Ep | 875
|  | 881 | Sh-Pre Bend Ls Ep |  | F,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 882 | Sh-Pre Bend Ls Ep | 881 | F,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 883 | Sh-Pre Bend Ls Ep | 882 | F,H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 884 | Sh-Pre Bend Ls Ep | 883 | F,H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
885 | Yes | 885 | Shell Rolling | 880
|  | 886 | Sh-Rolling 1/4 |  | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 887 | Sh-Rolling | 886 | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 888 | Sh-Rolling | 887 | F[2],H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 889 | Sh-Rolling | 888 | F[2],H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
890 | Yes | 890 | Shell Cir Length & Ep Correction | 885 | [13 empty] | 0
|  | 891 | Sh-Ls Correction |  | F,H[2] |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 892 | Sh-Ls Correction | 891 | F,H[2] |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 893 | Sh-Ls Correction | 892 | F,H[2] |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 894 | Sh-Ls Correction | 893 | F,H[2] |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
895 | Yes | 895 | Shell Ls Seams Fit Up | 890 | [13 empty] | 0
|  | 896 | Sh-Ls Fit Up |  |  |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 897 | Sh-Ls Fit Up | 896 | F[2],H,W |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 898 | Sh-Ls Fit Up | 897 | F[2],H,W |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 899 | Sh-Ls Fit Up | 898 | F[2],H,W |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
900 | Yes | 900 | Sh Ls Welding Arrangement | 895
|  | 901 | Sh-Ls Weld Arrangement |  | F,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 902 | Sh-Ls Weld Arrangement | 901 | F,H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 903 | Sh-Ls Weld Arrangement | 902 | F,H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 904 | Sh-Ls Weld Arrangement | 903 | F,H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
905 | Yes | 905 | Shell Long Seam Outer Welding | 900
|  | 906 | Sh-Ls Welding- Top Side |  | W,H |  | 12 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
|  | 907 | Sh-Ls Welding- Top Side | 906 | W,H |  | 12 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
|  | 908 | Sh-Ls Welding- Top Side | 907 | W,H |  | 12 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 2.5 | hr | 3.125 | 1 | 4.13 | Hrs
|  | 909 | Sh-Ls Welding- Top Side | 908 | W,H |  | 12 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
910 | Yes | 910 | Sh Ls Back Chip | 905
|  | 911 | Sh-Ls Welding- Back Chip |  | G |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 912 | Sh-Ls Welding- Back Chip | 911 | G |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
|  | 913 | Sh-Ls Welding- Back Chip | 912 | G |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 914 | Sh-Ls Welding- Back Chip | 913 | G |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
915 | Yes | 915 | Sh Ls Inner Welding | 910
|  | 916 | Sh-Ls Inner Welding |  | W,H |  | 6 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
|  | 917 | Sh-Ls Inner Welding | 916 | W,H |  | 6 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
|  | 918 | Sh-Ls Inner Welding | 917 | W,H |  | 6 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 0.9 | hr | 1.125 | 1 | 2.13 | Hrs
|  | 919 | Sh-Ls Inner Welding | 918 | W,H |  | 6 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 0.9 | hr | 0 | 1 | 1 | Hrs
920 | Yes | 920 | Sh Inner Ls Flush Grinding | 915
|  | 921 | Sh Inner Flush Grinding |  | G |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 922 | Sh Inner Flush Grinding | 921 | G |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
|  | 923 | Sh Inner Flush Grinding | 922 | G |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.63 | Hrs
|  | 924 | Sh Inner Flush Grinding | 923 | G |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs
925 | Yes | 925 | Sh Ls Radiography | 920
|  | 926 | Sh Ls Welding Rt |  | RT |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 927 | Sh Ls Welding Rt | 926 | RT |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 928 | Sh Ls Welding Rt | 927 | RT |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
|  | 929 | Sh Ls Welding Rt | 928 | RT |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
930 | Yes | 930 | Shell Re Rolling | 925 | [13 empty] | 0
|  | 931 | Sh Re Rolling |  | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 932 | Sh Re Rolling | 931 | F[2],H |  | 18 |  | 2500 | mm | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 933 | Sh Re Rolling | 932 | F[2],H |  | 18 |  | 1250 | mm | 1250 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 934 | Sh Re Rolling | 933 | F[2],H |  | 18 |  | 0 | mm | 0 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
935 | Yes | 935 | Sh Plate Cs Ep Correction | 930
|  | 936 | Sh Cir Ep Correction |  | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 937 | Sh Cir Ep Correction | 936 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 938 | Sh Cir Ep Correction | 937 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 939 | Sh Cir Ep Correction | 938 | F,H |  | 18 |  | 0 | mm id | 0 mm id | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
940 | Yes | 940 | Sh Cir Seam First Fit Up | 935
|  | 941 | Sh Cs Fit Up - [Ls1+Ls2] |  | F[2],H,W |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 942 | Sh Cs Tack Dp Check - [Ls1+Ls2] | 941 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
943 | Yes | 943 | Sh Cir Seam First Welding | 940
|  | 944 | Sh Cs Welding Transfere |  | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 945 | Sh Cs Welding Outer [Ls1+Ls2] | 944 | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 946 | Sh Cs Welding Back Chip [Ls1+Ls2] | 945 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 947 | Sh Cs Inner Welding [Ls1+Ls2] | 946 | W,H |  | 6 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 948 | Sh Cs Flush Grinding [Ls1+Ls2] | 947 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
949 | Yes | 949 | Sh Cir Seam Second Fitup | 943
|  | 950 | Sh Cs Fit Up - [Ls2+Ls3] |  | F[2],H,W |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 951 | Sh Cs Tack Dp Check - [Ls2+Ls3] | 950 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
952 | Yes | 952 | Sh Cir Seam Second Welding | 949 | [13 empty] | 0
|  | 953 | Sh Cs Welding Transfere-[Ls2+Ls3] |  | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 954 | Sh Cs Welding Outer [Ls2+Ls3] | 953 | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 955 | Sh Cs Welding Back Chip [Ls2+Ls3] | 954 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 956 | Sh Cs Inner Welding [Ls2+Ls3] | 955 | W,H |  | 6 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 957 | Sh Cs Flush Grinding [Ls2+Ls3] | 956 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
958 | Yes | 958 | Sh Cir Seam Iii Rd Fitup | 952
|  | 959 | Sh Cs Fit Up Cs3 |  | F[2],H,W |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 960 | Sh Cs Tack Dp Check Cs3 | 959 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
961 | Yes | 961 | Sh Cir Seam Third Welding | 958
|  | 962 | Sh Cs Welding Transfere Cs3 |  | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 963 | Sh Cs Welding Outer Cs3 | 962 | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 964 | Sh Cs Welding Back Chip Cs3 | 963 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 965 | Sh Cs Inner Welding Cs3 | 964 | W,H |  | 6 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 966 | Sh Cs Flush Grinding Cs3 | 965 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
967 | Yes | 967 | Sh Final Length Correction | 961
|  | 968 | Sh Length Marking |  | F[2] |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 969 | Length Cutting | 968 | C,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
|  | 970 | Grinding & Ep | 969 | G,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
971 | Yes | 971 | Sh Cir Seam Flange 1 Fitup | 967
|  | 972 | Sh Cs Fit Up Flg Cs1 |  | F[2],H,W |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 973 | Sh Cs Tack Dp Check Flg Cs1 | 972 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
974 | Yes | 974 | Sh Cir Seam Flange 1 Welding | 971
|  | 975 | Sh Cs Welding Transfere | 974 | F,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 976 | Sh Cs Welding Outer Flg Cs1 |  | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 977 | Sh Cs Welding Back Chip Flg Cs1 | 976 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 978 | Sh Cs Inner Welding Flg Cs1 | 977 | W,H |  | 6 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 979 | Sh Cs Flush Grinding Flg Cs1 | 978 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
980 | Yes | 980 | Sh Cs Fit Up Flg2 | 974
|  | 981 | Sh Cs Fit Up Flg 2 |  | F[2],H,W |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 982 | Sh Cs Tack Dp Check Flg2 | 981 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
983 | Yes | 983 | Sh Cs Welding Flg2 | 980
|  | 984 | Sh Cs Welding Transfere Flg2 |  | F,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 985 | Sh Cs Welding Outer Flg2 | 984 | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 986 | Sh Cs Welding Back Chip Flg2 | 985 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 987 | Sh Cs Inner Welding Flg2 | 986 | W,H |  | 6 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 988 | Sh Cs Flush Grinding Flg2 | 987 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
989 | Yes | 989 | Nozzle Orientation Marking | 983
|  | 990 | Sh-Noz Orientaion Marking |  | F[2] |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 991 | Sh-Noz Marking-N2A1 | 990 | F[2] |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 992 | Sh-Noz Marking-N2A1 | 991 | F[2] |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
993 | Yes | 993 | Sh Nozzle Openning | 989
|  | 994 | 26"Nb Srn - 1 |  | C,H |  | 18 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.31 | Hrs
|  | 995 | 26"Nb Srn - 1 | 994 | C,H |  | 18 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.31 | Hrs
996 | Yes | 996 | Inspection | 993 | C,H | [6 empty] | 2 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
997 | Yes | 997 | Sh Nozzle Ep | 996
|  | 998 | 26"Nb Srn - 1 |  | G |  | 18 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.05 | Hrs
|  | 999 | 26"Nb Srn - 1 | 998 | G |  | 18 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.05 | Hrs
|  | 1000 | Inspection | 999 | [7 empty] | 1 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
1001 | Yes | 1001 | Sh Nozzzle Fit Up | 997
|  | 1002 | 26"Nb Srn - 1 |  | F[2],H,W |  |  |  | 650 | NB | 650 NB | 1 | Nos | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1003 | 26"Nb Srn - 1 | 1002 | F[2],H,W |  |  |  | 650 | NB | 650 NB | 1 | Nos | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1004 | Dp Check | 1003 | [7 empty] | 2 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
1005 | Yes | 1005 | Sh Nozzle Fit Up Inspection | 1001
|  | 1006 | 26"Nb Srn - 1 |  | F,H |  |  |  | 650 | NB | 650 NB | 1 | Nos | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1007 | 26"Nb Srn - 1 | 1006 | F,H |  |  |  | 650 | NB | 650 NB | 1 | Nos | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1008 | Dp Check | 1007 | F,H |  |  |  | 650 | NB | 650 NB | 2 | Nos | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
1009 | Yes | 1009 | Sh Nozzle Welding | 1005
|  | 1010 | Sh Noz Welding Arrangement |  | T | [6 empty] | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
|  | 1011 | Sh-Noz Welding -N1A | 1010 | W,H |  | 12 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs
|  | 1012 | Sh-Noz Welding-N2A1 | 1011 | W,H |  | 12 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs
|  | 1013 | Sh-Noz Welding-N2A2 | 1012 | W,H |  | 12 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs
|  | 1014 | Sh Noz Root Dp Check | 1013 | F,H |  | 12 |  | 972 | mm lip od | 972 mm lip od | 2 | Nos | 6.108 | Mtr | 1 | hr | 6.108 | 1 | 7.11 | Hrs
|  | 1015 | Sh-Noz Inner Weld -N1A | 1014 | H,W |  | 8 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.15 | Hrs
|  | 1016 | Sh-Noz Inner Weld-N2A1 | 1015 | H,W |  | 8 |  | 972 | mm lip od | 972 mm lip od | 1 | Nos | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.15 | Hrs
|  | 1017 | Sh-Noz Inner Weld-N2A2 | 1016 | H,W |  | 8 |  | 972 | mm lip od | 972 mm lip od | 0 | Nos | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs
1018 | Yes | 1018 | Sh Saddle Welding | 1009
|  | 1019 | Sh-Saddle Pad Fit Up |  | F[2],W,H |  | 25 |  | 1596 | mm od | 1596 mm od | 2 | Nos | 20.0585 | Nos | 0.5 | Hr | 10.0293 | 1 | 11.03 | Hrs
|  | 1020 | Sh-Saddle Pad Welding | 1019 | W[2],H[2] |  | 12 |  | 1596 | mm od | 1596 mm od | 2 | Mtr | 20.0585 | Mtr | 1.6 | Hr | 32.0936 | 1 | 33.09 | Hrs
|  | 1021 | Sh-Saddle Matching | 1020 | F[2],G[2] |  |  |  | 1596 | mm od | 1596 mm od | 2 | Nos | 2 | Nos | 8 | Hr | 16 | 1 | 17 | Hrs
|  | 1022 | Sh-Saddle Fit Up | 1021 | W,F[2],H |  |  |  | 1596 | mm od | 1596 mm od | 2 | Nos | 2 | Nos | 6 | Hr | 12 | 1 | 13 | Hrs
|  | 1023 | Sh-Saddle Welding | 1022 | W[2],H[2] |  | 12 |  | 11400 | rmt | 11400 rmt | 1 | Nos | 16.0348 | Mtr | 1.6 | Hr | 25.6557 | 1 | 26.66 | Hrs
|  | 1024 | Sh-Saddle Dress Up | 1023 | G[2] | [6 empty] | 1 | Nos | 1 | Nos | 8 | Hr | 8 | 1 | 9 | Hrs
1025 | Yes | 1025 | Sh Davit Arm Welding | 1018
|  | 1026 | Sh-Davit Arm Arm Match |  | F,G | [6 empty] | 1 | Nos | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
|  | 1027 | Sh-Davit Arm Fit Up | 1026 | F,H,W | [6 empty] | 1 | Nos | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
|  | 1028 | Sh-Davit Arm Welding | 1027 | W,H |  | 12 |  |  |  |  | 6 | mtr | 5.16 | Mtr | 1.6 | Hr | 8.256 | 1 | 9.26 | Hrs
1029 | Yes | 1029 | Sh Nde Clearence | 1025
|  | 1030 | Sh-Sh Nde Clearence |  | F,H |  | 18 |  | 6130 | lg | 6130 lg | 1 | Nos | 1 |  | 12 | Hr | 12 | 1 | 13 | Hrs
|  | 1031 | Tpi Inspection | 1030 | F,H |  | 18 |  | 6130 | lg | 6130 lg | 1 | Nos | 1 |  | 1 | Day | 1 |  | 1 | Days
1032 | Yes | 1032 | Channel Fabrication
1033 | Yes | 1033 | Channel Shell Ls Welding | 1101
|  | 1034 | Ch Plate Trnasfer |  | T | [6 empty] | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Days
|  | 1035 | Ch-Marking | 1034 | F,H[2] |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 0.1 | hr | 0.0831 | 1 | 1.08 | Hrs
|  | 1036 | Ch-Cutting | 1035 | C,H |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 0.25 | hr | 0.20775 | 1 | 1.21 | Hrs
|  | 1037 | Ch Pl Side Grinding | 1036 | G |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 0.15 | hr | 0.12465 | 1 | 1.12 | Hrs
|  | 1038 | Ch-Bevelling Cir Side | 1037 | F,H[3] |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.42 | Hrs
|  | 1039 | Ch Ep Grinding | 1038 | G |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs
1040 | Yes | 1040 | Channel Sh Rolling | 1033
|  | 1041 | Ch-Pre Bend |  | F[2],H |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
|  | 1042 | Ch-Pre Bend Cut Off | 1041 | F[2],C |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1.662 | mtr | 0.3 | hr | 0.4986 | 1 | 1.5 | Hrs
|  | 1043 | Ch Ls Beveling | 1042 | F[2] |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.66 | Hrs
|  | 1044 | Ch-Rolling | 1043 | F[2],H |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
1045 | Yes | 1045 | Ch Shell Ls Fit Up | 1040
|  | 1046 | Ch-Ls Correction |  | F[2] |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.66 | Hrs
|  | 1047 | Ch-Ls Fit Up | 1046 | F[2],W,H |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs
1048 | Yes | 1048 | Ch Shell Ls Welding | 1045
|  | 1049 | Ch-Ls Weld Arrangement |  | F,H[2] |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1050 | Ch-Ls Welding- Top Side | 1049 | W,H |  | 12 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 2.5 | hr | 2.0775 | 1 | 3.08 | Hrs
|  | 1051 | Ch-Ls Welding- Back Chip | 1050 | G,H |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs
|  | 1052 | Ch-Ls Inner Welding | 1051 | W,H |  | 6 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 0.9 | hr | 0.7479 | 1 | 1.75 | Hrs
|  | 1053 | Ch-Ls Innner Flush Grind | 1052 | G |  | 6 |  | 831 | mm | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.42 | Hrs
|  | 1054 | Ch Re Rolling | 1053 | F[2],H |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
1055 | Yes | 1055 | Ch Ls Welding Radiography | 1048
|  | 1056 | Ch Ls Welding Rt |  | RT |  | 18 |  | 831 | mm | 831 mm | 1 | Nos | 1 | Nos | 1 | dya | 1 |  | 1 | Days
1057 | Yes | 1057 | Ch Cs Flg 1 Fit Up | 1055
|  | 1058 | Ch Cir Ep Correction |  | F[2] |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 9.803 | mtr | 0.45 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 1059 | Ch Cs Fit Up Flg1 | 1058 | F[2],W,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 1060 | Ch Cs Tack Dp Check Flg1 | 1059 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | mtr | 4 | hr | 4 | 1 | 5 | Hrs
1061 | Yes | 1061 | Ch Cs Flg 1 Welding | 1057
|  | 1062 | Ch Cs Welding Transfere |  | F,H[2] |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1063 | Ch Cs Welding Outer Flg1 | 1062 | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 1064 | Ch Cs Welding Back Chip Flg1 | 1063 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 1065 | Ch Cs Inner Welding Flg 1 | 1064 | W,H |  | 8 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1.36 | hr | 6.6661 | 1 | 7.67 | Hrs
|  | 1066 | Ch Cs Flush Grinding Flg1 | 1065 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
1067 | Yes | 1067 | Ch Cs Flg 2 Fit Up | 1061
|  | 1068 | Ch Length Cutting |  | C,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
|  | 1069 | Ch Cir Ep Correction | 1068 | F,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 1070 | Ch Cs Fit Up Flg2 | 1069 | F[2],W,H |  | 8 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 4 | hr | 19.6061 | 1 | 20.61 | Hrs
|  | 1071 | Ch Cs Tack Dp Check Flg1 | 1070 | F |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
1072 | Yes | 1072 | Ch Cs Flg 2 Welding | 1067
|  | 1073 | Ch Cs Welding Transfere Flg2 |  | F,H[2] |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1074 | Ch Cs Welding Outer Flg2 | 1073 | W,H |  | 12 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs
|  | 1075 | Ch Cs Welding Back Chip Flg2 | 1074 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs
|  | 1076 | Ch Cs Inner Welding Flg2 | 1075 | W,H |  | 6 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs
|  | 1077 | Ch Cs Flush Grinding Flg2 | 1076 | G |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs
1078 | Yes | 1078 | Ch Cs Flg 1 & 2 Welding Rt | 1072
|  | 1079 | Ch Cs Welding Rt |  | RT |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | n | 1 | Day | 1 |  | 1 | Days
1080 | Yes | 1080 | Channel Noz Marking | 1078
|  | 1081 | Ch- Noz Ireientation Nkg |  | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1082 | Ch-Noz Marking- 16"Nb - 2 Nos | 1081 | F,H |  | 18 |  | 1560 | mm id | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
1083 | Yes | 1083 | Ch Noz Opnning | 1080
|  | 1084 | Ch-Noz Openning-Top |  | C,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1085 | Ch-Noz Openning-Bot | 1084 | C,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
1086 | Yes | 1086 | Ch Noz Open Ep | 1083
|  | 1087 | Ch-Noz Ep -N3A |  | G,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1088 | Ch-Noz Ep-N4A | 1087 | G,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
1089 | Yes | 1089 | Ch Noz Fit Up | 1086
|  | 1090 | Ch-Noz Fit Up -N3A |  | F[2],W,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1091 | Ch-Noz Fit Up -N4A | 1090 | F[2],W,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
1092 | Yes | 1092 | Inter Connection Nozzle Welding | 1089 | [13 empty] | 0 |  |  | Hrs
|  | 1093 | Bot Sh , Ch And Top Sh ,Ch Stacking |  | F[2],H,W | [6 empty] | 1 | Nos | 1 | Mtr | 16 | hr | 16 | 1 | 17 | Hrs
|  | 1094 | Inter Con Noz Fit Up - On Sh |  | F[2],H,W |  | 650 | NB | 650 | NB | 650 NB | 1 | Nos | 1 | Mtr | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1095 | Inter Con Noz Fit Up- On Ch |  | F[2],H,W |  | 400 | NB | 400 | NB | 400 NB | 1 | Nos | 1 | Mtr | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1096 | Inter Con Noz Welding - On Sh |  | W,H |  | 18 |  | 972 | mm dia | 972 mm dia | 1 | Nos | 3.054 | Mtr | 4.9 | hr | 14.9647 | 1 | 15.96 | Hrs
|  | 1097 | Inter Con Noz Welding- On Ch |  | W,H |  | 18 |  | 407 | mm dia | 407 mm dia | 1 | Nos | 1.2788 | Mtr | 4.9 | hr | 6.2661 | 1 | 7.27 | Hrs
|  | 1098 | Dismantling |  | F[2],H,W | [6 empty] | 1 | Nos | 1 | Nos | 12 | hr | 12 | 1 | 13 | Hrs
|  | 1099 | Inter Con Noz Flush Grind & Dp-On Sh |  | G,H |  | 18 |  | 972 | mm dia | 972 mm dia | 1 | Nos | 3.054 | Mtr | 0.5 | hr | 1.527 | 1 | 2.53 | Hrs
|  | 1100 | Inter Con Noz Flush Grind & Dp-On Ch |  | G,H |  | 18 |  | 407 | mm dia | 407 mm dia | 1 | Nos | 1.2788 | Mtr | 0.5 | hr | 0.6394 | 1 | 1.64 | Hrs
|  | 1101 | In Con Noz Rt |  | RT |  | 18 |  | 972 | mm dia | 972 mm dia | 1 | Nos | 3.054 | Nos | 1 | Day | 3.054 |  | 3.05 | Hrs
1092 | Yes | 1092 | Ch Noz Fit Up Insp | 1092
|  | 1093 | Ch-Noz Inspn -N3A |  | F,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1094 | Ch-Noz Inspn-N4A | 1093 | F,H |  |  |  | 400 | NB | 400 NB | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
1095 | Yes | 1095 | Ch Noz Welding | 1092
|  | 1096 | Ch Noz Welding Arrangement |  | F,H[2] |  |  |  | 400 | NB | 400 NB | 2 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 1097 | Ch-Noz Welding -N3A | 1096 | W,H |  | 14 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs
|  | 1098 | Ch-Noz Welding-N4A | 1097 | W,H |  | 14 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs
|  | 1099 | Ch Noz Root Dp Check | 1098 | W,H |  | 14 |  | 407 | mm | 407 mm | 2 | Nos | 2 | Nos | 1 | hr | 2 | 1 | 3 | Hrs
|  | 1100 | Ch-Noz Inner Weld -N3A | 1099 | W,H |  | 6 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs
|  | 1101 | Ch-Noz Inner Weld-N4A | 1100 | W,H |  | 6 |  | 407 | mm | 407 mm | 1 | Nos | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs
|  | 1102 | Rf Pad Fit Up & Nozzle Fit Up | 1101 | W,H |  |  |  | 400 | NB | 400 NB | 2 | Nos | 2 | Set | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1103 | Rf Pad Fit Up Welding | 1102 | G,H |  | 18 |  |  |  |  | 2 | Nos | 2.5538 | Mtr | 6.8 | hr | 17.366 | 1 | 18.37 | Hrs
|  | 1104 | Noz Welding Flush Grind- 16"Nb | 1103 | G |  |  |  | 407 | mm | 407 mm | 2 | NoS | 2.5538 | Nos | 0.15 | hr | 0.38307 | 1 | 1.38 | Hrs
1105 | Yes | 1105 | Channel Pp Plate Fit Up | 1095
|  | 1106 | Ch- Pp Plate Fit Up |  | F[2],H,W |  | 24 |  | 14465 |  | 14465 | 1 | Nos | 14.465 | Nos | 0.5 | hr | 7.2325 | 1 | 8.23 | Hrs
|  | 1107 | Ch- Pp Plate Fit Up Insp | 1106 | F,H |  | 24 |  | 1560 | id | 1560 id | 3 | Nos | 4 | Nos | 0.5 | hr | 2 | 1 | 3 | Hrs
1108 | Yes | 1108 | Ch Pp Plate Welding | 1105
|  | 1109 | Ch- Pp Plate Welding |  | W,H |  | 24 |  | 1480 |  | 1480 | 3 | Nos | 4.44 |  | 11.2 | hr | 49.728 | 1 | 50.73 | Hrs
|  | 1110 | Ch- Pp Plate Face Grinding | 1109 | G,H |  | 12 |  | 12310 | mm | 12310 mm | 1 | Nos | 12.31 | Nos | 1.6 | hr | 19.696 | 1 | 20.7 | Hrs
1111 | Yes | 1111 | Channel Davit Arm Welding | 1108
|  | 1112 | Ch-Davit Arm Arm Match |  | F,H |  | 18 |  | 1480 | lg | 1480 lg | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1113 | Ch-Davit Arm Fit Up | 1112 | F,W,H |  | 18 |  | 1251 | lg | 1251 lg | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1114 | Ch-Davit Arm Welding | 1113 | W,H |  | 12 |  | 6 |  | 6 | 1 | Nos | 6 | mtr | 1.6 | hr | 9.6 | 1 | 10.6 | Hrs
1115 | Yes | 1115 | Channel Nde & Pwht | 1111
|  | 1116 | Ch All Welding Dressup & Dp Check |  | G[2] |  | 18 |  | 1480 | lg | 1480 lg | 1 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 1117 | Ch-Ch Nde Clearence | 1116 | F |  | 18 |  | 1480 | lg | 1480 lg | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Hrs
1118 | Yes | 1118 | Barrel Fabrication | 1115
1119 | Yes | 1119 | Barrel Sh Plate Cutting & Ep | 7 | [7 empty] | 1 | Nos | 1 | Nos | 4 | Day | 4 |  | 4 | Hrs
|  | 1120 | Barrel Plate Trnasfer |  | T |  | 18 |  | 373 | mm | 373 mm | 1 | Nos | 0.373 | mtr | 0.1 | Hr/mtr | 0.0373 | 1 | 1.04 | Hrs
|  | 1121 | Barrel-Marking | 1120 | F,H[2] |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 0.25 | Hr/mtr | 2.825 | 1 | 3.83 | Hrs
|  | 1122 | Barrel-Cutting | 1121 | C,H |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 0.15 | Hr/mtr | 1.695 | 1 | 2.7 | Hrs
|  | 1123 | Barrel Pl Side Grinding | 1122 | G |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 0.5 | Hr/mtr | 5.65 | 1 | 6.65 | Hrs
|  | 1124 | Barrel-Bevelling Cir Side | 1123 | F,H[3] |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs
|  | 1125 | Ch Ep Grinding | 1124 | G |  | 18 |  | 11300 | mm | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs
1126 | Yes | 1126 | Bar Shell Rolling | 1119
|  | 1127 | Barrel-Pre Bend |  | F[2],H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
|  | 1128 | Barrel-Pre Bend Cut Off | 1127 | F[2],C |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 3.328 | Nos | 0.3 | hr | 0.9984 | 1 | 2 | Hrs
|  | 1129 | Barrel -Pre Ls Ep | 1128 | F[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs
|  | 1130 | Barrel-Rolling | 1129 | F[2],H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
1131 | Yes | 1131 | Barrel Shell Ls Fit Up | 1126
|  | 1132 | Barrel-Ls Correction |  | F[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs
|  | 1133 | Barrel-Ls Fit Up | 1132 | F[2],W,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs
1134 | Yes | 1134 | Barrel Shell Ls Welding | 1131
|  | 1135 | Barrel-Ls Weld Arrangement |  | F,H[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1136 | Barrel-Ls Welding- Top Side | 1135 | W,H |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 2.5 | hr | 4.16 | 1 | 5.16 | Hrs
|  | 1137 | Barrel-Ls Welding- Back Chip | 1136 | G,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs
|  | 1138 | Barrel-Ls Inner Welding | 1137 | W,H |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.9 | hr | 1.4976 | 1 | 2.5 | Hrs
|  | 1139 | Barrel-Ls Innner Flush Grind | 1138 | G |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.5 | hr | 0.832 | 1 | 1.83 | Hrs
|  | 1140 | Barrel Re Rolling | 1139 | F[2],H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
1141 | Yes | 1141 | Barrel Ls Welding Rt | 1134
|  | 1142 | Bar Ls Welding Rt |  | RT |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
1143 | Yes | 1143 | Barrel Shell Cs Flg 1 Fit Up | 1141
|  | 1144 | Barrel Cir Ep Correction |  | F[2] |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 1145 | Barrel Cs Fit Up Flg1 | 1144 | F[2],W,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Nos | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 1146 | Barrel Cs Tack Dp Check Flg1 | 1145 | F,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Nos | 0.25 | hr | 1.3071 | 1 | 2.31 | Hrs
1147 | Yes | 1147 | Barrel Sh Cs Flg 1 Welding | 1143
|  | 1148 | Barrel Cs Welding Transfere |  | F,H[2] |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1149 | Barrel Cs Welding Outer Flg1 | 1148 | W,H |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs
|  | 1150 | Barrel Cs Welding Back Chip Flg1 | 1149 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 1151 | Barrel Cs Inner Welding Flg 1 | 1150 | W,H |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs
|  | 1152 | Barrel Cs Flush Grinding Flg1 | 1151 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs
1153 | Yes | 1153 | Barrel Cs Fit Up With Dish | 1147 | [13 empty] | 0
|  | 1154 | Barrel Length Cutting |  | C,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 1155 | Barrel Ep | 1154 | F,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 1156 | Barrel Cs Fit Up Dish | 1155 | F[2],W,H |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | mtr | 4 | hr | 20.9132 | 1 | 21.91 | Hrs
|  | 1157 | Barrel Cs Tack Dp Check Dish | 1156 | F |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Nos | 3.5 | hr | 18.299 | 1 | 19.3 | Hrs
1158 | Yes | 1158 | Barrel Cs Welding With Dish | 1153
|  | 1159 | Barrel Cs Welding Transfere Dish |  | F,H[2] |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
|  | 1160 | Barrel Cs Welding Outer Dish | 1159 | W,H |  | 12 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs
|  | 1161 | Barrel Cs Welding Back Chip Dish | 1160 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs
|  | 1162 | Barrel Cs Inner Welding Dish | 1161 | W,H |  | 6 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs
|  | 1163 | Barrel Cs Flush Grinding Dish | 1162 | G |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs
1164 | Yes | 1164 | Barrel Cs Flg 1 & Dish Welding Rt | 1158
|  | 1165 | Barrel Cs Welding Rt |  | RT |  | 18 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
1166 | Yes | 1166 | Barrel Noz Oreination Marking | 1164
|  | 1167 | Barrel- Noz Ireientation Nkg |  | F,H |  | 20 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 1168 | Barrel-Noz Marking- 2 | 1167 | F,H |  | 20 |  | 1664 | mm id | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
1169 | Yes | 1169 | Barrel Nozzle Oppening | 1166
|  | 1170 | Barrel-Noz Openning-40 Nb - Lwn |  | C,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
|  | 1171 | Barrel-Noz Openning-40 Nb - Lwn | 1170 | C,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
1172 | Yes | 1172 | Barrel Noz Edge Preparation | 1169
|  | 1173 | Barrel-Noz Openning-40 Nb - Lwn |  | G,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
|  | 1174 | Barrel-Noz Openning-40 Nb - Lwn | 1173 | G,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
1175 | Yes | 1175 | Barrel Nozzzle Fit Up | 1172
|  | 1176 | Barrel-Noz Fit Up -N5A |  | F[2],W,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
|  | 1177 | Barrel-Noz Fit Up -N6A | 1176 | F[2],W,H |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
1178 | Yes | 1178 | Barrel Noz Fit Up Inspection | 1175
|  | 1179 | Barrel-Noz Inspn -5A |  | INS |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 1180 | Barrel-Noz Inspn-6A | 1179 | INS |  |  |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
1181 | Yes | 1181 | Barrel Nozzle Welding | 1178
|  | 1182 | Barrel Noz Welding Arrangement |  | T |  | 40 | NB | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
|  | 1183 | Barrel-Noz Welding -N5A | 1182 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
|  | 1184 | Barrel-Noz Welding-N6A | 1183 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
|  | 1185 | Barrel Noz Root Dp | 1184 | F,H |  |  |  | 75 | mm | 75 mm | 2 | Nos | 2 |  | 0.5 | hr | 1 | 1 | 2 | Hrs
|  | 1186 | Barrel-Noz Inner Welding -N5A | 1185 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
|  | 1187 | Barrel-Noz Inner Welding-N6A | 1186 | W,H |  | 10 |  | 75 | mm | 75 mm | 1 | Nos | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs
1188 | Yes | 1188 | Barrel Noz Inner Weld Flush Grind | 1181
|  | 1189 | Barrel All Welding Dressup & Dp |  | G[2] |  | 20 |  | 40 | NB | 40 NB | 1 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 1190 | Barrel-Barrel Nde Clearence | 1189 | F |  | STD |  | 40 | NB | 40 NB | 1 | NoS | 1 | Nos | 1 | Day | 1 |  | 1 | Hrs
1191 | Yes | 1191 | Fl Head Fabrication
1192 | Yes | 1192 | Flaoting Head Dish Forming | 13
|  | 1193 | Fl Head Dish Pl Issue |  | T | [6 empty] | 1 | Nos | 1 |  | 4 | Day | 4 |  | 4 | Days
|  | 1194 | Fl Head Pl Marking | 1193 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.1 | hr | 0.62337 | 1 | 1.62 | Hrs
|  | 1195 | Fl Head Pl Stamping | 1194 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Hr | 1 | 1 | 2 | Hrs
|  | 1196 | Fl Head Pl Cutting | 1195 | C,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.25 | hr | 1.5584 | 1 | 2.56 | Hrs
|  | 1197 | Fl Head Pl Grinding | 1196 | G |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | mtr | 1 | hr | 6.2337 | 1 | 7.23 | Hrs
1198 | Yes | 1198 | Fl Head Formig | 1192
|  | 1199 | Fl Head Forming | 1198 | SC |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 10 | Day | 10 |  | 10 | Days
|  | 1200 | Fl Head Profile Check | 1199 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 |  | 1 | Days
1201 | Yes | 1201 | Fl Head Cutting | 1198
|  | 1202 | Fl Head Marking | 1201 | F,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 4 | Hr/No | 4 |  | 4 | Hrs
|  | 1203 | Fl Head Cutting | 1202 | C,H |  | 50 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 0.1 | hr | 0.62337 | 2 | 2.62 | Hrs
1204 | Yes | 1204 | Fl Head Ep | 1201
|  | 1205 | Fl Head Grinding | 1204 | G,H |  | 25 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs
1206 | Yes | 1206 | Fl Head Fit Up
|  | 1207 | Fl Head Fit Up | 1206 | F[2],W,H |  | 25 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs
1208 | Yes | 1208 | Fl Head Welding | 1206
|  | 1209 | Fl Head Welding |  | W,H |  | 30 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 16.8 | hr | 104.7266 | 2 | 106.73 | Hrs
|  | 1210 | Fl Head Pp Plate Fit Up | 1209 | F[2],H,W |  | 16 |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1211 | Fl Head Pp Pl Welding | 1210 | W,H |  | 16 |  | 3000 | mm | 3000 mm | 1 | Nos | 3 | Mtr | 2.8 | hr | 8.4 | 2 | 10.4 | Hrs
|  | 1212 | Fl Head Pp Pl Level Grinding | 1211 | F,H |  | 16 |  | 3000 | mm | 3000 mm | 1 | Nos | 1 | Nos | 6 | hr | 6 | 1 | 7 | Hrs
|  | 1213 | Fl Head Inspection | 1212 | F |  | 16 |  | 3000 | mm | 3000 mm | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
1214 | Yes | 1214 | Fl Head Sr & Machining | 1208
|  | 1215 | Fl Head Sr |  | SC |  |  |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 3 | Day | 3 | 0 | 3 | Hrs
|  | 1216 | Fl Head Final Machining | 1215 | SC |  |  |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 4 | Day | 4 | 0 | 4 | Hrs
|  | 1217 | Fl Head Hole Marking | 1216 | F,H |  |  |  | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 0.5 | Day | 0.5 | 0 | 0.5 | Hrs
|  | 1218 | Fl Head Hole Drilling | 1217 | SC |  | 140 | mm | 1550 | mm id | 1550 mm id | 72 | Hole | 1 | Nos | 4 | Day | 4 | 0 | 4 | Hrs
|  | 1219 | Fl Head Final Inspection | 1218 | F,H |  | 140 | mm | 1550 | mm id | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Day | 1 | 0 | 1 | Hrs
1220 | Yes | 1220 | Tube Bundle Fabrication
1221 | Yes | 1221 | Tube Bundle Assy
|  | 1222 | Frame Set Up & Tube Sht Set Up |  | F[2],W |  | 145 |  | 1308 | tube | 1308 tube |  |  | 1 |  | 1.5 | Day | 1.5 | 0 | 1.5 | Hrs
|  | 1223 | Skeliton Assy- 19 Baffle | 1222 | F[2],H[3] |  |  |  | 19 | baffle | 19 baffle | 1 | Nos | 19 | Nos | 0.5 | hr | 9.5 | 1 | 10.5 | Hrs
1224 | Yes | 1224 | Tube Insert | 1221
|  | 1225 | Tube Insert |  | F,H[4] |  | 25.4 | dia | 7000 | lg | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
|  | 1226 | Seal Rod Insert & Weld | 1225 | F[2],W,H[2] |  | 25.4 | dia | 5134 | lg | 5134 lg | 14 | Nos | 14 | Nos | 0.5 | Hr/no | 7 | 1 | 8 | Hrs
|  | 1227 | Tube Insert | 1226 | F,H[4] |  | 25.4 | dia | 7000 | lg | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
1228 | Yes | 1228 | Sliding Strip Fit Up Welding | 1224
|  | 1229 | Sealing Strip Fit Up |  | F,H |  | 8 |  | 4592 | mm lg | 4592 mm lg | 2 | Nos | 2 | Nos | 3 | Hr/no | 6 | 1 | 7 | Hrs
|  | 1230 | Sliding Strip Welding | 1229 | W,H |  | 8 |  | 60 | joints | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
|  | 1231 | Seal/Slid Trip Weld Grind | 1230 | G |  | 1500 |  | 60 | joints | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
1232 | Yes | 1232 | Tube Bundle Insert | 1228
|  | 1233 | Tube Bundle Insert In Shell |  | F[3],H[8] |  |  |  | 7000 | lg | 7000 lg | 1 | Nos | 1 | Nos | 16 | Hr/no | 16 | 1 | 17 | Hrs
|  | 1234 | Fl Head Tube Sht Fixing | 1233 | F[2],H[4] |  | 145 | mm |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr/no | 4 | 1 | 5 | Hrs
|  | 1235 | Test Flg & Gland Assy | 1234 | F[3],H[6] |  | 165 | mm | 1490 |  | 1490 | 1 | Nos | 56 | Bolts | 0.16667 | hr | 9.3333 | 1 | 10.33 | Hrs
1236 | Yes | 1236 | Tube Expansion In Grooves | 1232
|  | 1237 | Tube Exp - St Side - 1 Stage |  | F,H[2] |  | 150 | mm | 1308 | nos | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.016667 | hr | 21.8 | 1 | 22.8 | Hrs
|  | 1238 | Tube Exp - Fl Side - 1 Stage | 1237 | F,H[2] |  | Servo |  | 1308 | nos | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.0083333 | hr | 10.9 | 1 | 11.9 | Hrs
|  | 1239 | Tube Trimming Fl Side | 1238 | F,H |  | Servo |  | 1308 | nos | 1308 nos | 1308 | Nos | 1308 | Trimm | 0.033333 | hr | 43.6 | 1 | 44.6 | Hrs
|  | 1240 | Tube Exp Both Side - 4 Stage | 1239 | F[2],H[2] |  | 150 | mm | 2516 | roll | 2516 roll | 2616 | Nos | 2516 | Rolling | 0.0083333 | hr | 20.9667 | 1 | 21.97 | Hrs
1241 | Yes | 1241 | Tube Exp- Pnuematic Test | 1236
|  | 1242 | Tube Exp Pnuematic Test |  | F[2],H[2] | [6 empty] | 1 | Nos | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
|  | 1243 | Pnuematic Test Tpi Witness | 1242 | F,H | [6 empty] | 1 | Nos | 1 | Test | 1 | Day | 1 |  | 1 | Hrs
|  | 1244 | Cleaning | 1243 | F,H[3] | [6 empty] | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
1245 | Yes | 1245 | Tube Tube Sheet Welding- Ft Side | 1241
|  | 1246 | Tube Welding - St Side Root |  | TW,H |  | 2.77 |  | 25.4 | od | 25.4 od | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 1247 | Tube Welding - St Side Root Dp | 1246 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 1248 | Tube Welding - St Side Final Weld | 1247 | TW,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 1249 | Tube Welding - St Side Final Dp | 1248 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
1250 | Yes | 1250 | Tube To Tube Sheet Welding - Fl Head Side | 1245
|  | 1251 | Tube Welding - Flh Side Root |  | TW,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 1252 | Tube Welding - Flh Side Root Dp | 1251 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
|  | 1253 | Tube Welding - Flh Side Final Weld | 1252 | TW,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
|  | 1254 | Tube Welding - Flh Side Final Dp | 1253 | F,H |  | 2.77 |  |  |  |  | 1308 | Nos | 1 | Nos | 8 | hr | 8 | 1 | 9 | Hrs
1255 | Yes | 1255 | Shell Side Hydro | 1250
1256 | Yes | 1256 | Shell Side Water Filling
|  | 1257 | Shell Side Hydro | 1256 | F[2],H[2] |  |  |  | 6130 | lg | 6130 lg | 1 | Nos | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs
|  | 1258 | Shell Side Tpi Witness | 1257 | F[2] |  |  |  | 6130 | lg | 6130 lg | 1 | Nos | 1 | Test | 1 | Day | 1 | 0 | 1 | Hrs
|  | 1259 | De Watering & Dismantle Of Gland | 1258 | F[2],H[4] |  |  |  | 6130 | lg | 6130 lg | 1 | Nos | 1 | Test | 4 | hr | 4 | 0 | 4 | Hrs
1260 | Yes | 1260 | Channel Side Hydro - Stacked
|  | 1261 | He 1 & 2 Stacking |  | F,H[2] | [6 empty] | 1 | Set | 1 |  | 16 | hr | 16 | 1 | 17 | Hrs
|  | 1262 | Ch & Int Con Noz Tight | 1261 | F[2],H[2] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs
|  | 1263 | Water Fill | 1262 | F[2] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days
|  | 1264 | Ch Side Hydro | 1263 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs
|  | 1265 | Ch Side Hydro Tpi Witness | 1264 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days
|  | 1266 | De Watering | 1265 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs
1267 | Yes | 1267 | Shell Side Hydro - Stacked | 1260
|  | 1268 | Barrel Assy |  | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 16 | hr | 16 | 0 | 16 | Hrs
|  | 1269 | Water Fill | 1268 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs
|  | 1270 | Shell Side Hydro - Stacked | 1269 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs
|  | 1271 | Shell Side Hydro- Stacked Tpi Witness | 1270 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days
|  | 1272 | De Watering | 1271 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs
1273 | Yes | 1273 | Nitorgen Purging | 1267
|  | 1274 | N2 Gas Purging |  | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs
1275 | Yes | 1275 | Painting | 1273
|  | 1276 | Primer Painting |  | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days
|  | 1277 | Intermediate Painting | 1276 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days
|  | 1278 | Top Coat Painting | 1277 | F[2],H[4] |  |  |  | 9178 | lg | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days

## 4220D
1 | 1 | 133-EE-1006-A |  |  | status | THK | WORK DIMENSION | QTY | UOM | work volume | UOM | BMT | UOM | WORK-duration | ST | TOTAL DURATION | UOM
2 | 2 | RAW MATERIAL
3 | 3 | SHELL PLATE-SA 516 Gr60
4 | 4 | SHELL GIRTH FLANGE-SA266 Gr4
5 | 5 | CHANNEL PLATE-SA 516 Gr60
6 | 6 | CHANNEL GIRTH FLANGE-SA 266 Gr4
7 | 7 | BARREL SHEEL PLATE-SA 516 GR 60
8 | 8 | BARREL GIRTH FLANGE-SA 266 GR4
9 | 9 | BARREL DISH-SA 516 GR 60
10 | 10 | TUBE SHEET-1-SA 266 GR4
11 | 11 | TUBE SHEET -2-SA 266 GR4
12 | 12 | FLOATING HEAD FLG-SA 266 GR4
13 | 13 | FLOATING HEAD DISH-SA 516 GR60
14 | 14 | BACKING RING-SA 266 GR4
15 | 15 | BAFFLE PLATE-SA 516 GR60
16 | 16 | SEALING STRIP PLATE-SA 516 GR60
17 | 17 | SLIDING STRIP PLATE-SA 516 GR60
18 | 18 | SEAL ROD-SA 36
19 | 19 | NOZ SRN-SA 105
20 | 20 | TUBE -SA 179
21 | 21 | SPACER TUBE-SA 179
22 | 22 | TIE ROD-SA 36
23 | 23 | TEST RING & TEST FLG-SA 266 GR4
24 | 24 | MS ROD FOR HANDLE ETC
25 | 25 | MS PLATE FOR SADDLE
26 | 26 | DISH FORMING - 24T*1700 OD | 9
| 27 | BAR DISH BLANK ISSUENCE |  | T |  | 24 | ID dish | 1 | No | 1 | nos | 4 | Day | 4 |  | 4 | Days | 4 Days
| 28 | BAR-DISH BLANK MARKING - 24 * 1670 OD | 27 | F,H |  | 24 | 6723 MM | 1 | No | 6.723 | Dia-mtr | 0.1 | Hr/mtr | 0.6723 | 1 | 1.67 | Hrs | 1.67 Hrs
| 29 | BAR-DISH BLANK MARKING INSPECTION | 28 | F,H |  | 24 |  | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 30 | BAR-DISH BLANK CUTTING | 29 | C,H |  | 24 | 6723 MM | 1 | no | 6.723 | Dia-mtr | 0.25 | RMT | 1.6807 | 1 | 2.68 | Hrs | 2.68 Hrs
| 31 | BAR-DISH FORMING | 30 | SC |  | 24 | 6723 MM | 1 | no | 1 | No | 10 | Day | 10 |  | 10 | Days | 10 Days
| 32 | PROFILE INSP | 31 | F,H |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 33 | HEAT TREATMENT PREPARATION | 32 | SC |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 34 | STRESS RELEIVING- SUB CONT | 33 | SC |  | 24 | 6723 MM | 1 | no | 1 | No | 4 | Day | 4 |  | 4 | Days | 4 Days
| 35 | REMOVAL OF SPIDERS | 34 | F,H |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 36 | SURFACE PREPARATION | 35 | G |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 | 1 | 2 | Days | 2 Days
| 37 | INSPECTION | 36 | F |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 38 | TPI INSPECTION | 37 | F |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 39 | SF MARKING | 38 | F,H | enter | 24 | 1000 mm | 1 | no | 3.142 | Rmt | 0.1 | RMT | 0.3142 | 1 | 1.31 | Hrs | 1.31 Hrs
| 40 | SF CUTTING | 39 | C,H |  | 24 | 1000 mm | 1 | no | 3.142 | Rmt | 1 | RMT | 3.142 | 1 | 4.14 | Hrs | 4.14 Hrs
| 41 | SF GRIDNING & EP | 40 | G |  | 24 | 1000 mm | 1 | no | 3.142 | Rmt | 1 | RMT | 3.142 |  | 3.14 | Hrs | 3.14 Hrs
42 | 42 | TUBE SHEET
43 | 43 | TUBE SHEET MACHINING 1 OFF 2 | 10
| 44 | INWARD INSPECTION |  |  | enter | 145 t | 1000 mm | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | Days | 2 Days
| 45 | TUBE SHEET M/C - 1/2 | 44 | SC |  | 145 t | 1000 mm | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | Days | 5 Days
46 | 46 | TUBE SHEET DRILLING 1 OFF 2 | 43
| 47 | TUBE SHEET DRILLING -1/2 |  | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.27 | Days | 5.27 Days
| 48 | EXP GROOVE+WELDING GROOVE -1/2 | 47 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.54 | Days | 4.54 Days
| 49 | TIE ROD, PULLING, LIFTING HOLE - 1/2 | 48 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Days | 1 Days
| 50 | PASS PARTITION GROOVE M/C -1/2 | 49 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 51 | CLEANING ,GO/NO GO CHECK -1/2 | 50 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs | 65.4 Hrs
| 52 | FINAL INSPECTION -1/2 | 51 | F,H
53 | 53 | TUBE SHEET MACHINING 2 OFF 2 | 10
| 54 | INWARD INSPECTION |  |  |  | 145 t | 1670 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | Days | 2 Days
| 55 | TUBE SHEET M/C - 2/2 | 54 | SC |  | 145 t | 1548 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | Days | 5 Days
56 | 56 | TUBE SHEET DRILLING 2 OFF 2
| 57 | TUBE SHEET DRILLING -2/2 |  | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.27 | Days | 5.27 Days
| 58 | EXP GROOVE+WELDING GROOVE -2/2 | 57 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.54 | Days | 4.54 Days
| 59 | TIE ROD, PULLING, LIFTING HOLE - 2/2 | 58 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Days | 1 Days
| 60 | PASS PARTITION GROOVE M/C -2/2 | 59 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 61 | CLEANING ,GO/NO GO CHECK -2/2 | 60 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs | 65.4 Hrs
| 62 | FINAL INSPECTION -2/2 | 61 | F,H |  |  |  | 1 |  | 1050 | nos | 0.05 | RMT | 52.5 | 1 | 53.5 | Hrs | 53.5 Hrs
63 | 63 | NOZZLE FAB | 19
64 | 64 | SH NOZ PIPE MARKING | 3
| 65 | 26"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs | 3 Hrs
| 66 | 2" MP CON - 2 NO | 65 | F,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0.5 |  | 1 | 1 | 2 | Hrs | 2 Hrs
| 67 | INSPECTION OF MARKING | 66 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs | 3 Hrs
68 | 68 | SH NOZ PIPE CUTTING | 64
| 69 | 26"NB SRN - 2 NOS |  | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 70 | 2" MP CON - 2 NO | 69 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 71 | INSPECTION OF MARKING | 70 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
72 | 72 | SH NOZ PIPE EP | 68
| 73 | 26"NB SRN - 2 NOS |  | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs | 8 Hrs
| 74 | 2" MP CON - 2 NO | 73 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 75 | INSPECTION | 74 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
76 | 76 | SH NOZ+FLG FIITUP | 72
| 77 | 26"NB SRN - 2 NOS |  | F[2],W,H |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 78 | 2" MP CON - 2 NO | 77 | F[2],W,H |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 79 | INSPECTION | 78 | F[2],W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
80 | 80 | SH NOZ PIPE+FLG WELDING | 76
| 81 | 26"NB SRN - 2 NOS |  | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.38 | Hrs | 38.38 Hrs
| 82 | 2" MP CON - 2 NO | 81 | W,H |  | 2"nb | 272 MM | 2 | no | 0 | no |  | hr | 0 |  |  | Hrs
| 83 | INSPECTION | 82 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
84 | 84 | SH NOZ PIPE PROFILE MARKING | 80
| 85 | 26"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 86 | 2" MP CON - 2 NO | 85 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 87 | INSPECTION | 86 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
88 | 88 | SH NOZZLE PIPE PROFILE CUTTING | 84
| 89 | 26"NB SRN - 2 NOS |  | G,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 90 | 2" MP CON - 2 NO | 89 | G,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 91 | INSPECTION | 90 | G,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
92 | 92 | SH NOZZLE PIPE PR0FILE EP | 88
| 93 | 26"NB SRN - 2 NOS |  | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.11 | Hrs | 7.11 Hrs
| 94 | 2" MP CON - 2 NO | 93 | G,H |  | 18 | 272 MM | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.27 | Hrs | 1.27 Hrs
| 95 | INSPECTION | 94 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
96 | 96 | CH NOZ PIPE MARKING | 92
| 97 | 16"NB SRN - 2 NOS |  | F,H |  | 26" nb | 3054 mm | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs | 3 Hrs
| 98 | 2" MP CON - 2 NO | 97 | F,H |  | 2"nb | 272 MM | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs | 3 Hrs
| 99 | INSPECTION | 98 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs | 3 Hrs
100 | 100 | CH NOZ PIPE CUTTING | 96
| 101 | 16"NB SRN - 2 NOS |  | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 102 | 2" MP CON - 2 NO | 101 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 103 | INSPECTION | 102 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
104 | 104 | CH NOZ PIPE EP | 100
| 105 | 16"NB SRN - 2 NOS |  | G,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs | 8 Hrs
| 106 | 2" MP CON - 2 NO | 105 | G,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 107 | INSPECTION | 106 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
108 | 108 | CH NOZ+FLG FIT UP | 104
| 109 | 16"NB SRN - 2 NOS |  | F[2],W,H |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 110 | 2" MP CON - 2 NO | 109 | F[2],W,H |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 111 | INSPECTION | 110 | F[2],W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
112 | 112 | CH NOZ PIPE+FLG WELDING | 108
| 113 | 16"NB SRN - 2 NOS |  | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.38 | Hrs | 38.38 Hrs
| 114 | 2" MP CON - 2 NO | 113 | W,H |  | 2"nb | 272 MM | 2 | no | 0 | no |  | hr | 0 |  |  | Hrs
| 115 | INSPECTION | 114 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
116 | 116 | CH NOZ PIPE PROFILE MARKING | 112
| 117 | 16"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 118 | 2" MP CON - 2 NO | 117 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 119 | INSPECTION | 118 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
120 | 120 | CH NOZZLE PIPE PROFILE CUTTING | 116
| 121 | 16"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 122 | 2" MP CON - 2 NO | 121 | F,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 123 | INSPECTION | 122 | F,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
124 | 124 | CH NOZZLE PIPE PR0FILE EP | 120
| 125 | 16"NB SRN - 2 NOS |  | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.11 | Hrs | 7.11 Hrs
| 126 | 2" MP CON - 2 NO | 125 | G,H |  | 18 | 272 MM | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.27 | Hrs | 1.27 Hrs
| 127 | INSPECTION | 126 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
128 | 128 | SADDLE & OTHER
129 | 129 | TOP SADDLE FABRRICATION | 128
| 130 | PLATE ISSUENCE | [5 empty] | 1 | Set | 1 | Set | 4 | Day | 4 | 0 | 4 | Days | 4 Days
| 131 | BASE MARKING | 130 | F,H |  | 30/25 | 9 rmt | 1 | Set | 9 | mtr | 0.25 | hr | 2.25 | 1 | 3.25 | Hrs | 3.25 Hrs
| 132 | WEB PL MARKING | 131 | F,H |  | 30/25 | 29 rmt | 1 | Set | 29 | mtr | 0.25 | hr | 7.25 | 1 | 8.25 | Hrs | 8.25 Hrs
| 133 | RIBS MARKING | 132 | F,H |  | 25 | 10.5 Rmt | 1 | Set | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.63 | Hrs | 3.63 Hrs
134 | 134 | TOP SADLLE PLATE CUTTING | 129
| 135 | BASE CUTTING |  | C,H |  | 30/25 | 9 rmt | 1 | Nos | 9 | mtr | 0.5 | hr | 4.5 | 1 | 5.5 | Hrs | 5.5 Hrs
| 136 | WEB PL CUTTING | 135 | C,H |  | 30/25 | 29 rmt | 1 | Nos | 29 | mtr | 0.5 | hr | 14.5 | 1 | 15.5 | Hrs | 15.5 Hrs
| 137 | RIBS CUTTING | 136 | C,H |  | 25 | 10.5 Rmt | 1 | Nos | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.63 | Hrs | 3.63 Hrs
| 138 | GRINNDING OF ABOVE | 137 | G[2] |  | 25 |  |  |  | 48.5 | mtr | 0.15 | hr | 7.275 | 1 | 8.28 | Hrs | 8.28 Hrs
139 | 139 | SADDLE FIT UP & WELDING | 134
| 140 | BASE + WEB FIT UP |  | F,H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 141 | BASE + WEB WELDING | 140 | W,H |  | 18 |  | 1 | Set | 4 | No | 3.4 | hr | 13.6 | 1 | 14.6 | Hrs | 14.6 Hrs
| 142 | RIBS+WEB FIT UP | 141 | F,H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 143 | RIBS+WEB WELDING | 142 | W[2],H[2] |  | 18 |  | 1 | Set | 24.8 | No | 3.4 | hr | 84.32 | 1 | 85.32 | Hrs | 85.32 Hrs
144 | 144 | DAVIT PIPE FABRICATION | 139
| 145 | PIPE TRANSFERE |  | H[4] |  |  |  | 1 | SET | 1 | SET | 4 | Day | 4 |  | 4 | Days | 4 Days
| 146 | PIPE MARKING - 6 NOS | 145 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs | 3 Hrs
| 147 | SUPPORT PL MARKING | 146 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 148 | GUSSET PL MARKING | 147 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 149 | BASE HUB MARKING | 148 | F,H |  | 30 |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 150 | PIPE CUTTING - 6 NOS | 149 | C,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs | 3 Hrs
| 151 | SUPPORT PL CUTTING | 150 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 152 | PIPE GRINDING - 6 NOS | 151 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs | 3 Hrs
| 153 | SUPPORT PL GRINDING-10 NOS | 152 | G |  |  |  | 10 | Nos | 10 | Nos | 0.5 | Hr | 5 |  | 5 | Hrs | 5 Hrs
| 154 | PIVOT PL GRINDING | 153 | G |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 155 | PIPE FIT UP-2 NOS | 154 | F,H,W |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 156 | PIPE WELDING -2 NOS | 155 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 157 | PIVOT PL WELDING | 156 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 158 | SUPPORT PL WELDING -4 NOS | 157 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
159 | 159 | LIFTING LUG PAD | 144
| 160 | PLATE ISSUENCE | [5 empty] | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days | 4 Days
| 161 | LIFTING LUG PAD MARKING | 160 | F,H |  | 18 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 162 | LIFTING LUG PAD CUTTING | 161 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 163 | LIFTING LUGS PAD GRINDING | 162 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
164 | 164 | LIFTING LUG PREPARATION | 159
| 165 | LIFTING LUGS MARKING |  | F,H |  | 24 |  | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days | 4 Days
| 166 | LIFTING LUGS CUTTING | 165 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 167 | LIFTING LUGS GRINDING | 166 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 168 | LIFTING LUG DRILLING | 167 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
169 | 169 | CHANNEL COVER HANDLE PREPATAION | 164
| 170 | CH COVER RING FORMING |  | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days | 4 Days
| 171 | SLIDING SLING FORMING | 170 | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days | 4 Days
172 | 172 | INSULATION RING PRPARATION | 169
| 173 | INSULAION RING MARKING |  | F,H |  | 12 |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 174 | INSULAION RING CUTTING | 173 | C,H |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 175 | INSULAION RING HOLE MARKING | 174 | F,H |  |  |  | 1 | Nos | 1 | Nos | 2 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 176 | INSULAION RING HOLE DRILLING | 175 | F,H |  |  |  | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs | 1 Hrs
177 | 177 | BAFFLE & TB ITEMS FAB
178 | 178 | BAFFLE PREPARATION | 177
| 179 | BAFFLE PLATE TRANSFER | [5 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs | 4 Hrs
| 180 | BAFFLE MARKING | 179 | F,H |  | 14 |  | 19 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
| 181 | BAFFLE PROFILE CUTTING | 180 | C,H |  |  |  | 19 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Hrs | 5 Hrs
182 | 182 | BAFFLE BEND REMOVAL & STACKING
| 183 | BAFFLE PL BEND REMOVAL |  | F,H[2] |  |  |  | 19 | Nos | 19 | Nos | 1 | Hr | 19 |  | 19 | Hrs | 19 Hrs
| 184 | BAFFLE PL STACKING | 183 | F,H |  |  | 3 bundle | 3 | Nos | 3 | Nos | 2 | Hr | 6 |  | 6 | Hrs | 6 Hrs
185 | 185 | BAFFLE DRILLING | 182
| 186 | BAFFLE DRILLING | 185 | SC |  | 14 thk |  | 3 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 | Days | 10 Days
187 | 187 | BAFFLE DE STACKING & CHAMFERING | 185
| 188 | BAFFLE DE STACING |  | F,H |  |  |  | 3 | Bunch | 4 | Bunch | 6 | Hrs | 24 |  | 24 | Hrs | 24 Hrs
| 189 | BAFFLE CHAMFERING | 188 | F |  |  |  | 9 | Nos | 23544 | holes | 0.01 |  | 235.44 |  | 235.44 | Days | 235.44 Days
190 | 190 | BAFFLE STACKING & THRO HOLE CHECK | 187
| 191 | STACKING |  | F,H |  |  |  | 3 | Nos | 3 | Nos | 0.25 | Hr | 0.75 |  | 0.75 | Hrs | 0.75 Hrs
| 192 | BAFFLE HOLE ALINGMENT | 191 | F,H |  |  |  | 3 | Nos | 1 | SET | 1 | Hrs | 1 |  | 1 | Hrs | 1 Hrs
| 193 | BAFFLE HOLE RE DRILL | 192 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Days | 5 Days
| 194 | BAFFLE OD MACHINING | 193 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Days | 5 Days
| 195 | BAFFLE CLEANING | 194 | H[3] |  |  |  | 3 | Nos | 1 | SET | 1 | Day | 1 |  | 1 | Days | 1 Days
196 | 196 | SUPPORT PLATE MARKING | 190
| 197 | SUPPORT PLATE TRANSFER | [5 empty] | 2 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 198 | SUPPORT MARKING | 197 | SC |  | 20 |  | 2 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days | 1 Days
| 199 | SUPPORT PROFILE CUTTING | 198 | SC |  |  |  | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days | 5 Days
200 | 200 | SUPPORT PLATE BEND REMOVAL | 196
| 201 | SUPPORT PL BEND REMOVAL |  | F,H[3] |  |  |  | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 202 | SUPPORT PL STACKING | 201 | F,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
203 | 203 | SUPPORT PLATE DRLINNG | 200
| 204 | SUPPORT DRILLING | 203 | SC |  | 20THK |  | 1 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 |  | 10
205 | 205 | SUP PLATE DE STACKING & CHAMFERING | 203
| 206 | SUPPORT DE STACING |  | F,H |  |  |  | 1 | Bunch | 1 | Bunch | 3 | Hrs | 3 |  | 3 | Hrs | 3 Hrs
| 207 | SUPPORT HOLE CHAMFERING | 206 | F |  |  |  | 2 | Plate | 2616 | holes | 0.01 |  | 26.16 |  | 26.16 |  | 26.16
208 | 208 | TIE ROD PREPARATION | 22
| 209 | TIE ROD MATL TRANSFERE | [5 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 210 | ROD CUTTING | 209 | F,H |  |  |  | 22 | Nos | 22 | noS | 0.25 | Hr | 5.5 |  | 5.5 | Hrs | 5.5 Hrs
| 211 | THREAD MACHINING. | 210 | L |  |  |  | 22 | Nos | 22 | Nos | 0.45 | Hr | 9.9 |  | 9.9 | Hrs | 9.9 Hrs
| 212 | JOINING | 211 | W,F,H |  |  |  | 22 | Nos | 22 | Nos | 0.5 | Hr | 11 |  | 11 | Hrs | 11 Hrs
213 | 213 | SPACER TUBE PREPARATION | 21
| 214 | SPACER TUBE TRANSFERE | [5 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs | 4 Hrs
| 215 | LENGTH CUTTING 237NOS | 214 | F,H |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs | 41.4 Hrs
| 216 | LENNGTH MACHINING | 215 | L |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs | 41.4 Hrs
| 217 | CLEANINNG | 216 | H[3] |  |  |  | 414 | Nos | 414 | Nos | 0.016667 | Hr | 6.9 |  | 6.9 | Hrs | 6.9 Hrs
218 | 218 | SEALING STRIP PREPARATION | 16
| 219 | SEALING STRIP MARKING |  | F,H |  | 8 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.1 | Hr | 1.9044 |  | 1.9 | Hrs | 1.9 Hrs
| 220 | SEALING STRIP CUTTING | 219 | C,H |  | 25 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.25 | Hr | 4.761 |  | 4.76 | Hrs | 4.76 Hrs
| 221 | SEALING STRIP BEND REMOVAL | 220 | F,H[2] |  | 25 | 9522 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 222 | SEALING STRIP GRINDING | 221 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs | 16 Hrs
| 223 | SEALING STRIP JOINING | 222 | W,F,H |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 224 | SEALING STRIP DRESS UP | 223 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
225 | 225 | SLIDING STRIP PREPARATION | 17
| 226 | SLIDING STRIP MARKING |  | F,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.1 | Hr | 2.6732 |  | 2.67 | Hrs | 2.67 Hrs
| 227 | SLIDING STRIP CUTTING | 226 | C,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.25 | Hr | 6.683 |  | 6.68 | Hrs | 6.68 Hrs
| 228 | SLIDING STRIP BEND REMOVAL | 227 | F,H[2] |  | 8 | 13366 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 229 | SLIDING STRIP GRINDING | 228 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs | 16 Hrs
| 230 | SLIDING STRIP JOINING | 229 | W,F,H |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 231 | SLIDING STRIP DRESS UP | 230 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
232 | 232 | SEAL ROD PREPARATION | 18
| 233 | SEAL ROD ISSUENECE |  | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days | 4 Days
| 234 | SEAL ROD MARKING | 233 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.25 | Hr | 3.5 |  | 3.5 | Hrs | 3.5 Hrs
| 235 | SEAL ROD CUTTING | 234 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.5 | Hr | 7 |  | 7 | Hrs | 7 Hrs
| 236 | SEAL ROD BEND REMOVAL | 235 | F,H[2] |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 1 | Hr | 14 |  | 14 | Hrs | 14 Hrs
237 | 237 | SHELL FABRICATION | 236
238 | 238 | SHELL MARKING & CUTTING | 3
| 239 | SH PLATE TRNASFER |  | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days | 4 Days
| 240 | SH-MARKING | 239 | F,H[2] |  | 18 | 43000 mm | 1 | Nos | 43 | mtr | 0.1 | hr | 4.3 | 1 | 5.3 | Hrs | 5.3 Hrs
241 | 241 | SHELL PLATE CUTTING | 238
| 242 | SH-CUTTING |  | C,H[2] |  | 18 | 43000 mm | 3 | Nos | 129 | mtr | 0.25 | hr | 32.25 | 1 | 33.25 | Hrs | 33.25 Hrs
243 | 243 | SH PL SIDE GRINDING | 241
| 244 | SH PL SIDE BEVEL CUTTING |  | F,H[3] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 245 | SH PL SIDE BEVEL CUTTING | 244 | F,H[3] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 246 | SH PL SIDE BEVEL CUTTING | 245 | F,H[3] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.63 | Hrs | 1.63 Hrs
| 247 | SH PL SIDE BEVEL CUTTING | 246 | F,H[3] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 |  |  | Hrs
248 | 248 | SHELL PLATE EDGE PREPARATION | 243
| 249 | SH-BEVEL GRINDING |  | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 250 | SH-BEVEL GRINDING | 249 | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 251 | SH-BEVEL GRINDING | 250 | G,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 252 | SH-BEVEL GRINDING | 251 | G,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
253 | 253 | SHELL PRE BENDING | 248
| 254 | SH-PRE BEND |  | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 255 | SH-PRE BEND | 254 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 256 | SH-PRE BEND | 255 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 257 | SH-PRE BEND | 256 | F[2],H |  | 18 | 0 mm | 0 | Nos | 0 | No | 0.3 | hr | 0 |  |  | Hrs
258 | 258 | SHELL PL PRE BEND CUT OFF | 253
| 259 | SH-PRE BEND CUT OFF |  | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 260 | SH-PRE BEND CUT OFF | 259 | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 261 | SH-PRE BEND CUT OFF | 260 | F[2],H,C |  | 18 | 1250 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 262 | SH-PRE BEND CUT OFF | 261 | F[2],H,C |  | 18 | 0 mm | 1 | Nos | 0 | Nos | 0.3 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
263 | 263 | SHELL PLATE LS EP | 258
| 264 | SH-PRE BEND LS EP |  | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 265 | SH-PRE BEND LS EP | 264 | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 266 | SH-PRE BEND LS EP | 265 | F,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 267 | SH-PRE BEND LS EP | 266 | F,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
268 | 268 | SHELL ROLLING | 263
| 269 | SH-ROLLING 1/4 |  | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 270 | SH-ROLLING | 269 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 271 | SH-ROLLING | 270 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 272 | SH-ROLLING | 271 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
273 | 273 | SHELL CIR LENGTH & EP CORRECTION | 268 | [10 empty] | 0
| 274 | SH-LS CORRECTION |  | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 275 | SH-LS CORRECTION | 274 | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 276 | SH-LS CORRECTION | 275 | F,H[2] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 277 | SH-LS CORRECTION | 276 | F,H[2] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
278 | 278 | SHELL LS SEAMS FIT UP | 273 | [10 empty] | 0
| 279 | SH-LS FIT UP |  |  |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 280 | SH-LS FIT UP | 279 | F[2],H,W |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 281 | SH-LS FIT UP | 280 | F[2],H,W |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 282 | SH-LS FIT UP | 281 | F[2],H,W |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
283 | 283 | SH LS WELDING ARRANGEMENT | 278
| 284 | SH-LS WELD ARRANGEMENT |  | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 285 | SH-LS WELD ARRANGEMENT | 284 | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 286 | SH-LS WELD ARRANGEMENT | 285 | F,H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 287 | SH-LS WELD ARRANGEMENT | 286 | F,H |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
288 | 288 | SHELL LONG SEAM OUTER WELDING | 283
| 289 | SH-LS WELDING- TOP SIDE |  | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs | 7.25 Hrs
| 290 | SH-LS WELDING- TOP SIDE | 289 | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs | 7.25 Hrs
| 291 | SH-LS WELDING- TOP SIDE | 290 | W,H |  | 12 | 1250 mm | 1 | Nos | 1.25 | mtr | 2.5 | hr | 3.125 | 1 | 4.13 | Hrs | 4.13 Hrs
| 292 | SH-LS WELDING- TOP SIDE | 291 | W,H |  | 12 | 0 mm | 1 | Nos | 0 | mtr | 2.5 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
293 | 293 | SH LS BACK CHIP | 288
| 294 | SH-LS WELDING- BACK CHIP |  | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 295 | SH-LS WELDING- BACK CHIP | 294 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 296 | SH-LS WELDING- BACK CHIP | 295 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 297 | SH-LS WELDING- BACK CHIP | 296 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
298 | 298 | SH LS INNER WELDING | 293
| 299 | SH-LS INNER WELDING |  | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs | 3.25 Hrs
| 300 | SH-LS INNER WELDING | 299 | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs | 3.25 Hrs
| 301 | SH-LS INNER WELDING | 300 | W,H |  | 6 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.9 | hr | 1.125 | 1 | 2.13 | Hrs | 2.13 Hrs
| 302 | SH-LS INNER WELDING | 301 | W,H |  | 6 | 0 mm | 1 | Nos | 0 | mtr | 0.9 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
303 | 303 | SH INNER LS FLUSH GRINDING | 298
| 304 | SH INNER FLUSH GRINDING |  | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 305 | SH INNER FLUSH GRINDING | 304 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 306 | SH INNER FLUSH GRINDING | 305 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.63 | Hrs | 1.63 Hrs
| 307 | SH INNER FLUSH GRINDING | 306 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
308 | 308 | SH LS RADIOGRAPHY | 303
| 309 | SH LS WELDING RT |  | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 310 | SH LS WELDING RT | 309 | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 311 | SH LS WELDING RT | 310 | RT |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 312 | SH LS WELDING RT | 311 | RT |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
313 | 313 | SHELL RE ROLLING | 308 | [10 empty] | 0
| 314 | SH RE ROLLING |  | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 315 | SH RE ROLLING | 314 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 316 | SH RE ROLLING | 315 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 317 | SH RE ROLLING | 316 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
318 | 318 | SH PLATE CS EP CORRECTION | 313
| 319 | SH CIR EP CORRECTION |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 320 | SH CIR EP CORRECTION | 319 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 321 | SH CIR EP CORRECTION | 320 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 322 | SH CIR EP CORRECTION | 321 | F,H |  | 18 | 0 mm id | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
323 | 323 | SH CIR SEAM FIRST FIT UP | 318
| 324 | SH CS FIT UP - [LS1+LS2] |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 325 | SH CS TACK DP CHECK - [LS1+LS2] | 324 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
326 | 326 | SH CIR SEAM FIRST WELDING | 323
| 327 | SH CS WELDING TRANSFERE |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 328 | SH CS WELDING OUTER [LS1+LS2] | 327 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 329 | SH CS WELDING BACK CHIP [LS1+LS2] | 328 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 330 | SH CS INNER WELDING [LS1+LS2] | 329 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 331 | SH CS FLUSH GRINDING [LS1+LS2] | 330 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
332 | 332 | SH CIR SEAM SECOND FITUP | 326
| 333 | SH CS FIT UP - [LS2+LS3] |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 334 | SH CS TACK DP CHECK - [LS2+LS3] | 333 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
335 | 335 | SH CIR SEAM SECOND WELDING | 332 | [10 empty] | 0
| 336 | SH CS WELDING TRANSFERE-[LS2+LS3] |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 337 | SH CS WELDING OUTER [LS2+LS3] | 336 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 338 | SH CS WELDING BACK CHIP [LS2+LS3] | 337 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 339 | SH CS INNER WELDING [LS2+LS3] | 338 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 340 | SH CS FLUSH GRINDING [LS2+LS3] | 339 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
341 | 341 | SH CIR SEAM III RD FITUP | 335
| 342 | SH CS FIT UP CS3 |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 343 | SH CS TACK DP CHECK CS3 | 342 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
344 | 344 | SH CIR SEAM THIRD WELDING | 341
| 345 | SH CS WELDING TRANSFERE CS3 |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 346 | SH CS WELDING OUTER CS3 | 345 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 347 | SH CS WELDING BACK CHIP CS3 | 346 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 348 | SH CS INNER WELDING CS3 | 347 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 349 | SH CS FLUSH GRINDING CS3 | 348 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
350 | 350 | SH FINAL LENGTH CORRECTION | 344
| 351 | SH LENGTH MARKING |  | F[2] |  | 18 | 1560 mm id | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 352 | LENGTH CUTTING | 351 | C,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
| 353 | GRINDING & EP | 352 | G,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
354 | 354 | SH CIR SEAM FLANGE 1 FITUP | 350
| 355 | SH CS FIT UP FLG CS1 |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 356 | SH CS TACK DP CHECK FLG CS1 | 355 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
357 | 357 | SH CIR SEAM FLANGE 1 WELDING | 354
| 358 | SH CS WELDING TRANSFERE |  | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 359 | SH CS WELDING OUTER FLG CS1 | 358 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 360 | SH CS WELDING BACK CHIP FLG CS1 | 359 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 361 | SH CS INNER WELDING FLG CS1 | 360 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 362 | SH CS FLUSH GRINDING FLG CS1 | 361 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
363 | 363 | SH CS FIT UP FLG2 | 357
| 364 | SH CS FIT UP FLG 2 |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 365 | SH CS TACK DP CHECK FLG2 | 364 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
366 | 366 | SH CS WELDING FLG2 | 363
| 367 | SH CS WELDING TRANSFERE FLG2 |  | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 368 | SH CS WELDING OUTER FLG2 | 367 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 369 | SH CS WELDING BACK CHIP FLG2 | 368 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 370 | SH CS INNER WELDING FLG2 | 369 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 371 | SH CS FLUSH GRINDING FLG2 | 370 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
372 | 372 | NOZZLE ORIENTATION MARKING | 366
| 373 | SH-NOZ ORIENTAION MARKING |  | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 374 | SH-NOZ MARKING-N2A1 | 373 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 375 | SH-NOZ MARKING-N2A1 | 374 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
376 | 376 | SH NOZZLE OPENNING | 372
| 377 | 26"NB SRN - 1 |  | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.31 | Hrs | 1.31 Hrs
| 378 | 26"NB SRN - 1 | 377 | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.31 | Hrs | 1.31 Hrs
379 | 379 | INSPECTION | 376 | C,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
380 | 380 | SH NOZZLE EP | 379
| 381 | 26"NB SRN - 1 |  | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.05 | Hrs | 4.05 Hrs
| 382 | 26"NB SRN - 1 | 381 | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.05 | Hrs | 4.05 Hrs
| 383 | INSPECTION | 382 |  |  |  |  | 1 | No | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
384 | 384 | SH NOZZZLE FIT UP | 380
| 385 | 26"NB SRN - 1 |  | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 386 | 26"NB SRN - 1 | 385 | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 387 | DP CHECK | 386 |  |  |  |  | 2 | No | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
388 | 388 | SH NOZZLE FIT UP INSPECTION | 384
| 389 | 26"NB SRN - 1 |  | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 390 | 26"NB SRN - 1 | 389 | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 391 | DP CHECK | 390 | F,H |  |  | 650nb | 2 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
392 | 392 | SH NOZZLE WELDING | 388
| 393 | SH NOZ WELDING ARRANGEMENT |  | T |  |  |  | 1 | No | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 394 | SH-NOZ WELDING -N1A | 393 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs | 8.64 Hrs
| 395 | SH-NOZ WELDING-N2A1 | 394 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs | 8.64 Hrs
| 396 | SH-NOZ WELDING-N2A2 | 395 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs | 8.64 Hrs
| 397 | SH NOZ ROOT DP CHECK | 396 | F,H |  | 12 | 972 mm lip od | 2 | No | 6.108 | Mtr | 1 | hr | 6.108 | 1 | 7.11 | Hrs | 7.11 Hrs
| 398 | SH-NOZ INNER WELD -N1A | 397 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.15 | Hrs | 5.15 Hrs
| 399 | SH-NOZ INNER WELD-N2A1 | 398 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.15 | Hrs | 5.15 Hrs
| 400 | SH-NOZ INNER WELD-N2A2 | 399 | H,W |  | 8 | 972 mm lip od | 0 | No | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
401 | 401 | SH SADDLE WELDING | 392
| 402 | SH-SADDLE PAD FIT UP |  | F[2],W,H |  | 25 | 1596 mm od | 2 | No | 20.0585 | Nos | 0.5 | Hr | 10.0293 | 1 | 11.03 | Hrs | 11.03 Hrs
| 403 | SH-SADDLE PAD WELDING | 402 | W[2],H[2] |  | 12 | 1596 mm od | 2 | Mtr | 20.0585 | Mtr | 1.6 | Hr | 32.0936 | 1 | 33.09 | Hrs | 33.09 Hrs
| 404 | SH-SADDLE MATCHING | 403 | F[2],G[2] |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 8 | Hr | 16 | 1 | 17 | Hrs | 17 Hrs
| 405 | SH-SADDLE FIT UP | 404 | W,F[2],H |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 6 | Hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 406 | SH-SADDLE WELDING | 405 | W[2],H[2] |  | 12 | 11400 rmt | 1 | Nos | 16.0348 | Mtr | 1.6 | Hr | 25.6557 | 1 | 26.66 | Hrs | 26.66 Hrs
| 407 | SH-SADDLE dress up | 406 | G[2] |  |  |  | 1 | No | 1 | Nos | 8 | Hr | 8 | 1 | 9 | Hrs | 9 Hrs
408 | 408 | SH DAVIT ARM WELDING | 401
| 409 | SH-DAVIT ARM arm match |  | F,G |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 410 | SH-DAVIT ARM FIT UP | 409 | F,H,W |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 411 | SH-DAVIT ARM WELDING | 410 | W,H |  | 12 |  | 6 | mtr | 5.16 | Mtr | 1.6 | Hr | 8.256 | 1 | 9.26 | Hrs | 9.26 Hrs
412 | 412 | SH NDE CLEARENCE | 408
| 413 | SH-SH NDE CLEARENCE | 412 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 12 | Hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 414 | TPI INSPECTION | 413 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 1 | Day | 1 |  | 1 | Days | 1 Days
415 | 415 | CHANNEL FABRICATION
416 | 416 | CHANNEL SHELL LS WELDING | 5
| 417 | CH PLATE TRNASFER | 416 | T |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Days | 4 Days
| 418 | CH-MARKING | 417 | F,H[2] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.1 | hr | 0.0831 | 1 | 1.08 | Hrs | 1.08 Hrs
| 419 | CH-CUTTING | 418 | C,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.25 | hr | 0.20775 | 1 | 1.21 | Hrs | 1.21 Hrs
| 420 | CH PL SIDE GRINDING | 419 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.15 | hr | 0.12465 | 1 | 1.12 | Hrs | 1.12 Hrs
| 421 | CH-BEVELLING CIR SIDE | 420 | F,H[3] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.42 | Hrs | 1.42 Hrs
| 422 | CH EP GRINDING | 421 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs | 1.83 Hrs
423 | 423 | CHANNEL SH ROLLING | 416
| 424 | CH-PRE BEND |  | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 425 | CH-PRE BEND CUT OFF | 424 | F[2],C |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 0.3 | hr | 0.4986 | 1 | 1.5 | Hrs | 1.5 Hrs
| 426 | CH LS BEVELING | 425 | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.66 | Hrs | 2.66 Hrs
| 427 | CH-ROLLING | 426 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
428 | 428 | CH SHELL LS FIT UP | 423
| 429 | CH-LS CORRECTION |  | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.66 | Hrs | 2.66 Hrs
| 430 | CH-LS FIT UP | 429 | F[2],W,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs | 1.83 Hrs
431 | 431 | CH SHELL LS WELDING | 428
| 432 | CH-LS WELD ARRANGEMENT |  | F,H[2] |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 433 | CH-LS WELDING- TOP SIDE | 432 | W,H |  | 12 | 831 mm | 1 | Nos | 0.831 | mtr | 2.5 | hr | 2.0775 | 1 | 3.08 | Hrs | 3.08 Hrs
| 434 | CH-LS WELDING- BACK CHIP | 433 | G,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs | 1.83 Hrs
| 435 | CH-LS INNER WELDING | 434 | W,H |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.9 | hr | 0.7479 | 1 | 1.75 | Hrs | 1.75 Hrs
| 436 | CH-LS INNNER FLUSH GRIND | 435 | G |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.42 | Hrs | 1.42 Hrs
| 437 | CH RE ROLLING | 436 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
438 | 438 | CH LS WELDING RADIOGRAPHY | 431
| 439 | CH LS WELDING RT |  | RT |  | 18 | 831 mm | 1 | No | 1 | No | 1 | dya | 1 |  | 1 | Days | 1 Days
440 | 440 | CH CS FLG 1 FIT UP | 438
| 441 | CH CIR EP CORRECTION |  | F[2] |  | 18 | 1560 mm id | 1 | Nos | 9.803 | mtr | 0.45 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 442 | CH CS FIT UP FLG1 | 441 | F[2],W,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 443 | CH CS TACK DP CHECK FLG1 | 442 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
444 | 444 | CH CS FLG 1 WELDING | 440
| 445 | CH CS WELDING TRANSFERE |  | F,H[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 446 | CH CS WELDING OUTER FLG1 | 445 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 447 | CH CS WELDING BACK CHIP FLG1 | 446 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 448 | CH CS INNER WELDING FLG 1 | 447 | W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1.36 | hr | 6.6661 | 1 | 7.67 | Hrs | 7.67 Hrs
| 449 | CH CS FLUSH GRINDING FLG1 | 448 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
450 | 450 | CH CS FLG 2 FIT UP | 444
| 451 | CH LENGTH CUTTING |  | C,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
| 452 | CH CIR EP CORRECTION | 451 | F,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 453 | CH CS FIT UP FLG2 | 452 | F[2],W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 4 | hr | 19.6061 | 1 | 20.61 | Hrs | 20.61 Hrs
| 454 | CH CS TACK DP CHECK FLG1 | 453 | F |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
455 | 455 | CH CS FLG 2 WELDING | 450
| 456 | CH CS WELDING TRANSFERE FLG2 |  | F,H[2] |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 457 | CH CS WELDING OUTER FLG2 | 456 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 458 | CH CS WELDING BACK CHIP FLG2 | 457 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 459 | CH CS INNER WELDING FLG2 | 458 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 460 | CH CS FLUSH GRINDING FLG2 | 459 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
461 | 461 | CH CS FLG 1 & 2 WELDING rt | 455
| 462 | CH CS WELDING RT |  | RT |  | 18 | 1560 mm id | 1 | No | 1 | n | 1 | Day | 1 |  | 1 | Days | 1 Days
463 | 463 | CHANNEL NOZ MARKING | 461
| 464 | CH- NOZ IREIENTATION NKG |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 465 | CH-NOZ MARKING- 16"NB - 2 NOS | 464 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
466 | 466 | CH NOZ OPNNING | 463
| 467 | CH-NOZ OPENNING-TOP |  | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 468 | CH-NOZ OPENNING-Bot | 467 | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
469 | 469 | CH NOZ OPEN EP | 466
| 470 | CH-NOZ EP -N3A |  | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 471 | CH-NOZ EP-N4A | 470 | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
472 | 472 | CH NOZ FIT UP | 469
| 473 | CH-NOZ FIT UP -N3A |  | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 474 | CH-NOZ FIT UP -N4A | 473 | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
475 | 475 | CH NOZ FIT UP INSP | 472
| 476 | CH-NOZ INSPN -N3A |  | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 477 | CH-NOZ INSPN-N4A | 476 | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
478 | 478 | CH NOZ WELDING | 475
| 479 | CH NOZ WELDING ARRANGEMENT |  | F,H[2] |  |  | 400nb | 2 | Nos | 1 | No | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
| 480 | CH-NOZ WELDING -N3A | 479 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs | 5.11 Hrs
| 481 | CH-NOZ WELDING-N4A | 480 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs | 5.11 Hrs
| 482 | CH NOZ ROOT DP CHECK | 481 | W,H |  | 14 | 407 mm | 2 | No | 2 | Nos | 1 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
| 483 | CH-NOZ INNER WELD -N3A | 482 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs | 2.15 Hrs
| 484 | CH-NOZ INNER WELD-N4A | 483 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs | 2.15 Hrs
| 485 | RF PAD FIT UP & Nozzle fit up | 484 | W,H |  |  | 400nb | 2 | No | 2 | Set | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 486 | RF PAD FIT UP WELDING | 485 | G,H |  | 18 |  | 2 | No | 2.5538 | Mtr | 6.8 | hr | 17.366 | 1 | 18.37 | Hrs | 18.37 Hrs
| 487 | NOZ WELDING FLUSH GRIND- 16"NB | 486 | G |  |  | 407 mm | 2 | NoS | 2.5538 | No | 0.15 | hr | 0.38307 | 1 | 1.38 | Hrs | 1.38 Hrs
488 | 488 | CHANNEL PP PLATE FIT UP | 478
| 489 | CH- PP PLATE FIT UP |  | F[2],H,W |  | 24 | 14465 | 1 | No | 14.465 | Nos | 0.5 | hr | 7.2325 | 1 | 8.23 | Hrs | 8.23 Hrs
| 490 | CH- PP PLATE FIT UP INSP | 489 | F,H |  | 24 | 1560 id | 3 | No | 4 | Nos | 0.5 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
491 | 491 | CH PP PLATE WELDING | 488
| 492 | CH- PP PLATE WELDING |  | W,H |  | 24 | 1480 | 3 | No | 4.44 |  | 11.2 | hr | 49.728 | 1 | 50.73 | Hrs | 50.73 Hrs
| 493 | CH- PP PLATE FACE GRINDING | 492 | G,H |  | 12 | 12310 mm | 1 | No | 12.31 | No | 1.6 | hr | 19.696 | 1 | 20.7 | Hrs | 20.7 Hrs
494 | 494 | CHANNEL DAVIT ARM WELDING | 491
| 495 | CH-DAVIT ARM arm match |  | F,H |  | 18 | 1480 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 496 | CH-DAVIT ARM FIT UP | 495 | F,W,H |  | 18 | 1251 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 497 | CH-DAVIT ARM WELDING | 496 | W,H |  | 12 | 6 | 1 | No | 6 | mtr | 1.6 | hr | 9.6 | 1 | 10.6 | Hrs | 10.6 Hrs
498 | 498 | CHANNEL NDE & PWHT | 494
| 499 | CH ALL WELDING DRESSUP & DP CHECK |  | G[2] |  | 18 | 1480lg | 1 | No | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 500 | CH-CH NDE CLEARENCE | 499 | F |  | 18 | 1480lg | 1 | No | 1 | No | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
501 | 501 | BARREL FABRICATION
502 | 502 | BARREL SH PLATE CUTTING & EP | 7 |  |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Hrs | 4 Hrs
| 503 | BARREL PLATE TRNASFER |  | T |  | 18 | 373 mm | 1 | Nos | 0.373 | mtr | 0.1 | Hr/mtr | 0.0373 | 1 | 1.04 | Hrs | 1.04 Hrs
| 504 | BARREL-MARKING | 503 | F,H[2] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.25 | Hr/mtr | 2.825 | 1 | 3.83 | Hrs | 3.83 Hrs
| 505 | BARREL-CUTTING | 504 | C,H |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.15 | Hr/mtr | 1.695 | 1 | 2.7 | Hrs | 2.7 Hrs
| 506 | BARREL PL SIDE GRINDING | 505 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.5 | Hr/mtr | 5.65 | 1 | 6.65 | Hrs | 6.65 Hrs
| 507 | BARREL-BEVELLING CIR SIDE | 506 | F,H[3] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs | 12.3 Hrs
| 508 | CH EP GRINDING | 507 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs | 12.3 Hrs
509 | 509 | BAR SHELL ROLLING | 502
| 510 | BARREL-PRE BEND |  | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 511 | BARREL-PRE BEND CUT OFF | 510 | F[2],C |  | 18 | 1664 mm id | 1 | Nos | 3.328 | No | 0.3 | hr | 0.9984 | 1 | 2 | Hrs | 2 Hrs
| 512 | BARREL -PRE LS EP | 511 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs | 4.33 Hrs
| 513 | BARREL-ROLLING | 512 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
514 | 514 | BARREL SHELL LS FIT UP | 509
| 515 | BARREL-LS CORRECTION |  | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs | 4.33 Hrs
| 516 | BARREL-LS FIT UP | 515 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs | 2.66 Hrs
517 | 517 | BARREL SHELL LS WELDING | 514
| 518 | BARREL-LS WELD ARRANGEMENT |  | F,H[2] |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 519 | BARREL-LS WELDING- TOP SIDE | 518 | W,H |  | 12 | 1664 mm id | 1 | Nos | 1.664 | mtr | 2.5 | hr | 4.16 | 1 | 5.16 | Hrs | 5.16 Hrs
| 520 | BARREL-LS WELDING- BACK CHIP | 519 | G,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs | 2.66 Hrs
| 521 | BARREL-LS INNER WELDING | 520 | W,H |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.9 | hr | 1.4976 | 1 | 2.5 | Hrs | 2.5 Hrs
| 522 | BARREL-LS INNNER FLUSH GRIND | 521 | G |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.5 | hr | 0.832 | 1 | 1.83 | Hrs | 1.83 Hrs
| 523 | BARREL RE ROLLING | 522 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
524 | 524 | BARREL LS WELDING RT
| 525 | BAR LS WELDING RT |  | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
526 | 526 | BARREL SHELL CS FLG 1 FIT UP | 524
| 527 | BARREL CIR EP CORRECTION |  | F[2] |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 528 | BARREL CS FIT UP FLG1 | 527 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 529 | BARREL CS TACK DP CHECK FLG1 | 528 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | no | 0.25 | hr | 1.3071 | 1 | 2.31 | Hrs | 2.31 Hrs
530 | 530 | BARREL SH CS FLG 1 WELDING | 526
| 531 | BARREL CS WELDING TRANSFERE |  | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 532 | BARREL CS WELDING OUTER FLG1 | 531 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs | 14.07 Hrs
| 533 | BARREL CS WELDING BACK CHIP FLG1 | 532 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 534 | BARREL CS INNER WELDING FLG 1 | 533 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs | 5.71 Hrs
| 535 | BARREL CS FLUSH GRINDING FLG1 | 534 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs | 3.61 Hrs
536 | 536 | BARREL CS FIT UP WITH DISH | 530 | [10 empty] | 0
| 537 | BARREL LENGTH CUTTING | 536 | C,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 538 | BARREL EP | 537 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 539 | BARREL CS FIT UP DISH | 538 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 4 | hr | 20.9132 | 1 | 21.91 | Hrs | 21.91 Hrs
| 540 | BARREL CS TACK DP CHECK DISH | 539 | F |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 3.5 | hr | 18.299 | 1 | 19.3 | Hrs | 19.3 Hrs
541 | 541 | BARREL CS WELDING WITH DISH | 536
| 542 | BARREL CS WELDING TRANSFERE DISH |  | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 543 | BARREL CS WELDING OUTER DISH | 542 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs | 14.07 Hrs
| 544 | BARREL CS WELDING BACK CHIP DISH | 543 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 545 | BARREL CS INNER WELDING DISH | 544 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs | 5.71 Hrs
| 546 | BARREL CS FLUSH GRINDING DISH | 545 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs | 3.61 Hrs
547 | 547 | BARREL CS FLG 1 & DISH WELDING rt | 541
| 548 | BARREL CS WELDING RT |  | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
549 | 549 | BARREL NOZ OREINATION MARKING | 547
| 550 | BARREL- NOZ IREIENTATION NKG |  | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 551 | BARREL-NOZ MARKING- 2 | 550 | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
552 | 552 | BARREL NOZZLE OPPENING | 549
| 553 | BARREL-NOZ OPENNING-40 NB - LWN |  | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 554 | BARREL-NOZ OPENNING-40 NB - LWN | 553 | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
555 | 555 | BARREL NOZ EDGE PREPARATION | 552
| 556 | BARREL-NOZ OPENNING-40 NB - LWN |  | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
| 557 | BARREL-NOZ OPENNING-40 NB - LWN | 556 | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
558 | 558 | BARREL NOZZZLE FIT UP | 555
| 559 | BARREL-NOZ FIT UP -N5A |  | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 560 | BARREL-NOZ FIT UP -N6A | 559 | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
561 | 561 | BARREL NOZ FIT UP INSPECTION | 558
| 562 | BARREL-NOZ INSPN -5A |  | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
| 563 | BARREL-NOZ INSPN-6A | 562 | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
564 | 564 | BARREL NOZZLE WELDING | 561
| 565 | BARREL NOZ WELDING ARRANGEMENT |  | T |  | 40NB | 40NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
| 566 | BARREL-NOZ WELDING -N5A | 565 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
| 567 | BARREL-NOZ WELDING-N6A | 566 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
| 568 | BARREL NOZ ROOT DP | 567 | F,H |  |  | 75 MM | 2 | No | 2 |  | 0.5 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 569 | BARREL-NOZ INNER WELDING -N5A | 568 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
| 570 | BARREL-NOZ INNER WELDING-N6A | 569 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
571 | 571 | BARREL NOZ INNER WELD FLUSH GRIND | 564
| 572 | BARREL ALL WELDING DRESSUP & DP |  | G[2] |  | 20 | 40NB | 1 | No | 1 | NO | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 573 | BARREL-BARREL NDE CLEARENCE | 572 | F |  | STD | 40NB | 1 | NoS | 1 | No | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
574 | 574 | FL HEAD FABRICATION
575 | 575 | FLAOTING HEAD DISH FORMING | 13
| 576 | FL HEAD DISH PL ISSUE |  | T |  |  |  | 1 | No | 1 |  | 4 | Day | 4 |  | 4 | Days | 4 Days
| 577 | FL HEAD PL MARKING | 576 | F,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.1 | hr | 0.62337 | 1 | 1.62 | Hrs | 1.62 Hrs
| 578 | FL HEAD PL STAMPING | 577 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 579 | FL HEAD PL CUTTING | 578 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.25 | hr | 1.5584 | 1 | 2.56 | Hrs | 2.56 Hrs
| 580 | FL HEAD PL GRINDING | 579 | G |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 1 | hr | 6.2337 | 1 | 7.23 | Hrs | 7.23 Hrs
581 | 581 | FL HEAD FORMIG | 575
| 582 | FL HEAD FORMING |  | SC |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 10 | Day | 10 |  | 10 | Days | 10 Days
| 583 | FL HEAD PROFILE CHECK | 582 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
584 | 584 | FL HEAD CUTTING | 581
| 585 | FL HEAD MARKING |  | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 4 | Hr/No | 4 |  | 4 | Hrs | 4 Hrs
| 586 | FL HEAD CUTTING | 585 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 0.1 | hr | 0.62337 | 2 | 2.62 | Hrs | 2.62 Hrs
587 | 587 | FL HEAD EP | 584
| 588 | FL HEAD GRINDING |  | G,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs | 8.23 Hrs
589 | 589 | FL HEAD FIT UP | 587,12
| 590 | FL HEAD FIT UP |  | F[2],W,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs | 8.23 Hrs
591 | 591 | FL HEAD WELDING | 589
| 592 | FL HEAD WELDING |  | W,H |  | 30 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 16.8 | hr | 104.7266 | 2 | 106.73 | Hrs | 106.73 Hrs
| 593 | FL HEAD PP PLATE FIT UP | 592 | F[2],H,W |  | 16 | 1550 mm id | 1 | Nos | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 594 | FL HEAD PP PL WELDING | 593 | W,H |  | 16 | 3000 mm | 1 | Nos | 3 | Mtr | 2.8 | hr | 8.4 | 2 | 10.4 | Hrs | 10.4 Hrs
| 595 | FL HEAD PP PL LEVEL GRINDING | 594 | F,H |  | 16 | 3000 mm | 1 | Nos | 1 | No | 6 | hr | 6 | 1 | 7 | Hrs | 7 Hrs
| 596 | FL HEAD INSPECTION | 595 | F |  | 16 | 3000 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
597 | 597 | FL HEAD SR & MACHINING | 591
| 598 | FL HEAD SR |  | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 3 | Day | 3 | 0 | 3 | Hrs | 3 Hrs
| 599 | FL HEAD FINAL MACHINING | 598 | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs | 4 Hrs
| 600 | FL HEAD HOLE MARKING | 599 | F,H |  |  | 1550 mm id | 1 | Nos | 1 | No | 0.5 | Day | 0.5 | 0 | 0.5 | Hrs | 0.5 Hrs
| 601 | FL HEAD HOLE DRILLING | 600 | SC |  | 140 mm | 1550 mm id | 72 | hole | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs | 4 Hrs
| 602 | FL HEAD FINAL INSPECTION | 601 | F,H |  | 140 mm | 1550 mm id | 1 | No | 1 | No | 1 | Day | 1 | 0 | 1 | Hrs | 1 Hrs
603 | 603 | TUBE BUNDLE FABRICATION
604 | 604 | TUBE BUNDLE ASSY | 46,177
| 605 | FRAME SET UP & TUBE SHT SET UP |  | F[2],W |  | 145T | 1308 tube |  |  | 1 |  | 1.5 | Day | 1.5 | 0 | 1.5 | Hrs | 1.5 Hrs
| 606 | SKELITON ASSY- 19 baffle | 605 | F[2],H[3] |  |  | 19 baffle | 1 | Nos | 19 | Nos | 0.5 | hr | 9.5 | 1 | 10.5 | Hrs | 10.5 Hrs
607 | 607 | TUBE INSERT | 604,412
| 608 | TUBE INSERT |  | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs | 55.5 Hrs
| 609 | SEAL ROD INSERT & WELD | 608 | F[2],W,H[2] |  | 25.4 dia | 5134 lg | 14 | Nos | 14 | Nos | 0.5 | Hr/no | 7 | 1 | 8 | Hrs | 8 Hrs
| 610 | TUBE INSERT | 609 | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs | 55.5 Hrs
611 | 611 | SLIDING STRIP FIT UP WELDING | 607
| 612 | SEALING STRIP FIT UP |  | F,H |  | 8 | 4592 mm lg | 2 | Nos | 2 | Nos | 3 | Hr/no | 6 | 1 | 7 | Hrs | 7 Hrs
| 613 | SLIDING STRIP WELDING | 612 | W,H |  | 8 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs | 16 Hrs
| 614 | SEAL/SLID TRIP WELD GRIND | 613 | G |  | 1500 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs | 16 Hrs
615 | 615 | TUBE BUNDLE INSERT | 611
| 616 | TUBE BUNDLE INSERT IN SHELL |  | F[3],H[8] |  |  | 7000 LG | 1 | Nos | 1 | Nos | 16 | Hr/no | 16 | 1 | 17 | Hrs | 17 Hrs
| 617 | FL HEAD TUBE SHT FIXING | 616,56 | F[2],H[4] |  | 145MM |  | 1 | Nos | 1 | Nos | 4 | Hr/no | 4 | 1 | 5 | Hrs | 5 Hrs
| 618 | TEST FLG & GLAND ASSY | 617 | F[3],H[6] |  | 165 MM | 1490 | 1 | Nos | 56 | Bolts | 0.16667 | hr | 9.3333 | 1 | 10.33 | Hrs | 10.33 Hrs
619 | 619 | TUBE EXPANSION IN GROOVES | 615
| 620 | TUBE EXP - ST SIDE - 1 STAGE |  | F,H[2] |  | 150 mm | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.016667 | hr | 21.8 | 1 | 22.8 | Hrs | 22.8 Hrs
| 621 | TUBE EXP - FL SIDE - 1 STAGE | 620 | F,H[2] |  | Servo | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.0083333 | hr | 10.9 | 1 | 11.9 | Hrs | 11.9 Hrs
| 622 | TUBE TRIMMING FL SIDE | 621 | F,H |  | Servo | 1308 nos | 1308 | Nos | 1308 | Trimm | 0.033333 | hr | 43.6 | 1 | 44.6 | Hrs | 44.6 Hrs
| 623 | TUBE EXP BOTH SIDE - 4 STAGE | 622 | F[2],H[2] |  | 150MM | 2616 Roll | 2616 | Nos | 2616 | Rolling | 0.0083333 | hr | 21.8 | 1 | 22.8 | Hrs | 22.8 Hrs
624 | 624 | TUBE EXP- PNUEMATIC TEST | 619
| 625 | TUBE EXP PNUEMATIC TEST |  | F[2],H[2] |  |  |  | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 626 | PNUEMATIC TEST TPI WITNESS | 625 | F,H |  |  |  | 1 | No | 1 | Test | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
| 627 | CLEANING | 626 | F,H[3] |  |  |  | 1 | No | 1 | No | 1 | Hr | 1 |  | 1 | Hrs | 1 Hrs
628 | 628 | TUBE TUBE SHEET WELDING- FT SIDE | 624
| 629 | TUBE WELDING - ST SIDE ROOT |  | TW,H |  | 2.77 | 25.4 od | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 630 | TUBE WELDING - ST SIDE ROOT DP | 629 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 631 | TUBE WELDING - ST SIDE FINAL WELD | 630 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 632 | TUBE WELDING - ST SIDE FINAL DP | 631 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
633 | 633 | TUBE TO TUBE SHEET WELDING - FL HEAD SIDE | 628
| 634 | TUBE WELDING - FLH SIDE ROOT |  | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 635 | TUBE WELDING - FLH SIDE ROOT DP | 634 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 636 | TUBE WELDING - FLH SIDE FINAL WELD | 635 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 637 | TUBE WELDING - FLH SIDE FINAL DP | 636 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
638 | 638 | SHELL SIDE HYDRO | 633
| 639 | SHELL SIDE WATER FILLING | [5 empty] | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 640 | SHELL SIDE HYDRO | 639 | F[2],H[2] |  |  | 6130 lg | 1 | No | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 641 | SHELL SIDE TPI WITNESS | 640 | F[2] |  |  | 6130 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Hrs | 1 Hrs
| 642 | DE WATERING & DISMANTLE OF GLAND | 641 | F[2],H[4] |  |  | 6130 lg | 1 | No | 1 | Test | 4 | hr | 4 | 0 | 4 | Hrs | 4 Hrs
643 | 643 | DISH FORMING - 24T*1700 OD | 1263
| 644 | BAR DISH BLANK ISSUENCE |  | T |  | 24 | ID dish | 1 | No | 1 | nos | 4 | Day | 4 |  | 4 | Days | 4 Days
| 645 | BAR-DISH BLANK MARKING - 24 * 1670 | 644 | F,H |  | 24 | 6723 MM | 1 | No | 6.723 | Dia-mtr | 0.1 | Hr/mtr | 0.6723 | 1 | 1.67 | Hrs | 1.67 Hrs
| 646 | BAR-DISH BLANK MARKING INSPECTION | 645 | F,H |  | 24 |  | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 647 | BAR-DISH BLANK CUTTING | 646 | C,H |  | 24 | 6723 MM | 1 | no | 6.723 | Dia-mtr | 0.25 | RMT | 1.6807 | 1 | 2.68 | Hrs | 2.68 Hrs
| 648 | BAR-DISH FORMING | 647 | SC |  | 24 | 6723 MM | 1 | no | 1 | No | 10 | Day | 10 |  | 10 | Days | 10 Days
| 649 | PROFILE INSP | 648 | F,H |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 650 | HEAT TREATMENT PREPARATION | 649 | SC |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 651 | STRESS RELEIVING- SUB CONT | 650 | SC |  | 24 | 6723 MM | 1 | no | 1 | No | 4 | Day | 4 |  | 4 | Days | 4 Days
| 652 | REMOVAL OF SPIDERS | 651 | F,H |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 653 | SURFACE PREPARATION | 652 | G |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 | 1 | 2 | Days | 2 Days
| 654 | INSPECTION | 653 | F |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 655 | TPI INSPECTION | 654 | F |  | 24 | 6723 MM | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 656 | SF MARKING | 655 | F,H | enter | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 0.1 | RMT | 0.53163 | 1 | 1.53 | Hrs | 1.53 Hrs
| 657 | SF CUTTING | 656 | C,H |  | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 1 | RMT | 5.3163 | 1 | 6.32 | Hrs | 6.32 Hrs
| 658 | SF GRIDNING & EP | 657 | G |  | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 1 | RMT | 5.3163 |  | 5.32 | Hrs | 5.32 Hrs
659 | 659 | TUBE SHEET
660 | 660 | TUBE SHEET MACHINING 1 OFF 2 | 1264
| 661 | INWARD INSPECTION |  |  | enter | 145 t | 1692 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | Days | 2 Days
| 662 | TUBE SHEET M/C - 1/2 | 661 | SC |  | 145 t | 1692 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | Days | 5 Days
663 | 663 | TUBE SHEET DRILLING 1 OFF 2 | 660
| 664 | TUBE SHEET DRILLING -1/2 |  | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.27 | Days | 5.27 Days
| 665 | EXP GROOVE+WELDING GROOVE -1/2 | 664 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.54 | Days | 4.54 Days
| 666 | TIE ROD, PULLING, LIFTING HOLE - 1/2 | 665 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Days | 1 Days
| 667 | PASS PARTITION GROOVE M/C -1/2 | 666 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 668 | CLEANING ,GO/NO GO CHECK -1/2 | 667 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs | 65.4 Hrs
| 669 | FINAL INSPECTION -1/2 | 668 | F,H
670 | 670 | TUBE SHEET MACHINING 2 OFF 2 | 1264
| 671 | INWARD INSPECTION |  |  |  | 145 t | 1670 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | Days | 2 Days
| 672 | TUBE SHEET M/C - 2/2 | 671 | SC |  | 145 t | 1548 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | Days | 5 Days
673 | 673 | TUBE SHEET DRILLING 2 OFF 2
| 674 | TUBE SHEET DRILLING -2/2 |  | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.27 | Days | 5.27 Days
| 675 | EXP GROOVE+WELDING GROOVE -2/2 | 674 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.54 | Days | 4.54 Days
| 676 | TIE ROD, PULLING, LIFTING HOLE - 2/2 | 675 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Days | 1 Days
| 677 | PASS PARTITION GROOVE M/C -2/2 | 676 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 678 | CLEANING ,GO/NO GO CHECK -2/2 | 677 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs | 65.4 Hrs
| 679 | FINAL INSPECTION -2/2 | 678 | F,H |  |  |  | 1 |  | 1050 | nos | 0.05 | RMT | 52.5 | 1 | 53.5 | Hrs | 53.5 Hrs
680 | 680 | NOZZLE FAB
681 | 681 | SH NOZ PIPE MARKING | 1099
| 682 | 26"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 1 | Hr/no | 2 | 1 | 3 | Hrs | 3 Hrs
| 683 | 2" MP CON - 2 NO | 682 | F,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 1 | Hr/no | 2 | 1 | 3 | Hrs | 3 Hrs
| 684 | INSPECTION OF MARKING | 683 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr/no | 2 | 1 | 3 | Hrs | 3 Hrs
685 | 685 | SH NOZ PIPE CUTTING | 681
| 686 | 26"NB SRN - 2 NOS |  | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 | Hr/no | 0 | 0 |  | Hrs
| 687 | 2" MP CON - 2 NO | 686 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 | Hr/no | 0 | 0 |  | Hrs
| 688 | INSPECTION OF MARKING | 687 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 | Hr/no | 0 | 0 |  | Hrs
689 | 689 | SH NOZ PIPE EP | 685
| 690 | 26"NB SRN - 2 NOS |  | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs | 8 Hrs
| 691 | 2" MP CON - 2 NO | 690 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 692 | INSPECTION | 691 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
693 | 693 | SH NOZ+FLG FIITUP | 689
| 694 | 26"NB SRN - 2 NOS |  | F[2],W,H |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 695 | 2" MP CON - 2 NO | 694 | F[2],W,H |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 696 | INSPECTION | 695 | F[2],W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
697 | 697 | SH NOZ PIPE+FLG WELDING | 693
| 698 | 26"NB SRN - 2 NOS |  | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.38 | Hrs | 38.38 Hrs
| 699 | 2" MP CON - 2 NO | 698 | W,H |  | 2"nb | 272 MM | 2 | no | 0 | no |  | hr | 0 |  |  | Hrs
| 700 | INSPECTION | 699 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
701 | 701 | SH NOZ PIPE PROFILE MARKING | 697
| 702 | 26"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 703 | 2" MP CON - 2 NO | 702 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 704 | INSPECTION | 703 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
705 | 705 | SH NOZZLE PIPE PROFILE CUTTING | 701
| 706 | 26"NB SRN - 2 NOS |  | G,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 707 | 2" MP CON - 2 NO | 706 | G,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 708 | INSPECTION | 707 | G,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
709 | 709 | SH NOZZLE PIPE PR0FILE EP | 705
| 710 | 26"NB SRN - 2 NOS |  | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.11 | Hrs | 7.11 Hrs
| 711 | 2" MP CON - 2 NO | 710 | G,H |  | 18 | 272 MM | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.27 | Hrs | 1.27 Hrs
| 712 | INSPECTION | 711 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
713 | 713 | CH NOZ PIPE MARKING | 709
| 714 | 16"NB SRN - 2 NOS |  | F,H |  | 26" nb | 3054 mm | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs | 3 Hrs
| 715 | 2" MP CON - 2 NO | 714 | F,H |  | 2"nb | 272 MM | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs | 3 Hrs
| 716 | INSPECTION | 715 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs | 3 Hrs
717 | 717 | CH NOZ PIPE CUTTING | 713
| 718 | 16"NB SRN - 2 NOS |  | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 719 | 2" MP CON - 2 NO | 718 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 720 | INSPECTION | 719 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
721 | 721 | CH NOZ PIPE EP | 717
| 722 | 16"NB SRN - 2 NOS |  | G,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs | 8 Hrs
| 723 | 2" MP CON - 2 NO | 722 | G,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 |  | Hrs
| 724 | INSPECTION | 723 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 |  | Hrs
725 | 725 | CH NOZ+FLG FIT UP | 721
| 726 | 16"NB SRN - 2 NOS |  | F[2],W,H |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 727 | 2" MP CON - 2 NO | 726 | F[2],W,H |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 728 | INSPECTION | 727 | F[2],W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
729 | 729 | CH NOZ PIPE+FLG WELDING | 725
| 730 | 16"NB SRN - 2 NOS |  | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.38 | Hrs | 38.38 Hrs
| 731 | 2" MP CON - 2 NO | 730 | W,H |  | 2"nb | 272 MM | 2 | no | 0 | no |  | hr | 0 |  |  | Hrs
| 732 | INSPECTION | 731 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
733 | 733 | CH NOZ PIPE PROFILE MARKING | 729
| 734 | 16"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 735 | 2" MP CON - 2 NO | 734 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 736 | INSPECTION | 735 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
737 | 737 | CH NOZZLE PIPE PROFILE CUTTING | 733
| 738 | 16"NB SRN - 2 NOS |  | F,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 739 | 2" MP CON - 2 NO | 738 | F,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
| 740 | INSPECTION | 739 | F,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs | 1 Hrs
741 | 741 | CH NOZZLE PIPE PR0FILE EP | 737
| 742 | 16"NB SRN - 2 NOS |  | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.11 | Hrs | 7.11 Hrs
| 743 | 2" MP CON - 2 NO | 742 | G,H |  | 18 | 272 MM | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.27 | Hrs | 1.27 Hrs
| 744 | INSPECTION | 743 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
745 | 745 | SADDLE & OTHER
746 | 746 | TOP SADDLE FABRRICATION | 745
| 747 | PLATE ISSUENCE | [5 empty] | 1 | Set | 1 | Set | 4 | Day | 4 | 0 | 4 | Days | 4 Days
| 748 | BASE MARKING | 747 | F,H |  | 30/25 | 9 rmt | 1 | Set | 9 | mtr | 0.25 | hr | 2.25 | 1 | 3.25 | Hrs | 3.25 Hrs
| 749 | WEB PL MARKING | 748 | F,H |  | 30/25 | 29 rmt | 1 | Set | 29 | mtr | 0.25 | hr | 7.25 | 1 | 8.25 | Hrs | 8.25 Hrs
| 750 | RIBS MARKING | 749 | F,H |  | 25 | 10.5 Rmt | 1 | Set | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.63 | Hrs | 3.63 Hrs
751 | 751 | TOP SADLLE PLATE CUTTING | 746
| 752 | BASE CUTTING |  | C,H |  | 30/25 | 9 rmt | 1 | Nos | 9 | mtr | 0.5 | hr | 4.5 | 1 | 5.5 | Hrs | 5.5 Hrs
| 753 | WEB PL CUTTING | 752 | C,H |  | 30/25 | 29 rmt | 1 | Nos | 29 | mtr | 0.5 | hr | 14.5 | 1 | 15.5 | Hrs | 15.5 Hrs
| 754 | RIBS CUTTING | 753 | C,H |  | 25 | 10.5 Rmt | 1 | Nos | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.63 | Hrs | 3.63 Hrs
| 755 | GRINNDING OF ABOVE | 754 | G[2] |  | 25 |  |  |  | 48.5 | mtr | 0.15 | hr | 7.275 | 1 | 8.28 | Hrs | 8.28 Hrs
756 | 756 | SADDLE FIT UP & WELDING | 751
| 757 | BASE + WEB FIT UP |  | F,H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 758 | BASE + WEB WELDING | 757 | W,H |  | 18 |  | 1 | Set | 4 | No | 3.4 | hr | 13.6 | 1 | 14.6 | Hrs | 14.6 Hrs
| 759 | RIBS+WEB FIT UP | 758 | F,H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 760 | RIBS+WEB WELDING | 759 | W[2],H[2] |  | 18 |  | 1 | Set | 24.8 | No | 3.4 | hr | 84.32 | 1 | 85.32 | Hrs | 85.32 Hrs
761 | 761 | DAVIT PIPE FABRICATION | 756
| 762 | PIPE TRANSFERE |  | H[4] |  |  |  | 1 | SET | 1 | SET | 4 | Day | 4 |  | 4 | Days | 4 Days
| 763 | PIPE MARKING - 6 NOS | 762 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs | 3 Hrs
| 764 | SUPPORT PL MARKING | 763 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 765 | GUSSET PL MARKING | 764 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 766 | BASE HUB MARKING | 765 | F,H |  | 30 |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 767 | PIPE CUTTING - 6 NOS | 766 | C,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs | 3 Hrs
| 768 | SUPPORT PL CUTTING | 767 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 769 | PIPE GRINDING - 6 NOS | 768 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs | 3 Hrs
| 770 | SUPPORT PL GRINDING-10 NOS | 769 | G |  |  |  | 10 | Nos | 10 | Nos | 0.5 | Hr | 5 |  | 5 | Hrs | 5 Hrs
| 771 | PIVOT PL GRINDING | 770 | G |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 772 | PIPE FIT UP-2 NOS | 771 | F,H,W |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 773 | PIPE WELDING -2 NOS | 772 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 774 | PIVOT PL WELDING | 773 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 775 | SUPPORT PL WELDING -4 NOS | 774 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
776 | 776 | LIFTING LUG PAD | 761
| 777 | PLATE ISSUENCE | [5 empty] | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days | 4 Days
| 778 | LIFTING LUG PAD MARKING | 777 | F,H |  | 18 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 779 | LIFTING LUG PAD CUTTING | 778 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 780 | LIFTING LUGS PAD GRINDING | 779 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
781 | 781 | LIFTING LUG PREPARATION | 776
| 782 | LIFTING LUGS MARKING |  | F,H |  | 24 |  | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days | 4 Days
| 783 | LIFTING LUGS CUTTING | 782 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 784 | LIFTING LUGS GRINDING | 783 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 785 | LIFTING LUG DRILLING | 784 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs | 2 Hrs
786 | 786 | CHANNEL COVER HANDLE PREPATAION | 781
| 787 | CH COVER RING FORMING |  | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days | 4 Days
| 788 | SLIDING SLING FORMING | 787 | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days | 4 Days
789 | 789 | INSULATION RING PRPARATION | 786
| 790 | INSULAION RING MARKING |  | F,H |  | 12 |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 791 | INSULAION RING CUTTING | 790 | C,H |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 792 | INSULAION RING HOLE MARKING | 791 | F,H |  |  |  | 1 | Nos | 1 | Nos | 2 | Hr | 2 |  | 2 | Hrs | 2 Hrs
| 793 | INSULAION RING HOLE DRILLING | 792 | F,H |  |  |  | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs | 1 Hrs
794 | 794 | BAFFLE & TB ITEMS FAB
795 | 795 | BAFFLE PREPARATION | 794
| 796 | BAFFLE PLATE TRANSFER | 795 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs | 4 Hrs
| 797 | BAFFLE MARKING | 796 | F,H |  | 14 |  | 19 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
| 798 | BAFFLE PROFILE CUTTING | 797 | C,H |  |  |  | 19 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Hrs | 5 Hrs
799 | 799 | BAFFLE BEND REMOVAL & STACKING | 795
| 800 | BAFFLE PL BEND REMOVAL |  | F,H[2] |  |  |  | 19 | Nos | 19 | Nos | 1 | Hr | 19 |  | 19 | Hrs | 19 Hrs
| 801 | BAFFLE PL STACKING | 800 | F,H |  |  | 3 bundle | 3 | Nos | 3 | Nos | 2 | Hr | 6 |  | 6 | Hrs | 6 Hrs
802 | 802 | BAFFLE DRILLING | 799
| 803 | BAFFLE DRILLING |  | SC |  | 14 thk |  | 3 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 | Days | 10 Days
804 | 804 | BAFFLE DE STACKING & CHAMFERING | 802
| 805 | BAFFLE DE STACING |  | F,H |  |  |  | 3 | Bunch | 4 | Bunch | 6 | Hrs | 24 |  | 24 | Hrs | 24 Hrs
| 806 | BAFFLE CHAMFERING | 805 | F |  |  |  | 9 | Nos | 23544 | holes | 0.01 |  | 235.44 |  | 235.44 | Days | 235.44 Days
807 | 807 | BAFFLE STACKING & THRO HOLE CHECK | 804
| 808 | STACKING |  | F,H |  |  |  | 3 | Nos | 3 | Nos | 0.25 | Hr | 0.75 |  | 0.75 | Hrs | 0.75 Hrs
| 809 | BAFFLE HOLE ALINGMENT | 808 | F,H |  |  |  | 3 | Nos | 1 | SET | 1 | Hrs | 1 |  | 1 | Hrs | 1 Hrs
| 810 | BAFFLE HOLE RE DRILL | 809 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Days | 5 Days
| 811 | BAFFLE OD MACHINING | 810 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Days | 5 Days
| 812 | BAFFLE CLEANING | 811 | H[3] |  |  |  | 3 | Nos | 1 | SET | 1 | Day | 1 |  | 1 | Days | 1 Days
813 | 813 | SUPPORT PLATE MARKING | 807
| 814 | SUPPORT PLATE TRANSFER | [5 empty] | 2 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 815 | SUPPORT MARKING | 814 | SC |  | 20 |  | 2 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days | 1 Days
| 816 | SUPPORT PROFILE CUTTING | 815 | SC |  |  |  | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days | 5 Days
817 | 817 | SUPPORT PLATE BEND REMOVAL | 813
| 818 | SUPPORT PL BEND REMOVAL |  | F,H[3] |  |  |  | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 819 | SUPPORT PL STACKING | 818 | F,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs | 1 Hrs
820 | 820 | SUPPORT PLATE DRLINNG | 817
| 821 | SUPPORT DRILLING | 820 | SC |  | 20THK |  | 1 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 |  | 10
822 | 822 | SUP PLATE DE STACKING & CHAMFERING | 820
| 823 | SUPPORT DE STACING |  | F,H |  |  |  | 1 | Bunch | 1 | Bunch | 3 | Hrs | 3 |  | 3 | Hrs | 3 Hrs
| 824 | SUPPORT HOLE CHAMFERING | 823 | F |  |  |  | 2 | Plate | 2616 | holes | 0.01 |  | 26.16 |  | 26.16 |  | 26.16
825 | 825 | TIE ROD PREPARATION | 1276
| 826 | TIE ROD MATL TRANSFERE | [5 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days | 4 Days
| 827 | ROD CUTTING | 826 | F,H |  |  |  | 22 | Nos | 22 | noS | 0.25 | Hr | 5.5 |  | 5.5 | Hrs | 5.5 Hrs
| 828 | THREAD MACHINING. | 827 | L |  |  |  | 22 | Nos | 22 | Nos | 0.45 | Hr | 9.9 |  | 9.9 | Hrs | 9.9 Hrs
| 829 | JOINING | 828 | W,F,H |  |  |  | 22 | Nos | 22 | Nos | 0.5 | Hr | 11 |  | 11 | Hrs | 11 Hrs
830 | 830 | SPACER TUBE PREPARATION | 1275
| 831 | SPACER TUBE TRANSFERE | [5 empty] | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs | 4 Hrs
| 832 | LENGTH CUTTING 237NOS | 831 | F,H |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs | 41.4 Hrs
| 833 | LENNGTH MACHINING | 832 | L |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs | 41.4 Hrs
| 834 | CLEANINNG | 833 | H[3] |  |  |  | 414 | Nos | 414 | Nos | 0.016667 | Hr | 6.9 |  | 6.9 | Hrs | 6.9 Hrs
835 | 835 | SEALING STRIP PREPARATION | 1270
| 836 | SEALING STRIP MARKING |  | F,H |  | 8 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.1 | Hr | 1.9044 |  | 1.9 | Hrs | 1.9 Hrs
| 837 | SEALING STRIP CUTTING | 836 | C,H |  | 25 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.25 | Hr | 4.761 |  | 4.76 | Hrs | 4.76 Hrs
| 838 | SEALING STRIP BEND REMOVAL | 837 | F,H[2] |  | 25 | 9522 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 839 | SEALING STRIP GRINDING | 838 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs | 16 Hrs
| 840 | SEALING STRIP JOINING | 839 | W,F,H |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 841 | SEALING STRIP DRESS UP | 840 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
842 | 842 | SLIDING STRIP PREPARATION | 1271
| 843 | SLIDING STRIP MARKING |  | F,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.1 | Hr | 2.6732 |  | 2.67 | Hrs | 2.67 Hrs
| 844 | SLIDING STRIP CUTTING | 843 | C,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.25 | Hr | 6.683 |  | 6.68 | Hrs | 6.68 Hrs
| 845 | SLIDING STRIP BEND REMOVAL | 844 | F,H[2] |  | 8 | 13366 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 846 | SLIDING STRIP GRINDING | 845 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs | 16 Hrs
| 847 | SLIDING STRIP JOINING | 846 | W,F,H |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
| 848 | SLIDING STRIP DRESS UP | 847 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs | 4 Hrs
849 | 849 | SEAL ROD PREPARATION | 1272
| 850 | SEAL ROD ISSUENECE |  | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days | 4 Days
| 851 | SEAL ROD MARKING | 850 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.25 | Hr | 3.5 |  | 3.5 | Hrs | 3.5 Hrs
| 852 | SEAL ROD CUTTING | 851 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.5 | Hr | 7 |  | 7 | Hrs | 7 Hrs
| 853 | SEAL ROD BEND REMOVAL | 852 | F,H[2] |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 1 | Hr | 14 |  | 14 | Hrs | 14 Hrs
854 | 854 | SHELL FABRICATION
855 | 855 | SHELL MARKING & CUTTING | 1099
| 856 | SH PLATE TRNASFER |  | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days | 4 Days
| 857 | SH-MARKING | 856 | F,H[2] |  | 18 | 43000 mm | 1 | Nos | 43 | mtr | 0.1 | hr | 4.3 | 1 | 5.3 | Hrs | 5.3 Hrs
858 | 858 | SHELL PLATE CUTTING | 855
| 859 | SH-CUTTING | 858 | C,H[2] |  | 18 | 43000 mm | 3 | Nos | 129 | mtr | 0.25 | hr | 32.25 | 1 | 33.25 | Hrs | 33.25 Hrs
860 | 860 | SH PL SIDE GRINDING | 858
| 861 | SH PL SIDE BEVEL CUTTING | 860 | C,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 862 | SH PL SIDE BEVEL CUTTING | 861 | C,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 863 | SH PL SIDE BEVEL CUTTING | 862 | C,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.63 | Hrs | 1.63 Hrs
| 864 | SH PL SIDE BEVEL CUTTING | 863 | C,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 |  |  | Hrs
865 | 865 | SHELL PLATE EDGE PREPARATION | 860
| 866 | SH-BEVEL GRINDING |  | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 867 | SH-BEVEL GRINDING | 866 | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 868 | SH-BEVEL GRINDING | 867 | G,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 869 | SH-BEVEL GRINDING | 868 | G,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
870 | 870 | SHELL PRE BENDING | 865
| 871 | SH-PRE BEND |  | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 872 | SH-PRE BEND | 871 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 873 | SH-PRE BEND | 872 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 874 | SH-PRE BEND | 873 | F[2],H |  | 18 | 0 mm | 0 | Nos | 0 | No | 0 | hr | 0 |  |  | Hrs
875 | 875 | SHELL PL PRE BEND CUT OFF | 870
| 876 | SH-PRE BEND CUT OFF |  | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 877 | SH-PRE BEND CUT OFF | 876 | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 878 | SH-PRE BEND CUT OFF | 877 | F[2],H,C |  | 18 | 1250 mm | 1 | Nos | 1 | Nos | 0.3 | hr | 0.3 | 1 | 1.3 | Hrs | 1.3 Hrs
| 879 | SH-PRE BEND CUT OFF | 878 | F[2],H,C |  | 18 | 0 mm | 1 | Nos | 0 | Nos | 0.3 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
880 | 880 | SHELL PLATE LS EP | 875
| 881 | SH-PRE BEND LS EP |  | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 882 | SH-PRE BEND LS EP | 881 | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 883 | SH-PRE BEND LS EP | 882 | F,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 884 | SH-PRE BEND LS EP | 883 | F,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
885 | 885 | SHELL ROLLING | 880
| 886 | SH-ROLLING 1/4 |  | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 887 | SH-ROLLING | 886 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 888 | SH-ROLLING | 887 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 889 | SH-ROLLING | 888 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
890 | 890 | SHELL CIR LENGTH & EP CORRECTION | 885 | [10 empty] | 0
| 891 | SH-LS CORRECTION |  | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 892 | SH-LS CORRECTION | 891 | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 893 | SH-LS CORRECTION | 892 | F,H[2] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 894 | SH-LS CORRECTION | 893 | F,H[2] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
895 | 895 | SHELL LS SEAMS FIT UP | 890 | [10 empty] | 0
| 896 | SH-LS FIT UP |  |  |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 897 | SH-LS FIT UP | 896 | F[2],H,W |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 898 | SH-LS FIT UP | 897 | F[2],H,W |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 899 | SH-LS FIT UP | 898 | F[2],H,W |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
900 | 900 | SH LS WELDING ARRANGEMENT | 895
| 901 | SH-LS WELD ARRANGEMENT |  | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 902 | SH-LS WELD ARRANGEMENT | 901 | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 903 | SH-LS WELD ARRANGEMENT | 902 | F,H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 904 | SH-LS WELD ARRANGEMENT | 903 | F,H |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
905 | 905 | SHELL LONG SEAM OUTER WELDING | 900
| 906 | SH-LS WELDING- TOP SIDE |  | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs | 7.25 Hrs
| 907 | SH-LS WELDING- TOP SIDE | 906 | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs | 7.25 Hrs
| 908 | SH-LS WELDING- TOP SIDE | 907 | W,H |  | 12 | 1250 mm | 1 | Nos | 1.25 | mtr | 2.5 | hr | 3.125 | 1 | 4.13 | Hrs | 4.13 Hrs
| 909 | SH-LS WELDING- TOP SIDE | 908 | W,H |  | 12 | 0 mm | 1 | Nos | 0 | mtr | 2.5 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
910 | 910 | SH LS BACK CHIP | 905
| 911 | SH-LS WELDING- BACK CHIP |  | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 912 | SH-LS WELDING- BACK CHIP | 911 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs | 3.5 Hrs
| 913 | SH-LS WELDING- BACK CHIP | 912 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 914 | SH-LS WELDING- BACK CHIP | 913 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
915 | 915 | SH LS INNER WELDING | 910
| 916 | SH-LS INNER WELDING |  | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs | 3.25 Hrs
| 917 | SH-LS INNER WELDING | 916 | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs | 3.25 Hrs
| 918 | SH-LS INNER WELDING | 917 | W,H |  | 6 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.9 | hr | 1.125 | 1 | 2.13 | Hrs | 2.13 Hrs
| 919 | SH-LS INNER WELDING | 918 | W,H |  | 6 | 0 mm | 1 | Nos | 0 | mtr | 0.9 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
920 | 920 | SH INNER LS FLUSH GRINDING | 915
| 921 | SH INNER FLUSH GRINDING |  | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 922 | SH INNER FLUSH GRINDING | 921 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs | 2.25 Hrs
| 923 | SH INNER FLUSH GRINDING | 922 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.63 | Hrs | 1.63 Hrs
| 924 | SH INNER FLUSH GRINDING | 923 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
925 | 925 | SH LS RADIOGRAPHY | 920
| 926 | SH LS WELDING RT |  | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 927 | SH LS WELDING RT | 926 | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 928 | SH LS WELDING RT | 927 | RT |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
| 929 | SH LS WELDING RT | 928 | RT |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
930 | 930 | SHELL RE ROLLING | 925 | [10 empty] | 0
| 931 | SH RE ROLLING |  | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 932 | SH RE ROLLING | 931 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 933 | SH RE ROLLING | 932 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 934 | SH RE ROLLING | 933 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
935 | 935 | SH PLATE CS EP CORRECTION | 930
| 936 | SH CIR EP CORRECTION |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 937 | SH CIR EP CORRECTION | 936 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 938 | SH CIR EP CORRECTION | 937 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 939 | SH CIR EP CORRECTION | 938 | F,H |  | 18 | 0 mm id | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
940 | 940 | SH CIR SEAM FIRST FIT UP | 935
| 941 | SH CS FIT UP - [LS1+LS2] |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 942 | SH CS TACK DP CHECK - [LS1+LS2] | 941 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
943 | 943 | SH CIR SEAM FIRST WELDING | 940
| 944 | SH CS WELDING TRANSFERE |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 945 | SH CS WELDING OUTER [LS1+LS2] | 944 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 946 | SH CS WELDING BACK CHIP [LS1+LS2] | 945 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 947 | SH CS INNER WELDING [LS1+LS2] | 946 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 948 | SH CS FLUSH GRINDING [LS1+LS2] | 947 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
949 | 949 | SH CIR SEAM SECOND FITUP | 943
| 950 | SH CS FIT UP - [LS2+LS3] |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 951 | SH CS TACK DP CHECK - [LS2+LS3] | 950 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
952 | 952 | SH CIR SEAM SECOND WELDING | 949 | [10 empty] | 0
| 953 | SH CS WELDING TRANSFERE-[LS2+LS3] |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 954 | SH CS WELDING OUTER [LS2+LS3] | 953 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 955 | SH CS WELDING BACK CHIP [LS2+LS3] | 954 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 956 | SH CS INNER WELDING [LS2+LS3] | 955 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 957 | SH CS FLUSH GRINDING [LS2+LS3] | 956 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
958 | 958 | SH CIR SEAM III RD FITUP | 952
| 959 | SH CS FIT UP CS3 |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 960 | SH CS TACK DP CHECK CS3 | 959 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
961 | 961 | SH CIR SEAM THIRD WELDING | 958
| 962 | SH CS WELDING TRANSFERE CS3 |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 963 | SH CS WELDING OUTER CS3 | 962 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 964 | SH CS WELDING BACK CHIP CS3 | 963 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 965 | SH CS INNER WELDING CS3 | 964 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 966 | SH CS FLUSH GRINDING CS3 | 965 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
967 | 967 | SH FINAL LENGTH CORRECTION | 961
| 968 | SH LENGTH MARKING |  | F[2] |  | 18 | 1560 mm id | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 969 | LENGTH CUTTING | 968 | C,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
| 970 | GRINDING & EP | 969 | G,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
971 | 971 | SH CIR SEAM FLANGE 1 FITUP | 967
| 972 | SH CS FIT UP FLG CS1 |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 973 | SH CS TACK DP CHECK FLG CS1 | 972 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
974 | 974 | SH CIR SEAM FLANGE 1 WELDING | 971
| 975 | SH CS WELDING TRANSFERE | 974 | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 976 | SH CS WELDING OUTER FLG CS1 |  | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 977 | SH CS WELDING BACK CHIP FLG CS1 | 976 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 978 | SH CS INNER WELDING FLG CS1 | 977 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 979 | SH CS FLUSH GRINDING FLG CS1 | 978 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
980 | 980 | SH CS FIT UP FLG2 | 974
| 981 | SH CS FIT UP FLG 2 |  | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 982 | SH CS TACK DP CHECK FLG2 | 981 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
983 | 983 | SH CS WELDING FLG2 | 980
| 984 | SH CS WELDING TRANSFERE FLG2 |  | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 985 | SH CS WELDING OUTER FLG2 | 984 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 986 | SH CS WELDING BACK CHIP FLG2 | 985 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 987 | SH CS INNER WELDING FLG2 | 986 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 988 | SH CS FLUSH GRINDING FLG2 | 987 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
989 | 989 | NOZZLE ORIENTATION MARKING | 983
| 990 | SH-NOZ ORIENTAION MARKING |  | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 991 | SH-NOZ MARKING-N2A1 | 990 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 992 | SH-NOZ MARKING-N2A1 | 991 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
993 | 993 | SH NOZZLE OPENNING | 989
| 994 | 26"NB SRN - 1 |  | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.31 | Hrs | 1.31 Hrs
| 995 | 26"NB SRN - 1 | 994 | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.31 | Hrs | 1.31 Hrs
996 | 996 | INSPECTION | 993 | C,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
997 | 997 | SH NOZZLE EP | 996
| 998 | 26"NB SRN - 1 |  | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.05 | Hrs | 4.05 Hrs
| 999 | 26"NB SRN - 1 | 998 | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.05 | Hrs | 4.05 Hrs
| 1000 | INSPECTION | 999 |  |  |  |  | 1 | No | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
1001 | 1001 | SH NOZZZLE FIT UP | 997
| 1002 | 26"NB SRN - 1 |  | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1003 | 26"NB SRN - 1 | 1002 | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1004 | DP CHECK | 1003 |  |  |  |  | 2 | No | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
1005 | 1005 | SH NOZZLE FIT UP INSPECTION | 1001
| 1006 | 26"NB SRN - 1 |  | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1007 | 26"NB SRN - 1 | 1006 | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1008 | DP CHECK | 1007 | F,H |  |  | 650nb | 2 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
1009 | 1009 | SH NOZZLE WELDING | 1005
| 1010 | SH NOZ WELDING ARRANGEMENT |  | T |  |  |  | 1 | No | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs | 1 Hrs
| 1011 | SH-NOZ WELDING -N1A | 1010 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs | 8.64 Hrs
| 1012 | SH-NOZ WELDING-N2A1 | 1011 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs | 8.64 Hrs
| 1013 | SH-NOZ WELDING-N2A2 | 1012 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.64 | Hrs | 8.64 Hrs
| 1014 | SH NOZ ROOT DP CHECK | 1013 | F,H |  | 12 | 972 mm lip od | 2 | No | 6.108 | Mtr | 1 | hr | 6.108 | 1 | 7.11 | Hrs | 7.11 Hrs
| 1015 | SH-NOZ INNER WELD -N1A | 1014 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.15 | Hrs | 5.15 Hrs
| 1016 | SH-NOZ INNER WELD-N2A1 | 1015 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.15 | Hrs | 5.15 Hrs
| 1017 | SH-NOZ INNER WELD-N2A2 | 1016 | H,W |  | 8 | 972 mm lip od | 0 | No | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs | 1 Hrs
1018 | 1018 | SH SADDLE WELDING | 1009
| 1019 | SH-SADDLE PAD FIT UP |  | F[2],W,H |  | 25 | 1596 mm od | 2 | No | 20.0585 | Nos | 0.5 | Hr | 10.0293 | 1 | 11.03 | Hrs | 11.03 Hrs
| 1020 | SH-SADDLE PAD WELDING | 1019 | W[2],H[2] |  | 12 | 1596 mm od | 2 | Mtr | 20.0585 | Mtr | 1.6 | Hr | 32.0936 | 1 | 33.09 | Hrs | 33.09 Hrs
| 1021 | SH-SADDLE MATCHING | 1020 | F[2],G[2] |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 8 | Hr | 16 | 1 | 17 | Hrs | 17 Hrs
| 1022 | SH-SADDLE FIT UP | 1021 | W,F[2],H |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 6 | Hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 1023 | SH-SADDLE WELDING | 1022 | W[2],H[2] |  | 12 | 11400 rmt | 1 | Nos | 16.0348 | Mtr | 1.6 | Hr | 25.6557 | 1 | 26.66 | Hrs | 26.66 Hrs
| 1024 | SH-SADDLE dress up | 1023 | G[2] |  |  |  | 1 | No | 1 | Nos | 8 | Hr | 8 | 1 | 9 | Hrs | 9 Hrs
1025 | 1025 | SH DAVIT ARM WELDING | 1018
| 1026 | SH-DAVIT ARM arm match |  | F,G |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1027 | SH-DAVIT ARM FIT UP | 1026 | F,H,W |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1028 | SH-DAVIT ARM WELDING | 1027 | W,H |  | 12 |  | 6 | mtr | 5.16 | Mtr | 1.6 | Hr | 8.256 | 1 | 9.26 | Hrs | 9.26 Hrs
1029 | 1029 | SH NDE CLEARENCE | 1025
| 1030 | SH-SH NDE CLEARENCE |  | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 12 | Hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 1031 | TPI INSPECTION | 1030 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 1 | Day | 1 |  | 1 | Days | 1 Days
1032 | 1032 | CHANNEL FABRICATION
1033 | 1033 | CHANNEL SHELL LS WELDING | 1101
| 1034 | CH PLATE TRNASFER |  | T |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Days | 4 Days
| 1035 | CH-MARKING | 1034 | F,H[2] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.1 | hr | 0.0831 | 1 | 1.08 | Hrs | 1.08 Hrs
| 1036 | CH-CUTTING | 1035 | C,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.25 | hr | 0.20775 | 1 | 1.21 | Hrs | 1.21 Hrs
| 1037 | CH PL SIDE GRINDING | 1036 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.15 | hr | 0.12465 | 1 | 1.12 | Hrs | 1.12 Hrs
| 1038 | CH-BEVELLING CIR SIDE | 1037 | F,H[3] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.42 | Hrs | 1.42 Hrs
| 1039 | CH EP GRINDING | 1038 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs | 1.83 Hrs
1040 | 1040 | CHANNEL SH ROLLING | 1033
| 1041 | CH-PRE BEND |  | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 1042 | CH-PRE BEND CUT OFF | 1041 | F[2],C |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 0.3 | hr | 0.4986 | 1 | 1.5 | Hrs | 1.5 Hrs
| 1043 | CH LS BEVELING | 1042 | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.66 | Hrs | 2.66 Hrs
| 1044 | CH-ROLLING | 1043 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
1045 | 1045 | CH SHELL LS FIT UP | 1040
| 1046 | CH-LS CORRECTION |  | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.66 | Hrs | 2.66 Hrs
| 1047 | CH-LS FIT UP | 1046 | F[2],W,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs | 1.83 Hrs
1048 | 1048 | CH SHELL LS WELDING | 1045
| 1049 | CH-LS WELD ARRANGEMENT |  | F,H[2] |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1050 | CH-LS WELDING- TOP SIDE | 1049 | W,H |  | 12 | 831 mm | 1 | Nos | 0.831 | mtr | 2.5 | hr | 2.0775 | 1 | 3.08 | Hrs | 3.08 Hrs
| 1051 | CH-LS WELDING- BACK CHIP | 1050 | G,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.83 | Hrs | 1.83 Hrs
| 1052 | CH-LS INNER WELDING | 1051 | W,H |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.9 | hr | 0.7479 | 1 | 1.75 | Hrs | 1.75 Hrs
| 1053 | CH-LS INNNER FLUSH GRIND | 1052 | G |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.42 | Hrs | 1.42 Hrs
| 1054 | CH RE ROLLING | 1053 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
1055 | 1055 | CH LS WELDING RADIOGRAPHY | 1048
| 1056 | CH LS WELDING RT |  | RT |  | 18 | 831 mm | 1 | No | 1 | No | 1 | dya | 1 |  | 1 | Days | 1 Days
1057 | 1057 | CH CS FLG 1 FIT UP | 1055
| 1058 | CH CIR EP CORRECTION |  | F[2] |  | 18 | 1560 mm id | 1 | Nos | 9.803 | mtr | 0.45 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 1059 | CH CS FIT UP FLG1 | 1058 | F[2],W,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 1060 | CH CS TACK DP CHECK FLG1 | 1059 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
1061 | 1061 | CH CS FLG 1 WELDING | 1057
| 1062 | CH CS WELDING TRANSFERE |  | F,H[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1063 | CH CS WELDING OUTER FLG1 | 1062 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 1064 | CH CS WELDING BACK CHIP FLG1 | 1063 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 1065 | CH CS INNER WELDING FLG 1 | 1064 | W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1.36 | hr | 6.6661 | 1 | 7.67 | Hrs | 7.67 Hrs
| 1066 | CH CS FLUSH GRINDING FLG1 | 1065 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
1067 | 1067 | CH CS FLG 2 FIT UP | 1061
| 1068 | CH LENGTH CUTTING |  | C,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
| 1069 | CH CIR EP CORRECTION | 1068 | F,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 1070 | CH CS FIT UP FLG2 | 1069 | F[2],W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 4 | hr | 19.6061 | 1 | 20.61 | Hrs | 20.61 Hrs
| 1071 | CH CS TACK DP CHECK FLG1 | 1070 | F |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
1072 | 1072 | CH CS FLG 2 WELDING | 1067
| 1073 | CH CS WELDING TRANSFERE FLG2 |  | F,H[2] |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1074 | CH CS WELDING OUTER FLG2 | 1073 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.25 | Hrs | 13.25 Hrs
| 1075 | CH CS WELDING BACK CHIP FLG2 | 1074 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9 | Hrs | 5.9 Hrs
| 1076 | CH CS INNER WELDING FLG2 | 1075 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.41 | Hrs | 5.41 Hrs
| 1077 | CH CS FLUSH GRINDING FLG2 | 1076 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.45 | Hrs | 3.45 Hrs
1078 | 1078 | CH CS FLG 1 & 2 WELDING rt | 1072
| 1079 | CH CS WELDING RT |  | RT |  | 18 | 1560 mm id | 1 | No | 1 | n | 1 | Day | 1 |  | 1 | Days | 1 Days
1080 | 1080 | CHANNEL NOZ MARKING | 1078
| 1081 | CH- NOZ IREIENTATION NKG |  | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1082 | CH-NOZ MARKING- 16"NB - 2 NOS | 1081 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
1083 | 1083 | CH NOZ OPNNING | 1080
| 1084 | CH-NOZ OPENNING-TOP |  | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1085 | CH-NOZ OPENNING-Bot | 1084 | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
1086 | 1086 | CH NOZ OPEN EP | 1083
| 1087 | CH-NOZ EP -N3A |  | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1088 | CH-NOZ EP-N4A | 1087 | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
1089 | 1089 | CH NOZ FIT UP | 1086
| 1090 | CH-NOZ FIT UP -N3A |  | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1091 | CH-NOZ FIT UP -N4A | 1090 | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
1092 | 1092 | INTER CONNECTION NOZZLE WELDING | 1089 | [10 empty] | 0 |  |  | Hrs
| 1093 | BOT SH , CH AND TOP SH ,CH STACKING |  | F[2],H,W |  |  |  | 1 | No | 1 | Mtr | 16 | hr | 16 | 1 | 17 | Hrs | 17 Hrs
| 1094 | INTER CON NOZ FIT UP - ON SH |  | F[2],H,W |  | 650nb | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1095 | INTER CON NOZ FIT UP- ON CH |  | F[2],H,W |  | 400nb | 400NB | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1096 | INTER CON NOZ WELDING - ON SH |  | W,H |  | 18 | 972 mm dia | 1 | No | 3.054 | Mtr | 4.9 | hr | 14.9647 | 1 | 15.96 | Hrs | 15.96 Hrs
| 1097 | INTER CON NOZ WELDING- ON CH |  | W,H |  | 18 | 407 mm dia | 1 | No | 1.2788 | Mtr | 4.9 | hr | 6.2661 | 1 | 7.27 | Hrs | 7.27 Hrs
| 1098 | DISMANTLING |  | F[2],H,W |  |  |  | 1 | No | 1 | No | 12 | hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 1099 | INTER CON NOZ FLUSH GRIND & DP-ON SH |  | G,H |  | 18 | 972 mm dia | 1 | No | 3.054 | Mtr | 0.5 | hr | 1.527 | 1 | 2.53 | Hrs | 2.53 Hrs
| 1100 | INTER CON NOZ FLUSH GRIND & DP-ON CH |  | G,H |  | 18 | 407 mm dia | 1 | No | 1.2788 | Mtr | 0.5 | hr | 0.6394 | 1 | 1.64 | Hrs | 1.64 Hrs
| 1101 | IN CON NOZ RT |  | RT |  | 18 | 972 mm dia | 1 | No | 3.054 | No | 1 | Day | 3.054 |  | 3.05 | Hrs | 3.05 Hrs
1092 | 1092 | CH NOZ FIT UP INSP | 1092
| 1093 | CH-NOZ INSPN -N3A |  | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1094 | CH-NOZ INSPN-N4A | 1093 | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
1095 | 1095 | CH NOZ WELDING | 1092
| 1096 | CH NOZ WELDING ARRANGEMENT |  | F,H[2] |  |  | 400nb | 2 | Nos | 1 | No | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
| 1097 | CH-NOZ WELDING -N3A | 1096 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs | 5.11 Hrs
| 1098 | CH-NOZ WELDING-N4A | 1097 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.11 | Hrs | 5.11 Hrs
| 1099 | CH NOZ ROOT DP CHECK | 1098 | W,H |  | 14 | 407 mm | 2 | No | 2 | Nos | 1 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
| 1100 | CH-NOZ INNER WELD -N3A | 1099 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs | 2.15 Hrs
| 1101 | CH-NOZ INNER WELD-N4A | 1100 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.15 | Hrs | 2.15 Hrs
| 1102 | RF PAD FIT UP & Nozzle fit up | 1101 | W,H |  |  | 400nb | 2 | No | 2 | Set | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1103 | RF PAD FIT UP WELDING | 1102 | G,H |  | 18 |  | 2 | No | 2.5538 | Mtr | 6.8 | hr | 17.366 | 1 | 18.37 | Hrs | 18.37 Hrs
| 1104 | NOZ WELDING FLUSH GRIND- 16"NB | 1103 | G |  |  | 407 mm | 2 | NoS | 2.5538 | No | 0.15 | hr | 0.38307 | 1 | 1.38 | Hrs | 1.38 Hrs
1105 | 1105 | CHANNEL PP PLATE FIT UP | 1095
| 1106 | CH- PP PLATE FIT UP |  | F[2],H,W |  | 24 | 14465 | 1 | No | 14.465 | Nos | 0.5 | hr | 7.2325 | 1 | 8.23 | Hrs | 8.23 Hrs
| 1107 | CH- PP PLATE FIT UP INSP | 1106 | F,H |  | 24 | 1560 id | 3 | No | 4 | Nos | 0.5 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
1108 | 1108 | CH PP PLATE WELDING | 1105
| 1109 | CH- PP PLATE WELDING |  | W,H |  | 24 | 1480 | 3 | No | 4.44 |  | 11.2 | hr | 49.728 | 1 | 50.73 | Hrs | 50.73 Hrs
| 1110 | CH- PP PLATE FACE GRINDING | 1109 | G,H |  | 12 | 12310 mm | 1 | No | 12.31 | No | 1.6 | hr | 19.696 | 1 | 20.7 | Hrs | 20.7 Hrs
1111 | 1111 | CHANNEL DAVIT ARM WELDING | 1108
| 1112 | CH-DAVIT ARM arm match |  | F,H |  | 18 | 1480 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1113 | CH-DAVIT ARM FIT UP | 1112 | F,W,H |  | 18 | 1251 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1114 | CH-DAVIT ARM WELDING | 1113 | W,H |  | 12 | 6 | 1 | No | 6 | mtr | 1.6 | hr | 9.6 | 1 | 10.6 | Hrs | 10.6 Hrs
1115 | 1115 | CHANNEL NDE & PWHT | 1111
| 1116 | CH ALL WELDING DRESSUP & DP CHECK |  | G[2] |  | 18 | 1480lg | 1 | No | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 1117 | CH-CH NDE CLEARENCE | 1116 | F |  | 18 | 1480lg | 1 | No | 1 | No | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
1118 | 1118 | BARREL FABRICATION | 1115
1119 | 1119 | BARREL SH PLATE CUTTING & EP | 7 |  |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Hrs | 4 Hrs
| 1120 | BARREL PLATE TRNASFER |  | T |  | 18 | 373 mm | 1 | Nos | 0.373 | mtr | 0.1 | Hr/mtr | 0.0373 | 1 | 1.04 | Hrs | 1.04 Hrs
| 1121 | BARREL-MARKING | 1120 | F,H[2] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.25 | Hr/mtr | 2.825 | 1 | 3.83 | Hrs | 3.83 Hrs
| 1122 | BARREL-CUTTING | 1121 | C,H |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.15 | Hr/mtr | 1.695 | 1 | 2.7 | Hrs | 2.7 Hrs
| 1123 | BARREL PL SIDE GRINDING | 1122 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.5 | Hr/mtr | 5.65 | 1 | 6.65 | Hrs | 6.65 Hrs
| 1124 | BARREL-BEVELLING CIR SIDE | 1123 | F,H[3] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs | 12.3 Hrs
| 1125 | CH EP GRINDING | 1124 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hrs | 12.3 Hrs
1126 | 1126 | BAR SHELL ROLLING | 1119
| 1127 | BARREL-PRE BEND |  | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 1128 | BARREL-PRE BEND CUT OFF | 1127 | F[2],C |  | 18 | 1664 mm id | 1 | Nos | 3.328 | No | 0.3 | hr | 0.9984 | 1 | 2 | Hrs | 2 Hrs
| 1129 | BARREL -PRE LS EP | 1128 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs | 4.33 Hrs
| 1130 | BARREL-ROLLING | 1129 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
1131 | 1131 | BARREL SHELL LS FIT UP | 1126
| 1132 | BARREL-LS CORRECTION |  | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.33 | Hrs | 4.33 Hrs
| 1133 | BARREL-LS FIT UP | 1132 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs | 2.66 Hrs
1134 | 1134 | BARREL SHELL LS WELDING | 1131
| 1135 | BARREL-LS WELD ARRANGEMENT |  | F,H[2] |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1136 | BARREL-LS WELDING- TOP SIDE | 1135 | W,H |  | 12 | 1664 mm id | 1 | Nos | 1.664 | mtr | 2.5 | hr | 4.16 | 1 | 5.16 | Hrs | 5.16 Hrs
| 1137 | BARREL-LS WELDING- BACK CHIP | 1136 | G,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.66 | Hrs | 2.66 Hrs
| 1138 | BARREL-LS INNER WELDING | 1137 | W,H |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.9 | hr | 1.4976 | 1 | 2.5 | Hrs | 2.5 Hrs
| 1139 | BARREL-LS INNNER FLUSH GRIND | 1138 | G |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.5 | hr | 0.832 | 1 | 1.83 | Hrs | 1.83 Hrs
| 1140 | BARREL RE ROLLING | 1139 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
1141 | 1141 | BARREL LS WELDING RT | 1134
| 1142 | BAR LS WELDING RT |  | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
1143 | 1143 | BARREL SHELL CS FLG 1 FIT UP | 1141
| 1144 | BARREL CIR EP CORRECTION |  | F[2] |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 1145 | BARREL CS FIT UP FLG1 | 1144 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 1146 | BARREL CS TACK DP CHECK FLG1 | 1145 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | no | 0.25 | hr | 1.3071 | 1 | 2.31 | Hrs | 2.31 Hrs
1147 | 1147 | BARREL SH CS FLG 1 WELDING | 1143
| 1148 | BARREL CS WELDING TRANSFERE |  | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1149 | BARREL CS WELDING OUTER FLG1 | 1148 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs | 14.07 Hrs
| 1150 | BARREL CS WELDING BACK CHIP FLG1 | 1149 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 1151 | BARREL CS INNER WELDING FLG 1 | 1150 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs | 5.71 Hrs
| 1152 | BARREL CS FLUSH GRINDING FLG1 | 1151 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs | 3.61 Hrs
1153 | 1153 | BARREL CS FIT UP WITH DISH | 1147 | [10 empty] | 0
| 1154 | BARREL LENGTH CUTTING |  | C,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 1155 | BARREL EP | 1154 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 1156 | BARREL CS FIT UP DISH | 1155 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 4 | hr | 20.9132 | 1 | 21.91 | Hrs | 21.91 Hrs
| 1157 | BARREL CS TACK DP CHECK DISH | 1156 | F |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 3.5 | hr | 18.299 | 1 | 19.3 | Hrs | 19.3 Hrs
1158 | 1158 | BARREL CS WELDING WITH DISH | 1153
| 1159 | BARREL CS WELDING TRANSFERE DISH |  | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1160 | BARREL CS WELDING OUTER DISH | 1159 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.07 | Hrs | 14.07 Hrs
| 1161 | BARREL CS WELDING BACK CHIP DISH | 1160 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.23 | Hrs | 6.23 Hrs
| 1162 | BARREL CS INNER WELDING DISH | 1161 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.71 | Hrs | 5.71 Hrs
| 1163 | BARREL CS FLUSH GRINDING DISH | 1162 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.61 | Hrs | 3.61 Hrs
1164 | 1164 | BARREL CS FLG 1 & DISH WELDING rt | 1158
| 1165 | BARREL CS WELDING RT |  | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
1166 | 1166 | BARREL NOZ OREINATION MARKING | 1164
| 1167 | BARREL- NOZ IREIENTATION NKG |  | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 1168 | BARREL-NOZ MARKING- 2 | 1167 | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
1169 | 1169 | BARREL NOZZLE OPPENING | 1166
| 1170 | BARREL-NOZ OPENNING-40 NB - LWN |  | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
| 1171 | BARREL-NOZ OPENNING-40 NB - LWN | 1170 | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs | 4 Hrs
1172 | 1172 | BARREL NOZ EDGE PREPARATION | 1169
| 1173 | BARREL-NOZ OPENNING-40 NB - LWN |  | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
| 1174 | BARREL-NOZ OPENNING-40 NB - LWN | 1173 | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs | 3 Hrs
1175 | 1175 | BARREL NOZZZLE FIT UP | 1172
| 1176 | BARREL-NOZ FIT UP -N5A |  | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
| 1177 | BARREL-NOZ FIT UP -N6A | 1176 | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs | #N/A
1178 | 1178 | BARREL NOZ FIT UP INSPECTION | 1175
| 1179 | BARREL-NOZ INSPN -5A |  | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
| 1180 | BARREL-NOZ INSPN-6A | 1179 | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
1181 | 1181 | BARREL NOZZLE WELDING | 1178
| 1182 | BARREL NOZ WELDING ARRANGEMENT |  | T |  | 40NB | 40NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs | 1.5 Hrs
| 1183 | BARREL-NOZ WELDING -N5A | 1182 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
| 1184 | BARREL-NOZ WELDING-N6A | 1183 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
| 1185 | BARREL NOZ ROOT DP | 1184 | F,H |  |  | 75 MM | 2 | No | 2 |  | 0.5 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1186 | BARREL-NOZ INNER WELDING -N5A | 1185 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
| 1187 | BARREL-NOZ INNER WELDING-N6A | 1186 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.44 | Hrs | 1.44 Hrs
1188 | 1188 | BARREL NOZ INNER WELD FLUSH GRIND | 1181
| 1189 | BARREL ALL WELDING DRESSUP & DP |  | G[2] |  | 20 | 40NB | 1 | No | 1 | NO | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 1190 | BARREL-BARREL NDE CLEARENCE | 1189 | F |  | STD | 40NB | 1 | NoS | 1 | No | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
1191 | 1191 | FL HEAD FABRICATION
1192 | 1192 | FLAOTING HEAD DISH FORMING | 13
| 1193 | FL HEAD DISH PL ISSUE |  | T |  |  |  | 1 | No | 1 |  | 4 | Day | 4 |  | 4 | Days | 4 Days
| 1194 | FL HEAD PL MARKING | 1193 | F,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.1 | hr | 0.62337 | 1 | 1.62 | Hrs | 1.62 Hrs
| 1195 | FL HEAD PL STAMPING | 1194 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Hr | 1 | 1 | 2 | Hrs | 2 Hrs
| 1196 | FL HEAD PL CUTTING | 1195 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.25 | hr | 1.5584 | 1 | 2.56 | Hrs | 2.56 Hrs
| 1197 | FL HEAD PL GRINDING | 1196 | G |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 1 | hr | 6.2337 | 1 | 7.23 | Hrs | 7.23 Hrs
1198 | 1198 | FL HEAD FORMIG | 1192
| 1199 | FL HEAD FORMING | 1198 | SC |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 10 | Day | 10 |  | 10 | Days | 10 Days
| 1200 | FL HEAD PROFILE CHECK | 1199 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Days | 1 Days
1201 | 1201 | FL HEAD CUTTING | 1198
| 1202 | FL HEAD MARKING | 1201 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 4 | Hr/No | 4 |  | 4 | Hrs | 4 Hrs
| 1203 | FL HEAD CUTTING | 1202 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 0.1 | hr | 0.62337 | 2 | 2.62 | Hrs | 2.62 Hrs
1204 | 1204 | FL HEAD EP | 1201
| 1205 | FL HEAD GRINDING | 1204 | G,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs | 8.23 Hrs
1206 | 1206 | FL HEAD FIT UP
| 1207 | FL HEAD FIT UP | 1206 | F[2],W,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.23 | Hrs | 8.23 Hrs
1208 | 1208 | FL HEAD WELDING | 1206
| 1209 | FL HEAD WELDING |  | W,H |  | 30 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 16.8 | hr | 104.7266 | 2 | 106.73 | Hrs | 106.73 Hrs
| 1210 | FL HEAD PP PLATE FIT UP | 1209 | F[2],H,W |  | 16 | 1550 mm id | 1 | Nos | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1211 | FL HEAD PP PL WELDING | 1210 | W,H |  | 16 | 3000 mm | 1 | Nos | 3 | Mtr | 2.8 | hr | 8.4 | 2 | 10.4 | Hrs | 10.4 Hrs
| 1212 | FL HEAD PP PL LEVEL GRINDING | 1211 | F,H |  | 16 | 3000 mm | 1 | Nos | 1 | No | 6 | hr | 6 | 1 | 7 | Hrs | 7 Hrs
| 1213 | FL HEAD INSPECTION | 1212 | F |  | 16 | 3000 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs | 2 Hrs
1214 | 1214 | FL HEAD SR & MACHINING | 1208
| 1215 | FL HEAD SR |  | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 3 | Day | 3 | 0 | 3 | Hrs | 3 Hrs
| 1216 | FL HEAD FINAL MACHINING | 1215 | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs | 4 Hrs
| 1217 | FL HEAD HOLE MARKING | 1216 | F,H |  |  | 1550 mm id | 1 | Nos | 1 | No | 0.5 | Day | 0.5 | 0 | 0.5 | Hrs | 0.5 Hrs
| 1218 | FL HEAD HOLE DRILLING | 1217 | SC |  | 140 mm | 1550 mm id | 72 | hole | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs | 4 Hrs
| 1219 | FL HEAD FINAL INSPECTION | 1218 | F,H |  | 140 mm | 1550 mm id | 1 | No | 1 | No | 1 | Day | 1 | 0 | 1 | Hrs | 1 Hrs
1220 | 1220 | TUBE BUNDLE FABRICATION
1221 | 1221 | TUBE BUNDLE ASSY
| 1222 | FRAME SET UP & TUBE SHT SET UP |  | F[2],W |  | 145T | 1308 tube |  |  | 1 |  | 1.5 | Day | 1.5 | 0 | 1.5 | Hrs | 1.5 Hrs
| 1223 | SKELITON ASSY- 19 baffle | 1222 | F[2],H[3] |  |  | 19 baffle | 1 | Nos | 19 | Nos | 0.5 | hr | 9.5 | 1 | 10.5 | Hrs | 10.5 Hrs
1224 | 1224 | TUBE INSERT | 1221
| 1225 | TUBE INSERT |  | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs | 55.5 Hrs
| 1226 | SEAL ROD INSERT & WELD | 1225 | F[2],W,H[2] |  | 25.4 dia | 5134 lg | 14 | Nos | 14 | Nos | 0.5 | Hr/no | 7 | 1 | 8 | Hrs | 8 Hrs
| 1227 | TUBE INSERT | 1226 | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs | 55.5 Hrs
1228 | 1228 | SLIDING STRIP FIT UP WELDING | 1224
| 1229 | SEALING STRIP FIT UP |  | F,H |  | 8 | 4592 mm lg | 2 | Nos | 2 | Nos | 3 | Hr/no | 6 | 1 | 7 | Hrs | 7 Hrs
| 1230 | SLIDING STRIP WELDING | 1229 | W,H |  | 8 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs | 16 Hrs
| 1231 | SEAL/SLID TRIP WELD GRIND | 1230 | G |  | 1500 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs | 16 Hrs
1232 | 1232 | TUBE BUNDLE INSERT | 1228
| 1233 | TUBE BUNDLE INSERT IN SHELL |  | F[3],H[8] |  |  | 7000 LG | 1 | Nos | 1 | Nos | 16 | Hr/no | 16 | 1 | 17 | Hrs | 17 Hrs
| 1234 | FL HEAD TUBE SHT FIXING | 1233 | F[2],H[4] |  | 145MM |  | 1 | Nos | 1 | Nos | 4 | Hr/no | 4 | 1 | 5 | Hrs | 5 Hrs
| 1235 | TEST FLG & GLAND ASSY | 1234 | F[3],H[6] |  | 165 MM | 1490 | 1 | Nos | 56 | Bolts | 0.16667 | hr | 9.3333 | 1 | 10.33 | Hrs | 10.33 Hrs
1236 | 1236 | TUBE EXPANSION IN GROOVES | 1232
| 1237 | TUBE EXP - ST SIDE - 1 STAGE |  | F,H[2] |  | 150 mm | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.016667 | hr | 21.8 | 1 | 22.8 | Hrs | 22.8 Hrs
| 1238 | TUBE EXP - FL SIDE - 1 STAGE | 1237 | F,H[2] |  | Servo | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.0083333 | hr | 10.9 | 1 | 11.9 | Hrs | 11.9 Hrs
| 1239 | TUBE TRIMMING FL SIDE | 1238 | F,H |  | Servo | 1308 nos | 1308 | Nos | 1308 | Trimm | 0.033333 | hr | 43.6 | 1 | 44.6 | Hrs | 44.6 Hrs
| 1240 | TUBE EXP BOTH SIDE - 4 STAGE | 1239 | F[2],H[2] |  | 150MM | 2616 Roll | 2616 | Nos | 2616 | Rolling | 0.0083333 | hr | 21.8 | 1 | 22.8 | Hrs | 22.8 Hrs
1241 | 1241 | TUBE EXP- PNUEMATIC TEST | 1236
| 1242 | TUBE EXP PNUEMATIC TEST |  | F[2],H[2] |  |  |  | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs | 5 Hrs
| 1243 | PNUEMATIC TEST TPI WITNESS | 1242 | F,H |  |  |  | 1 | No | 1 | Test | 1 | Day | 1 |  | 1 | Hrs | 1 Hrs
| 1244 | CLEANING | 1243 | F,H[3] |  |  |  | 1 | No | 1 | No | 1 | Hr | 1 |  | 1 | Hrs | 1 Hrs
1245 | 1245 | TUBE TUBE SHEET WELDING- FT SIDE | 1241
| 1246 | TUBE WELDING - ST SIDE ROOT |  | TW,H |  | 2.77 | 25.4 od | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 1247 | TUBE WELDING - ST SIDE ROOT DP | 1246 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 1248 | TUBE WELDING - ST SIDE FINAL WELD | 1247 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 1249 | TUBE WELDING - ST SIDE FINAL DP | 1248 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
1250 | 1250 | TUBE TO TUBE SHEET WELDING - FL HEAD SIDE | 1245
| 1251 | TUBE WELDING - FLH SIDE ROOT |  | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 1252 | TUBE WELDING - FLH SIDE ROOT DP | 1251 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
| 1253 | TUBE WELDING - FLH SIDE FINAL WELD | 1252 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs | 110 Hrs
| 1254 | TUBE WELDING - FLH SIDE FINAL DP | 1253 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs | 9 Hrs
1255 | 1255 | SHELL SIDE HYDRO | 1250
1256 | 1256 | SHELL SIDE WATER FILLING
| 1257 | SHELL SIDE HYDRO | 1256 | F[2],H[2] |  |  | 6130 lg | 1 | No | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 1258 | SHELL SIDE TPI WITNESS | 1257 | F[2] |  |  | 6130 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Hrs | 1 Hrs
| 1259 | DE WATERING & DISMANTLE OF GLAND | 1258 | F[2],H[4] |  |  | 6130 lg | 1 | No | 1 | Test | 4 | hr | 4 | 0 | 4 | Hrs | 4 Hrs
1260 | 1260 | CHANNEL SIDE HYDRO - STACKED
| 1261 | HE 1 & 2 STACKING |  | F,H[2] |  |  |  | 1 | Set | 1 |  | 16 | hr | 16 | 1 | 17 | Hrs | 17 Hrs
| 1262 | CH & INT CON NOZ TIGHT | 1261 | F[2],H[2] |  |  | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs | 13 Hrs
| 1263 | WATER FILL | 1262 | F[2] |  |  | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days | 1 Days
| 1264 | CH SIDE HYDRO | 1263 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs | 12 Hrs
| 1265 | CH SIDE HYDRO TPI WITNESS | 1264 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days | 1 Days
| 1266 | DE WATERING | 1265 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs | 6 Hrs
1267 | 1267 | SHELL SIDE HYDRO - STACKED | 1260
| 1268 | BARREL ASSY |  | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 16 | hr | 16 | 0 | 16 | Hrs | 16 Hrs
| 1269 | WATER FILL | 1268 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs | 6 Hrs
| 1270 | SHELL SIDE HYDRO - STACKED | 1269 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs | 12 Hrs
| 1271 | SHELL SIDE HYDRO- STACKED TPI WITNESS | 1270 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days | 1 Days
| 1272 | DE WATERING | 1271 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs | 6 Hrs
1273 | 1273 | NITORGEN PURGING | 1267
| 1274 | N2 GAS PURGING |  | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs | 12 Hrs
1275 | 1275 | PAINTING | 1273
| 1276 | PRIMER PAINTING |  | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days | 1 Days
| 1277 | INTERMEDIATE PAINTING | 1276 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days | 1 Days
| 1278 | TOP COAT PAINTING | 1277 | F[2],H[4] |  |  | 9178 lg | 1 | Set | 1 | Test | 1 | Day | 1 | 0 | 1 | Days | 1 Days

## PLAN IN EXCEL (hidden)
1 | 1 | 133-EE-1006-A |  |  | status | THK | WORK DIMENSION | QTY | UOM | work volume | UOM | BMT | UOM | WORK-duration | ST | TOTAL DURATION | UOM
2 | 2 | RAW MATERIAL
3 | 3 | SH PLATE-SA 516 Gr60
4 | 4 | SH GIRTH FLANGE-SA266 Gr4
5 | 5 | CH PLATE-SA 516 Gr60
6 | 6 | CH GIRTH FLANGE-SA 266 Gr4
7 | 7 | BARREL SHEEL PLATE-SA 516 GR 60
8 | 8 | BARREL GIRTH FLANGE-SA 266 GR4
9 | 9 | BARREL DISH-SA 516 GR 60
10 | 10 | TUBE SHEET-1-SA 266 GR4
11 | 11 | TUBE SHEET -2-SA 266 GR4
12 | 12 | FLOATING HEAD FLG-SA 266 GR4
13 | 13 | FLOATING HEAD DISH-SA 516 GR60
14 | 14 | BACKING RING-SA 266 GR4
15 | 15 | BAFFLE PLATE-SA 516 GR60
16 | 16 | SEALING STRIP PLATE-SA 516 GR60
17 | 17 | SLIDING STRIP PLATE-SA 516 GR60
18 | 18 | SEAL ROD-SA 36
19 | 19 | NOZ SRN-SA 105
20 | 20 | TUBE -SA 179
21 | 21 | SPACER TUBE-SA 179
22 | 22 | TIE ROD-SA 36
23 | 23 | TEST RING & TEST FLG-SA 266 GR4
24 | 24 | MS ROD FOR HANDLE ETC
25 | 25 | MS PLATE FOR SADDLE
26 | 26 | DISH FORMING - 24T*1700 OD | 9
| 27 | BARREL DISH BLANK ISSUENCE |  | T |  | 24 | ID dish | 1 | No | 1 | nos | 4 | Day | 4 |  | 4 | Days
| 28 | BARREL-DISH BLANK MARKING - 24 * 1670 OD | 27 | F,H |  | 24 | 6723 MM | 1 | No | 6.723 | Dia-mtr | 0.1 | Hr/mtr | 0.6723 | 1 | 1.6723 | Hr
| 29 | BARREL-DISH BLANK MARKING INSPECTION | 28 | F,H |  | 24 |  | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days
| 30 | BARREL-DISH BLANK CUTTING | 29 | C,H |  | 24 | 6723 MM | 1 | no | 6.723 | Dia-mtr | 0.25 | RMT | 1.6807 | 1 | 2.6807 | Hr
| 31 | BARREL-DISH FORMING | 30 | SC |  | 24 | 1664 id | 1 | no | 1 | No | 10 | Day | 10 |  | 10 | Days
| 32 | PROFILE INSP | 31 | F,H |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days
| 33 | HEAT TREATMENT PREPARATION | 32 | SC |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 34 | STRESS RELEIVING- SUB CONT | 33 | SC |  | 24 | 1664 id | 1 | no | 1 | No | 4 | Day | 4 |  | 4
| 35 | REMOVAL OF SPIDERS | 34 | F,H |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 36 | SURFACE PREPARATION | 35 | G |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 | 1 | 2 | 1
| 37 | INSPECTION | 36 | F |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 38 | TPI INSPECTION | 37 | F |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 39 | SF MARKING | 38 | F,H | enter | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 0.1 | RMT | 0.53163 | 1 | 1.5316 | Hr
| 40 | SF CUTTING | 39 | C,H |  | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 1 | RMT | 5.3163 | 1 | 6.3163 | Hr
| 41 | SF GRIDNING & EP | 40 | G |  | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 1 | RMT | 5.3163 |  | 5.3163 | Hr
42 | 42 | TUBE SHEET
43 | 43 | TUBE SHEET MACHINING 1 OFF 2 | 10
| 44 | INWARD INSPECTION |  |  | enter | 145 t | 1670 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | day
| 45 | TUBE SHEET M/C - 1/2 | 44 | SC |  | 145 t | 1548 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | day
46 | 46 | TUBE SHEET DRILLING 1 OFF 2 | 43
| 47 | TUBE SHEET DRILLING -1/2 | 46 | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.2683 | Day
| 48 | EXP GROOVE+WELDING GROOVE -1/2 | 47 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.5417 | Day
| 49 | TIE ROD, PULLING, LIFTING HOLE - 1/2 | 48 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Day
| 50 | PASS PARTITION GROOVE M/C -1/2 | 49 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Day
| 51 | CLEANING ,GO/NO GO CHECK -1/2 | 50 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs
| 52 | FINAL INSPECTION -1/2 | 51 | F,H
53 | 53 | TUBE SHEET MACHINING 2 OFF 2 | 10
| 54 | INWARD INSPECTION | 53 |  |  | 145 t | 1670 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | day
| 55 | TUBE SHEET M/C - 2/2 | 54 | SC |  | 145 t | 1548 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | day
56 | 56 | TUBE SHEET DRILLING 2 OFF 2
| 57 | TUBE SHEET DRILLING -2/2 | 47 | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.2683 | Day
| 58 | EXP GROOVE+WELDING GROOVE -2/2 | 57 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.5417 | Day
| 59 | TIE ROD, PULLING, LIFTING HOLE - 2/2 | 58 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Day
| 60 | PASS PARTITION GROOVE M/C -2/2 | 59 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Day
| 61 | CLEANING ,GO/NO GO CHECK -2/2 | 60 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs
| 62 | FINAL INSPECTION -2/2 | 61 | F,H |  |  |  | 1 |  | 1050 | nos | 0.05 | RMT | 52.5 | 1 | 53.5 | 1
63 | 63 | NOZ FAB | 19
64 | 64 | SH NOZ PIPE MARKING | 3
| 65 | 26"NB SRN - 2 NOS | 64 | F,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 66 | 2" MP CON - 2 NO | 65 | F,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 67 | INSPECTION OF MARKING | 66 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs
68 | 68 | SH NOZ PIPE CUTTING | 64
| 69 | 26"NB SRN - 2 NOS | 68 | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 70 | 2" MP CON - 2 NO | 69 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 71 | INSPECTION OF MARKING | 70 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
72 | 72 | SH NOZ PIPE EP | 68
| 73 | 26"NB SRN - 2 NOS | 72 | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
| 74 | 2" MP CON - 2 NO | 73 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 75 | INSPECTION | 74 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
76 | 76 | SH NOZ+FLG FIITUP | 72
| 77 | 26"NB SRN - 2 NOS | 76 | F[2],W,H[2] |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs
| 78 | 2" MP CON - 2 NO | 77 | F[2],W,H[2] |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs
| 79 | INSPECTION | 78 | F[2],W,H[2] |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
80 | 80 | SH NOZ PIPE+FLG WELDING | 76
| 81 | 26"NB SRN - 2 NOS | 80 | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.381 | Hrs
| 82 | 2" MP CON - 2 NO | 81 | W,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 |  | 0 | Hrs
| 83 | INSPECTION | 82 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
84 | 84 | SH NOZ PIPE PROFILE MARKING | 80
| 85 | 26"NB SRN - 2 NOS | 84 | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs
| 86 | 2" MP CON - 2 NO | 85 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
| 87 | INSPECTION | 86 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
88 | 88 | SH NOZ PIPE PROFILE CUTTING | 84
| 89 | 26"NB SRN - 2 NOS | 88 | G,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 90 | 2" MP CON - 2 NO | 89 | G,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 91 | INSPECTION | 90 | G,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
92 | 92 | SH NOZ PIPE PR0FILE EP | 88
| 93 | 26"NB SRN - 2 NOS | 92 | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.108 | Hrs
| 94 | 2" MP CON - 2 NO | 93 | G,H |  | 18 | 272 mm | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.272 | Hrs
| 95 | INSPECTION | 94 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
96 | 96 | CH NOZ PIPE MARKING | 92
| 97 | 16"NB SRN - 2 NOS | 96 | F,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 98 | 2" MP CON - 2 NO | 97 | F,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 99 | INSPECTION | 98 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs
100 | 100 | CH NOZ PIPE CUTTING | 96
| 101 | 16"NB SRN - 2 NOS | 100 | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 102 | 2" MP CON - 2 NO | 101 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 103 | INSPECTION | 102 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
104 | 104 | CH NOZ PIPE EP | 100
| 105 | 16"NB SRN - 2 NOS | 104 | G,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
| 106 | 2" MP CON - 2 NO | 105 | G,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 107 | INSPECTION | 106 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
108 | 108 | CH NOZ+FLG FIT UP | 104
| 109 | 16"NB SRN - 2 NOS | 108 | F[2],W,H[2] |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs
| 110 | 2" MP CON - 2 NO | 109 | F[2],W,H[2] |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs
| 111 | INSPECTION | 110 | F[2],W,H[2] |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
112 | 112 | CH NOZ PIPE+FLG WELDING | 108
| 113 | 16"NB SRN - 2 NOS | 112 | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.381 | Hrs
| 114 | 2" MP CON - 2 NO | 113 | W,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 |  | 0 | Hrs
| 115 | INSPECTION | 114 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
116 | 116 | CH NOZ PIPE PROFILE MARKING | 112
| 117 | 16"NB SRN - 2 NOS | 116 | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs
| 118 | 2" MP CON - 2 NO | 117 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
| 119 | INSPECTION | 118 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
120 | 120 | CH NOZ PIPE PROFILE CUTTING | 116
| 121 | 16"NB SRN - 2 NOS | 120 | F,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 122 | 2" MP CON - 2 NO | 121 | F,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 123 | INSPECTION | 122 | F,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
124 | 124 | CH NOZ PIPE PR0FILE EP | 120
| 125 | 16"NB SRN - 2 NOS | 124 | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.108 | Hrs
| 126 | 2" MP CON - 2 NO | 125 | G,H |  | 18 | 272 mm | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.272 | Hrs
| 127 | INSPECTION | 126 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
128 | 128 | SADDLE & OTHER | 124
129 | 129 | TOP SADDLE FABRRICATION | 128
| 130 | PLATE ISSUENCE | 129 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 | 0 | 4 | Day
| 131 | BASE MARKING | 130 | F,H |  | 30/25 | 9 rmt | 1 | Set | 9 | mtr | 0.25 | hr | 2.25 | 1 | 3.25 | Hr
| 132 | WEB PL MARKING | 131 | F,H |  | 30/25 | 29 rmt | 1 | Set | 29 | mtr | 0.25 | hr | 7.25 | 1 | 8.25 | Hr
| 133 | RIBS MARKING | 132 | F,H |  | 25 | 10.5 Rmt | 1 | Set | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.625 | Hr
134 | 134 | TOP SADLLE PLATE CUTTING | 129
| 135 | BASE CUTTING | 134 | C,H |  | 30/25 | 9 rmt | 1 | Nos | 9 | mtr | 0.5 | hr | 4.5 | 1 | 5.5 | Hrs
| 136 | WEB PL CUTTING | 135 | C,H |  | 30/25 | 29 rmt | 1 | Nos | 29 | mtr | 0.5 | hr | 14.5 | 1 | 15.5 | Hrs
| 137 | RIBS CUTTING | 136 | C,H |  | 25 | 10.5 Rmt | 1 | Nos | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.625 | Hrs
| 138 | GRINNDING OF ABOVE | 137 | G[2] |  | 25 |  |  |  | 48.5 | mtr | 0.15 | hr | 7.275 | 1 | 8.275 | Hrs
139 | 139 | SADDLE FIT UP & WELDING | 134
| 140 | BASE + WEB FIT UP | 139 | F[2],H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 141 | BASE + WEB WELDING | 140 | W,H |  | 18 |  | 1 | Set | 4 | No | 3.4 | hr | 13.6 | 1 | 14.6 | Hrs
| 142 | RIBS+WEB FIT UP | 141 | F[2],H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 143 | RIBS+WEB WELDING | 142 | W[2],H[2] |  | 18 |  | 1 | Set | 24.8 | No | 3.4 | hr | 84.32 | 1 | 85.32 | Hrs
144 | 144 | DAVIT PIPE FABRICATION | 139
| 145 | PIPE TRANSFERE | 144 | H[4] |  |  |  | 1 | SET | 1 | SET | 4 | Day | 4 |  | 4 | Days
| 146 | PIPE MARKING - 6 NOS | 145 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
| 147 | SUPPORT PL MARKING | 146 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 148 | GUSSET PL MARKING | 147 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 149 | BASE HUB MARKING | 148 | F,H |  | 30 |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 150 | PIPE CUTTING - 6 NOS | 149 | C,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
| 151 | SUPPORT PL CUTTING | 150 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 152 | PIPE GRINDING - 6 NOS | 151 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
| 153 | SUPPORT PL GRINDING-10 NOS | 152 | G |  |  |  | 10 | Nos | 10 | Nos | 0.5 | Hr | 5 |  | 5 | Hrs
| 154 | PIVOT PL GRINDING | 153 | G |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 155 | PIPE FIT UP-2 NOS | 154 | F,H,W |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 156 | PIPE WELDING -2 NOS | 155 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 157 | PIVOT PL WELDING | 156 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 158 | SUPPORT PL WELDING -4 NOS | 157 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
159 | 159 | LIFTING LUG PAD | 144
| 160 | PLATE ISSUENCE | 159 |  |  |  |  | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days
| 161 | LIFTING LUG PAD MARKING | 160 | F,H |  | 18 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 162 | LIFTING LUG PAD CUTTING | 161 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 163 | LIFTING LUGS PAD GRINDING | 162 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
164 | 164 | LIFTING LUG PREPARATION | 159
| 165 | LIFTING LUGS MARKING | 164 | F,H |  | 24 |  | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days
| 166 | LIFTING LUGS CUTTING | 165 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 167 | LIFTING LUGS GRINDING | 166 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 168 | LIFTING LUG DRILLING | 167 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
169 | 169 | CH COVER HANDLE PREPATAION | 164
| 170 | CH COVER RING FORMING | 169 | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days
| 171 | SLIDING SLING FORMING | 170 | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days
172 | 172 | INSULATION RING PRPARATION | 169
| 173 | INSULAION RING MARKING | 172 | F,H |  | 12 |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs
| 174 | INSULAION RING CUTTING | 173 | C,H |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs
| 175 | INSULAION RING HOLE MARKING | 174 | F,H |  |  |  | 1 | Nos | 1 | Nos | 2 | Hr | 2 |  | 2 | Hrs
| 176 | INSULAION RING HOLE DRILLING | 175 | F,H |  |  |  | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
177 | 177 | BAFFLE & TB ITEMS FAB | 176
178 | 178 | BAFFLE PREPARATION | 177
| 179 | BAFFLE PLATE TRANSFER | 178 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
| 180 | BAFFLE MARKING | 179 | F,H |  | 14 |  | 19 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Hrs
| 181 | BAFFLE PROFILE CUTTING | 180 | C,H |  |  |  | 19 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Hrs
182 | 182 | BAFFLE BEND REMOVAL & STACKING | 178
| 183 | BAFFLE PL BEND REMOVAL | 182 | F,H[2] |  |  |  | 19 | Nos | 19 | Nos | 1 | Hr | 19 |  | 19 | Hrs
| 184 | BAFFLE PL STACKING | 183 | F,H |  |  | 3 bundle | 3 | Nos | 3 | Nos | 2 | Hr | 6 |  | 6 | Hrs
185 | 185 | BAFFLE DRILLING | 182
| 186 | BAFFLE DRILLING | 185 | SC |  | 14 thk |  | 3 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 | Day
187 | 187 | BAFFLE DE STACKING & CHAMFERING | 185
| 188 | BAFFLE DE STACING | 187 | F,H |  |  |  | 3 | Bunch | 4 | Bunch | 6 | Hrs | 24 |  | 24 | Hr
| 189 | BAFFLE CHAMFERING | 188 | F |  |  |  | 9 | Nos | 23544 | holes | 0.01 |  | 235.44 |  | 14.715 | Days
190 | 190 | BAFFLE STACKING & THRO HOLE CHECK | 187
| 191 | STACKING | 190 | F,H |  |  |  | 3 | Nos | 3 | Nos | 0.25 | Hr | 0.75 |  | 0.75 | Hrs
| 192 | BAFFLE HOLE ALINGMENT | 191 | F,H |  |  |  | 3 | Nos | 1 | SET | 1 | Hrs | 1 |  | 1 | Hrs
| 193 | BAFFLE HOLE RE DRILL | 192 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Day
| 194 | BAFFLE OD MACHINING | 193 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Day
| 195 | BAFFLE CLEANING | 194 | H[3] |  |  |  | 3 | Nos | 1 | SET | 1 | Day | 1 |  | 1 | Day
196 | 196 | SUPPORT PLATE MARKING | 190
| 197 | SUPPORT PLATE TRANSFER | 196 |  |  |  |  | 2 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days
| 198 | SUPPORT MARKING | 197 | SC |  | 20 |  | 2 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days
| 199 | SUPPORT PROFILE CUTTING | 198 | SC |  |  |  | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
200 | 200 | SUPPORT PLATE BEND REMOVAL | 196
| 201 | SUPPORT PL BEND REMOVAL | 200 | F,H[3] |  |  |  | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hr
| 202 | SUPPORT PL STACKING | 201 | F,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hr
203 | 203 | SUPPORT PLATE DRLINNG | 200
| 204 | SUPPORT DRILLING | 203 | SC |  | 20THK |  | 1 | Bunch | 1 | Set | 10 | Day | 10 |  | 10
205 | 205 | SUP PLATE DE STACKING & CHAMFERING | 203
| 206 | SUPPORT DE STACING | 205 | F,H |  |  |  | 1 | Bunch | 1 | Bunch | 3 | Hrs | 3 |  | 3 | Hrs
| 207 | SUPPORT HOLE CHAMFERING | 206 | F |  |  |  | 2 | Plate | 2616 | holes | 0.01 |  | 26.16 |  | 26.16
208 | 208 | TIE ROD PREPARATION | 22
| 209 | TIE ROD MATL TRANSFERE | 208 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Day
| 210 | ROD CUTTING | 209 | F,H |  |  |  | 22 | Nos | 22 | noS | 0.25 | Hr | 5.5 |  | 5.5 | Hrs
| 211 | THREAD MACHINING. | 210 | L |  |  |  | 22 | Nos | 22 | Nos | 0.45 | Hr | 9.9 |  | 9.9 | Hra
| 212 | JOINING | 211 | W,F,H |  |  |  | 22 | Nos | 22 | Nos | 0.5 | Hr | 11 |  | 11 | Hrs
213 | 213 | SPACER TUBE PREPARATION | 21
| 214 | SPACER TUBE TRANSFERE | 213 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
| 215 | LENGTH CUTTING 237NOS | 214 | F,H |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs
| 216 | LENNGTH MACHINING | 215 | L |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs
| 217 | CLEANINNG | 216 | H[3] |  |  |  | 414 | Nos | 414 | Nos | 0.016667 | Hr | 6.9 |  | 6.9 | Hrs
218 | 218 | SEALING STRIP PREPARATION | 16
| 219 | SEALING STRIP MARKING | 218 | F,H |  | 8 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.1 | Hr | 1.9044 |  | 1.9044 | Hrs
| 220 | SEALING STRIP CUTTING | 219 | C,H |  | 25 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.25 | Hr | 4.761 |  | 4.761 | Hrs
| 221 | SEALING STRIP BEND REMOVAL | 220 | F,H[2] |  | 25 | 9522 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
| 222 | SEALING STRIP GRINDING | 221 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
| 223 | SEALING STRIP JOINING | 222 | W,F,H |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
| 224 | SEALING STRIP DRESS UP | 223 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
225 | 225 | SLIDING STRIP PREPARATION | 17
| 226 | SLIDING STRIP MARKING | 225 | F,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.1 | Hr | 2.6732 |  | 2.6732 | Hrs
| 227 | SLIDING STRIP CUTTING | 226 | C,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.25 | Hr | 6.683 |  | 6.683 | Hrs
| 228 | SLIDING STRIP BEND REMOVAL | 227 | F,H[2] |  | 8 | 13366 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
| 229 | SLIDING STRIP GRINDING | 228 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
| 230 | SLIDING STRIP JOINING | 229 | W,F,H |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
| 231 | SLIDING STRIP DRESS UP | 230 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
232 | 232 | SEAL ROD PREPARATION | 18
| 233 | SEAL ROD ISSUENECE | 232 | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days
| 234 | SEAL ROD MARKING | 233 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.25 | Hr | 3.5 |  | 3.5 | Hrs
| 235 | SEAL ROD CUTTING | 234 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.5 | Hr | 7 |  | 7 | Hrs
| 236 | SEAL ROD BEND REMOVAL | 235 | F,H[2] |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 1 | Hr | 14 |  | 14 | Hrs
237 | 237 | SHELL FABRICATION | 236
238 | 238 | SH MARKING & CUTTING | 3
| 239 | SH PLATE TRNASFER | 238 | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Day
| 240 | SH-MARKING | 239 | F,H[2] |  | 18 | 43000 mm | 1 | Nos | 43 | mtr | 0.1 | hr | 4.3 | 1 | 5.3 | Hrs
241 | 241 | SH PLATE CUTTING | 238
| 242 | SH-CUTTING | 241 | C,H[2] |  | 18 | 43000 mm | 3 | Nos | 129 | mtr | 0.25 | hr | 32.25 | 1 | 33.25 | Hrs
243 | 243 | SH PL SIDE GRINDING | 241
| 244 | SH PL SIDE BEVEL CUTTING | 243 | F,H[3] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 245 | SH PL SIDE BEVEL CUTTING | 244 | F,H[3] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 246 | SH PL SIDE BEVEL CUTTING | 245 | F,H[3] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.625 | Hrs
| 247 | SH PL SIDE BEVEL CUTTING | 246 | F,H[3] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 |  | 0 | Hrs
248 | 248 | SH PLATE EDGE PREPARATION | 243
| 249 | SH-BEVEL GRINDING | 248 | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 250 | SH-BEVEL GRINDING | 249 | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 251 | SH-BEVEL GRINDING | 250 | G,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 252 | SH-BEVEL GRINDING | 251 | G,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
253 | 253 | SH PRE BENDING | 248
| 254 | SH-PRE BEND | 253 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 255 | SH-PRE BEND | 254 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 256 | SH-PRE BEND | 255 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 257 | SH-PRE BEND | 256 | F[2],H |  | 18 | 0 mm | 0 | Nos | 0 | No | 0 | hr | 0 |  | 0 | Hrs
258 | 258 | SH PL PRE BEND CUT OFF | 253
| 259 | SH-PRE BEND CUT OFF | 258 | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 260 | SH-PRE BEND CUT OFF | 259 | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 261 | SH-PRE BEND CUT OFF | 260 | F[2],H,C |  | 18 | 1250 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 262 | SH-PRE BEND CUT OFF | 261 | F[2],H,C |  | 18 | 0 mm | 1 | Nos | 0 | Nos | 3 | hr | 0 | 1 | 1 | Hrs
263 | 263 | SH PLATE LS EP | 258
| 264 | SH-PRE BEND LS EP | 263 | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 265 | SH-PRE BEND LS EP | 264 | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 266 | SH-PRE BEND LS EP | 265 | F,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 267 | SH-PRE BEND LS EP | 266 | F,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
268 | 268 | SH ROLLING | 263
| 269 | SH-ROLLING 1/4 | 268 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 270 | SH-ROLLING | 269 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 271 | SH-ROLLING | 270 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 272 | SH-ROLLING | 271 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
273 | 273 | SH CIR LENGTH & EP CORRECTION | 268 | [10 empty] | 0 |  | 0
| 274 | SH-LS CORRECTION | 273 | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 275 | SH-LS CORRECTION | 274 | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 276 | SH-LS CORRECTION | 275 | F,H[2] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 277 | SH-LS CORRECTION | 276 | F,H[2] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
278 | 278 | SH LS SEAMS FIT UP | 273 | [10 empty] | 0 |  | 0
| 279 | SH-LS FIT UP | 278 |  |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 280 | SH-LS FIT UP | 279 | F[2],H,W |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 281 | SH-LS FIT UP | 280 | F[2],H,W |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 282 | SH-LS FIT UP | 281 | F[2],H,W |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
283 | 283 | SH LS WELDING ARRANGEMENT | 278
| 284 | SH-LS WELD ARRANGEMENT | 283 | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 285 | SH-LS WELD ARRANGEMENT | 284 | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 286 | SH-LS WELD ARRANGEMENT | 285 | F,H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 287 | SH-LS WELD ARRANGEMENT | 286 | F,H |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
288 | 288 | SH LONG SEAM OUTER WELDING | 283
| 289 | SH-LS WELDING- TOP SIDE | 288 | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
| 290 | SH-LS WELDING- TOP SIDE | 289 | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
| 291 | SH-LS WELDING- TOP SIDE | 290 | W,H |  | 12 | 1250 mm | 1 | Nos | 1.25 | mtr | 2.5 | hr | 3.125 | 1 | 4.125 | Hrs
| 292 | SH-LS WELDING- TOP SIDE | 291 | W,H |  | 12 | 0 mm | 1 | Nos | 0 | mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
293 | 293 | SH LS BACK CHIP | 288
| 294 | SH-LS WELDING- BACK CHIP | 293 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 295 | SH-LS WELDING- BACK CHIP | 294 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 296 | SH-LS WELDING- BACK CHIP | 295 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 297 | SH-LS WELDING- BACK CHIP | 296 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
298 | 298 | SH LS INNER WELDING | 293
| 299 | SH-LS INNER WELDING | 298 | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
| 300 | SH-LS INNER WELDING | 299 | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
| 301 | SH-LS INNER WELDING | 300 | W,H |  | 6 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.9 | hr | 1.125 | 1 | 2.125 | Hrs
| 302 | SH-LS INNER WELDING | 301 | W,H |  | 6 | 0 mm | 1 | Nos | 0 | mtr | 0.9 | hr | 0 | 1 | 1 | Hrs
303 | 303 | SH INNER LS FLUSH GRINDING | 298
| 304 | SH INNER FLUSH GRINDING | 303 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 305 | SH INNER FLUSH GRINDING | 304 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 306 | SH INNER FLUSH GRINDING | 305 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.625 | Hrs
| 307 | SH INNER FLUSH GRINDING | 306 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs
308 | 308 | SH LS RADIOGRAPHY | 303
| 309 | SH LS WELDING RT | 308 | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
| 310 | SH LS WELDING RT | 309 | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
| 311 | SH LS WELDING RT | 310 | RT |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
| 312 | SH LS WELDING RT | 311 | RT |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
313 | 313 | SH RE ROLLING | 308 | [10 empty] | 0
| 314 | SH RE ROLLING | 313 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 315 | SH RE ROLLING | 314 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 316 | SH RE ROLLING | 315 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 317 | SH RE ROLLING | 316 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
318 | 318 | SH PLATE CS EP CORRECTION | 313
| 319 | SH CIR EP CORRECTION | 318 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 320 | SH CIR EP CORRECTION | 319 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 321 | SH CIR EP CORRECTION | 320 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 322 | SH CIR EP CORRECTION | 321 | F,H |  | 18 | 0 mm id | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
323 | 323 | SH CIR SEAM FIRST FIT UP | 318
| 324 | SH CS FIT UP - [LS1+LS2] | 323 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 325 | SH CS TACK DP CHECK - [LS1+LS2] | 324 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
326 | 326 | SH CIR SEAM FIRST WELDING | 323
| 327 | SH CS WELDING TRANSFERE | 326 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
| 328 | SH CS WELDING OUTER [LS1+LS2] | 327 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 329 | SH CS WELDING BACK CHIP [LS1+LS2] | 328 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 330 | SH CS INNER WELDING [LS1+LS2] | 329 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 331 | SH CS FLUSH GRINDING [LS1+LS2] | 330 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
332 | 332 | SH CIR SEAM SECOND FITUP | 326
| 333 | SH CS FIT UP - [LS2+LS3] | 332 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 334 | SH CS TACK DP CHECK - [LS2+LS3] | 333 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
335 | 335 | SH CIR SEAM SECOND WELDING | 332 | [10 empty] | 0 |  | 0
| 336 | SH CS WELDING TRANSFERE-[LS2+LS3] | 335 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 337 | SH CS WELDING OUTER [LS2+LS3] | 336 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 338 | SH CS WELDING BACK CHIP [LS2+LS3] | 337 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 339 | SH CS INNER WELDING [LS2+LS3] | 338 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 340 | SH CS FLUSH GRINDING [LS2+LS3] | 339 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
341 | 341 | SH CIR SEAM III RD FITUP | 335
| 342 | SH CS FIT UP CS3 | 341 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 343 | SH CS TACK DP CHECK CS3 | 342 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
344 | 344 | SH CIR SEAM THIRD WELDING | 341
| 345 | SH CS WELDING TRANSFERE CS3 | 344 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 346 | SH CS WELDING OUTER CS3 | 345 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 347 | SH CS WELDING BACK CHIP CS3 | 346 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 348 | SH CS INNER WELDING CS3 | 347 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 349 | SH CS FLUSH GRINDING CS3 | 348 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
350 | 350 | SH FINAL LENGTH CORRECTION | 344
| 351 | SH LENGTH MARKING | 350 | F[2] |  | 18 | 1560 mm id | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 352 | LENGTH CUTTING | 351 | C,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
| 353 | GRINDING & EP | 352 | G,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
354 | 354 | SH CIR SEAM FLANGE 1 FITUP | 350
| 355 | SH CS FIT UP FLG CS1 | 354 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 356 | SH CS TACK DP CHECK FLG CS1 | 355 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
357 | 357 | SH CIR SEAM FLANGE 1 WELDING | 354
| 358 | SH CS WELDING TRANSFERE | 357 | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 359 | SH CS WELDING OUTER FLG CS1 | 358 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 360 | SH CS WELDING BACK CHIP FLG CS1 | 359 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 361 | SH CS INNER WELDING FLG CS1 | 360 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 362 | SH CS FLUSH GRINDING FLG CS1 | 361 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
363 | 363 | SH CS FIT UP FLG2 | 357
| 364 | SH CS FIT UP FLG 2 | 363 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 365 | SH CS TACK DP CHECK FLG2 | 364 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
366 | 366 | SH CS WELDING FLG2 | 363
| 367 | SH CS WELDING TRANSFERE FLG2 | 366 | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 368 | SH CS WELDING OUTER FLG2 | 367 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 369 | SH CS WELDING BACK CHIP FLG2 | 368 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 370 | SH CS INNER WELDING FLG2 | 369 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 371 | SH CS FLUSH GRINDING FLG2 | 370 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
372 | 372 | NOZ ORIENTATION MARKING | 366
| 373 | SH-NOZ ORIENTAION MARKING | 372 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
| 374 | SH-NOZ MARKING-N2A1 | 373 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
| 375 | SH-NOZ MARKING-N2A1 | 374 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
376 | 376 | SH NOZ OPENNING | 372
| 377 | 26"NB SRN - 1 | 376 | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.3054 | Hrs
| 378 | 26"NB SRN - 1 | 377 | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.3054 | Hrs
379 | 379 | INSPECTION | 376 | C,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
380 | 380 | SH NOZ EP | 379
| 381 | 26"NB SRN - 1 | 380 | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.054 | Hrs
| 382 | 26"NB SRN - 1 | 381 | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.054 | Hrs
| 383 | INSPECTION | 382 |  |  |  |  | 1 | No | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
384 | 384 | SH NOZZZLE FIT UP | 380
| 385 | 26"NB SRN - 1 | 384 | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 386 | 26"NB SRN - 1 | 385 | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 387 | DP CHECK | 386 |  |  |  |  | 2 | No | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
388 | 388 | SH NOZ FIT UP INSPECTION | 384
| 389 | 26"NB SRN - 1 | 388 | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
| 390 | 26"NB SRN - 1 | 389 | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
| 391 | DP CHECK | 390 | F,H |  |  | 650nb | 2 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
392 | 392 | SH NOZ WELDING | 388
| 393 | SH NOZ WELDING ARRANGEMENT | 392 | T |  |  |  | 1 | No | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
| 394 | SH-NOZ WELDING -N1A | 393 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.6351 | Hrs
| 395 | SH-NOZ WELDING-N2A1 | 394 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.6351 | Hrs
| 396 | SH-NOZ WELDING-N2A2 | 395 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.6351 | Hrs
| 397 | SH NOZ ROOT DP CHECK | 396 | F,H |  | 12 | 972 mm lip od | 2 | No | 6.108 | Mtr | 1 | hr | 6.108 | 1 | 7.108 | Hrs
| 398 | SH-NOZ INNER WELD -N1A | 397 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.1535 | Hrs
| 399 | SH-NOZ INNER WELD-N2A1 | 398 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.1535 | Hrs
| 400 | SH-NOZ INNER WELD-N2A2 | 399 | H,W |  | 8 | 972 mm lip od | 0 | No | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs
401 | 401 | SH SADDLE WELDING | 392
| 402 | SH-SADDLE PAD FIT UP | 401 | F[2],W,H |  | 25 | 1596 mm od | 2 | No | 20.0585 | Nos | 0.5 | Hr | 10.0293 | 1 | 11.0293 | Hrs
| 403 | SH-SADDLE PAD WELDING | 402 | W[2],H[2] |  | 12 | 1596 mm od | 2 | Mtr | 20.0585 | Mtr | 1.6 | Hr | 32.0936 | 1 | 33.0936 | Hrs
| 404 | SH-SADDLE MATCHING | 403 | F[2],G[2] |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 8 | Hr | 16 | 1 | 17 | Hrs
| 405 | SH-SADDLE FIT UP | 404 | W,F[2],H |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 6 | Hr | 12 | 1 | 13 | Hrs
| 406 | SH-SADDLE WELDING | 405 | W[2],H[2] |  | 12 | 11400 rmt | 1 | Nos | 16.0348 | Mtr | 1.6 | Hr | 25.6557 | 1 | 26.6557 | Hrs |  | 4014.8286
| 407 | SH-SADDLE dress up | 406 | G[2] |  |  |  | 1 | No | 1 | Nos | 8 | Hr | 8 | 1 | 9 | Hrs
408 | 408 | SH DAVIT ARM WELDING | 401
| 409 | SH-DAVIT ARM arm match | 408 | F,G |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
| 410 | SH-DAVIT ARM FIT UP | 409 | F,H,W |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
| 411 | SH-DAVIT ARM WELDING | 410 | W,H |  | 12 |  | 6 | mtr | 5.16 | Mtr | 1.6 | Hr | 8.256 | 1 | 9.256 | Hrs
412 | 412 | SH NDE CLEARENCE | 408
| 413 | SH-SH NDE CLEARENCE | 412 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 12 | Hr | 12 | 1 | 13 | Hrs
| 414 | TPI INSPECTION | 413 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 1 | Day | 1 |  | 1 | Day
415 | 415 | CH FABRICATION
416 | 416 | CH SHELL LS WELDING | 5
| 417 | CH PLATE TRNASFER | 416 | T |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Day
| 418 | CH-MARKING | 417 | F,H[2] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.1 | hr | 0.0831 | 1 | 1.0831 | Hrs
| 419 | CH-CUTTING | 418 | C,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.25 | hr | 0.20775 | 1 | 1.2078 | Hrs
| 420 | CH PL SIDE GRINDING | 419 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.15 | hr | 0.12465 | 1 | 1.1246 | Hrs
| 421 | CH-BEVELLING CIR SIDE | 420 | F,H[3] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.4155 | Hrs
| 422 | CH EP GRINDING | 421 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.831 | Hrs
423 | 423 | CH SH ROLLING | 416
| 424 | CH-PRE BEND | 423 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
| 425 | CH-PRE BEND CUT OFF | 424 | F[2],C |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 0.3 | hr | 0.4986 | 1 | 1.4986 | Hrs
| 426 | CH LS BEVELING | 425 | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.662 | Hrs
| 427 | CH-ROLLING | 426 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
428 | 428 | CH SHELL LS FIT UP | 423
| 429 | CH-LS CORRECTION | 428 | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.662 | Hrs
| 430 | CH-LS FIT UP | 429 | F[2],W,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.831 | Hrs
431 | 431 | CH SHELL LS WELDING | 428
| 432 | CH-LS WELD ARRANGEMENT | 431 | F,H[2] |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 433 | CH-LS WELDING- TOP SIDE | 432 | W,H |  | 12 | 831 mm | 1 | Nos | 0.831 | mtr | 2.5 | hr | 2.0775 | 1 | 3.0775 | Hrs
| 434 | CH-LS WELDING- BACK CHIP | 433 | G,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.831 | Hrs
| 435 | CH-LS INNER WELDING | 434 | W,H |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.9 | hr | 0.7479 | 1 | 1.7479 | Hrs
| 436 | CH-LS INNNER FLUSH GRIND | 435 | G |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.4155 | Hrs
| 437 | CH RE ROLLING | 436 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
438 | 438 | CH LS WELDING RADIOGRAPHY | 431
| 439 | CH LS WELDING RT | 438 | RT |  | 18 | 831 mm | 1 | No | 1 | No | 1 | dya | 1 |  | 1 | Day
440 | 440 | CH CS FLG 1 FIT UP | 438
| 441 | CH CIR EP CORRECTION | 440 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 9.803 | mtr | 0.45 | hr | 4.4114 | 1 | 5.4114 | Hr
| 442 | CH CS FIT UP FLG1 | 441 | F[2],W,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hr
| 443 | CH CS TACK DP CHECK FLG1 | 442 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 4 | hr | 4 | 1 | 5 | Hr
444 | 444 | CH CS FLG 1 WELDING | 440
| 445 | CH CS WELDING TRANSFERE | 444 | F,H[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hr
| 446 | CH CS WELDING OUTER FLG1 | 445 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | hr
| 447 | CH CS WELDING BACK CHIP FLG1 | 446 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9015 | hr
| 448 | CH CS INNER WELDING FLG 1 | 447 | W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1.36 | hr | 6.6661 | 1 | 7.6661 | hr
| 449 | CH CS FLUSH GRINDING FLG1 | 448 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
450 | 450 | CH CS FLG 2 FIT UP | 444
| 451 | CH LENGTH CUTTING | 450 | C,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
| 452 | CH CIR EP CORRECTION | 451 | F,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | hr
| 453 | CH CS FIT UP FLG2 | 452 | F[2],W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 4 | hr | 19.6061 | 1 | 20.6061 | hr
| 454 | CH CS TACK DP CHECK FLG1 | 453 | F |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
455 | 455 | CH CS FLG 2 WELDING | 450
| 456 | CH CS WELDING TRANSFERE FLG2 | 455 | F,H[2] |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | hr
| 457 | CH CS WELDING OUTER FLG2 | 456 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | hr
| 458 | CH CS WELDING BACK CHIP FLG2 | 457 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9015 | hr
| 459 | CH CS INNER WELDING FLG2 | 458 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | hr
| 460 | CH CS FLUSH GRINDING FLG2 | 459 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
461 | 461 | CH CS FLG 1 & 2 WELDING rt | 455
| 462 | CH CS WELDING RT | 461 | RT |  | 18 | 1560 mm id | 1 | No | 1 | n | 1 | Day | 1 |  | 1 | Day
463 | 463 | CH NOZ MARKING | 461
| 464 | CH- NOZ IREIENTATION NKG | 463 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
| 465 | CH-NOZ MARKING- 16"NB - 2 NOS | 464 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
466 | 466 | CH NOZ OPNNING | 463
| 467 | CH-NOZ OPENNING-TOP | 466 | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 468 | CH-NOZ OPENNING-Bot | 467 | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
469 | 469 | CH NOZ OPEN EP | 466
| 470 | CH-NOZ EP -N3A | 469 | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 471 | CH-NOZ EP-N4A | 470 | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
472 | 472 | CH NOZ FIT UP | 469
| 473 | CH-NOZ FIT UP -N3A | 472 | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 474 | CH-NOZ FIT UP -N4A | 473 | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs
475 | 475 | CH NOZ FIT UP INSP | 472
| 476 | CH-NOZ INSPN -N3A | 475 | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 477 | CH-NOZ INSPN-N4A | 476 | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
478 | 478 | CH NOZ WELDING | 475
| 479 | CH NOZ WELDING ARRANGEMENT | 478 | F,H[2] |  |  | 400nb | 2 | Nos | 1 | No | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
| 480 | CH-NOZ WELDING -N3A | 479 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.1116 | Hrs
| 481 | CH-NOZ WELDING-N4A | 480 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.1116 | Hrs
| 482 | CH NOZ ROOT DP CHECK | 481 | W,H |  | 14 | 407 mm | 2 | No | 2 | Nos | 1 | hr | 2 | 1 | 3 | Hrs
| 483 | CH-NOZ INNER WELD -N3A | 482 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.1492 | Hrs
| 484 | CH-NOZ INNER WELD-N4A | 483 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.1492 | Hrs
| 485 | RF PAD FIT UP & NOZ fit up | 484 | W,H |  |  | 400nb | 2 | No | 2 | Set | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 486 | RF PAD FIT UP WELDING | 485 | G,H |  | 18 |  | 2 | No | 2.5538 | Mtr | 6.8 | hr | 17.366 | 1 | 18.366 | Hrs
| 487 | NOZ WELDING FLUSH GRIND- 16"NB | 486 | G |  |  | 407 mm | 2 | NoS | 2.5538 | No | 0.15 | hr | 0.38307 | 1 | 1.3831 | Hrs
488 | 488 | CH PP PLATE FIT UP | 478
| 489 | CH- PP PLATE FIT UP | 488 | F[2],H,W |  | 24 | 14465 | 1 | No | 14.465 | Nos | 0.5 | hr | 7.2325 | 1 | 8.2325 | Hrs | 14465
| 490 | CH- PP PLATE FIT UP INSP | 489 | F,H |  | 24 | 1560 id | 3 | No | 4 | Nos | 0.5 | hr | 2 | 1 | 3 | Hrs
491 | 491 | CH PP PLATE WELDING | 488
| 492 | CH- PP PLATE WELDING | 491 | W,H |  | 24 | 1480 | 3 | No | 4.44 |  | 11.2 | hr | 49.728 | 1 | 50.728 | Hrs
| 493 | CH- PP PLATE FACE GRINDING | 492 | G,H |  | 12 | 12310 mm | 1 | No | 12.31 | No | 1.6 | hr | 19.696 | 1 | 20.696 | Hrs | 12310
494 | 494 | CH DAVIT ARM WELDING | 491
| 495 | CH-DAVIT ARM arm match | 494 | F,H |  | 18 | 1480 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 496 | CH-DAVIT ARM FIT UP | 495 | F,W,H |  | 18 | 1251 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 497 | CH-DAVIT ARM WELDING | 496 | W,H |  | 12 | 6 | 1 | No | 6 | mtr | 1.6 | hr | 9.6 | 1 | 10.6 | Hrs
498 | 498 | CH NDE & PWHT | 494
| 499 | CH ALL WELDING DRESSUP & DP CHECK | 498 | G[2] |  | 18 | 1480lg | 1 | No | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 500 | CH-CH NDE CLEARENCE | 499 | F |  | 18 | 1480lg | 1 | No | 1 | No | 1 | Day | 1 |  | 1 | Hrs
501 | 501 | BARREL FABRICATION | 498
502 | 502 | BARREL SH PLATE CUTTING & EP | 7 |  |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Hr
| 503 | BARREL PLATE TRNASFER | 502 | T |  | 18 | 373 mm | 1 | Nos | 0.373 | mtr | 0.1 | Hr/mtr | 0.0373 | 1 | 1.0373 | Hr
| 504 | BARREL-MARKING | 503 | F,H[2] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.25 | Hr/mtr | 2.825 | 1 | 3.825 | Hr
| 505 | BARREL-CUTTING | 504 | C,H |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.15 | Hr/mtr | 1.695 | 1 | 2.695 | Hr
| 506 | BARREL PL SIDE GRINDING | 505 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.5 | Hr/mtr | 5.65 | 1 | 6.65 | Hr
| 507 | BARREL-BEVELLING CIR SIDE | 506 | F,H[3] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hr
| 508 | CH EP GRINDING | 507 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hr
509 | 509 | BARREL SHELL ROLLING | 502
| 510 | BARREL-PRE BEND | 509 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hr
| 511 | BARREL-PRE BEND CUT OFF | 510 | F[2],C |  | 18 | 1664 mm id | 1 | Nos | 3.328 | No | 0.3 | hr | 0.9984 | 1 | 1.9984 | Hr
| 512 | BARREL -PRE LS EP | 511 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.328 | Hr
| 513 | BARREL-ROLLING | 512 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hr
514 | 514 | BARREL SHELL LS FIT UP | 509
| 515 | BARREL-LS CORRECTION | 514 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.328 | Hr
| 516 | BARREL-LS FIT UP | 515 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.664 | Hr
517 | 517 | BARREL SHELL LS WELDING | 514
| 518 | BARREL-LS WELD ARRANGEMENT | 517 | F,H[2] |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hr
| 519 | BARREL-LS WELDING- TOP SIDE | 518 | W,H |  | 12 | 1664 mm id | 1 | Nos | 1.664 | mtr | 2.5 | hr | 4.16 | 1 | 5.16 | Hr
| 520 | BARREL-LS WELDING- BACK CHIP | 519 | G,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.664 | Hr
| 521 | BARREL-LS INNER WELDING | 520 | W,H |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.9 | hr | 1.4976 | 1 | 2.4976 | Hr
| 522 | BARREL-LS INNNER FLUSH GRIND | 521 | G |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.5 | hr | 0.832 | 1 | 1.832 | Hr
| 523 | BARREL RE ROLLING | 522 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hr
524 | 524 | BARREL LS WELDING RT | 517
| 525 | BAR LS WELDING RT | 524 | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
526 | 526 | BARREL SHELL CS FLG 1 FIT UP | 524
| 527 | BARREL CIR EP CORRECTION | 526 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 528 | BARREL CS FIT UP FLG1 | 527 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 529 | BARREL CS TACK DP CHECK FLG1 | 528 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | no | 0.25 | hr | 1.3071 | 1 | 2.3071 | Hrs
530 | 530 | BARREL SH CS FLG 1 WELDING | 526
| 531 | BARREL CS WELDING TRANSFERE | 530 | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 532 | BARREL CS WELDING OUTER FLG1 | 531 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.0707 | Hrs
| 533 | BARREL CS WELDING BACK CHIP FLG1 | 532 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 534 | BARREL CS INNER WELDING FLG 1 | 533 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.7055 | Hrs
| 535 | BARREL CS FLUSH GRINDING FLG1 | 534 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.6141 | Hrs
536 | 536 | BARREL CS FIT UP WITH DISH | 530
| 537 | BARREL LENGTH CUTTING | 536 | C,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 538 | BARREL EP | 537 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 539 | BARREL CS FIT UP DISH | 538 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 4 | hr | 20.9132 | 1 | 21.9132 | Hrs
| 540 | BARREL CS TACK DP CHECK DISH | 539 | F |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 3.5 | hr | 18.299 | 1 | 19.299 | Hrs
541 | 541 | BARREL CS WELDING WITH DISH | 536
| 542 | BARREL CS WELDING TRANSFERE DISH | 541 | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 543 | BARREL CS WELDING OUTER DISH | 542 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.0707 | Hrs
| 544 | BARREL CS WELDING BACK CHIP DISH | 543 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 545 | BARREL CS INNER WELDING DISH | 544 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.7055 | Hrs
| 546 | BARREL CS FLUSH GRINDING DISH | 545 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.6141 | Hrs
547 | 547 | BARREL CS FLG 1 & DISH WELDING rt | 541
| 548 | BARREL CS WELDING RT | 547 | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
549 | 549 | BARREL NOZ OREINATION MARKING | 547
| 550 | BARREL- NOZ IREIENTATION NKG | 549 | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 551 | BARREL-NOZ MARKING- 2 | 550 | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
552 | 552 | BARREL NOZ OPPENING | 549
| 553 | BARREL-NOZ OPENNING-40 NB - LWN | 552 | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 554 | BARREL-NOZ OPENNING-40 NB - LWN | 553 | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
555 | 555 | BARREL NOZ EDGE PREPARATION | 552
| 556 | BARREL-NOZ OPENNING-40 NB - LWN | 555 | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
| 557 | BARREL-NOZ OPENNING-40 NB - LWN | 556 | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
558 | 558 | BARREL NOZZZLE FIT UP | 555
| 559 | BARREL-NOZ FIT UP -N5A | 558 | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 560 | BARREL-NOZ FIT UP -N6A | 559 | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
561 | 561 | BARREL NOZ FIT UP INSPECTION | 558
| 562 | BARREL-NOZ INSPN -5A | 561 | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
| 563 | BARREL-NOZ INSPN-6A | 562 | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
564 | 564 | BARREL NOZ WELDING | 561
| 565 | BARREL NOZ WELDING ARRANGEMENT | 564 | T |  | 40NB | 40NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
| 566 | BARREL-NOZ WELDING -N5A | 565 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
| 567 | BARREL-NOZ WELDING-N6A | 566 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
| 568 | BARREL NOZ ROOT DP | 567 | F,H |  |  | 75 MM | 2 | No | 2 |  | 0.5 | hr | 1 | 1 | 2 | Hrs
| 569 | BARREL-NOZ INNER WELDING -N5A | 568 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
| 570 | BARREL-NOZ INNER WELDING-N6A | 569 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
571 | 571 | BARREL NOZ INNER WELD FLUSH GRIND | 564
| 572 | BARREL ALL WELDING DRESSUP & DP | 571 | G[2] |  | 20 | 40NB | 1 | No | 1 | NO | 8 | hr | 8 | 1 | 9 | Hrs
| 573 | BARREL-BARREL NDE CLEARENCE | 572 | F |  | STD | 40NB | 1 | NoS | 1 | No | 1 | Day | 1 |  | 1 | Hrs
574 | 574 | FL HEAD FABRICATION
575 | 575 | FLAOTING HEAD DISH FORMING | 13
| 576 | FL HEAD DISH PL ISSUE | 575 | T |  |  |  | 1 | No | 1 |  | 4 | Day | 4 |  | 4 | Hrs
| 577 | FL HEAD PL MARKING | 576 | F,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.1 | hr | 0.62337 | 1 | 1.6234 | Hrs
| 578 | FL HEAD PL STAMPING | 577 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Hr | 1 | 1 | 2 | Hrs
| 579 | FL HEAD PL CUTTING | 578 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.25 | hr | 1.5584 | 1 | 2.5584 | Hrs
| 580 | FL HEAD PL GRINDING | 579 | G |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 1 | hr | 6.2337 | 1 | 7.2337 | Hrs
581 | 581 | FL HEAD FORMIG | 575
| 582 | FL HEAD FORMING | 581 | SC |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 10 | Day | 10 |  | 10 | Hrs
| 583 | FL HEAD PROFILE CHECK | 582 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Hrs
584 | 584 | FL HEAD CUTTING | 581
| 585 | FL HEAD MARKING | 584 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 4 | Hr/No | 4 |  | 4 | Hrs
| 586 | FL HEAD CUTTING | 585 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 0.1 | hr | 0.62337 | 2 | 2.6234 | Hrs
587 | 587 | FL HEAD EP | 584
| 588 | FL HEAD GRINDING | 587 | G,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.2337 | Hrs
589 | 589 | FL HEAD FIT UP | 587
| 590 | FL HEAD FIT UP | 589 | F[2],W,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.2337 | Hrs
591 | 591 | FL HEAD WELDING | 589
| 592 | FL HEAD WELDING | 591 | W,H |  | 30 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 16.8 | hr | 104.7266 | 2 | 106.7266 | Hrs
| 593 | FL HEAD PP PLATE FIT UP | 592 | F[2],H,W |  | 16 | 1550 mm id | 1 | Nos | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 594 | FL HEAD PP PL WELDING | 593 | W,H |  | 16 | 3000 mm | 1 | Nos | 3 | Mtr | 2.8 | hr | 8.4 | 2 | 10.4 | Hrs
| 595 | FL HEAD PP PL LEVEL GRINDING | 594 | F,H |  | 16 | 3000 mm | 1 | Nos | 1 | No | 6 | hr | 6 | 1 | 7 | Hrs
| 596 | FL HEAD INSPECTION | 595 | F |  | 16 | 3000 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
597 | 597 | FL HEAD SR & MACHINING | 591
| 598 | FL HEAD SR | 597 | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 3 | Day | 3 | 0 | 3 | Hrs
| 599 | FL HEAD FINAL MACHINING | 598 | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs
| 600 | FL HEAD HOLE MARKING | 599 | F,H |  |  | 1550 mm id | 1 | Nos | 1 | No | 0.5 | Day | 0.5 | 0 | 0.5 | Hrs
| 601 | FL HEAD HOLE DRILLING | 600 | SC |  | 140 mm | 1550 mm id | 72 | hole | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs
| 602 | FL HEAD FINAL INSPECTION | 601 | F,H |  | 140 mm | 1550 mm id | 1 | No | 1 | No | 1 | Day | 1 | 0 | 1 | Hrs
603 | 603 | TUBE BUNDLE FABRICATION
604 | 604 | TUBE BUNDLE ASSY
| 605 | FRAME SET UP & TUBE SHT SET UP | 604 | F[2],W |  | 145T | 1308 tube |  |  | 1 |  | 1.5 | Day | 1.5 | 0 | 1.5 | Hrs
| 606 | SKELITON ASSY- 19 baffle | 605 | F[2],H[3] |  |  | 19 baffle | 1 | Nos | 19 | Nos | 0.5 | hr | 9.5 | 1 | 10.5 | Hrs
607 | 607 | TUBE INSERT | 604
| 608 | TUBE INSERT | 607 | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
| 609 | SEAL ROD INSERT & WELD | 608 | F[2],W,H[2] |  | 25.4 dia | 5134 lg | 14 | Nos | 14 | Nos | 0.5 | Hr/no | 7 | 1 | 8 | Hrs
| 610 | TUBE INSERT | 609 | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
611 | 611 | SLIDING STRIP FIT UP WELDING | 607
| 612 | SEALING STRIP FIT UP | 611 | F,H |  | 8 | 4592 mm lg | 2 | Nos | 2 | Nos | 3 | Hr/no | 6 | 1 | 7 | Hrs
| 613 | SLIDING STRIP WELDING | 612 | W,H |  | 8 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
| 614 | SEALING TRIP WELD GRIND | 613 | G |  | 1500 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
615 | 615 | TUBE BUNDLE INSERT | 611
| 616 | TUBE BUNDLE INSERT IN SHELL | 615 | F[3],H[8] |  |  | 7000 LG | 1 | Nos | 1 | Nos | 16 | Hr/no | 16 | 1 | 17 | Hrs
| 617 | FL HEAD TUBE SHT FIXING | 616 | F[2],H[4] |  | 145MM |  | 1 | Nos | 1 | Nos | 4 | Hr/no | 4 | 1 | 5 | Hrs
| 618 | TEST FLG & GLAND ASSY | 617 | F[3],H[6] |  | 165 MM | 1490 | 1 | Nos | 56 | Bolts | 0.16667 | hr | 9.3333 | 1 | 10.3333 | Hrs
619 | 619 | TUBE EXPANSION IN GROOVES | 615
| 620 | TUBE EXP - ST SIDE - 1 STAGE | 619 | F,H[2] |  | 150 mm | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.016667 | hr | 21.8 | 1 | 22.8 | Hrs
| 621 | TUBE EXP - FL SIDE - 1 STAGE | 620 | F,H[2] |  | Servo | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.0083333 | hr | 10.9 | 1 | 11.9 | Hrs
| 622 | TUBE TRIMMING FL SIDE | 621 | F,H |  | Servo | 1308 nos | 1308 | Nos | 1308 | Trimm | 0.033333 | hr | 43.6 | 1 | 44.6 | Hrs
| 623 | TUBE EXP BOTH SIDE - 4 STAGE | 622 | F[2],H[2] |  | 150MM | 2616 Roll | 2616 | Nos | 2616 | Rolling | 0.0083333 | hr | 21.8 | 1 | 22.8 | Hrs
624 | 624 | TUBE EXP- PNUEMATIC TEST | 619
| 625 | TUBE EXP PNUEMATIC TEST | 624 | F[2],H[2] |  |  |  | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
| 626 | PNUEMATIC TEST TPI WITNESS | 625 | F,H |  |  |  | 1 | No | 1 | Test | 1 | Day | 1 |  | 1 | Hrs
| 627 | CLEANING | 626 | F,H[3] |  |  |  | 1 | No | 1 | No | 1 | Hr | 1 |  | 1 | Hrs
628 | 628 | TUBE TUBE SHEET WELDING- FT SIDE | 624
| 629 | TUBE WELDING - ST SIDE ROOT | 628 | TW,H |  | 2.77 | 25.4 od | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 630 | TUBE WELDING - ST SIDE ROOT DP | 629 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 631 | TUBE WELDING - ST SIDE FINAL WELD | 630 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 632 | TUBE WELDING - ST SIDE FINAL DP | 631 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
633 | 633 | TUBE TO TUBE SHEET WELDING - FL HEAD SIDE | 628
| 634 | TUBE WELDING - FLH SIDE ROOT | 633 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 635 | TUBE WELDING - FLH SIDE ROOT DP | 634 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 636 | TUBE WELDING - FLH SIDE FINAL WELD | 635 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 637 | TUBE WELDING - FLH SIDE FINAL DP | 636 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
638 | 638 | SH SIDE HYDRO
639 | 639 | SH SIDE WATER FILLING | [5 empty] | 1 | No | 1 | Hrs | 6 | Hrs | 6 |  | 6 | Hrs
| 640 | SH SIDE HYDRO | 639 | F[2],H[2] |  |  | 6130 lg | 1 | No | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs
| 641 | SH SIDE TPI WITNESS | 640 | F[2] |  |  | 6130 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day
| 642 | DE WATERING & DISMANTLE OF GLAND | 641 | F[2],H[4] |  |  | 6130 lg | 1 | No | 1 | Test | 8 | hr | 8 | 0 | 8 | Hrs
643 | 643 | 133-EE-1006-B
644 | 644 | DISH FORMING - 24T*1700 OD | 628
| 645 | BARREL DISH BLANK ISSUENCE |  | T |  | 24 | ID dish | 1 | No | 1 | nos | 4 | Day | 4 |  | 4 | Days
| 646 | BARREL-DISH BLANK MARKING - 24 * 1670 OD | 645 | F,H |  | 24 | 6723 MM | 1 | No | 6.723 | Dia-mtr | 0.1 | Hr/mtr | 0.6723 | 1 | 1.6723 | Hr
| 647 | BARREL-DISH BLANK MARKING INSPECTION | 646 | F,H |  | 24 |  | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days
| 648 | BARREL-DISH BLANK CUTTING | 647 | C,H |  | 24 | 6723 MM | 1 | no | 6.723 | Dia-mtr | 0.25 | RMT | 1.6807 | 1 | 2.6807 | Hr
| 649 | BARREL-DISH FORMING | 648 | SC |  | 24 | 1664 id | 1 | no | 1 | No | 10 | Day | 10 |  | 10 | Days
| 650 | PROFILE INSP | 649 | F,H |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1 | Days
| 651 | HEAT TREATMENT PREPARATION | 650 | SC |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 652 | STRESS RELEIVING- SUB CONT | 651 | SC |  | 24 | 1664 id | 1 | no | 1 | No | 4 | Day | 4 |  | 4
| 653 | REMOVAL OF SPIDERS | 652 | F,H |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 654 | SURFACE PREPARATION | 653 | G |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 | 1 | 2 | 1
| 655 | INSPECTION | 654 | F |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 656 | TPI INSPECTION | 655 | F |  | 24 | 1664 id | 1 | no | 1 | No | 1 | Day | 1 |  | 1
| 657 | SF MARKING | 656 | F,H | enter | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 0.1 | RMT | 0.53163 | 1 | 1.5316 | Hr
| 658 | SF CUTTING | 657 | C,H |  | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 1 | RMT | 5.3163 | 1 | 6.3163 | Hr
| 659 | SF GRIDNING & EP | 658 | G |  | 24 | 1692 od | 1 | no | 5.3163 | Rmt | 1 | RMT | 5.3163 |  | 5.3163 | Hr
660 | 660 | TUBE SHEET
661 | 661 | TUBE SHEET MACHINING 1 OFF 2 | 629
| 662 | INWARD INSPECTION |  |  | enter | 145 t | 1670 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | day
| 663 | TUBE SHEET M/C - 1/2 | 662 | SC |  | 145 t | 1548 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | day
664 | 664 | TUBE SHEET DRILLING 1 OFF 2 | 661
| 665 | TUBE SHEET DRILLING -1/2 | 664 | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.2683 | Day
| 666 | EXP GROOVE+WELDING GROOVE -1/2 | 665 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.5417 | Day
| 667 | TIE ROD, PULLING, LIFTING HOLE - 1/2 | 666 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Day
| 668 | PASS PARTITION GROOVE M/C -1/2 | 667 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Day
| 669 | CLEANING ,GO/NO GO CHECK -1/2 | 668 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs
| 670 | FINAL INSPECTION -1/2 | 669 | F,H
671 | 671 | TUBE SHEET MACHINING 2 OFF 2 | 629
| 672 | INWARD INSPECTION | 671 |  |  | 145 t | 1670 od | 1 | No | 1 | no | 2 | Day | 2 |  | 2 | day
| 673 | TUBE SHEET M/C - 2/2 | 672 | SC |  | 145 t | 1548 od | 1 | No | 1 | no | 5 | Day | 5 |  | 5 | day
674 | 674 | TUBE SHEET DRILLING 2 OFF 2
| 675 | TUBE SHEET DRILLING -2/2 | 665 | SC |  | 145 t | 1308 holes | 1 | No | 189.66 | rmt | 0.66667 | Hr/mtr | 5.2683 |  | 5.2683 | Day
| 676 | EXP GROOVE+WELDING GROOVE -2/2 | 675 | SC |  | 145 t | 1308 holes | 1 | nos | 1308 | Nos | 0.083333 | Hr/mtr | 4.5417 |  | 4.5417 | Day
| 677 | TIE ROD, PULLING, LIFTING HOLE - 2/2 | 676 | SC |  | 145 t |  | 1 | set | 1 | Set | 1 | Day | 1 |  | 1 | Day
| 678 | PASS PARTITION GROOVE M/C -2/2 | 677 | SC |  | 145 t |  | 1 | set | 1 | Set | 4 | Day | 4 |  | 4 | Day
| 679 | CLEANING ,GO/NO GO CHECK -2/2 | 678 | F,H |  | 145 t | 1308 holes | 1 | nos | 1308 | nos | 0.05 | Hr/no | 65.4 |  | 65.4 | Hrs
| 680 | FINAL INSPECTION -2/2 | 679 | F,H |  |  |  | 1 |  | 1050 | nos | 0.05 | RMT | 52.5 | 1 | 53.5 | 1
681 | 681 | NOZ FAB | 638
682 | 682 | SH NOZ PIPE MARKING | 622
| 683 | 26"NB SRN - 2 NOS | 682 | F,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 684 | 2" MP CON - 2 NO | 683 | F,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 685 | INSPECTION OF MARKING | 684 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs
686 | 686 | SH NOZ PIPE CUTTING | 682
| 687 | 26"NB SRN - 2 NOS | 686 | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 688 | 2" MP CON - 2 NO | 687 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 689 | INSPECTION OF MARKING | 688 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
690 | 690 | SH NOZ PIPE EP | 686
| 691 | 26"NB SRN - 2 NOS | 690 | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
| 692 | 2" MP CON - 2 NO | 691 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 693 | INSPECTION | 692 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
694 | 694 | SH NOZ+FLG FIITUP | 690
| 695 | 26"NB SRN - 2 NOS | 694 | F[2],W,H[2] |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs
| 696 | 2" MP CON - 2 NO | 695 | F[2],W,H[2] |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs
| 697 | INSPECTION | 696 | F[2],W,H[2] |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
698 | 698 | SH NOZ PIPE+FLG WELDING | 694
| 699 | 26"NB SRN - 2 NOS | 698 | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.381 | Hrs
| 700 | 2" MP CON - 2 NO | 699 | W,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 |  | 0 | Hrs
| 701 | INSPECTION | 700 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
702 | 702 | SH NOZ PIPE PROFILE MARKING | 698
| 703 | 26"NB SRN - 2 NOS | 702 | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs
| 704 | 2" MP CON - 2 NO | 703 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
| 705 | INSPECTION | 704 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
706 | 706 | SH NOZ PIPE PROFILE CUTTING | 702
| 707 | 26"NB SRN - 2 NOS | 706 | G,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 708 | 2" MP CON - 2 NO | 707 | G,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 709 | INSPECTION | 708 | G,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
710 | 710 | SH NOZ PIPE PR0FILE EP | 706
| 711 | 26"NB SRN - 2 NOS | 710 | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.108 | Hrs
| 712 | 2" MP CON - 2 NO | 711 | G,H |  | 18 | 272 mm | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.272 | Hrs
| 713 | INSPECTION | 712 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
714 | 714 | CH NOZ PIPE MARKING | 710
| 715 | 16"NB SRN - 2 NOS | 714 | F,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 716 | 2" MP CON - 2 NO | 715 | F,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 1 |  | 2 | 1 | 3 | Hrs
| 717 | INSPECTION | 716 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 |  | 2 | 1 | 3 | Hrs
718 | 718 | CH NOZ PIPE CUTTING | 714
| 719 | 16"NB SRN - 2 NOS | 718 | C,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 720 | 2" MP CON - 2 NO | 719 | C,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 721 | INSPECTION | 720 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
722 | 722 | CH NOZ PIPE EP | 718
| 723 | 16"NB SRN - 2 NOS | 722 | G,H |  | 26" nb |  | 2 | Nos | 2 | Nos | 4 |  | 8 | 0 | 8 | Hrs
| 724 | 2" MP CON - 2 NO | 723 | G,H |  | 2"nb |  | 2 | Nos | 2 | Nos | 0 |  | 0 | 0 | 0 | Hrs
| 725 | INSPECTION | 724 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0 |  | 0 | 0 | 0 | Hrs
726 | 726 | CH NOZ+FLG FIT UP | 722
| 727 | 16"NB SRN - 2 NOS | 726 | F[2],W,H[2] |  | 26" nb |  | 2 | no | 2 | no | 4 | hr | 8 | 1 | 9 | Hrs
| 728 | 2" MP CON - 2 NO | 727 | F[2],W,H[2] |  | 2"nb |  | 2 | no | 2 | no | 0 | hr | 0 | 1 | 1 | Hrs
| 729 | INSPECTION | 728 | F[2],W,H[2] |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
730 | 730 | CH NOZ PIPE+FLG WELDING | 726
| 731 | 16"NB SRN - 2 NOS | 730 | W,H |  | 18 t | 3054 mm | 2 | no | 6.108 | no | 6.12 | hr | 37.381 | 1 | 38.381 | Hrs
| 732 | 2" MP CON - 2 NO | 731 | W,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 |  | 0 | Hrs
| 733 | INSPECTION | 732 | W,H |  |  |  | 4 | no | 4 | no | 0.25 | hr | 1 | 1 | 2 | Hrs
734 | 734 | CH NOZ PIPE PROFILE MARKING | 730
| 735 | 16"NB SRN - 2 NOS | 734 | F,H |  | 26" nb |  | 2 | no | 1 | no | 4 | hr | 4 | 1 | 5 | Hrs
| 736 | 2" MP CON - 2 NO | 735 | F,H |  | 2"nb |  | 2 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
| 737 | INSPECTION | 736 | F,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
738 | 738 | CH NOZ PIPE PROFILE CUTTING | 734
| 739 | 16"NB SRN - 2 NOS | 738 | F,H |  | 26" nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 740 | 2" MP CON - 2 NO | 739 | F,H |  | 2"nb |  | 2 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
| 741 | INSPECTION | 740 | F,H |  |  |  | 4 | no | 0 | no |  | hr | 0 | 1 | 1 | Hrs
742 | 742 | CH NOZ PIPE PR0FILE EP | 738
| 743 | 16"NB SRN - 2 NOS | 742 | G,H |  | 18t | 3054 mm | 2 | no | 6.108 | no | 1 | hr | 6.108 | 1 | 7.108 | Hrs
| 744 | 2" MP CON - 2 NO | 743 | G,H |  | 18 | 272 mm | 2 | no | 0.544 | no | 0.5 | hr | 0.272 | 1 | 1.272 | Hrs
| 745 | INSPECTION | 744 | G,H |  |  |  | 4 | no | 1 | no | 1 | hr | 1 | 1 | 2 | Hrs
746 | 746 | SADDLE & OTHER | 742
747 | 747 | TOP SADDLE FABRRICATION | 746
| 748 | PLATE ISSUENCE | 747 |  |  |  |  | 1 | Set | 1 | Set | 4 | Day | 4 | 0 | 4 | Day
| 749 | BASE MARKING | 748 | F,H |  | 30/25 | 9 rmt | 1 | Set | 9 | mtr | 0.25 | hr | 2.25 | 1 | 3.25 | Hr
| 750 | WEB PL MARKING | 749 | F,H |  | 30/25 | 29 rmt | 1 | Set | 29 | mtr | 0.25 | hr | 7.25 | 1 | 8.25 | Hr
| 751 | RIBS MARKING | 750 | F,H |  | 25 | 10.5 Rmt | 1 | Set | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.625 | Hr
752 | 752 | TOP SADLLE PLATE CUTTING | 747
| 753 | BASE CUTTING | 752 | C,H |  | 30/25 | 9 rmt | 1 | Nos | 9 | mtr | 0.5 | hr | 4.5 | 1 | 5.5 | Hrs
| 754 | WEB PL CUTTING | 753 | C,H |  | 30/25 | 29 rmt | 1 | Nos | 29 | mtr | 0.5 | hr | 14.5 | 1 | 15.5 | Hrs
| 755 | RIBS CUTTING | 754 | C,H |  | 25 | 10.5 Rmt | 1 | Nos | 10.5 | mtr | 0.25 | hr | 2.625 | 1 | 3.625 | Hrs
| 756 | GRINNDING OF ABOVE | 755 | G[2] |  | 25 |  |  |  | 48.5 | mtr | 0.15 | hr | 7.275 | 1 | 8.275 | Hrs
757 | 757 | SADDLE FIT UP & WELDING | 752
| 758 | BASE + WEB FIT UP | 757 | F[2],H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 759 | BASE + WEB WELDING | 758 | W,H |  | 18 |  | 1 | Set | 4 | No | 3.4 | hr | 13.6 | 1 | 14.6 | Hrs
| 760 | RIBS+WEB FIT UP | 759 | F[2],H[2],W |  |  |  | 1 | Set | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 761 | RIBS+WEB WELDING | 760 | W[2],H[2] |  | 18 |  | 1 | Set | 24.8 | No | 3.4 | hr | 84.32 | 1 | 85.32 | Hrs
762 | 762 | DAVIT PIPE FABRICATION | 757
| 763 | PIPE TRANSFERE | 762 | H[4] |  |  |  | 1 | SET | 1 | SET | 4 | Day | 4 |  | 4 | Days
| 764 | PIPE MARKING - 6 NOS | 763 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
| 765 | SUPPORT PL MARKING | 764 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 766 | GUSSET PL MARKING | 765 | F,H |  | 16 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 767 | BASE HUB MARKING | 766 | F,H |  | 30 |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 768 | PIPE CUTTING - 6 NOS | 767 | C,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
| 769 | SUPPORT PL CUTTING | 768 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 770 | PIPE GRINDING - 6 NOS | 769 | F,H |  |  |  | 6 | Nos | 6 | Nos | 0.5 | Hr | 3 |  | 3 | Hrs
| 771 | SUPPORT PL GRINDING-10 NOS | 770 | G |  |  |  | 10 | Nos | 10 | Nos | 0.5 | Hr | 5 |  | 5 | Hrs
| 772 | PIVOT PL GRINDING | 771 | G |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 773 | PIPE FIT UP-2 NOS | 772 | F,H,W |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 774 | PIPE WELDING -2 NOS | 773 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 775 | PIVOT PL WELDING | 774 | W,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hrs
| 776 | SUPPORT PL WELDING -4 NOS | 775 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
777 | 777 | LIFTING LUG PAD | 762
| 778 | PLATE ISSUENCE | 777 |  |  |  |  | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days
| 779 | LIFTING LUG PAD MARKING | 778 | F,H |  | 18 |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 780 | LIFTING LUG PAD CUTTING | 779 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 781 | LIFTING LUGS PAD GRINDING | 780 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
782 | 782 | LIFTING LUG PREPARATION | 777
| 783 | LIFTING LUGS MARKING | 782 | F,H |  | 24 |  | 1 | SET | 1 | SET | 4 | dAY | 4 |  | 4 | Days
| 784 | LIFTING LUGS CUTTING | 783 | C,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 785 | LIFTING LUGS GRINDING | 784 | G,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
| 786 | LIFTING LUG DRILLING | 785 | F,H |  |  |  | 4 | Nos | 4 | Nos | 0.5 | Hr | 2 |  | 2 | Hrs
787 | 787 | CH COVER HANDLE PREPATAION | 782
| 788 | CH COVER RING FORMING | 787 | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days
| 789 | SLIDING SLING FORMING | 788 | F,H |  |  |  | 4 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Days
790 | 790 | INSULATION RING PRPARATION | 787
| 791 | INSULAION RING MARKING | 790 | F,H |  | 12 |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs
| 792 | INSULAION RING CUTTING | 791 | C,H |  |  |  | 1 | Nos | 1 | Nos | 4 | Hr | 4 |  | 4 | Hrs
| 793 | INSULAION RING HOLE MARKING | 792 | F,H |  |  |  | 1 | Nos | 1 | Nos | 2 | Hr | 2 |  | 2 | Hrs
| 794 | INSULAION RING HOLE DRILLING | 793 | F,H |  |  |  | 1 | Nos | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
795 | 795 | BAFFLE & TB ITEMS FAB | 794
796 | 796 | BAFFLE PREPARATION | 795
| 797 | BAFFLE PLATE TRANSFER | 796 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
| 798 | BAFFLE MARKING | 797 | F,H |  | 14 |  | 19 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Hrs
| 799 | BAFFLE PROFILE CUTTING | 798 | C,H |  |  |  | 19 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Hrs
800 | 800 | BAFFLE BEND REMOVAL & STACKING | 796
| 801 | BAFFLE PL BEND REMOVAL | 800 | F,H[2] |  |  |  | 19 | Nos | 19 | Nos | 1 | Hr | 19 |  | 19 | Hrs
| 802 | BAFFLE PL STACKING | 801 | F,H |  |  | 3 bundle | 3 | Nos | 3 | Nos | 2 | Hr | 6 |  | 6 | Hrs
803 | 803 | BAFFLE DRILLING | 800
| 804 | BAFFLE DRILLING | 803 | SC |  | 14 thk |  | 3 | Bunch | 1 | Set | 10 | Day | 10 |  | 10 | Day
805 | 805 | BAFFLE DE STACKING & CHAMFERING | 803
| 806 | BAFFLE DE STACING | 805 | F,H |  |  |  | 3 | Bunch | 4 | Bunch | 6 | Hrs | 24 |  | 24 | Hr
| 807 | BAFFLE CHAMFERING | 806 | F |  |  |  | 9 | Nos | 23544 | holes | 0.01 |  | 235.44 |  | 14.715 | Days
808 | 808 | BAFFLE STACKING & THRO HOLE CHECK | 805
| 809 | STACKING | 808 | F,H |  |  |  | 3 | Nos | 3 | Nos | 0.25 | Hr | 0.75 |  | 0.75 | Hrs
| 810 | BAFFLE HOLE ALINGMENT | 809 | F,H |  |  |  | 3 | Nos | 1 | SET | 1 | Hrs | 1 |  | 1 | Hrs
| 811 | BAFFLE HOLE RE DRILL | 810 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Day
| 812 | BAFFLE OD MACHINING | 811 | SC |  |  |  | 3 | Nos | 1 | SET | 5 | Day | 5 |  | 5 | Day
| 813 | BAFFLE CLEANING | 812 | H[3] |  |  |  | 3 | Nos | 1 | SET | 1 | Day | 1 |  | 1 | Day
814 | 814 | SUPPORT PLATE MARKING | 808
| 815 | SUPPORT PLATE TRANSFER | 814 |  |  |  |  | 2 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Days
| 816 | SUPPORT MARKING | 815 | SC |  | 20 |  | 2 | Nos | 1 | Set | 1 | Day | 1 |  | 1 | Days
| 817 | SUPPORT PROFILE CUTTING | 816 | SC |  |  |  | 2 | Nos | 1 | Set | 5 | Day | 5 |  | 5 | Days
818 | 818 | SUPPORT PLATE BEND REMOVAL | 814
| 819 | SUPPORT PL BEND REMOVAL | 818 | F,H[3] |  |  |  | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hr
| 820 | SUPPORT PL STACKING | 819 | F,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | Hr | 1 |  | 1 | Hr
821 | 821 | SUPPORT PLATE DRLINNG | 818
| 822 | SUPPORT DRILLING | 821 | SC |  | 20THK |  | 1 | Bunch | 1 | Set | 10 | Day | 10 |  | 10
823 | 823 | SUP PLATE DE STACKING & CHAMFERING | 821
| 824 | SUPPORT DE STACING | 823 | F,H |  |  |  | 1 | Bunch | 1 | Bunch | 3 | Hrs | 3 |  | 3 | Hrs
| 825 | SUPPORT HOLE CHAMFERING | 824 | F |  |  |  | 2 | Plate | 2616 | holes | 0.01 |  | 26.16 |  | 26.16
826 | 826 | TIE ROD PREPARATION | 641
| 827 | TIE ROD MATL TRANSFERE | 826 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Day
| 828 | ROD CUTTING | 827 | F,H |  |  |  | 22 | Nos | 22 | noS | 0.25 | Hr | 5.5 |  | 5.5 | Hrs
| 829 | THREAD MACHINING. | 828 | L |  |  |  | 22 | Nos | 22 | Nos | 0.45 | Hr | 9.9 |  | 9.9 | Hra
| 830 | JOINING | 829 | W,F,H |  |  |  | 22 | Nos | 22 | Nos | 0.5 | Hr | 11 |  | 11 | Hrs
831 | 831 | SPACER TUBE PREPARATION | 640
| 832 | SPACER TUBE TRANSFERE | 831 |  |  |  |  | 1 | Nos | 1 | Set | 4 | Day | 4 |  | 4 | Hrs
| 833 | LENGTH CUTTING 237NOS | 832 | F,H |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs
| 834 | LENNGTH MACHINING | 833 | L |  |  |  | 414 | Nos | 414 | noS | 0.1 | Hr | 41.4 |  | 41.4 | Hrs
| 835 | CLEANINNG | 834 | H[3] |  |  |  | 414 | Nos | 414 | Nos | 0.016667 | Hr | 6.9 |  | 6.9 | Hrs
836 | 836 | SEALING STRIP PREPARATION | 635
| 837 | SEALING STRIP MARKING | 836 | F,H |  | 8 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.1 | Hr | 1.9044 |  | 1.9044 | Hrs
| 838 | SEALING STRIP CUTTING | 837 | C,H |  | 25 | 9522 mm | 2 | Nos | 19.044 | Mtr | 0.25 | Hr | 4.761 |  | 4.761 | Hrs
| 839 | SEALING STRIP BEND REMOVAL | 838 | F,H[2] |  | 25 | 9522 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
| 840 | SEALING STRIP GRINDING | 839 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
| 841 | SEALING STRIP JOINING | 840 | W,F,H |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
| 842 | SEALING STRIP DRESS UP | 841 | G |  | 25 | 9522 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
843 | 843 | SLIDING STRIP PREPARATION | 636
| 844 | SLIDING STRIP MARKING | 843 | F,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.1 | Hr | 2.6732 |  | 2.6732 | Hrs
| 845 | SLIDING STRIP CUTTING | 844 | C,H |  | 8 | 13366 mm | 2 | Nos | 26.732 | Mtr | 0.25 | Hr | 6.683 |  | 6.683 | Hrs
| 846 | SLIDING STRIP BEND REMOVAL | 845 | F,H[2] |  | 8 | 13366 mm | 2 | Nos | 2 | Nos | 2 | Hr | 4 |  | 4 | Hrs
| 847 | SLIDING STRIP GRINDING | 846 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 4 | Hr | 16 |  | 16 | Hrs
| 848 | SLIDING STRIP JOINING | 847 | W,F,H |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
| 849 | SLIDING STRIP DRESS UP | 848 | G |  | 8 | 13366 mm | 2 | Nos | 4 | Nos | 1 | Hr | 4 |  | 4 | Hrs
850 | 850 | SEAL ROD PREPARATION | 637
| 851 | SEAL ROD ISSUENECE | 850 | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Days
| 852 | SEAL ROD MARKING | 851 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.25 | Hr | 3.5 |  | 3.5 | Hrs
| 853 | SEAL ROD CUTTING | 852 | F,H |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 0.5 | Hr | 7 |  | 7 | Hrs
| 854 | SEAL ROD BEND REMOVAL | 853 | F,H[2] |  | 25.4 dia | 14 | 14 | Nos | 14 | Nos | 1 | Hr | 14 |  | 14 | Hrs
855 | 855 | SHELL FABRICATION | 854
856 | 856 | SH MARKING & CUTTING | 622
| 857 | SH PLATE TRNASFER | 856 | T |  |  |  | 1 | Set | 1 |  | 4 | Day | 4 |  | 4 | Day
| 858 | SH-MARKING | 857 | F,H[2] |  | 18 | 43000 mm | 1 | Nos | 43 | mtr | 0.1 | hr | 4.3 | 1 | 5.3 | Hrs
859 | 859 | SH PLATE CUTTING | 856
| 860 | SH-CUTTING | 859 | C,H[2] |  | 18 | 43000 mm | 3 | Nos | 129 | mtr | 0.25 | hr | 32.25 | 1 | 33.25 | Hrs
861 | 861 | SH PL SIDE GRINDING | 859
| 862 | SH PL SIDE BEVEL CUTTING | 861 | F,H[3] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 863 | SH PL SIDE BEVEL CUTTING | 862 | F,H[3] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 864 | SH PL SIDE BEVEL CUTTING | 863 | F,H[3] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.625 | Hrs
| 865 | SH PL SIDE BEVEL CUTTING | 864 | F,H[3] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 |  | 0 | Hrs
866 | 866 | SH PLATE EDGE PREPARATION | 861
| 867 | SH-BEVEL GRINDING | 866 | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 868 | SH-BEVEL GRINDING | 867 | G,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 869 | SH-BEVEL GRINDING | 868 | G,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 870 | SH-BEVEL GRINDING | 869 | G,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
871 | 871 | SH PRE BENDING | 866
| 872 | SH-PRE BEND | 871 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 873 | SH-PRE BEND | 872 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 874 | SH-PRE BEND | 873 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 875 | SH-PRE BEND | 874 | F[2],H |  | 18 | 0 mm | 0 | Nos | 0 | No | 0 | hr | 0 |  | 0 | Hrs
876 | 876 | SH PL PRE BEND CUT OFF | 871
| 877 | SH-PRE BEND CUT OFF | 876 | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 878 | SH-PRE BEND CUT OFF | 877 | F[2],H,C |  | 18 | 2500 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 879 | SH-PRE BEND CUT OFF | 878 | F[2],H,C |  | 18 | 1250 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 880 | SH-PRE BEND CUT OFF | 879 | F[2],H,C |  | 18 | 0 mm | 1 | Nos | 0 | Nos | 3 | hr | 0 | 1 | 1 | Hrs
881 | 881 | SH PLATE LS EP | 876
| 882 | SH-PRE BEND LS EP | 881 | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 883 | SH-PRE BEND LS EP | 882 | F,H |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 884 | SH-PRE BEND LS EP | 883 | F,H |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 885 | SH-PRE BEND LS EP | 884 | F,H |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
886 | 886 | SH ROLLING | 881
| 887 | SH-ROLLING 1/4 | 886 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 888 | SH-ROLLING | 887 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 889 | SH-ROLLING | 888 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 890 | SH-ROLLING | 889 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
891 | 891 | SH CIR LENGTH & EP CORRECTION | 886 | [10 empty] | 0 |  | 0
| 892 | SH-LS CORRECTION | 891 | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 893 | SH-LS CORRECTION | 892 | F,H[2] |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 894 | SH-LS CORRECTION | 893 | F,H[2] |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 895 | SH-LS CORRECTION | 894 | F,H[2] |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
896 | 896 | SH LS SEAMS FIT UP | 891 | [10 empty] | 0 |  | 0
| 897 | SH-LS FIT UP | 896 |  |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 898 | SH-LS FIT UP | 897 | F[2],H,W |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 899 | SH-LS FIT UP | 898 | F[2],H,W |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 900 | SH-LS FIT UP | 899 | F[2],H,W |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
901 | 901 | SH LS WELDING ARRANGEMENT | 896
| 902 | SH-LS WELD ARRANGEMENT | 901 | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 903 | SH-LS WELD ARRANGEMENT | 902 | F,H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 904 | SH-LS WELD ARRANGEMENT | 903 | F,H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 905 | SH-LS WELD ARRANGEMENT | 904 | F,H |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
906 | 906 | SH LONG SEAM OUTER WELDING | 901
| 907 | SH-LS WELDING- TOP SIDE | 906 | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
| 908 | SH-LS WELDING- TOP SIDE | 907 | W,H |  | 12 | 2500 mm | 1 | Nos | 2.5 | mtr | 2.5 | hr | 6.25 | 1 | 7.25 | Hrs
| 909 | SH-LS WELDING- TOP SIDE | 908 | W,H |  | 12 | 1250 mm | 1 | Nos | 1.25 | mtr | 2.5 | hr | 3.125 | 1 | 4.125 | Hrs
| 910 | SH-LS WELDING- TOP SIDE | 909 | W,H |  | 12 | 0 mm | 1 | Nos | 0 | mtr | 2.5 | hr | 0 | 1 | 1 | Hrs
911 | 911 | SH LS BACK CHIP | 906
| 912 | SH-LS WELDING- BACK CHIP | 911 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 913 | SH-LS WELDING- BACK CHIP | 912 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 1 | hr | 2.5 | 1 | 3.5 | Hrs
| 914 | SH-LS WELDING- BACK CHIP | 913 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 1 | hr | 1.25 | 1 | 2.25 | Hrs
| 915 | SH-LS WELDING- BACK CHIP | 914 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
916 | 916 | SH LS INNER WELDING | 911
| 917 | SH-LS INNER WELDING | 916 | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
| 918 | SH-LS INNER WELDING | 917 | W,H |  | 6 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.9 | hr | 2.25 | 1 | 3.25 | Hrs
| 919 | SH-LS INNER WELDING | 918 | W,H |  | 6 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.9 | hr | 1.125 | 1 | 2.125 | Hrs
| 920 | SH-LS INNER WELDING | 919 | W,H |  | 6 | 0 mm | 1 | Nos | 0 | mtr | 0.9 | hr | 0 | 1 | 1 | Hrs
921 | 921 | SH INNER LS FLUSH GRINDING | 916
| 922 | SH INNER FLUSH GRINDING | 921 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 923 | SH INNER FLUSH GRINDING | 922 | G |  | 18 | 2500 mm | 1 | Nos | 2.5 | mtr | 0.5 | hr | 1.25 | 1 | 2.25 | Hrs
| 924 | SH INNER FLUSH GRINDING | 923 | G |  | 18 | 1250 mm | 1 | Nos | 1.25 | mtr | 0.5 | hr | 0.625 | 1 | 1.625 | Hrs
| 925 | SH INNER FLUSH GRINDING | 924 | G |  | 18 | 0 mm | 1 | Nos | 0 | mtr | 0.5 | hr | 0 | 1 | 1 | Hrs
926 | 926 | SH LS RADIOGRAPHY | 921
| 927 | SH LS WELDING RT | 926 | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
| 928 | SH LS WELDING RT | 927 | RT |  | 18 | 2500 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
| 929 | SH LS WELDING RT | 928 | RT |  | 18 | 1250 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
| 930 | SH LS WELDING RT | 929 | RT |  | 18 | 0 mm | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
931 | 931 | SH RE ROLLING | 926 | [10 empty] | 0
| 932 | SH RE ROLLING | 931 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 933 | SH RE ROLLING | 932 | F[2],H |  | 18 | 2500 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 934 | SH RE ROLLING | 933 | F[2],H |  | 18 | 1250 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
| 935 | SH RE ROLLING | 934 | F[2],H |  | 18 | 0 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
936 | 936 | SH PLATE CS EP CORRECTION | 931
| 937 | SH CIR EP CORRECTION | 936 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 938 | SH CIR EP CORRECTION | 937 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 939 | SH CIR EP CORRECTION | 938 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 940 | SH CIR EP CORRECTION | 939 | F,H |  | 18 | 0 mm id | 1 | Nos | 0 | mtr | 1 | hr | 0 | 1 | 1 | Hrs
941 | 941 | SH CIR SEAM FIRST FIT UP | 936
| 942 | SH CS FIT UP - [LS1+LS2] | 941 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 943 | SH CS TACK DP CHECK - [LS1+LS2] | 942 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
944 | 944 | SH CIR SEAM FIRST WELDING | 941
| 945 | SH CS WELDING TRANSFERE | 944 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
| 946 | SH CS WELDING OUTER [LS1+LS2] | 945 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 947 | SH CS WELDING BACK CHIP [LS1+LS2] | 946 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 948 | SH CS INNER WELDING [LS1+LS2] | 947 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 949 | SH CS FLUSH GRINDING [LS1+LS2] | 948 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
950 | 950 | SH CIR SEAM SECOND FITUP | 944
| 951 | SH CS FIT UP - [LS2+LS3] | 950 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 952 | SH CS TACK DP CHECK - [LS2+LS3] | 951 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
953 | 953 | SH CIR SEAM SECOND WELDING | 950 | [10 empty] | 0 |  | 0
| 954 | SH CS WELDING TRANSFERE-[LS2+LS3] | 953 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 955 | SH CS WELDING OUTER [LS2+LS3] | 954 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 956 | SH CS WELDING BACK CHIP [LS2+LS3] | 955 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 957 | SH CS INNER WELDING [LS2+LS3] | 956 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 958 | SH CS FLUSH GRINDING [LS2+LS3] | 957 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
959 | 959 | SH CIR SEAM III RD FITUP | 953
| 960 | SH CS FIT UP CS3 | 959 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 961 | SH CS TACK DP CHECK CS3 | 960 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
962 | 962 | SH CIR SEAM THIRD WELDING | 959
| 963 | SH CS WELDING TRANSFERE CS3 | 962 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 964 | SH CS WELDING OUTER CS3 | 963 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 965 | SH CS WELDING BACK CHIP CS3 | 964 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 966 | SH CS INNER WELDING CS3 | 965 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 967 | SH CS FLUSH GRINDING CS3 | 966 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
968 | 968 | SH FINAL LENGTH CORRECTION | 962
| 969 | SH LENGTH MARKING | 968 | F[2] |  | 18 | 1560 mm id | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 970 | LENGTH CUTTING | 969 | C,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
| 971 | GRINDING & EP | 970 | G,H |  | 18 | 1560 mm id | 1 | No | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
972 | 972 | SH CIR SEAM FLANGE 1 FITUP | 968
| 973 | SH CS FIT UP FLG CS1 | 972 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 974 | SH CS TACK DP CHECK FLG CS1 | 973 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
975 | 975 | SH CIR SEAM FLANGE 1 WELDING | 972
| 976 | SH CS WELDING TRANSFERE | 975 | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 977 | SH CS WELDING OUTER FLG CS1 | 976 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 978 | SH CS WELDING BACK CHIP FLG CS1 | 977 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 979 | SH CS INNER WELDING FLG CS1 | 978 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 980 | SH CS FLUSH GRINDING FLG CS1 | 979 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
981 | 981 | SH CS FIT UP FLG2 | 975
| 982 | SH CS FIT UP FLG 2 | 981 | F[2],H,W |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 983 | SH CS TACK DP CHECK FLG2 | 982 | F,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
984 | 984 | SH CS WELDING FLG2 | 981
| 985 | SH CS WELDING TRANSFERE FLG2 | 984 | F,H |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 986 | SH CS WELDING OUTER FLG2 | 985 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | Hrs
| 987 | SH CS WELDING BACK CHIP FLG2 | 986 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hrs
| 988 | SH CS INNER WELDING FLG2 | 987 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | Hrs
| 989 | SH CS FLUSH GRINDING FLG2 | 988 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | Hrs
990 | 990 | NOZ ORIENTATION MARKING | 984
| 991 | SH-NOZ ORIENTAION MARKING | 990 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
| 992 | SH-NOZ MARKING-N2A1 | 991 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
| 993 | SH-NOZ MARKING-N2A1 | 992 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
994 | 994 | SH NOZ OPENNING | 990
| 995 | 26"NB SRN - 1 | 994 | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.3054 | Hrs
| 996 | 26"NB SRN - 1 | 995 | C,H |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 0.1 | hr | 0.3054 | 1 | 1.3054 | Hrs
997 | 997 | INSPECTION | 994 | C,H |  |  |  | 2 | Nos | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
998 | 998 | SH NOZ EP | 997
| 999 | 26"NB SRN - 1 | 998 | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.054 | Hrs
| 1000 | 26"NB SRN - 1 | 999 | G |  | 18 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1 | hr | 3.054 | 1 | 4.054 | Hrs
| 1001 | INSPECTION | 1000 |  |  |  |  | 1 | No | 2 | Nos | 0.5 | hr | 1 | 1 | 2 | Hrs
1002 | 1002 | SH NOZZZLE FIT UP | 998
| 1003 | 26"NB SRN - 1 | 1002 | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1004 | 26"NB SRN - 1 | 1003 | F[2],H,W |  |  | 650nb | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1005 | DP CHECK | 1004 |  |  |  |  | 2 | No | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
1006 | 1006 | SH NOZ FIT UP INSPECTION | 1002
| 1007 | 26"NB SRN - 1 | 1006 | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
| 1008 | 26"NB SRN - 1 | 1007 | F,H |  |  | 650nb | 1 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
| 1009 | DP CHECK | 1008 | F,H |  |  | 650nb | 2 | No | 1 | Hrs | 1 | hr | 1 | 1 | 2 | Hrs
1010 | 1010 | SH NOZ WELDING | 1006
| 1011 | SH NOZ WELDING ARRANGEMENT | 1010 | T |  |  |  | 1 | No | 1 | Nos | 1 | Hr | 1 |  | 1 | Hrs
| 1012 | SH-NOZ WELDING -N1A | 1011 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.6351 | Hrs
| 1013 | SH-NOZ WELDING-N2A1 | 1012 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.6351 | Hrs
| 1014 | SH-NOZ WELDING-N2A2 | 1013 | W,H |  | 12 | 972 mm lip od | 1 | No | 3.054 | Mtr | 2.5 | hr | 7.6351 | 1 | 8.6351 | Hrs
| 1015 | SH NOZ ROOT DP CHECK | 1014 | F,H |  | 12 | 972 mm lip od | 2 | No | 6.108 | Mtr | 1 | hr | 6.108 | 1 | 7.108 | Hrs
| 1016 | SH-NOZ INNER WELD -N1A | 1015 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.1535 | Hrs
| 1017 | SH-NOZ INNER WELD-N2A1 | 1016 | H,W |  | 8 | 972 mm lip od | 1 | No | 3.054 | Mtr | 1.36 | hr | 4.1535 | 1 | 5.1535 | Hrs
| 1018 | SH-NOZ INNER WELD-N2A2 | 1017 | H,W |  | 8 | 972 mm lip od | 0 | No | 0 | Mtr | 1.36 | hr | 0 | 1 | 1 | Hrs
1019 | 1019 | SH SADDLE WELDING | 1010
| 1020 | SH-SADDLE PAD FIT UP | 1019 | F[2],W,H |  | 25 | 1596 mm od | 2 | No | 20.0585 | Nos | 0.5 | Hr | 10.0293 | 1 | 11.0293 | Hrs
| 1021 | SH-SADDLE PAD WELDING | 1020 | W[2],H[2] |  | 12 | 1596 mm od | 2 | Mtr | 20.0585 | Mtr | 1.6 | Hr | 32.0936 | 1 | 33.0936 | Hrs
| 1022 | SH-SADDLE MATCHING | 1021 | F[2],G[2] |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 8 | Hr | 16 | 1 | 17 | Hrs
| 1023 | SH-SADDLE FIT UP | 1022 | W,F[2],H |  |  | 1596 mm od | 2 | Nos | 2 | Nos | 6 | Hr | 12 | 1 | 13 | Hrs
| 1024 | SH-SADDLE WELDING | 1023 | W[2],H[2] |  | 12 | 11400 rmt | 1 | Nos | 16.0348 | Mtr | 1.6 | Hr | 25.6557 | 1 | 26.6557 | Hrs |  | 4014.8286
| 1025 | SH-SADDLE dress up | 1024 | G[2] |  |  |  | 1 | No | 1 | Nos | 8 | Hr | 8 | 1 | 9 | Hrs
1026 | 1026 | SH DAVIT ARM WELDING | 1019
| 1027 | SH-DAVIT ARM arm match | 1026 | F,G |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
| 1028 | SH-DAVIT ARM FIT UP | 1027 | F,H,W |  |  |  | 1 | No | 1 | Nos | 4 | Hr | 4 | 1 | 5 | Hrs
| 1029 | SH-DAVIT ARM WELDING | 1028 | W,H |  | 12 |  | 6 | mtr | 5.16 | Mtr | 1.6 | Hr | 8.256 | 1 | 9.256 | Hrs
1030 | 1030 | SH NDE CLEARENCE | 1026
| 1031 | SH-SH NDE CLEARENCE | 1030 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 12 | Hr | 12 | 1 | 13 | Hrs
| 1032 | TPI INSPECTION | 1031 | F,H |  | 18 | 6130 lg | 1 | No | 1 |  | 1 | Day | 1 |  | 1 | Day
1033 | 1033 | CH FABRICATION
1034 | 1034 | CH SHELL LS WELDING | 624
| 1035 | CH PLATE TRNASFER | 1034 | T |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Day
| 1036 | CH-MARKING | 1035 | F,H[2] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.1 | hr | 0.0831 | 1 | 1.0831 | Hrs
| 1037 | CH-CUTTING | 1036 | C,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.25 | hr | 0.20775 | 1 | 1.2078 | Hrs
| 1038 | CH PL SIDE GRINDING | 1037 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.15 | hr | 0.12465 | 1 | 1.1246 | Hrs
| 1039 | CH-BEVELLING CIR SIDE | 1038 | F,H[3] |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.4155 | Hrs
| 1040 | CH EP GRINDING | 1039 | G |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.831 | Hrs
1041 | 1041 | CH SH ROLLING | 1034
| 1042 | CH-PRE BEND | 1041 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hrs
| 1043 | CH-PRE BEND CUT OFF | 1042 | F[2],C |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 0.3 | hr | 0.4986 | 1 | 1.4986 | Hrs
| 1044 | CH LS BEVELING | 1043 | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.662 | Hrs
| 1045 | CH-ROLLING | 1044 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hrs
1046 | 1046 | CH SHELL LS FIT UP | 1041
| 1047 | CH-LS CORRECTION | 1046 | F[2] |  | 18 | 831 mm | 1 | Nos | 1.662 | mtr | 1 | hr | 1.662 | 1 | 2.662 | Hrs
| 1048 | CH-LS FIT UP | 1047 | F[2],W,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.831 | Hrs
1049 | 1049 | CH SHELL LS WELDING | 1046
| 1050 | CH-LS WELD ARRANGEMENT | 1049 | F,H[2] |  | 18 | 831 mm | 1 | Nos | 1 | mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 1051 | CH-LS WELDING- TOP SIDE | 1050 | W,H |  | 12 | 831 mm | 1 | Nos | 0.831 | mtr | 2.5 | hr | 2.0775 | 1 | 3.0775 | Hrs
| 1052 | CH-LS WELDING- BACK CHIP | 1051 | G,H |  | 18 | 831 mm | 1 | Nos | 0.831 | mtr | 1 | hr | 0.831 | 1 | 1.831 | Hrs
| 1053 | CH-LS INNER WELDING | 1052 | W,H |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.9 | hr | 0.7479 | 1 | 1.7479 | Hrs
| 1054 | CH-LS INNNER FLUSH GRIND | 1053 | G |  | 6 | 831 mm | 1 | Nos | 0.831 | mtr | 0.5 | hr | 0.4155 | 1 | 1.4155 | Hrs
| 1055 | CH RE ROLLING | 1054 | F[2],H |  | 18 | 831 mm | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
1056 | 1056 | CH LS WELDING RADIOGRAPHY | 1049
| 1057 | CH LS WELDING RT | 1056 | RT |  | 18 | 831 mm | 1 | No | 1 | No | 1 | dya | 1 |  | 1 | Day
1058 | 1058 | CH CS FLG 1 FIT UP | 1056
| 1059 | CH CIR EP CORRECTION | 1058 | F[2] |  | 18 | 1560 mm id | 1 | Nos | 9.803 | mtr | 0.45 | hr | 4.4114 | 1 | 5.4114 | Hr
| 1060 | CH CS FIT UP FLG1 | 1059 | F[2],W,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | Hr
| 1061 | CH CS TACK DP CHECK FLG1 | 1060 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | mtr | 4 | hr | 4 | 1 | 5 | Hr
1062 | 1062 | CH CS FLG 1 WELDING | 1058
| 1063 | CH CS WELDING TRANSFERE | 1062 | F,H[2] |  | 18 | 1560 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hr
| 1064 | CH CS WELDING OUTER FLG1 | 1063 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | hr
| 1065 | CH CS WELDING BACK CHIP FLG1 | 1064 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9015 | hr
| 1066 | CH CS INNER WELDING FLG 1 | 1065 | W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1.36 | hr | 6.6661 | 1 | 7.6661 | hr
| 1067 | CH CS FLUSH GRINDING FLG1 | 1066 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
1068 | 1068 | CH CS FLG 2 FIT UP | 1062
| 1069 | CH LENGTH CUTTING | 1068 | C,H |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
| 1070 | CH CIR EP CORRECTION | 1069 | F,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 1 | hr | 4.9015 | 1 | 5.9015 | hr
| 1071 | CH CS FIT UP FLG2 | 1070 | F[2],W,H |  | 8 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 4 | hr | 19.6061 | 1 | 20.6061 | hr
| 1072 | CH CS TACK DP CHECK FLG1 | 1071 | F |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
1073 | 1073 | CH CS FLG 2 WELDING | 1068
| 1074 | CH CS WELDING TRANSFERE FLG2 | 1073 | F,H[2] |  | 12 | 1560 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | hr
| 1075 | CH CS WELDING OUTER FLG2 | 1074 | W,H |  | 12 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 2.5 | hr | 12.2538 | 1 | 13.2538 | hr
| 1076 | CH CS WELDING BACK CHIP FLG2 | 1075 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 1 | hr | 4.9015 | 1 | 5.9015 | hr
| 1077 | CH CS INNER WELDING FLG2 | 1076 | W,H |  | 6 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.9 | hr | 4.4114 | 1 | 5.4114 | hr
| 1078 | CH CS FLUSH GRINDING FLG2 | 1077 | G |  | 18 | 1560 mm id | 1 | Nos | 4.9015 | Mtr | 0.5 | hr | 2.4508 | 1 | 3.4508 | hr
1079 | 1079 | CH CS FLG 1 & 2 WELDING rt | 1073
| 1080 | CH CS WELDING RT | 1079 | RT |  | 18 | 1560 mm id | 1 | No | 1 | n | 1 | Day | 1 |  | 1 | Day
1081 | 1081 | CH NOZ MARKING | 1079
| 1082 | CH- NOZ IREIENTATION NKG | 1081 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
| 1083 | CH-NOZ MARKING- 16"NB - 2 NOS | 1082 | F,H |  | 18 | 1560 mm id | 1 | Nos | 1 | Nos | 4 | hr | 4 | 1 | 5 | Hrs
1084 | 1084 | CH NOZ OPNNING | 1081
| 1085 | CH-NOZ OPENNING-TOP | 1084 | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1086 | CH-NOZ OPENNING-Bot | 1085 | C,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
1087 | 1087 | CH NOZ OPEN EP | 1084
| 1088 | CH-NOZ EP -N3A | 1087 | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1089 | CH-NOZ EP-N4A | 1088 | G,H |  |  | 400nb | 1 | No | 1 |  | #N/A | hr | #N/A | 1 | #N/A | Hrs
1090 | 1090 | CH NOZ FIT UP | 1087
| 1091 | CH-NOZ FIT UP -N3A | 1090 | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1092 | CH-NOZ FIT UP -N4A | 1091 | F[2],W,H |  |  | 400nb | 1 | No | 1 | No | #N/A | hr | #N/A | 1 | #N/A | Hrs
1093 | 1093 | CH NOZ FIT UP INSP | 1090
| 1094 | CH-NOZ INSPN -N3A | 1093 | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
| 1095 | CH-NOZ INSPN-N4A | 1094 | F,H |  |  | 400nb | 1 | No | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
1096 | 1096 | CH NOZ WELDING | 1093
| 1097 | CH NOZ WELDING ARRANGEMENT | 1096 | F,H[2] |  |  | 400nb | 2 | Nos | 1 | No | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
| 1098 | CH-NOZ WELDING -N3A | 1097 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.1116 | Hrs
| 1099 | CH-NOZ WELDING-N4A | 1098 | W,H |  | 14 | 407 mm | 1 | No | 1.2769 | Mtr | 3.22 | hr | 4.1116 | 1 | 5.1116 | Hrs
| 1100 | CH NOZ ROOT DP CHECK | 1099 | W,H |  | 14 | 407 mm | 2 | No | 2 | Nos | 1 | hr | 2 | 1 | 3 | Hrs
| 1101 | CH-NOZ INNER WELD -N3A | 1100 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.1492 | Hrs
| 1102 | CH-NOZ INNER WELD-N4A | 1101 | W,H |  | 6 | 407 mm | 1 | No | 1.2769 | Mtr | 0.9 | hr | 1.1492 | 1 | 2.1492 | Hrs
| 1103 | RF PAD FIT UP & NOZ fit up | 1102 | W,H |  |  | 400nb | 2 | No | 2 | Set | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1104 | RF PAD FIT UP WELDING | 1103 | G,H |  | 18 |  | 2 | No | 2.5538 | Mtr | 6.8 | hr | 17.366 | 1 | 18.366 | Hrs
| 1105 | NOZ WELDING FLUSH GRIND- 16"NB | 1104 | G |  |  | 407 mm | 2 | NoS | 2.5538 | No | 0.15 | hr | 0.38307 | 1 | 1.3831 | Hrs
1106 | 1106 | INTER CONNECTION NOZ WELDING | 1104 | [10 empty] | 0 |  | 0
| 1107 | BOT SH , CH AND TOP SH ,CH STACKING |  | F[2],H,W |  |  |  | 1 | No | 1 | Mtr | 16 | hr | 16 | 1 | 17 | 1
| 1108 | INTER CON NOZ FIT UP - ON SH |  | F[2],H,W |  | 650nb |  | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | 1
| 1109 | INTER CON NOZ FIT UP- ON CH |  | F[2],H,W |  | 400nb |  | 1 | No | 1 | Mtr | #N/A | hr | #N/A | 1 | #N/A | 1
| 1110 | INTER CON NOZ WELDING - ON SH |  | W,H |  | 18 | Dia | 1 | No | #REF! | Mtr | 4.9 | hr | #REF! | 1 | #REF! | 1
| 1111 | INTER CON NOZ WELDING- ON CH |  | W,H |  | 18 | Dia | 1 | No | #REF! | Mtr | 4.9 | hr | #REF! | 1 | #REF! | 1
| 1112 | DISMANTLING |  | F[2],H,W |  |  |  | 1 | No | 1 | Mtr | 12 | hr | 12 | 1 | 13 | 1
| 1113 | INTER CON NOZ FLUSH GRIND & DP - ON SH |  | G,H |  | 18 |  | 1 | No | #REF! | Mtr | 0.5 | hr | #REF! | 1 | #REF! | 1
| 1114 | INTER CON NOZ FLUSH GRIND & DP - ON CH |  | G,H |  | 18 |  | 1 | No | #REF! | Mtr | 0.5 | hr | #REF! | 1 | #REF! | 1
| 1115 | IN CON NOZ RT |  | RT |  | 18 | 0 | 1 | No | #REF! | No | 1 | Day | #REF! |  | #REF!
1116 | 1116 | CH PP PLATE FIT UP | 1106
| 1117 | CH- PP PLATE FIT UP | 1116 | F[2],H,W |  | 24 | 14465 | 1 | No | 14.465 | Nos | 0.5 | hr | 7.2325 | 1 | 8.2325 | Hrs | 14465
| 1118 | CH- PP PLATE FIT UP INSP | 1117 | F,H |  | 24 | 1560 id | 3 | No | 4 | Nos | 0.5 | hr | 2 | 1 | 3 | Hrs
1119 | 1119 | CH PP PLATE WELDING | 1116
| 1120 | CH- PP PLATE WELDING | 1119 | W,H |  | 24 | 1480 | 3 | No | 4.44 |  | 11.2 | hr | 49.728 | 1 | 50.728 | Hrs
| 1121 | CH- PP PLATE FACE GRINDING | 1120 | G,H |  | 12 | 12310 mm | 1 | No | 12.31 | No | 1.6 | hr | 19.696 | 1 | 20.696 | Hrs | 12310
1122 | 1122 | CH DAVIT ARM WELDING | 1119
| 1123 | CH-DAVIT ARM arm match | 1122 | F,H |  | 18 | 1480 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 1124 | CH-DAVIT ARM FIT UP | 1123 | F,W,H |  | 18 | 1251 lg | 1 | No | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 1125 | CH-DAVIT ARM WELDING | 1124 | W,H |  | 12 | 6 | 1 | No | 6 | mtr | 1.6 | hr | 9.6 | 1 | 10.6 | Hrs
1126 | 1126 | CH NDE & PWHT | 1122
| 1127 | CH ALL WELDING DRESSUP & DP CHECK | 1126 | G[2] |  | 18 | 1480lg | 1 | No | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 1128 | CH-CH NDE CLEARENCE | 1127 | F |  | 18 | 1480lg | 1 | No | 1 | No | 1 | Day | 1 |  | 1 | Hrs
1129 | 1129 | BARREL FABRICATION | 1126
1130 | 1130 | BARREL SH PLATE CUTTING & EP | 635 |  |  |  |  | 1 | No | 1 | No | 4 | Day | 4 |  | 4 | Hr
| 1131 | BARREL PLATE TRNASFER | 1130 | T |  | 18 | 373 mm | 1 | Nos | 0.373 | mtr | 0.1 | Hr/mtr | 0.0373 | 1 | 1.0373 | Hr
| 1132 | BARREL-MARKING | 1131 | F,H[2] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.25 | Hr/mtr | 2.825 | 1 | 3.825 | Hr
| 1133 | BARREL-CUTTING | 1132 | C,H |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.15 | Hr/mtr | 1.695 | 1 | 2.695 | Hr
| 1134 | BARREL PL SIDE GRINDING | 1133 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 0.5 | Hr/mtr | 5.65 | 1 | 6.65 | Hr
| 1135 | BARREL-BEVELLING CIR SIDE | 1134 | F,H[3] |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hr
| 1136 | CH EP GRINDING | 1135 | G |  | 18 | 11300 mm | 1 | Nos | 11.3 | mtr | 1 | Hr/mtr | 11.3 | 1 | 12.3 | Hr
1137 | 1137 | BARREL SHELL ROLLING | 1130
| 1138 | BARREL-PRE BEND | 1137 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hr
| 1139 | BARREL-PRE BEND CUT OFF | 1138 | F[2],C |  | 18 | 1664 mm id | 1 | Nos | 3.328 | No | 0.3 | hr | 0.9984 | 1 | 1.9984 | Hr
| 1140 | BARREL -PRE LS EP | 1139 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.328 | Hr
| 1141 | BARREL-ROLLING | 1140 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 3 | hr | 3 | 1 | 4 | Hr
1142 | 1142 | BARREL SHELL LS FIT UP | 1137
| 1143 | BARREL-LS CORRECTION | 1142 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 3.328 | mtr | 1 | hr | 3.328 | 1 | 4.328 | Hr
| 1144 | BARREL-LS FIT UP | 1143 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.664 | Hr
1145 | 1145 | BARREL SHELL LS WELDING | 1142
| 1146 | BARREL-LS WELD ARRANGEMENT | 1145 | F,H[2] |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hr
| 1147 | BARREL-LS WELDING- TOP SIDE | 1146 | W,H |  | 12 | 1664 mm id | 1 | Nos | 1.664 | mtr | 2.5 | hr | 4.16 | 1 | 5.16 | Hr
| 1148 | BARREL-LS WELDING- BACK CHIP | 1147 | G,H |  | 18 | 1664 mm id | 1 | Nos | 1.664 | mtr | 1 | hr | 1.664 | 1 | 2.664 | Hr
| 1149 | BARREL-LS INNER WELDING | 1148 | W,H |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.9 | hr | 1.4976 | 1 | 2.4976 | Hr
| 1150 | BARREL-LS INNNER FLUSH GRIND | 1149 | G |  | 6 | 1664 mm id | 1 | Nos | 1.664 | mtr | 0.5 | hr | 0.832 | 1 | 1.832 | Hr
| 1151 | BARREL RE ROLLING | 1150 | F[2],H |  | 18 | 1664 mm id | 1 | Nos | 1 | mtr | 3 | hr | 3 | 1 | 4 | Hr
1152 | 1152 | BARREL LS WELDING RT | 1145
| 1153 | BAR LS WELDING RT | 1152 | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
1154 | 1154 | BARREL SHELL CS FLG 1 FIT UP | 1152
| 1155 | BARREL CIR EP CORRECTION | 1154 | F[2] |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 1156 | BARREL CS FIT UP FLG1 | 1155 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 1157 | BARREL CS TACK DP CHECK FLG1 | 1156 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | no | 0.25 | hr | 1.3071 | 1 | 2.3071 | Hrs
1158 | 1158 | BARREL SH CS FLG 1 WELDING | 1154
| 1159 | BARREL CS WELDING TRANSFERE | 1158 | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 1160 | BARREL CS WELDING OUTER FLG1 | 1159 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.0707 | Hrs
| 1161 | BARREL CS WELDING BACK CHIP FLG1 | 1160 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 1162 | BARREL CS INNER WELDING FLG 1 | 1161 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.7055 | Hrs
| 1163 | BARREL CS FLUSH GRINDING FLG1 | 1162 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.6141 | Hrs
1164 | 1164 | BARREL CS FIT UP WITH DISH | 1158
| 1165 | BARREL LENGTH CUTTING | 1164 | C,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 1166 | BARREL EP | 1165 | F,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 1167 | BARREL CS FIT UP DISH | 1166 | F[2],W,H |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | mtr | 4 | hr | 20.9132 | 1 | 21.9132 | Hrs
| 1168 | BARREL CS TACK DP CHECK DISH | 1167 | F |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | No | 3.5 | hr | 18.299 | 1 | 19.299 | Hrs
1169 | 1169 | BARREL CS WELDING WITH DISH | 1164
| 1170 | BARREL CS WELDING TRANSFERE DISH | 1169 | F,H[2] |  | 12 | 1664 mm id | 1 | Nos | 1 | Mtr | 1 | hr | 1 | 1 | 2 | Hrs
| 1171 | BARREL CS WELDING OUTER DISH | 1170 | W,H |  | 12 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 2.5 | hr | 13.0707 | 1 | 14.0707 | Hrs
| 1172 | BARREL CS WELDING BACK CHIP DISH | 1171 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 1 | hr | 5.2283 | 1 | 6.2283 | Hrs
| 1173 | BARREL CS INNER WELDING DISH | 1172 | W,H |  | 6 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.9 | hr | 4.7055 | 1 | 5.7055 | Hrs
| 1174 | BARREL CS FLUSH GRINDING DISH | 1173 | G |  | 18 | 1664 mm id | 1 | Nos | 5.2283 | Mtr | 0.5 | hr | 2.6141 | 1 | 3.6141 | Hrs
1175 | 1175 | BARREL CS FLG 1 & DISH WELDING rt | 1169
| 1176 | BARREL CS WELDING RT | 1175 | RT |  | 18 | 1664 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Day
1177 | 1177 | BARREL NOZ OREINATION MARKING | 1175
| 1178 | BARREL- NOZ IREIENTATION NKG | 1177 | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 1179 | BARREL-NOZ MARKING- 2 | 1178 | F,H |  | 20 | 1664 mm id | 1 | Nos | 1 | Nos | 1 | hr | 1 | 1 | 2 | Hrs
1180 | 1180 | BARREL NOZ OPPENING | 1177
| 1181 | BARREL-NOZ OPENNING-40 NB - LWN | 1180 | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
| 1182 | BARREL-NOZ OPENNING-40 NB - LWN | 1181 | C,H |  |  | 40NB | 1 | No | 1 | Nos | 3 | hr | 3 | 1 | 4 | Hrs
1183 | 1183 | BARREL NOZ EDGE PREPARATION | 1180
| 1184 | BARREL-NOZ OPENNING-40 NB - LWN | 1183 | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
| 1185 | BARREL-NOZ OPENNING-40 NB - LWN | 1184 | G,H |  |  | 40NB | 1 | No | 1 | Nos | 2 | hr | 2 | 1 | 3 | Hrs
1186 | 1186 | BARREL NOZZZLE FIT UP | 1183
| 1187 | BARREL-NOZ FIT UP -N5A | 1186 | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
| 1188 | BARREL-NOZ FIT UP -N6A | 1187 | F[2],W,H |  |  | 40NB | 1 | NO | 1 | Nos | #N/A | hr | #N/A | 1 | #N/A | Hrs
1189 | 1189 | BARREL NOZ FIT UP INSPECTION | 1186
| 1190 | BARREL-NOZ INSPN -5A | 1189 | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
| 1191 | BARREL-NOZ INSPN-6A | 1190 | INS |  |  | 40NB | 1 | NO | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
1192 | 1192 | BARREL NOZ WELDING | 1189
| 1193 | BARREL NOZ WELDING ARRANGEMENT | 1192 | T |  | 40NB | 40NB | 1 | Nos | 1 | Nos | 0.5 | hr | 0.5 | 1 | 1.5 | Hrs
| 1194 | BARREL-NOZ WELDING -N5A | 1193 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
| 1195 | BARREL-NOZ WELDING-N6A | 1194 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
| 1196 | BARREL NOZ ROOT DP | 1195 | F,H |  |  | 75 MM | 2 | No | 2 |  | 0.5 | hr | 1 | 1 | 2 | Hrs
| 1197 | BARREL-NOZ INNER WELDING -N5A | 1196 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
| 1198 | BARREL-NOZ INNER WELDING-N6A | 1197 | W,H |  | 10 | 75 MM | 1 | No | 0.23565 |  | 1.88 | hr | 0.44302 | 1 | 1.443 | Hrs
1199 | 1199 | BARREL NOZ INNER WELD FLUSH GRIND | 1192
| 1200 | BARREL ALL WELDING DRESSUP & DP | 1199 | G[2] |  | 20 | 40NB | 1 | No | 1 | NO | 8 | hr | 8 | 1 | 9 | Hrs
| 1201 | BARREL-BARREL NDE CLEARENCE | 1200 | F |  | STD | 40NB | 1 | NoS | 1 | No | 1 | Day | 1 |  | 1 | Hrs
1202 | 1202 | FL HEAD FABRICATION
1203 | 1203 | FLAOTING HEAD DISH FORMING | 641
| 1204 | FL HEAD DISH PL ISSUE | 1203 | T |  |  |  | 1 | No | 1 |  | 4 | Day | 4 |  | 4 | Hrs
| 1205 | FL HEAD PL MARKING | 1204 | F,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.1 | hr | 0.62337 | 1 | 1.6234 | Hrs
| 1206 | FL HEAD PL STAMPING | 1205 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | Nos | 1 | Hr | 1 | 1 | 2 | Hrs
| 1207 | FL HEAD PL CUTTING | 1206 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 0.25 | hr | 1.5584 | 1 | 2.5584 | Hrs
| 1208 | FL HEAD PL GRINDING | 1207 | G |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | mtr | 1 | hr | 6.2337 | 1 | 7.2337 | Hrs
1209 | 1209 | FL HEAD FORMIG | 1203
| 1210 | FL HEAD FORMING | 1209 | SC |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 10 | Day | 10 |  | 10 | Hrs
| 1211 | FL HEAD PROFILE CHECK | 1210 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 1 | Day | 1 |  | 1 | Hrs
1212 | 1212 | FL HEAD CUTTING | 1209
| 1213 | FL HEAD MARKING | 1212 | F,H |  | 50 | 1550 mm id | 1 | Nos | 1 | No | 4 | Hr/No | 4 |  | 4 | Hrs
| 1214 | FL HEAD CUTTING | 1213 | C,H |  | 50 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 0.1 | hr | 0.62337 | 2 | 2.6234 | Hrs
1215 | 1215 | FL HEAD EP | 1212
| 1216 | FL HEAD GRINDING | 1215 | G,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.2337 | Hrs
1217 | 1217 | FL HEAD FIT UP | 1215
| 1218 | FL HEAD FIT UP | 1217 | F[2],W,H |  | 25 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 1 | hr | 6.2337 | 2 | 8.2337 | Hrs
1219 | 1219 | FL HEAD WELDING | 1217
| 1220 | FL HEAD WELDING | 1219 | W,H |  | 30 | 1550 mm id | 1 | Nos | 6.2337 | Mtr | 16.8 | hr | 104.7266 | 2 | 106.7266 | Hrs
| 1221 | FL HEAD PP PLATE FIT UP | 1220 | F[2],H,W |  | 16 | 1550 mm id | 1 | Nos | 1 | No | 4 | hr | 4 | 1 | 5 | Hrs
| 1222 | FL HEAD PP PL WELDING | 1221 | W,H |  | 16 | 3000 mm | 1 | Nos | 3 | Mtr | 2.8 | hr | 8.4 | 2 | 10.4 | Hrs
| 1223 | FL HEAD PP PL LEVEL GRINDING | 1222 | F,H |  | 16 | 3000 mm | 1 | Nos | 1 | No | 6 | hr | 6 | 1 | 7 | Hrs
| 1224 | FL HEAD INSPECTION | 1223 | F |  | 16 | 3000 mm | 1 | Nos | 1 | No | 1 | hr | 1 | 1 | 2 | Hrs
1225 | 1225 | FL HEAD SR & MACHINING | 1219
| 1226 | FL HEAD SR | 1225 | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 3 | Day | 3 | 0 | 3 | Hrs
| 1227 | FL HEAD FINAL MACHINING | 1226 | SC |  |  | 1550 mm id | 1 | Nos | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs
| 1228 | FL HEAD HOLE MARKING | 1227 | F,H |  |  | 1550 mm id | 1 | Nos | 1 | No | 0.5 | Day | 0.5 | 0 | 0.5 | Hrs
| 1229 | FL HEAD HOLE DRILLING | 1228 | SC |  | 140 mm | 1550 mm id | 72 | hole | 1 | No | 4 | Day | 4 | 0 | 4 | Hrs
| 1230 | FL HEAD FINAL INSPECTION | 1229 | F,H |  | 140 mm | 1550 mm id | 1 | No | 1 | No | 1 | Day | 1 | 0 | 1 | Hrs
1231 | 1231 | TUBE BUNDLE FABRICATION
1232 | 1232 | TUBE BUNDLE ASSY
| 1233 | FRAME SET UP & TUBE SHT SET UP | 1232 | F[2],W |  | 145T | 1308 tube |  |  | 1 |  | 1.5 | Day | 1.5 | 0 | 1.5 | Hrs
| 1234 | SKELITON ASSY- 19 baffle | 1233 | F[2],H[3] |  |  | 19 baffle | 1 | Nos | 19 | Nos | 0.5 | hr | 9.5 | 1 | 10.5 | Hrs
1235 | 1235 | TUBE INSERT | 1232
| 1236 | TUBE INSERT | 1235 | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
| 1237 | SEAL ROD INSERT & WELD | 1236 | F[2],W,H[2] |  | 25.4 dia | 5134 lg | 14 | Nos | 14 | Nos | 0.5 | Hr/no | 7 | 1 | 8 | Hrs
| 1238 | TUBE INSERT | 1237 | F,H[4] |  | 25.4 dia | 7000 lg | 654 | Nos | 654 | Nos | 0.083333 | Hr/no | 54.5 | 1 | 55.5 | Hrs
1239 | 1239 | SLIDING STRIP FIT UP WELDING | 1235
| 1240 | SEALING STRIP FIT UP | 1239 | F,H |  | 8 | 4592 mm lg | 2 | Nos | 2 | Nos | 3 | Hr/no | 6 | 1 | 7 | Hrs
| 1241 | SLIDING STRIP WELDING | 1240 | W,H |  | 8 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
| 1242 | SEALING TRIP WELD GRIND | 1241 | G |  | 1500 | 60 joints | 1 | Set | 60 | Joint | 0.25 | Hr/no | 15 | 1 | 16 | Hrs
1243 | 1243 | TUBE BUNDLE INSERT | 1239
| 1244 | TUBE BUNDLE INSERT IN SHELL | 1243 | F[3],H[8] |  |  | 7000 LG | 1 | Nos | 1 | Nos | 16 | Hr/no | 16 | 1 | 17 | Hrs
| 1245 | FL HEAD TUBE SHT FIXING | 1244 | F[2],H[4] |  | 145MM |  | 1 | Nos | 1 | Nos | 4 | Hr/no | 4 | 1 | 5 | Hrs
| 1246 | TEST FLG & GLAND ASSY | 1245 | F[3],H[6] |  | 165 MM | 1490 | 1 | Nos | 56 | Bolts | 0.16667 | hr | 9.3333 | 1 | 10.3333 | Hrs
1247 | 1247 | TUBE EXPANSION IN GROOVES | 1243
| 1248 | TUBE EXP - ST SIDE - 1 STAGE | 1247 | F,H[2] |  | 150 mm | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.016667 | hr | 21.8 | 1 | 22.8 | Hrs
| 1249 | TUBE EXP - FL SIDE - 1 STAGE | 1248 | F,H[2] |  | Servo | 1308 nos | 1308 | Nos | 1308 | Rolling | 0.0083333 | hr | 10.9 | 1 | 11.9 | Hrs
| 1250 | TUBE TRIMMING FL SIDE | 1249 | F,H |  | Servo | 1308 nos | 1308 | Nos | 1308 | Trimm | 0.033333 | hr | 43.6 | 1 | 44.6 | Hrs
| 1251 | TUBE EXP BOTH SIDE - 4 STAGE | 1250 | F[2],H[2] |  | 150MM | 2616 Roll | 2616 | Nos | 2616 | Rolling | 0.0083333 | hr | 21.8 | 1 | 22.8 | Hrs
1252 | 1252 | TUBE EXP- PNUEMATIC TEST | 1247
| 1253 | TUBE EXP PNUEMATIC TEST | 1252 | F[2],H[2] |  |  |  | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
| 1254 | PNUEMATIC TEST TPI WITNESS | 1253 | F,H |  |  |  | 1 | No | 1 | Test | 1 | Day | 1 |  | 1 | Hrs
| 1255 | CLEANING | 1254 | F,H[3] |  |  |  | 1 | No | 1 | No | 1 | Hr | 1 |  | 1 | Hrs
1256 | 1256 | TUBE TUBE SHEET WELDING- FT SIDE | 1252
| 1257 | TUBE WELDING - ST SIDE ROOT | 1256 | TW,H |  | 2.77 | 25.4 od | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 1258 | TUBE WELDING - ST SIDE ROOT DP | 1257 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 1259 | TUBE WELDING - ST SIDE FINAL WELD | 1258 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 1260 | TUBE WELDING - ST SIDE FINAL DP | 1259 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
1261 | 1261 | TUBE TO TUBE SHEET WELDING - FL HEAD SIDE | 1256
| 1262 | TUBE WELDING - FLH SIDE ROOT | 1261 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 1263 | TUBE WELDING - FLH SIDE ROOT DP | 1262 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
| 1264 | TUBE WELDING - FLH SIDE FINAL WELD | 1263 | TW,H |  | 2.77 |  | 1308 | Nos | 1308 | Run | 0.083333 | hr | 109 | 1 | 110 | Hrs
| 1265 | TUBE WELDING - FLH SIDE FINAL DP | 1264 | F,H |  | 2.77 |  | 1308 | Nos | 1 | No | 8 | hr | 8 | 1 | 9 | Hrs
1266 | 1266 | SH SIDE HYDRO
1267 | 1267 | SH SIDE WATER FILLING | [5 empty] | 1 | No | 1 | Hrs | 6 | Hrs | 6 |  | 6 | Hrs
| 1268 | SH SIDE HYDRO | 1267 | F[2],H[2] |  |  | 6130 lg | 1 | No | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs
| 1269 | SH SIDE TPI WITNESS | 1268 | F[2] |  |  | 6130 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day
| 1270 | DE WATERING & DISMANTLE OF GLAND | 1269 | F[2],H[4] |  |  | 6130 lg | 1 | No | 1 | Test | 8 | hr | 8 | 0 | 8 | Hrs
1271 | 1271 | CH SIDE HYDRO - STACKED
| 1272 | HE 1 & 2 STACKING |  | F,H[2] |  |  |  | 1 | Set | 1 | Test | 16 | hr | 16 | 0 | 16 | Hrs
| 1273 | CH & INT CON NOZ TIGHT | 1272 | F[2],H[2] |  |  | 9178 lg | 1 | No | 1 | Test | 12 | hr | 12 | 1 | 13 | Hrs
| 1274 | WATER FILL | 1273 | F[2] |  |  | 9178 lg | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
| 1275 | CH SIDE HYDRO | 1274 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 4 | hr | 4 | 0 | 4 | Hrs
| 1276 | CH SIDE HYDRO TPI WITNESS | 1275 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day
| 1277 | DE WATERING | 1276 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 4 | hr | 4 | 1 | 5 | Hrs
1278 | 1278 | SH SIDE HYDRO - STACKED | 1271
| 1279 | BARREL ASSEBLY |  | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 16 | hr | 16 | 0 | 16 | Hrs
| 1280 | WATER FILL | 1279 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 8 | hr | 8 | 0 | 8 | Hrs
| 1281 | SHELL SIDE HYDRO - STACKED | 1280 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 16 | hr | 16 | 0 | 16 | Hrs
| 1282 | SHELL SIDE HYDRO- STACKED TPI WITNESS | 1281 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day
| 1283 | DE WATERING | 1282 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 6 | hr | 6 | 0 | 6 | Hrs
1284 | 1284 | NITORGEN PURGING | 1278 | F[2],H[4]
| 1285 | N2 GAS PURGING |  | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 12 | hr | 12 | 0 | 12 | Hrs
1286 | 1286 | PAINTING | 1284 | F[2],H[4]
| 1287 | PRIMER PAINTING |  | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day
| 1288 | INTERMEDIATE PAINTING | 1287 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day
| 1289 | TOP COAT PAINTING | 1288 | F[2],H[4] |  |  | 9178 lg | 1 | No | 1 | Test | 1 | Day | 1 | 0 | 1 | Day

## NOZZLE
NOZ MARK | SERVICE | LOC | NB | SCH | TYPE | CLASS | PROJ | QTY | RFP-THK | RFP-DIA
N1 | Shell Inlet | SH | 6" | 80 | WNRF | 300# |  | 1
N2 | Shell Outlet |  | 6" | 80 | WNRF | 300# |  | 1
N3 | Channel Inlet |  | 6" | 80 | WNRF | 300# |  | 1
N4 | Channel Outlet |  | 6" | 80 | WNRF | 300# |  | 1
N5 | Shell Vent |  | 1.5" | 160 | WNRF | 300# |  | 1
N6 | Shell Drain |  | 1.5" | 160 | WNRF | 300# |  | 1
N7 | MP Connection |  | 2" | 160 | WNRF | 300# |  | 1
N8 | MP Connection |  | 2" | 160 | WNRF | 300# |  | 1
N9 | MP Connection |  | 1.5" | 160 | WNRF | 300# |  | 1
N10 | MP Connection |  | 1.5" | 160 | WNRF | 300# |  | 1
SUM
| 26"NB | 4 NO
| 16"NB | 4 NO

## BM
Work Duration for Plateness
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
| PLATE THK | MARKING | CUTTING | SURFACE GRINDING | BEVEL CUTTING | BEVEL GRINDING | PRE BENDING | PRE BEND CUT OFF | LONG SEAM EP | LS FIT UP | WELDING ARRANGEMENT | LS WELDING | CS EP CORRECTION | SH LENGTH CUTTING | CIR SEAM EP | CIR SEAM FIT UP | CIR SEAM WELDING | CIR SEAM BACK CHIP | CIR SEAM INSIDE WELD | CIR SEAM FLUSH GRIND | DAVIT ARM FIT UP | FILLET WELDING | FILLET +GROOVE WELDING
| 6 | 0.1 | 0.25 | 0.15 | 0.5 | 0.5 | 2 | 0.25 | 0.5 | 1 | 0.5 | 0.9 | 0.5 | 0.5 | 1 | 1 | 0.9 | 1 | 0.9 | 0.5 | 1 | 0.6 | 1.2
| 8 | 0.1 | 0.25 | 0.15 | 0.5 | 0.5 | 2 | 0.25 | 0.5 | 1 | 0.5 | 1.36 | 0.5 | 0.5 | 1 | 1 | 1.36 | 1 | 1.36 | 0.5 | 1 | 0.8 | 1.6
| 10 | 0.1 | 0.25 | 0.15 | 0.5 | 0.5 | 2 | 0.25 | 0.5 | 1 | 0.5 | 1.88 | 0.5 | 0.5 | 1 | 1 | 1.88 | 1 | 1.88 | 0.5 | 2 | 1.2 | 2.4
| 12 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.3 | 1 | 1 | 0.5 | 2.5 | 0.45 | 0.5 | 1 | 1 | 2.5 | 1 | 2.5 | 0.5 | 2 | 1.6 | 3.2
| 14 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.3 | 1 | 1 | 0.5 | 3.22 | 0.45 | 0.5 | 1 | 1 | 3.22 | 1 | 3.22 | 0.5 | 2 | 2.2 | 4.4
| 16 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.3 | 1 | 1 | 1 | 4.02 | 0.45 | 0.5 | 1 | 1 | 4.02 | 1 | 4.02 | 0.5 | 2 | 2.8 | 5.6
| 18 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.3 | 1 | 1 | 1 | 4.9 | 0.45 | 0.5 | 1 | 1 | 4.9 | 1 | 4.9 | 0.5 | 2 | 3.4 | 6.8
| 20 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | 6.2 | 1 | 0.5 | 1 | 1 | 6.2 | 1 | 6.2 | 0.5 | 2 | 4 | 8
| 22 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | 6.94 | 1 | 0.5 | 1 | 1 | 6.94 | 1 | 6.94 | 0.5 | 2 | 4.8 | 9.6
| 24 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | 8.68 | 1 | 0.5 | 1 | 1 | 8.68 | 1 | 8.68 | 0.5 | 2 | 5.6 | 11.2
| 25 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | 8.68 | 1 | 0.5 | 1 | 1 | 8.68 | 1 | 8.68 | 0.5 | 2 | 6 | 12
| 28 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | 10.64 | 1 | 0.5 | 1 | 1 | 10.64 | 1 | 10.64 | 0.5 | 2 | 7.4 | 14.8
| 30 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | 12.06 | 1 | 0.5 | 1 | 1 | 12.06 | 1 | 12.06 | 0.5 | 2 | 8.4 | 16.8
| 35 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | FALSE | 1 | 0.5 | 1 | 1 | FALSE | 1 | FALSE | 0.5 | 2 | FALSE | 0
| 40 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | FALSE | 1 | 0.5 | 1 | 1 | FALSE | 1 | FALSE | 0.5 | 2 | FALSE | 0
| 50 | 0.1 | 0.25 | 0.15 | 0.5 | 1 | 2 | 0.5 | 1 | 1 | 1 | FALSE | 1 | 0.5 | 1 | 1 | FALSE | 1 | FALSE | 0.5 | 2 | FALSE | 0
Work Duration for Pipe
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| PIPE | PIPE MARKING | PIPE CUTTING | PIPE EP | PIPE+FLG FIT UP | NOZZLE OPEN | PIPE FLUSH GRIND | PIPE PROFILE MARKING | PIPE PROFILE CUTTING | PIPE PROFILE GRINDING | NOZ+SHELL FIT UP | RF PAD CUTTING | RF PAD GRINDING | RF PAD FORMING | RF PAD FITP | RF PAD WELDING | RF PAD AIR TEST | RF PAD MARKING
NB | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | [6 empty] | 0.5
NB | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | [6 empty] | 0.5
NB | 50 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | [6 empty] | 0.5
NB | 65 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | [6 empty] | 0.5
NB | 80 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | [6 empty] | 0.5
NB | 100 | 0.45 | 0.5 | 0.5 | 0.45 | 0.5 | 0.45 | 0.45 | 0.45 | 0.45 | 1 | 1 | 1 | 2 | 2 |  | 1 | 0.45
NB | 150 | 0.45 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 |  | 1 | 0.45
NB | 200 | 0.45 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 |  | 1 | 0.45
NB | 250 | 1 | 1 | 1.7162 | 1 | 0.85808 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 |  | 1 | 1
NB | 300 | 1 | 1 | 2.0354 | 2 | 1.0177 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 2 |  | 1 | 1
NB | 350 | 2 | 1 | 2.2346 | 2 | 1.1173 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 3 | 3 |  | 1 | 2 |  |  | 762
NB | 400 | 2 | 1 | 2.5538 | 2 | 1.2769 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 3 | 3 |  | 1 | 2
NB | 450 | 2 | 1 | 2.873 | 2 | 1.4365 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
NB | 500 | 2 | 1 | 3.1923 | 2 | 1.5961 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
NB | 600 | 2 | 1 | 3.8307 | 2 | 1.9154 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
NB | 600 | 2 | 1 | 3.8307 | 2 | 1.9154 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
NB | 600 | 2 | 1 | 3.8307 | 2 | 1.9154 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
NB | 650 | 2 | 1 | 3.8307 | 2 | 1.9154 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
NB | 750 | 2 | 1 | 4.7884 | 2 | 1.9154 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 4 |  | 1 | 2
Work Duration for Assembly
NOZZLE WORK
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 23 | 24 | 25
| DIA | FRAME SET UP | ST TUBE SET ASSY | TIE ROD FIX | BAFFLE FIXING | TUBE INSERT | FL HEAD TUBE SHT FIX | SEAL+SLID ST FIT UP | SEAL+SLID ST WELDING | SEAL ROD WELDING | SEAL/SLID WELD GRIND | BUNDLE INSERT | BOLT ASSY | BOLT LOOSENNING | CHANNEL ASSY | CH COVER ASSY | FL HEAD ASSY | BARREL ASSY | TUBE EXP | TUBE TRIMMING | TUBE WELDING | DP CHECK |  | SHELL SIDE HYDRO
| 250 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 500 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 750 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 1000 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 1250 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 1500 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 1750 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
| 2000 | 12 | 4 | 0.15 | 0.5 | 0.083333 | 4 | 2 | 0.25 | 0.25 | 1 | 16 | 0.5 | 0.16667 | 16 | 16 | 16 | 16 | 0.016667 | 0.05 | 0.083333 | 8 |  | 12
Work Duration for Shell & Dish Marking
2
|  | 500 | 1
|  | 1000 | 2
|  | 1250 | 2.5
|  | 1500 | 3
|  | 1750 | 3.5
|  | 2000 | 4

## ACTIVITY (2) (hidden)
ACTIVITY J 4220 B | MOC |  | THK | W | LONG/ CIR | QTY | WORK | UOM | BENCH MARK TIME |  | WORK | SETTING TIME | DURATION -HR
SH-MARKING | CS |  | 18 | 2500 | 5000 | 2 | 30 | M | 0.1 |  | 3 | 1 | 4
SH-MARKING | CS |  | 18 | 2000 | 5000 | 1 | 14 | M | 0.1 |  | 1.4 | 1 | 2.4
SH-MARKING | CS |  | 18 | 1250 | 5000 | 1 | 12.5 | M | 0.1 |  | 1.25 | 1 | 2.25
-
SH-CUTTING | CS |  | 18 | 2500 | 5000 | 2 | 30 | M | 0.25 |  | 7.5 | 1 | 8.5
SH-CUTTING | CS |  | 18 | 2000 | 5000 | 1 | 14 | M | 0.25 |  | 3.5 | 1 | 4.5
SH-CUTTING | CS |  | 18 | 1250 | 5000 | 1 | 12.5 | M | 0.25 |  | 3.125 | 1 | 4.125
SH-SIDE GRINDING | CS |  | 18 | 2500 | 5000 | 2 | 30 | M | 0.15 |  | 4.5 | 1 | 5.5
SH-SIDE GRINDING | CS |  | 18 | 2000 | 5000 | 1 | 14 | M | 0.15 |  | 2.1 | 1 | 3.1
SH-SIDE GRINDING | CS |  | 18 | 1250 | 5000 | 1 | 12.5 | M | 0.15 |  | 1.875 | 1 | 2.875
SH-BEVEL CUTTING | CS |  | 18 | 2500 | 5000 | 2 | 20 | M | 0.5 |  | 10 | 1 | 11
SH-BEVEL CUTTING | CS |  | 18 | 2000 | 5000 | 1 | 10 | M | 0.5 |  | 5 | 1 | 6
SH-BEVEL CUTTING | CS |  | 18 | 1000 | 5000 | 1 | 10 | M | 0.5 |  | 5 | 1 | 6
SH-BEVEL GRINDING | CS |  | 18 | 2500 | 5000 | 2 | 20 | M | 1 |  | 20 | 1 | 21
SH-BEVEL GRINDING | CS |  | 18 | 2000 | 5000 | 1 | 10 | M | 1 |  | 10 | 1 | 11
SH-BEVEL GRINDING | CS |  | 18 | 1250 | 5000 | 1 | 10 | M | 1 |  | 10 | 1 | 11
SH-PRE BENDING | CS |  | 18 | 2500 | 5000 | 1 | 1 | No | 2 |  | 2 | 1 | 3
SH-PRE BENDING | CS |  | 18 | 2500 | 5000 | 1 | 1 | No | 2 |  | 2 | 1 | 3
SH-PRE BENDING | CS |  | 18 | 2000 | 5000 | 1 | 1 | NO | 2 |  | 2 | 1 | 3
SH-PRE BENDING | CS |  | 18 | 1250 | 5000 | 1 | 1 | NO | 2 |  | 2 | 1 | 3
SH-PRE BEND CUT OFF | CS |  | 18 | 2500 | 5000 | 1 | 5 | M | 0.3 |  | 1.5 | 1 | 2.5
SH-PRE BEND CUT OFF | CS |  | 18 | 2500 | 5000 | 1 | 5 | M | 0.3 |  | 1.5 | 1 | 2.5
SH-PRE BEND CUT OFF | CS |  | 18 | 2000 | 5000 | 1 | 4 | M | 0.3 |  | 1.2 | 1 | 2.2
SH-PRE BEND CUT OFF | CS |  | 18 | 1250 | 5000 | 1 | 2.5 | M | 0.3 |  | 0.75 | 1 | 1.75
SH-LONG SEAM BEVEL | CS |  | 18 | 2500 | 4769 | 2 | 5 | M | 1 |  | 5 | 1 | 6
SH-LONG SEAM BEVEL | CS |  | 18 | 2500 | 4769 | 1 | 5 | M | 1 |  | 5 | 1 | 6
SH-LONG SEAM BEVEL | CS |  | 18 | 2000 | 4769 | 1 | 4 | M | 1 |  | 4 | 1 | 5
SH-LONG SEAM BEVEL | CS |  | 18 | 1250 | 4769 | 1 | 2.5 | M | 1 |  | 2.5 | 1 | 3.5
SH-LS EP | CS |  | 18 | 2500 | 4769 | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
SH-LS EP | CS |  | 24 | 2500 | 4769 | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
SH-LS EP | CS |  | 24 | 2000 | 4769 | 1 | 2 | MTR | 1 |  | 2 | 1 | 3
SH-LS EP | CS |  | 24 | 1250 | 4769 | 1 | 1.25 | MTR | 1 |  | 1.25 | 1 | 2.25
SH-ROLLING | CS | STD | 24 | 2500 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
SH-ROLLING | CS | STD | 24 | 2500 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
SH-ROLLING | CS | STD | 24 | 2000 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
SH-ROLLING | CS | STD | 24 | 1250 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
SH-LS FIT UP | CS |  | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
SH-LS FIT UP | CS |  | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
SH-LS FIT UP | CS |  | 24 | 2000 | 1500 ID | 1 | 2 | MTR | 1 |  | 2 | 1 | 3
SH-LS FIT UP | CS |  | 24 | 1250 | 1500 ID | 1 | 1.25 | MTR | 1 |  | 1.25 | 1 | 2.25
SH-LS TACK DP CHECK | CS | STD | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
SH-LS TACK DP CHECK | CS | STD | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
SH-LS TACK DP CHECK | CS | STD | 24 | 2000 | 1500 ID | 1 | 2 | MTR | 1 |  | 2 | 1 | 3
SH-LS TACK DP CHECK | CS | STD | 24 | 1250 | 1500 ID | 1 | 1.25 | MTR | 1 |  | 1.25 | 1 | 2.25
SH-LS WELDING ARRANGMENT | CS | STD | 24 | 2500 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
SH-LS WELDING ARRANGMENT | CS | STD | 24 | 2500 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
SH-LS WELDING ARRANGMENT | CS | STD | 24 | 2000 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
SH-LS WELDING ARRANGMENT | CS | STD | 24 | 1250 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
SH-LS WELDING- OUTER | CS |  | 12 | 2500 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
SH-LS WELDING- OUTER | CS |  | 12 | 2500 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
SH-LS WELDING- OUTER | CS |  | 12 | 2000 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
SH-LS WELDING- OUTER | CS |  | 12 | 1250 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 2500 | 1 | 2.5 | No | 1 |  | 2.5 | 1 | 3.5
SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 2500 | 1 | 2.5 | No | 1 |  | 2.5 | 1 | 3.5
SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 2500 | 1 | 2.5 | No | 1 |  | 2.5 | 1 | 3.5
SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 1250 | 1 | 1.25 | No | 1 |  | 1.25 | 1 | 2.25
SH-LS WELDING INNER | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | Mtr | 2.5 |  | 6.25 | 1 | 7.25
SH-LS WELDING INNER | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | Mtr | 2.5 |  | 6.25 | 1 | 7.25
SH-LS WELDING INNER | CS |  | 12 | 2000 | 1500 id | 1 | 2 | Mtr | 2.5 |  | 5 | 1 | 6
SH-LS WELDING INNER | CS |  | 12 | 1250 | 1500 id | 1 | 1.25 | Mtr | 2.5 |  | 3.125 | 1 | 4.125
SH-LS WLDING FLUSH GRIND | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | MTR | 0.5 |  | 1.25 | 1 | 2.25
SH-LS WLDING FLUSH GRIND | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | MTR | 0.5 |  | 1.25 | 1 | 2.25
SH-LS WLDING FLUSH GRIND | CS |  | 12 | 2000 | 1500 id | 1 | 2 | MTR | 0.5 |  | 1 | 1 | 2
SH-LS WLDING FLUSH GRIND | CS |  | 12 | 1250 | 1500 id | 1 | 1.25 | MTR | 0.5 |  | 0.625 | 1 | 1.625
SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
SH- LS RT | CS | STD | 12 | 1550 ID | 2500 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
SH- LS RT | CS | STD | 12 | 1550 ID | 2500 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
SH- LS RT | CS | STD | 12 | 1550 ID | 2000 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
SH- LS RT | CS | STD | 12 | 1550 ID | 1000 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
SH-CS EP CORRECTION | CS | STD | 24 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
SH-CS EP CORRECTION | CS | STD | 24 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
SH-CS EP CORRECTION | CS | STD | 24 | 2000 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
SH-CS EP CORRECTION | CS | STD | 24 | 1000 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
SH-CIR SEAM FIT UP -1 | CS |  | 18 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
SH-CIR SEAM FIT UP -2 | CS |  | 18 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-CIR SEAM WLDING-1 | CS |  | 18 | 1500 | 2500 | 1 | 4.7696 | MTR | 4.9 | HR/MTR | 23.3708 | 1 | 24.3708
SH-CIR SEAM WLDING-2 | CS |  | 18 | 1500 | 2500 | 1 | 4.7696 | MTR | 4.9 | HR/MTR | 23.3708 | 1 | 24.3708
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-CIR SEAM BACK CHIP-1 | CS |  | 16 | 1500 |  | 1 | 4.7633 | MTR | 1 |  | 4.7633 | 1 | 5.7633
SH-CIR SEAM BACK CHIP-2 | CS |  | 16 | 1500 |  | 1 | 4.7633 | MTR | 1 |  | 4.7633 | 1 | 5.7633
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-CIR SEAM INNER WELDING-1 | CS |  | 6 | 1500 |  | 1 | 4.7319 | MTR | 0.9 |  | 4.2587 | 1 | 5.2587
SH-CIR SEAM INNER WELDING-2 | CS |  | 6 | 1500 |  | 1 | 4.7319 | MTR | 0.9 |  | 4.2587 | 1 | 5.2587
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-CIR SEAM FIT UP - 8 MTR | CS |  | 18 | 1500 |  | 1 | 4.713 | MTR | 1 |  | 4.713 | 1 | 5.713
SH-CIR SEAM WELDING | CS |  | 12 | 1500 |  | 1 | 4.713 | MTR | 2.5 |  | 11.7825 | 1 | 12.7825
SH-CIR SEAM BACK CHIP | CS |  | 18 | 1500 |  | 1 | 4.713 | MTR | 1 |  | 4.713 | 1 | 5.713
SH-CIR SEAM INNER WELDING | CS |  | 6 | 1500 |  | 1 | 4.713 | MTR | 0.9 |  | 4.2417 | 1 | 5.2417
SH-CIR SEAM FLUSH GRIND | CS |  | 18 | 1500 |  | 1 | 4.713 | MTR | 0.5 |  | 2.3565 | 1 | 3.3565
SH-CIR SEAM RT | CS | STD | 18 | 1500 |  | 1 | 4.713 | NO | 1 |  | 4.713 |  | 4.713
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-TOTAL LENGTH MKG | CS |  | 24 | 1500 |  | 1 | 4.713 | Mtr | 0.1 |  | 0.4713 | 0.5 | 0.9713
SH- TOTAL LENGTH CTG | CS |  | 24 | 1500 |  | 1 | 4.713 | Mtr | 0.5 |  | 2.3565 | 0.5 | 2.8565
SH- CS EP BOTH SIDE | CS |  | 24 | 1500 |  | 2 | 4.713 | Mtr | 1 |  | 4.713 | 0.5 | 5.213
SH-CS FLG 1&2 FIT UP | CS |  | 24 | 1500 |  | 2 | 4.713 | Mtr | 1 |  | 4.713 | 0.5 | 5.213
SH-CS FLG 1&2 WELDING | CS |  | 16 | 1500 |  | 2 | 4.713 | Mtr | 4.02 |  | 18.9463 | 0.5 | 19.4463
SH-CS FLG 1&2 BACK CHIP | CS |  | 16 | 1500 |  | 2 | 4.713 | Mtr | 1 |  | 4.713 | 0.5 | 5.213
SH-CS FLG 1&2 INNER WELD | CS |  | 10 | 1500 |  | 2 | 4.713 | Mtr | 1.88 |  | 8.8604 | 0.5 | 9.3604
SH-CIR SEAM FLUSH GRIND | CS |  | 10 | 1500 |  | 2 | 4.713 | Mtr | 0.5 |  | 2.3565 | 0.5 | 2.8565
SH-CIR SEAM RT | CS | STD | 10 | 1500 |  | 2 |  |  | 1 DAY |  |  |  | 1 DAY
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-OREINTAION MARKING |  | STD | 18 | 1500 | 8437 LG | 1 | 1 | No | 4 |  | 4 | 1 | 5
SH-NOZZLE MARKING | std |  | 30" | SRN |  | 3 | 3 | Nos | 4 |  | 12 | 1 | 13
SH-NOZZLE OPENNIING | STD |  | 30" |  | ON SHELL | 3 | 3 | NO | 4 |  | 12 | 1 | 13
SH-NOZZLE OPENNIING EP | STD |  | 30" |  | ON SHELL | 3 | 3 | Nos | 8 |  | 24 | 1 | 25
SH-NOZ FIT UP | STD |  | 30" |  |  | 2 | 2 | NO | 4 |  | 8 | 1 | 9
SH-NOZ WELDING |  |  | 12 | 1197 |  | 1 | 3.761 | MTR | 2.5 |  | 9.4024 | 1 | 10.4024
SH-NOZ WELDIG BACK CHIP |  |  | 18 | 1197 |  | 1 | 3.761 | MTR | 1 |  | 3.761 | 1 | 4.761
SH-NOZ INNER WELDING |  |  | 8 | 1197 |  | 1 | 3.761 | MTR | 1.36 |  | 5.1149 | 1 | 6.1149
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SH-SUPPORT PAD FIT UP |  |  | 30 | 1500 |  | 2 | 9.6145 | MTR | 1 |  | 9.6145 | 1 | 10.6145
SH-WELDING |  |  | 20 | 1500 |  | 2 | 18.852 | MTR | 4 |  | 75.408 | 1 | 76.408
SH-SUPPORT FIT UP |  | std |  |  |  | 2 | 2 | Nos | 4 |  | 8 | 1 | 9
SH-SUPPORT WELDING |  |  | 20 |  |  |  | 11.6 | MTR | 4 |  | 46.4 | 1 | 47.4
SH- DAVIT SUPPORT FIT UP | [6 empty] | 2 | Nos | 2 |  | 4 | 1 | 5
SH- DAVIT WELDING |  |  | 12 |  |  |  | 3 | MTR | 1.6 |  | 4.8 | 1 | 5.8
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-DISH BLANK MARKING | CS |  | 24 | 1700 |  | 1 | 2.125 | MTR | 0.1 |  | 0.2125 | 1 | 1.2125
SC- DISH BLANK CUTTING | CS |  | 30 | 1700 |  | 1 | 2.125 | MTR | 0.25 |  | 0.53125 | 1 | 1.5312
SC- DISH BLANK GRINDING | CS |  | 20 | 1700 |  | 1 | 2.125 | MTR | 0.15 |  | 0.31875 | 1 | 1.3188
SC-SH MARKING | CS |  | 20 | 1640 | 425 | 1 | 4.13 | MTR | 0.1 |  | 0.413 | 1 | 1.413
SC- SH CUTTING | CS |  | 24 | 1640 | 425 | 1 | 11.3066 | MTR | 0.25 |  | 2.8266 | 1 | 3.8266
SC- SH GRINDING | CS |  | 24 | 1640 | 425 | 1 | 11.3066 | MTR | 0.15 |  | 1.696 | 1 | 2.696
SC- SH BEVEL CUTTING | CS |  | 24 | 1640 | 425 | 1 | 11.3066 | M | 0.5 |  | 5.6533 | 1 | 6.6533
SC- SH BEVEL GRINDING | CS |  | 20 | 1700 |  | 1 | 2.125 | M | 1 |  | 2.125 | 1 | 3.125
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-PRE BENDING | CS | STD | 24 | 1640 ID | 425 LG | 1 | 1 |  | 2 |  | 2 | 1 | 3
SC-PRE BEND CUT OFF | CS |  | 24 | 1640 ID | 425 | 1 | 0.425 |  | 0.5 |  | 0.2125 | 1 | 1.2125
SC-LONG SEAM BEVEL | CS |  | 24 | 1640 ID | 425 | 1 | 0.425 |  | 1 |  | 0.425 | 1 | 1.425
SC-ROLLING | CS | STD | 24 | 1640 ID | 425LG | 1 | 1 |  | 2 |  | 2 | 1 | 3
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-LS CORRECTION | CS | STD | 24 | 1640 | 512 | 1 | 0.512 | MTR | 1 |  | 0.512 | 1 | 1.512
SC-LS FIT UP | CS |  | 24 | 1640 | 512 | 1 | 0.512 | MTR | 1 |  | 0.512 | 1 | 1.512
SC-LS WELDING ARRANGMENT | CS | STD | 24 | 1640 | 512 | 1 | 0.512 | MTR | 2 |  | 1.024 | 1 | 2.024
SC-LS WELDING- OUTER | CS |  | 16 | 1640 | 512 | 1 | 0.512 | MTR | 4.02 |  | 2.0582 | 1 | 3.0582
SC-LS WELDING BACK CHIIP | CS |  | 16 | 1640 | 512 | 1 | 0.512 | MTR | 1 |  | 0.512 | 1 | 1.512
SC-LS WELDING INNER | CS |  | 12 | 1640 | 512 | 1 | 0.512 | MTR | 2.5 |  | 1.28 | 1 | 2.28
SC-LS WLDING FLUSH GRIND | CS |  | 12 | 1640 | 512 | 1 | 0.512 | MTR | 0.5 |  | 0.256 | 1 | 1.256
SC-RE ROLLING | CS | STD | 12 | 1640 | 512 | 1 | 1 | No |  |  |  |  | 1 DAY
SC- LS RT | CS | STD | 12 | 1640 | 512 | 1 | 1 | No |  |  |  |  | 1 DAY
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-CS EP CORRECTION | CS | STD | 20 | 1640 | 512 | 1 | 1 | No | 1 |  | 1 | 1 | 2
SC-CIR SEAM FIT UP -DISH | CS |  | 20 | 1640 | 512 | 1 | 5.2157 | MTR | 1 |  | 5.2157 | 1 | 6.2157
SC-CIR SEAM WLDING | CS |  | 14 | 1640 | 512 | 1 | 5.1969 | MTR | 3.22 |  | 16.7339 | 1 | 17.7339
SC-CIR SEAM BACK CHIP | CS |  | 18 | 1640 | 512 | 1 | 5.2094 | MTR | 1 |  | 5.2094 | 1 | 6.2094
SC-CIR SEAM INNER WELDING | CS |  | 6 | 1640 | 512 | 1 | 5.1717 | MTR | 0.9 |  | 4.6546 | 1 | 5.6546
SC-CIR SEAM FIT UP FLG | CS |  | 20 | 1640 | 512 | 1 | 5.2157 | MTR | 1 |  | 5.2157 | 1 | 6.2157
SC-CIR SEAM WELDING | CS |  | 14 | 1640 | 512 | 1 | 5.1969 | MTR | 3.22 |  | 16.7339 | 1 | 17.7339
SC-CIR SEAM BACK CHIP | CS |  | 6 | 1640 | 512 | 1 | 5.1717 | MTR | 1 |  | 5.1717 | 1 | 6.1717
SC-CIR SEAM INNER WELDING | CS |  | 6 | 1640 | 512 | 1 | 5.1717 | MTR | 0.9 |  | 4.6546 | 1 | 5.6546
SC-CIR SEAM FLUSH GRIND | CS |  | 20 | 1640 | 512 | 1 | 5.2157 | MTR | 0.5 |  | 2.6079 | 1 | 3.6079
SC-CIR SEAM RT | CS | STD |  | 1640 | 512 | 1 | 1 | NO |  |  |  |  | 1 DAY
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-OREINTAION MARKING |  |  | 20 | 1640 | 512 | 1 | 1 | NO | 4 |  | 4 | 0 | 4
SC-NOZZLE OPENNIING | STD |  | 2"NB |  |  | 2 | 2 | NO | 2 |  | 4 | 0.5 | 4.5
SC-NOZZLE EP | STD |  | 2"NB |  |  | 2 | 2 | NO | 2 |  | 4 | 0.5 | 4.5
SC-NOZ FIT UP | STD |  | 2"NB |  |  | 2 | 2 | NO | 2 |  | 4 | 0.5 | 4.5
SC-NOZ WELDING |  |  | 14 |  | 0.3142 | 2 | 0.6284 | MTR | 4.4 |  | 2.765 | 1 | 3.765
SC-NOZ WELDING |  |  | 14 |  | 0.3142 | 2 | 0.6284 | MTR | 4.4 |  | 2.765 | 1 | 3.765
SC-NOZ INNER WELDING |  |  | 6 |  | 0.3142 | 2 | 0.6284 | MTR | 0.6 |  | 0.37704 | 1 | 1.377
SC-NOZ INNER WELDING |  |  | 6 |  | 0.3142 | 2 | 0.6284 | MTR | 0.6 |  | 0.37704 | 1 | 1.377
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH-MARKING | CS |  | 18 | 1500 | 921 | 1 | 4.842 | MTR | 0.1 |  | 0.4842 | 1 | 1.4842
CH-CUTTING | CS |  | 18 | 1500 | 921 | 1 | 11.3811 | MTR | 0.25 |  | 2.8453 | 1 | 3.8453
CH-SIDE GRINDING | CS |  | 18 | 1500 | 921 | 1 | 11.3811 | MTR | 0.15 |  | 1.7072 | 1 | 2.7072
CH-BEVEL CUTTING | CS |  | 18 | 1500 | 921 | 1 | 9.5391 | MTR | 0.5 |  | 4.7696 | 1 | 5.7696
CH-BEVEL GRINDING | CS |  | 18 | 1500 | 921 | 1 | 9.5391 | MTR | 1 |  | 9.5391 | 1 | 10.5391
CH-PRE BENDING | CS | STD | 18 | 1500 | 921 | 1 | 1 |  | 2 |  | 2 | 1 | 3
CH-PRE BEND CUT OFF | CS |  | 18 | 1500 | 921 | 1 | 4.684 | MTR | 0.3 |  | 1.4052 | 1 | 2.4052
CH-LONG SEAM BEVEL | CS |  | 18 | 1500 | 921 | 1 | 3 | MTR | 1 |  | 3 | 1 | 4
CH-ROLLING | CS | STD | 18 | 1500 | 921 | 1 | 1 | NO | 3 |  | 3 | 1 | 4
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH-LS EP CORRECTION | CS |  | 18 | 1500 | 921 | 1 | 1.842 | MTR | 0.45 |  | 0.8289 | 1
CH-LS FIT UP | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 1 |  | 0.921 | 1 | 1.921
CH-LS WELDING ARRANGMENT | CS | STD | 18 | 1500 | 921 | 1 | 1 | No | 2 |  | 2 | 1 | 3
CH-LS WELDING- OUTER | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 4.9 |  | 4.5129 | 1 | 5.5129
CH-LS WELDING BACK CHIIP | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 1 |  | 0.921 | 1 | 1.921
CH-LS WELDING INNER | CS |  | 18 | 1500 | 921 | 1 | 0.921 | Mtr | 4.9 |  | 4.5129 | 1 | 5.5129
CH-LS WLDING FLUSH GRIND | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 0.5 |  | 0.4605 | 1 | 1.4605
CH-RE ROLLING | CS | STD | 18 | 1500 | 921 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
CH- LS RT | CS | STD | 18 | 1500 | 921 | 1 | 1 | No | 1 |  | 1 |  | 1
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH-CS LENGTH & EP COR | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 0.45 |  | 0.41445 | 11 | 11.4145
CH-CIR SEAM FIT UP - 2 FLG | CS |  | 18 | 1500 | 921 | 2 | 9.5391 | MTR | 1 |  | 9.5391 | 1 | 10.5391
CH-CIR SEAM WLDING | CS |  | 12 | 1500 | 921 | 2 | 9.5014 | MTR | 2.5 |  | 23.7535 | 1 | 24.7535
CH-CIR SEAM BACK CHIP | CS |  | 18 | 1500 | 921 | 2 | 9.5391 | MTR | 1 |  | 9.5391 | 1 | 10.5391
CH-CIR SEAM INNER WELDING | CS |  | 8 | 1500 | 921 | 2 | 9.4763 | MTR | 1 |  | 9.4763 | 1 | 10.4763
CH-CIR SEAM FLUSH GRIND | CS |  | 18 | 1500 | 921 | 2 | 9.5391 | MTR | 0.5 |  | 4.7696 | 1 | 5.7696
CH-CIR SEAM RT | CS | STD | 18 | 1500 | 921 | 2 | 1 | NO | 1 |  |  |  | 1 DAY
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH-OREINTAION MARKING | CS |  | 18 | 1500 | 921 | 1 | 1 | NO | 3 |  | 3 | 1 | 3
CH-NOZZLE OPENNIING | STD |  | 400NB | 1500 | 921 | 2 | 2 | NO | 4 |  | 8 | 1 | 9
CH-NOZ FIT UP | STD |  | 400NB | 1500 | 921 | 2 | 2 | NO | 4 |  | 8 | 1 | 9
CH-NOZ WELDING |  |  | 18 | 1500 | 921 | 2 | 2.5538 | MTR | 6.8 |  | 17.366 | 1 | 18.366
CHC-NOZ WELD BACK CHIP |  |  | 18 | 1500 | 921 | 2 | 2.5538 | MTR | 1 |  | 2.5538 | 1 | 3.5538
CH-NOZ INNER WELDING |  |  | 10 | 1500 | 921 | 2 | 2.5538 | MTR | 1.2 |  | 3.0646 | 1 | 4.0646
CH-NOZ INNER WELD FLUSH GRIND |  |  | 8 | 1500 | 921 | 2 | 2.5538 | MTR | 0.5 |  | 1.2769 | 1 | 2.2769
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH-PP PL MARKING | CS |  | 25 | 735 | 1275 | 1 | 4.02 | MTR | 0.1 | HR/MTR | 0.402 | 1 | 1.402
CH-PP PL MARKING | CS |  | 25 | 1080 | 1275 | 1 | 4.71 | MTR | 0.1 | HR/MTR | 0.471 | 1 | 1.471
CH-PP PL MARKING | CS |  | 25 | 543 | 1275 | 1 | 3.636 | MTR | 0.1 | HR/MTR | 0.3636 | 1 | 1.3636
CH-PP PL MARKING | CS |  | 25 | 522 | 1275 | 1 | 3.594 | MTR | 0.1 | HR/MTR | 0.3594 | 1 | 1.3594
CH-PP PL CUTTING | CS |  | 25 |  |  |  | 15.96 | MTR | 0.25 | HR/MTR | 3.99 | 1 | 4.99
CH-PP PL GRINDING | CS |  | 25 |  |  | 1 | 15.96 | MTR | 0.15 | HR/MTR | 2.394 | 1 | 3.394
CH-PP PL FIT UP | CS | STD | 25 |  |  |  | 4 | Nos | 2 | No | 8 | 1 | 9
CH-PP PL WELDING | CS |  | 16 |  | 1291 | 8 | 10.328 | MTR | 5.6 | HR/MTR | 57.8368 | 1 | 58.8368
SH- DAVIT SUPPORT FIT UP |  | STD |  |  |  |  | 1 | Nos | 6 | Hr/no | 6 | 1 | 7
SH- DAVIT WELDING |  | STD | 12 |  |  |  | 1 | Nos | 4 | Hr/no | 4 | 1 | 5
SH- all welding dress up |  | STD |  |  |  |  | 1 | Nos | 12 | Hr/no | 12 | 1 | 13
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
FL H DISH MARKING | CS |  | 35 | 1445 |  | 1 | 1.7051 | MTR | 0.1 |  | 0.17051 | 1 | 1.1705
FL H DISH CUTTING | CS |  | 30 | 1445 |  | 1 | 1.7051 | MTR | 0.25 |  | 0.42627 | 1 | 1.4263
FL H DISH GRINDING | CS |  | 30 | 1445 |  | 1 | 1.7051 | MTR | 0.15 |  | 0.25576 | 1 | 1.2558
FL H DISH FORMING | CS | STD | 30 | 1445 |  | 1 | 1.7051 | NO | 10 | DAYS |  |  | 10 DAYS
FL H DISH MKG AFTER FORM | CS |  | 30 | 1445 |  | 1 | 1.7051 | MTR | 0.1 |  | 0.17051 | 1 | 1.1705
FL H DISH CUTTING | CS |  | 30 | 1445 |  | 1 | 4.5402 | MTR | 0.25 |  | 1.135 | 1 | 2.135
FL H DISH BEVEL CUTTING | CS |  | 30 | 1445 | BOTH SIDE | 2 | 9.0804 | MTR | 0.5 |  | 4.5402 | 1 | 5.5402
FL H DISH BEVEL GRINDING | CS |  | 30 | 1450 |  | 2 | 9.1118 | MTR | 1 |  | 9.1118 | 1 | 10.1118
FL H DISH FIT UP | CS |  | 30 | 1450 | BOTH SIDE | 1 | 4.5559 | MTR | 1 |  | 4.5559 | 1 | 5.5559
FL H DISH WELDING | CS |  | 16 | 1450 |  | 1 | 4.5559 | MTR | 5.6 |  | 25.513 | 1 | 26.513
FH-PP PL MARKING | CS |  | 25 | 300 | 1450 | 1 | 3.5 | MTR | 0.1 | HR/MTR | 0.35 | 1 | 1.35
FH-PP PL CUTTING | CS |  | 25 | 300 | 1450 | 1 | 3.5 | MTR | 0.25 | HR/MTR | 0.875 | 1 | 1.875
FH-PP PL GRINDING | CS |  | 25 | 300 | 1450 | 1 | 3.5 | MTR | 0.15 | HR/MTR | 0.525 | 1 | 1.525
FH-PP PL FIT UP | CS | STD | 25 |  |  |  | 1 | Nos | 4 | No | 4 | 1 | 5
FH-PP PL WELDING | CS |  | 18 |  | 1450 | 2 | 2.9 | MTR | 3.4 | HR/MTR | 9.86 | 1 | 10.86
FH GRINDING | [12 empty] | 12
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SEAL ST-MARKING | CS
SLAIDING ST-MARKING | CS |  | 20 | 70 | 8571 | 2 | 34.564 |  | 0.1 |  | 3.4564 | 1 | 4.4564
IMP PL MARKING | CS
IMP ROD MARKING |  |  |  | DIA 25.4 | ~ 1450 | 43 | 43 | No | 0.083333 | HR/ NO | 3.5833
SEAL ROD MARKING |  |  |  | DIA 25.4 | ~7000 | 7 | 7 | No | 0.083333 | HR/ NO | 0.58333
TIE ROD MARKING |  |  |  | DIA 12 | ~ 8000 | 14 | 14 | No | 0.083333 | HR/ NO | 1.1667
SPACER MARKING |  |  |  | 21.8 d |  | 419 | 419 | No | 0.083333 | HR/ NO | 34.9167
CON PIECE MARKING | CS |  | 24 | 100 | 500 | 2 | 2.4 |  | 0.1 |  | 0.24 | 1 | 1.24
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SEAL ST-CUTTING | CS
SLAIDING ST-CUTTING | CS |  | 20 | 70 | 8571 | 2 | 34.564 |  | 0.25 |  | 8.641 | 1 | 9.641
IMP PL CUTTING | CS
IMP ROD CUTTING |  |  |  | DIA 25.4 | ~ 1450 | 43 | 43 | No | 0.16667 | HR/ NO | 7.1667 |  | 7.1667
SEAL ROD CUTTING |  |  |  | DIA 25.4 | ~7000 | 7 | 7 | No | 0.16667 | HR/ NO | 1.1667 |  | 1.1667
TIE ROD CUTTING |  |  |  | DIA 12 | ~ 8000 | 14 | 14 | No | 0.16667 | HR/ NO | 2.3333 |  | 2.3333
SPACER CUTTING |  |  |  | 21.8 d |  | 419 | 419 | No | 0.083333 | HR/ NO | 34.9167 |  | 34.9167
CON PIECE CUTTING | CS |  | 24 | 100 | 500 | 2 | 2.4 |  | 0.25 |  | 0.6 | 1 | 1.6
ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SEAL ST-GRINDING | CS
SLAIDING ST-GRINDING | CS |  | 20 | 70 | 8571 | 2 | 2 |  | 8 |  | 16 | 1 | 17
IMP PL GRININD | CS
IMP ROD M/C |  |  |  | DIA 25.4 | ~ 1450 | 43 | 43 | No | 0.5 | HR/ NO | 21.5 |  | 21.5
SEAL ROD M/C |  |  |  | DIA 25.4 | ~7000 | 7 | 7 | No | 0.5 | HR/ NO | 3.5 |  | 3.5
TIE ROD M/C |  |  |  | DIA 12 | ~ 8000 | 14 | 14 | No | 0.5 | HR/ NO | 7 |  | 7
SPACER M/C |  |  |  | 21.8 d |  | 419 | 419 | No | 0.16667 | HR/ NO | 69.8333 |  | 69.8333
CON PIECE DRILLING | CS |  | 24 | 100 | 500 | 2 | 1 |  | 6 |  | 6 | 1 | 7
FRAME SET UP |  |  | 1000 |  |  | 1 | 1 |  | 12 |  | 12 | 1 | 13
TS ASSY |  |  | 1000 |  |  | 1 | 1 | Nos | 4 |  | 4 | 1 | 5
TIE ROD ASSY |  |  | 1000 |  |  | 17 | 17 | Nos | 0.15 |  | 2.55 | 1 | 3.55
BAFFLE ASSY |  |  | 1000 |  |  | 22 | 22 | Nos | 0.5 |  | 11 | 1 | 12
TUBE INSERT |  |  | 1000 |  |  | 500 | 500 | Nos | 0.083333 |  | 41.6667 | 1 | 42.6667
SEAL ROD ASSY |  |  | 1000 |  |  | 10 | 10 | Nos | 0.25 |  | 2.5 | 1 | 3.5
TUBE INSERT |  |  | 1000 |  |  | 550 | 550 | Nos | 0.083333 |  | 45.8333 | 1 | 46.8333
SEAL STRIP FITUP |  |  | 1000 |  |  | 0 | 0 | Nos | 2 |  | 0 | 1 | 1
SLIDING STRIP FIT UP |  |  | 1000 |  |  | 2 | 2 | Nos | 2 |  | 4 | 1 | 5
WELDING |  |  | 1000 |  |  | 60 | 60 | Nos | 0.25 |  | 15 | 1 | 16
GRINDING |  |  | 1000 |  |  | 60 | 60 | Nos | 0.15 |  | 9 | 1 | 10
BUNDLE INDERT |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
FLH TUBE SHEET ASSY |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
GLAND & TEST RING ASSY |  |  | 1000 |  |  | 56 | 56 | Nos | 0.5 |  | 28 | 1 | 29
TUBE EXP ST SIDE STG1 |  |  | 1000 |  |  | 1050 | 1050 | Nos | 0.05 |  | 52.5 | 1 | 53.5
TUBE EXP FL SIDE STG1 |  |  | 1000 |  |  | 1050 | 1050 | Nos | 0.05 |  | 52.5 | 1 | 53.5
TUBE TRIMMING |  |  | 1000 |  |  | 1461 | 1461 | Nos | 0.05 |  | 73.05 | 1 | 74.05
TUBE EXPANSION BOTH SIDE |  |  | 1000 |  |  | 2100 | 2100 | Nos | 0.05 |  | 105 | 1 | 106
AIR LEAK TEST |  |  | STD |  |  | 1 | 1 | Nos | 10 |  | 10 | 1 | 11
SHELL SIDE HYDRO |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
DISMANTLE TEST RING |  |  | 1000 |  |  | 55 | 55 | BOLT | 0.16667 |  | 9.1667 | 1 | 10.1667
ASSY OF CH & FL HEAD |  |  | 1000 |  |  | 55 | 55 | BOLT | 0.5 |  | 27.5 | 1 | 28.5
CH SIDE HYDRO |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
ASSY OF BARREL |  |  | 1000 |  |  | 55 | 55 | Nos | 0.5 |  | 27.5 | 1 | 28.5
SHELL SIDE HYDRO |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
NOZ PIPE-MARKING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE-MARKING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE-CUTTING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE-CUTTING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE-EP |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE-EP |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE+FIT UP |  |  | 400NB |  |  |  | 1 |  | #N/A |  | #N/A | 1 | #N/A
NOZ PIPE+FIT UP |  |  | 400NB |  |  |  | 1 |  | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
NOZ PIPE + FLG WELD |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 4.02 |  | 5.1332 | 1 | 6.1332
NOZ PIPE + FLG WELD |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 4.02 |  | 5.1332 | 1 | 6.1332
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
NOZ BORE FLUSH GRIND |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 0.5 |  | 0.63845 | 1 | 1.6385
NOZ BORE FLUSH GRIND |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 0.5 |  | 0.63845 | 1 | 1.6385
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
NOZ PROFILE MARKING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
NOZ PROFILE MARKING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
NOZ PROFILE CUTTING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
NOZ PROFILE CUTTING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
NOZ PROFILE GRINDING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
NOZ PROFILE GRINDING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | NB | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
RF PAD MARKING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
RF PAD MARKING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
RF PAD CUTTING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
RF PAD CUTTING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
RF PAD EP |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
RF PAD EP |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
RF PAD FORMING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
RF PAD FORMING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
ACTIVITY J 4220 B | MOC |  | THK | WIDTH | LENGTH | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SAD PAD- TOP-MARKING | CS |  | 25 | 320 | 1736 | 0 | 0 |  | 0.1 |  | 0 | 1 | 1
SAD PAD- BOT-MARKING | CS |  | 25 | 320 | 4904 | 2 | 20.896 |  | 0.1 |  | 2.0896 | 1 | 3.0896
SAD BASE- TOP-MARKING | CS |  | 30 | 320 | 1890 | 0 | 0 |  | 0.1 |  | 0 | 1 | 1
SAD BASE- BOT-MARKING | CS |  | 30 | 320 | 1890 | 4 | 17.68 |  | 0.1 |  | 1.768 | 1 | 2.768
SAD WEB- TOP-MARKING | CS |  | 25 | 2336 | 1890 | 0 | 0 |  | 0.1 |  | 0 | 1 | 1
SAD RIB-MARKING | CS |  | 30 | 135 | 400 | 16 | 17.12 |  | 0.1 |  | 1.712 | 1 | 2.712
11.5696
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SAD PAD- TOP-CUTTING | CS |  | 25 | 320 | 1736 | 0 | 0 |  | 0.25 |  | 0 | 1 | 1
SAD PAD- BOT-CUTTING | CS |  | 25 | 320 | 4904 | 2 | 20.896 |  | 0.25 |  | 5.224 | 1 | 6.224
SAD BASE- TOP-CUTTING | CS |  | 30 | 320 | 1890 | 0 | 0 |  | 0.25 |  | 0 | 1 | 1
SAD BASE- BOT-CUTTING | CS |  | 30 | 320 | 1890 | 4 | 17.68 |  | 0.25 |  | 4.42 | 1 | 5.42
SAD WEB- TOP-CUTTING | CS |  | 25 | 2336 | 1890 | 0 | 0 |  | 0.25 |  | 0 | 1 | 1
SAD RIB-CUTTING | CS |  | 30 | 135 | 400 | 16 | 17.12 |  | 0.25 |  | 4.28 | 1 | 5.28
19.924
ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SAD PAD- TOP-CUTTING | CS |  | 25 | 320 | 1736 | 0 | 0 |  | 0.15 |  | 0 | 1 | 1
SAD PAD- BOT-CUTTING | CS |  | 25 | 320 | 4904 | 2 | 20.896 |  | 0.15 |  | 3.1344 | 1 | 4.1344
SAD BASE- TOP-CUTTING | CS |  | 30 | 320 | 1890 | 0 | 0 |  | 0.15 |  | 0 | 1 | 1
SAD BASE- BOT-CUTTING | CS |  | 30 | 320 | 1890 | 4 | 17.68 |  | 0.15 |  | 2.652 | 1 | 3.652
SAD WEB- TOP-CUTTING | CS |  | 25 | 2336 | 1890 | 0 | 0 |  | 0.15 |  | 0 | 1 | 1
SAD RIB-CUTTING | CS |  | 30 | 135 | 400 | 16 | 17.12 |  | 0.15 |  | 2.568 | 1 | 3.568
14.3544
ACTIVITY J 4220 B | MOC |  | THK |  |  | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SADDLE FIT UP | CS |  | 25 |  |  | 2 | 2 | Nos | 12 |  | 24 | 1 | 25
SADDLE FIT WELDING | CS |  | 25 |  |  | 2 | 0 |  | 0.15 |  | 0 | 1 | 1
vessel od | 1536
Pad thk | 25
Total OD | 1561
Half Support |  | thk | fillet size | Long | Qty | Length of welding | welding hr | welding time - Hr
Saddle base + Web |  |  | 18 | 1890 | 1 | 1890 | 3.4 | 6.426
Web+Rib |  |  | 18 | 539 | 4 | 4312 | 3.4 | 14.6608
Base to Rib |  |  | 18 | 138 | 4 | 1104 | 3.4 | 3.7536
24.8404
[6 empty] | No of Side | 4
[6 empty] | Tolal long |  | 99.3616 | Hrs
vessel od | 1536
Pad thk | 25
Total OD | 1561
FULL SUPPOR |  | thk | fillet size | Long | Qty | Length of welding | welding hr | welding time - Hr
Base to Web- Bot & bot |  |  | 18 | 1890 | 2 | 1890 | 3.4 | 6.426
Web to side |  |  | 18 | 2336 | 2 | 9344 | 3.4 | 31.7696
Side to base |  |  | 18 | 320 | 1 | 640 | 3.4 | 2.176
Rib to Web |  |  | 18 | 775 | 4 | 6200 | 3.4 | 38.1956
Rib to base |  |  | 18 | 160 | 4 | 2560 | 3.4 | 33.9456
112.5128
[6 empty] | No of Side | 4 | 450.0512

## ACTIVITY (hidden)
| ACTIVITY J 4220 B | MOC |  | THK | W | LONG/ CIR | QTY | WORK | UOM | BENCH MARK TIME |  | WORK | SETTING TIME | DURATION -HR
| SH-MARKING | CS |  | 18 | 2500 | 5000 | 2 | 30 | M | 0.1 |  | 3 | 1 | 4
| SH-MARKING | CS |  | 18 | 2000 | 5000 | 1 | 14 | M | 0.1 |  | 1.4 | 1 | 2.4
| SH-MARKING | CS |  | 18 | 1250 | 5000 | 1 | 12.5 | M | 0.1 |  | 1.25 | 1 | 2.25
-
| SH-CUTTING | CS |  | 18 | 2500 | 5000 | 2 | 30 | M | 0.25 |  | 7.5 | 1 | 8.5
| SH-CUTTING | CS |  | 18 | 2000 | 5000 | 1 | 14 | M | 0.25 |  | 3.5 | 1 | 4.5
| SH-CUTTING | CS |  | 18 | 1250 | 5000 | 1 | 12.5 | M | 0.25 |  | 3.125 | 1 | 4.125
| SH-SIDE GRINDING | CS |  | 18 | 2500 | 5000 | 2 | 30 | M | 0.15 |  | 4.5 | 1 | 5.5
| SH-SIDE GRINDING | CS |  | 18 | 2000 | 5000 | 1 | 14 | M | 0.15 |  | 2.1 | 1 | 3.1
| SH-SIDE GRINDING | CS |  | 18 | 1250 | 5000 | 1 | 12.5 | M | 0.15 |  | 1.875 | 1 | 2.875
| SH-BEVEL CUTTING | CS |  | 18 | 2500 | 5000 | 2 | 20 | M | 0.5 |  | 10 | 1 | 11
| SH-BEVEL CUTTING | CS |  | 18 | 2000 | 5000 | 1 | 10 | M | 0.5 |  | 5 | 1 | 6
| SH-BEVEL CUTTING | CS |  | 18 | 1000 | 5000 | 1 | 10 | M | 0.5 |  | 5 | 1 | 6
| SH-BEVEL GRINDING | CS |  | 18 | 2500 | 5000 | 2 | 20 | M | 1 |  | 20 | 1 | 21
| SH-BEVEL GRINDING | CS |  | 18 | 2000 | 5000 | 1 | 10 | M | 1 |  | 10 | 1 | 11
| SH-BEVEL GRINDING | CS |  | 18 | 1250 | 5000 | 1 | 10 | M | 1 |  | 10 | 1 | 11
| SH-PRE BENDING | CS |  | 18 | 2500 | 5000 | 1 | 1 | No | 2 |  | 2 | 1 | 3
| SH-PRE BENDING | CS |  | 18 | 2500 | 5000 | 1 | 1 | No | 2 |  | 2 | 1 | 3
| SH-PRE BENDING | CS |  | 18 | 2000 | 5000 | 1 | 1 | NO | 2 |  | 2 | 1 | 3
| SH-PRE BENDING | CS |  | 18 | 1250 | 5000 | 1 | 1 | NO | 2 |  | 2 | 1 | 3
| SH-PRE BEND CUT OFF | CS |  | 18 | 2500 | 5000 | 1 | 5 | M | 0.3 |  | 1.5 | 1 | 2.5
| SH-PRE BEND CUT OFF | CS |  | 18 | 2500 | 5000 | 1 | 5 | M | 0.3 |  | 1.5 | 1 | 2.5
| SH-PRE BEND CUT OFF | CS |  | 18 | 2000 | 5000 | 1 | 4 | M | 0.3 |  | 1.2 | 1 | 2.2
| SH-PRE BEND CUT OFF | CS |  | 18 | 1250 | 5000 | 1 | 2.5 | M | 0.3 |  | 0.75 | 1 | 1.75
| SH-LONG SEAM BEVEL | CS |  | 18 | 2500 | 4769 | 2 | 5 | M | 1 |  | 5 | 1 | 6
| SH-LONG SEAM BEVEL | CS |  | 18 | 2500 | 4769 | 1 | 5 | M | 1 |  | 5 | 1 | 6
| SH-LONG SEAM BEVEL | CS |  | 18 | 2000 | 4769 | 1 | 4 | M | 1 |  | 4 | 1 | 5
| SH-LONG SEAM BEVEL | CS |  | 18 | 1250 | 4769 | 1 | 2.5 | M | 1 |  | 2.5 | 1 | 3.5
| SH-LS EP | CS |  | 18 | 2500 | 4769 | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
| SH-LS EP | CS |  | 24 | 2500 | 4769 | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
| SH-LS EP | CS |  | 24 | 2000 | 4769 | 1 | 2 | MTR | 1 |  | 2 | 1 | 3
| SH-LS EP | CS |  | 24 | 1250 | 4769 | 1 | 1.25 | MTR | 1 |  | 1.25 | 1 | 2.25
| SH-ROLLING | CS | STD | 24 | 2500 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
| SH-ROLLING | CS | STD | 24 | 2500 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
| SH-ROLLING | CS | STD | 24 | 2000 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
| SH-ROLLING | CS | STD | 24 | 1250 | 4769 | 1 | 1 | No | 3 |  | 3 | 1 | 4
| SH-LS FIT UP | CS |  | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
| SH-LS FIT UP | CS |  | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
| SH-LS FIT UP | CS |  | 24 | 2000 | 1500 ID | 1 | 2 | MTR | 1 |  | 2 | 1 | 3
| SH-LS FIT UP | CS |  | 24 | 1250 | 1500 ID | 1 | 1.25 | MTR | 1 |  | 1.25 | 1 | 2.25
| SH-LS TACK DP CHECK | CS | STD | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
| SH-LS TACK DP CHECK | CS | STD | 24 | 2500 | 1500 ID | 1 | 2.5 | MTR | 1 |  | 2.5 | 1 | 3.5
| SH-LS TACK DP CHECK | CS | STD | 24 | 2000 | 1500 ID | 1 | 2 | MTR | 1 |  | 2 | 1 | 3
| SH-LS TACK DP CHECK | CS | STD | 24 | 1250 | 1500 ID | 1 | 1.25 | MTR | 1 |  | 1.25 | 1 | 2.25
| SH-LS WELDING ARRANGMENT | CS | STD | 24 | 2500 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
| SH-LS WELDING ARRANGMENT | CS | STD | 24 | 2500 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
| SH-LS WELDING ARRANGMENT | CS | STD | 24 | 2000 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
| SH-LS WELDING ARRANGMENT | CS | STD | 24 | 1250 | 1500 ID | 1 | 1 | No | 2 |  | 2 | 1 | 3
| SH-LS WELDING- OUTER | CS |  | 12 | 2500 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
| SH-LS WELDING- OUTER | CS |  | 12 | 2500 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
| SH-LS WELDING- OUTER | CS |  | 12 | 2000 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
| SH-LS WELDING- OUTER | CS |  | 12 | 1250 | 4769 | 1 | 4.769 | No | 2.5 |  | 11.9225 | 1 | 12.9225
| SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 2500 | 1 | 2.5 | No | 1 |  | 2.5 | 1 | 3.5
| SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 2500 | 1 | 2.5 | No | 1 |  | 2.5 | 1 | 3.5
| SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 2500 | 1 | 2.5 | No | 1 |  | 2.5 | 1 | 3.5
| SH-LS WELDING BACK CHIIP | CS |  | 6 | 1500 id | 1250 | 1 | 1.25 | No | 1 |  | 1.25 | 1 | 2.25
| SH-LS WELDING INNER | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | Mtr | 2.5 |  | 6.25 | 1 | 7.25
| SH-LS WELDING INNER | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | Mtr | 2.5 |  | 6.25 | 1 | 7.25
| SH-LS WELDING INNER | CS |  | 12 | 2000 | 1500 id | 1 | 2 | Mtr | 2.5 |  | 5 | 1 | 6
| SH-LS WELDING INNER | CS |  | 12 | 1250 | 1500 id | 1 | 1.25 | Mtr | 2.5 |  | 3.125 | 1 | 4.125
| SH-LS WLDING FLUSH GRIND | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | MTR | 0.5 |  | 1.25 | 1 | 2.25
| SH-LS WLDING FLUSH GRIND | CS |  | 12 | 2500 | 1500 id | 1 | 2.5 | MTR | 0.5 |  | 1.25 | 1 | 2.25
| SH-LS WLDING FLUSH GRIND | CS |  | 12 | 2000 | 1500 id | 1 | 2 | MTR | 0.5 |  | 1 | 1 | 2
| SH-LS WLDING FLUSH GRIND | CS |  | 12 | 1250 | 1500 id | 1 | 1.25 | MTR | 0.5 |  | 0.625 | 1 | 1.625
| SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
| SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
| SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
| SH-RE ROLLING | CS | STD | 12 | 1500ID | 5000 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
| SH- LS RT | CS | STD | 12 | 1550 ID | 2500 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
| SH- LS RT | CS | STD | 12 | 1550 ID | 2500 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
| SH- LS RT | CS | STD | 12 | 1550 ID | 2000 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
| SH- LS RT | CS | STD | 12 | 1550 ID | 1000 LG | 1 | 1 | No | 1 DAY |  |  |  | 1 DAY
| SH-CS EP CORRECTION | CS | STD | 24 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
| SH-CS EP CORRECTION | CS | STD | 24 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
| SH-CS EP CORRECTION | CS | STD | 24 | 2000 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
| SH-CS EP CORRECTION | CS | STD | 24 | 1000 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
| SH-CIR SEAM FIT UP -1 | CS |  | 18 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
| SH-CIR SEAM FIT UP -2 | CS |  | 18 | 2500 | 4945 | 1 | 4.945 | MTR | 1 |  | 4.945 | 1 | 5.945
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-CIR SEAM WLDING-1 | CS |  | 18 | 1500 | 2500 | 1 | 4.7696 | MTR | 4.9 | HR/MTR | 23.3708 | 1 | 24.3708
| SH-CIR SEAM WLDING-2 | CS |  | 18 | 1500 | 2500 | 1 | 4.7696 | MTR | 4.9 | HR/MTR | 23.3708 | 1 | 24.3708
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-CIR SEAM BACK CHIP-1 | CS |  | 16 | 1500 |  | 1 | 4.7633 | MTR | 1 |  | 4.7633 | 1 | 5.7633
| SH-CIR SEAM BACK CHIP-2 | CS |  | 16 | 1500 |  | 1 | 4.7633 | MTR | 1 |  | 4.7633 | 1 | 5.7633
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-CIR SEAM INNER WELDING-1 | CS |  | 6 | 1500 |  | 1 | 4.7319 | MTR | 0.9 |  | 4.2587 | 1 | 5.2587
| SH-CIR SEAM INNER WELDING-2 | CS |  | 6 | 1500 |  | 1 | 4.7319 | MTR | 0.9 |  | 4.2587 | 1 | 5.2587
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-CIR SEAM FIT UP - 8 MTR | CS |  | 18 | 1500 |  | 1 | 4.713 | MTR | 1 |  | 4.713 | 1 | 5.713
| SH-CIR SEAM WELDING | CS |  | 12 | 1500 |  | 1 | 4.713 | MTR | 2.5 |  | 11.7825 | 1 | 12.7825
| SH-CIR SEAM BACK CHIP | CS |  | 18 | 1500 |  | 1 | 4.713 | MTR | 1 |  | 4.713 | 1 | 5.713
| SH-CIR SEAM INNER WELDING | CS |  | 6 | 1500 |  | 1 | 4.713 | MTR | 0.9 |  | 4.2417 | 1 | 5.2417
| SH-CIR SEAM FLUSH GRIND | CS |  | 18 | 1500 |  | 1 | 4.713 | MTR | 0.5 |  | 2.3565 | 1 | 3.3565
| SH-CIR SEAM RT | CS | STD | 18 | 1500 |  | 1 | 4.713 | NO | 1 |  | 4.713 |  | 4.713
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-TOTAL LENGTH MKG | CS |  | 24 | 1500 |  | 1 | 4.713 | Mtr | 0.1 |  | 0.4713 | 0.5 | 0.9713
| SH- TOTAL LENGTH CTG | CS |  | 24 | 1500 |  | 1 | 4.713 | Mtr | 0.5 |  | 2.3565 | 0.5 | 2.8565
| SH- CS EP BOTH SIDE | CS |  | 24 | 1500 |  | 2 | 4.713 | Mtr | 1 |  | 4.713 | 0.5 | 5.213
| SH-CS FLG 1&2 FIT UP | CS |  | 24 | 1500 |  | 2 | 4.713 | Mtr | 1 |  | 4.713 | 0.5 | 5.213
| SH-CS FLG 1&2 WELDING | CS |  | 16 | 1500 |  | 2 | 4.713 | Mtr | 4.02 |  | 18.9463 | 0.5 | 19.4463
| SH-CS FLG 1&2 BACK CHIP | CS |  | 16 | 1500 |  | 2 | 4.713 | Mtr | 1 |  | 4.713 | 0.5 | 5.213
| SH-CS FLG 1&2 INNER WELD | CS |  | 10 | 1500 |  | 2 | 4.713 | Mtr | 1.88 |  | 8.8604 | 0.5 | 9.3604
| SH-CIR SEAM FLUSH GRIND | CS |  | 10 | 1500 |  | 2 | 4.713 | Mtr | 0.5 |  | 2.3565 | 0.5 | 2.8565
| SH-CIR SEAM RT | CS | STD | 10 | 1500 |  | 2 |  |  | 1 DAY |  |  |  | 1 DAY
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-OREINTAION MARKING |  | STD | 18 | 1500 | 8437 LG | 1 | 1 | No | 4 |  | 4 | 1 | 5
| SH-NOZZLE MARKING | std |  | 30" | SRN |  | 3 | 3 | Nos | 4 |  | 12 | 1 | 13
| SH-NOZZLE OPENNIING | STD |  | 30" |  | ON SHELL | 3 | 3 | NO | 4 |  | 12 | 1 | 13
| SH-NOZZLE OPENNIING EP | STD |  | 30" |  | ON SHELL | 3 | 3 | Nos | 8 |  | 24 | 1 | 25
| SH-NOZ FIT UP | STD |  | 30" |  |  | 2 | 2 | NO | 4 |  | 8 | 1 | 9
| SH-NOZ WELDING |  |  | 12 | 1197 |  | 1 | 3.761 | MTR | 2.5 |  | 9.4024 | 1 | 10.4024
| SH-NOZ WELDIG BACK CHIP |  |  | 18 | 1197 |  | 1 | 3.761 | MTR | 1 |  | 3.761 | 1 | 4.761
| SH-NOZ INNER WELDING |  |  | 8 | 1197 |  | 1 | 3.761 | MTR | 1.36 |  | 5.1149 | 1 | 6.1149
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SH-SUPPORT PAD FIT UP |  |  | 30 | 1500 |  | 2 | 9.6145 | MTR | 1 |  | 9.6145 | 1 | 10.6145
| SH-WELDING |  |  | 20 | 1500 |  | 2 | 18.852 | MTR | 4 |  | 75.408 | 1 | 76.408
| SH-SUPPORT FIT UP |  | std |  |  |  | 2 | 2 | Nos | 4 |  | 8 | 1 | 9
| SH-SUPPORT WELDING |  |  | 20 |  |  |  | 11.6 | MTR | 4 |  | 46.4 | 1 | 47.4
| SH- DAVIT SUPPORT FIT UP | [6 empty] | 2 | Nos | 2 |  | 4 | 1 | 5
| SH- DAVIT WELDING |  |  | 12 |  |  |  | 3 | MTR | 1.6 |  | 4.8 | 1 | 5.8
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-SH MARKING ,CUTTING & GRINDING | SC-DISH BLANK MARKING | CS |  | 24 | 1700 |  | 1 | 2.125 | MTR | 0.1 |  | 0.2125 | 1 | 1.2125
| SC- DISH BLANK CUTTING | CS |  | 30 | 1700 |  | 1 | 2.125 | MTR | 0.25 |  | 0.53125 | 1 | 1.5312
| SC- DISH BLANK GRINDING | CS |  | 20 | 1700 |  | 1 | 2.125 | MTR | 0.15 |  | 0.31875 | 1 | 1.3188
| SC-SH MARKING | CS |  | 20 | 1640 | 425 | 1 | 4.13 | MTR | 0.1 |  | 0.413 | 1 | 1.413
| SC- SH CUTTING | CS |  | 24 | 1640 | 425 | 1 | 11.3066 | MTR | 0.25 |  | 2.8266 | 1 | 3.8266
| SC- SH GRINDING | CS |  | 24 | 1640 | 425 | 1 | 11.3066 | MTR | 0.15 |  | 1.696 | 1 | 2.696
| SC- SH BEVEL CUTTING | CS |  | 24 | 1640 | 425 | 1 | 11.3066 | M | 0.5 |  | 5.6533 | 1 | 6.6533
| SC- SH BEVEL GRINDING | CS |  | 20 | 1700 |  | 1 | 2.125 | M | 1 |  | 2.125 | 1 | 3.125
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC-SH PRE BEND | SC-PRE BENDING | CS | STD | 24 | 1640 ID | 425 LG | 1 | 1 |  | 2 |  | 2 | 1 | 3
| SC-PRE BEND CUT OFF | CS |  | 24 | 1640 ID | 425 | 1 | 0.425 |  | 0.5 |  | 0.2125 | 1 | 1.2125
| SC-LONG SEAM BEVEL | CS |  | 24 | 1640 ID | 425 | 1 | 0.425 |  | 1 |  | 0.425 | 1 | 1.425
| SC-ROLLING | CS | STD | 24 | 1640 ID | 425LG | 1 | 1 |  | 2 |  | 2 | 1 | 3
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC- SH ROLLING & LS FIT UP | SC-LS CORRECTION | CS | STD | 24 | 1640 | 512 | 1 | 0.512 | MTR | 1 |  | 0.512 | 1 | 1.512
| SC-LS FIT UP | CS |  | 24 | 1640 | 512 | 1 | 0.512 | MTR | 1 |  | 0.512 | 1 | 1.512
| SC-LS WELDING ARRANGMENT | CS | STD | 24 | 1640 | 512 | 1 | 0.512 | MTR | 2 |  | 1.024 | 1 | 2.024
| SC-LS WELDING- OUTER | CS |  | 16 | 1640 | 512 | 1 | 0.512 | MTR | 4.02 |  | 2.0582 | 1 | 3.0582
| SC-LS WELDING BACK CHIIP | CS |  | 16 | 1640 | 512 | 1 | 0.512 | MTR | 1 |  | 0.512 | 1 | 1.512
| SC-LS WELDING INNER | CS |  | 12 | 1640 | 512 | 1 | 0.512 | MTR | 2.5 |  | 1.28 | 1 | 2.28
| SC-LS WLDING FLUSH GRIND | CS |  | 12 | 1640 | 512 | 1 | 0.512 | MTR | 0.5 |  | 0.256 | 1 | 1.256
| SC-RE ROLLING | CS | STD | 12 | 1640 | 512 | 1 | 1 | No |  |  |  |  | 1 DAY
| SC- LS RT | CS | STD | 12 | 1640 | 512 | 1 | 1 | No |  |  |  |  | 1 DAY
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
SC- DISH FLG FIT UP & WELDING | SC-CS EP CORRECTION | CS | STD | 20 | 1640 | 512 | 1 | 1 | No | 1 |  | 1 | 1 | 2
| SC-CIR SEAM FIT UP -DISH | CS |  | 20 | 1640 | 512 | 1 | 5.2157 | MTR | 1 |  | 5.2157 | 1 | 6.2157
| SC-CIR SEAM WLDING | CS |  | 14 | 1640 | 512 | 1 | 5.1969 | MTR | 3.22 |  | 16.7339 | 1 | 17.7339
| SC-CIR SEAM BACK CHIP | CS |  | 18 | 1640 | 512 | 1 | 5.2094 | MTR | 1 |  | 5.2094 | 1 | 6.2094
| SC-CIR SEAM INNER WELDING | CS |  | 6 | 1640 | 512 | 1 | 5.1717 | MTR | 0.9 |  | 4.6546 | 1 | 5.6546
| SC-CIR SEAM FIT UP FLG | CS |  | 20 | 1640 | 512 | 1 | 5.2157 | MTR | 1 |  | 5.2157 | 1 | 6.2157
| SC-CIR SEAM WELDING | CS |  | 14 | 1640 | 512 | 1 | 5.1969 | MTR | 3.22 |  | 16.7339 | 1 | 17.7339
| SC-CIR SEAM BACK CHIP | CS |  | 6 | 1640 | 512 | 1 | 5.1717 | MTR | 1 |  | 5.1717 | 1 | 6.1717
| SC-CIR SEAM INNER WELDING | CS |  | 6 | 1640 | 512 | 1 | 5.1717 | MTR | 0.9 |  | 4.6546 | 1 | 5.6546
| SC-CIR SEAM FLUSH GRIND | CS |  | 20 | 1640 | 512 | 1 | 5.2157 | MTR | 0.5 |  | 2.6079 | 1 | 3.6079
| SC-CIR SEAM RT | CS | STD |  | 1640 | 512 | 1 | 1 | NO |  |  |  |  | 1 DAY
SHELL COVER ORENTAION MARKING | ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SC-OREINTAION MARKING |  |  | 20 | 1640 | 512 | 1 | 1 | NO | 4 |  | 4 | 0 | 4
| SC-NOZZLE OPENNIING | STD |  | 2"NB |  |  | 2 | 2 | NO | 2 |  | 4 | 0.5 | 4.5
| SC-NOZZLE EP | STD |  | 2"NB |  |  | 2 | 2 | NO | 2 |  | 4 | 0.5 | 4.5
| SC-NOZ FIT UP | STD |  | 2"NB |  |  | 2 | 2 | NO | 2 |  | 4 | 0.5 | 4.5
| SC-NOZ WELDING |  |  | 14 |  | 0.3142 | 2 | 0.6284 | MTR | 4.4 |  | 2.765 | 1 | 3.765
| SC-NOZ WELDING |  |  | 14 |  | 0.3142 | 2 | 0.6284 | MTR | 4.4 |  | 2.765 | 1 | 3.765
| SC-NOZ INNER WELDING |  |  | 6 |  | 0.3142 | 2 | 0.6284 | MTR | 0.6 |  | 0.37704 | 1 | 1.377
| SC-NOZ INNER WELDING |  |  | 6 |  | 0.3142 | 2 | 0.6284 | MTR | 0.6 |  | 0.37704 | 1 | 1.377
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH MARKING ,CUTTING & ROLLING | CH-MARKING | CS |  | 18 | 1500 | 921 | 1 | 4.842 | MTR | 0.1 |  | 0.4842 | 1 | 1.4842
| CH-CUTTING | CS |  | 18 | 1500 | 921 | 1 | 11.3811 | MTR | 0.25 |  | 2.8453 | 1 | 3.8453
| CH-SIDE GRINDING | CS |  | 18 | 1500 | 921 | 1 | 11.3811 | MTR | 0.15 |  | 1.7072 | 1 | 2.7072
| CH-BEVEL CUTTING | CS |  | 18 | 1500 | 921 | 1 | 9.5391 | MTR | 0.5 |  | 4.7696 | 1 | 5.7696
| CH-BEVEL GRINDING | CS |  | 18 | 1500 | 921 | 1 | 9.5391 | MTR | 1 |  | 9.5391 | 1 | 10.5391
| CH-PRE BENDING | CS | STD | 18 | 1500 | 921 | 1 | 1 |  | 2 |  | 2 | 1 | 3
| CH-PRE BEND CUT OFF | CS |  | 18 | 1500 | 921 | 1 | 4.684 | MTR | 0.3 |  | 1.4052 | 1 | 2.4052
| CH-LONG SEAM BEVEL | CS |  | 18 | 1500 | 921 | 1 | 3 | MTR | 1 |  | 3 | 1 | 4
| CH-ROLLING | CS | STD | 18 | 1500 | 921 | 1 | 1 | NO | 3 |  | 3 | 1 | 4
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH LS FIT & WELDING | CH-LS EP CORRECTION | CS |  | 18 | 1500 | 921 | 1 | 1.842 | MTR | 0.45 |  | 0.8289 | 1
| CH-LS FIT UP | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 1 |  | 0.921 | 1 | 1.921
| CH-LS WELDING ARRANGMENT | CS | STD | 18 | 1500 | 921 | 1 | 1 | No | 2 |  | 2 | 1 | 3
| CH-LS WELDING- OUTER | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 4.9 |  | 4.5129 | 1 | 5.5129
| CH-LS WELDING BACK CHIIP | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 1 |  | 0.921 | 1 | 1.921
| CH-LS WELDING INNER | CS |  | 18 | 1500 | 921 | 1 | 0.921 | Mtr | 4.9 |  | 4.5129 | 1 | 5.5129
| CH-LS WLDING FLUSH GRIND | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 0.5 |  | 0.4605 | 1 | 1.4605
| CH-RE ROLLING | CS | STD | 18 | 1500 | 921 | 1 | 1 | No | 0.5 |  | 0.5 | 1 | 1.5
| CH- LS RT | CS | STD | 18 | 1500 | 921 | 1 | 1 | No | 1 |  | 1 |  | 1
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH FLG FIT & WELDING | CH-CS LENGTH & EP COR | CS |  | 18 | 1500 | 921 | 1 | 0.921 | MTR | 0.45 |  | 0.41445 | 11 | 11.4145
| CH-CIR SEAM FIT UP - 2 FLG | CS |  | 18 | 1500 | 921 | 2 | 9.5391 | MTR | 1 |  | 9.5391 | 1 | 10.5391
| CH-CIR SEAM WLDING | CS |  | 12 | 1500 | 921 | 2 | 9.5014 | MTR | 2.5 |  | 23.7535 | 1 | 24.7535
| CH-CIR SEAM BACK CHIP | CS |  | 18 | 1500 | 921 | 2 | 9.5391 | MTR | 1 |  | 9.5391 | 1 | 10.5391
| CH-CIR SEAM INNER WELDING | CS |  | 8 | 1500 | 921 | 2 | 9.4763 | MTR | 1 |  | 9.4763 | 1 | 10.4763
| CH-CIR SEAM FLUSH GRIND | CS |  | 18 | 1500 | 921 | 2 | 9.5391 | MTR | 0.5 |  | 4.7696 | 1 | 5.7696
| CH-CIR SEAM RT | CS | STD | 18 | 1500 | 921 | 2 | 1 | NO | 1 |  |  |  | 1 DAY
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH OIRENTAION NOZ WELDING | CH-OREINTAION MARKING | CS |  | 18 | 1500 | 921 | 1 | 1 | NO | 3 |  | 3 | 1 | 3
| CH-NOZZLE OPENNIING | STD |  | 400NB | 1500 | 921 | 2 | 2 | NO | 4 |  | 8 | 1 | 9
| CH-NOZ FIT UP | STD |  | 400NB | 1500 | 921 | 2 | 2 | NO | 4 |  | 8 | 1 | 9
| CH-NOZ WELDING |  |  | 18 | 1500 | 921 | 2 | 2.5538 | MTR | 6.8 |  | 17.366 | 1 | 18.366
| CHC-NOZ WELD BACK CHIP |  |  | 18 | 1500 | 921 | 2 | 2.5538 | MTR | 1 |  | 2.5538 | 1 | 3.5538
| CH-NOZ INNER WELDING |  |  | 10 | 1500 | 921 | 2 | 2.5538 | MTR | 1.2 |  | 3.0646 | 1 | 4.0646
| CH-NOZ INNER WELD FLUSH GRIND |  |  | 8 | 1500 | 921 | 2 | 2.5538 | MTR | 0.5 |  | 1.2769 | 1 | 2.2769
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
CH PP PLATE MKG, CTG,WELDING | CH-PP PL MARKING | CS |  | 25 | 735 | 1275 | 1 | 4.02 | MTR | 0.1 | HR/MTR | 0.402 | 1 | 1.402
| CH-PP PL MARKING | CS |  | 25 | 1080 | 1275 | 1 | 4.71 | MTR | 0.1 | HR/MTR | 0.471 | 1 | 1.471
| CH-PP PL MARKING | CS |  | 25 | 543 | 1275 | 1 | 3.636 | MTR | 0.1 | HR/MTR | 0.3636 | 1 | 1.3636
| CH-PP PL MARKING | CS |  | 25 | 522 | 1275 | 1 | 3.594 | MTR | 0.1 | HR/MTR | 0.3594 | 1 | 1.3594
| CH-PP PL CUTTING | CS |  | 25 |  |  |  | 15.96 | MTR | 0.25 | HR/MTR | 3.99 | 1 | 4.99
| CH-PP PL GRINDING | CS |  | 25 |  |  | 1 | 15.96 | MTR | 0.15 | HR/MTR | 2.394 | 1 | 3.394
| CH-PP PL FIT UP | CS | STD | 25 |  |  |  | 4 | Nos | 2 | No | 8 | 1 | 9
| CH-PP PL WELDING | CS |  | 16 |  | 1291 | 8 | 10.328 | MTR | 5.6 | HR/MTR | 57.8368 | 1 | 58.8368
| SH- DAVIT SUPPORT FIT UP |  | STD |  |  |  |  | 1 | Nos | 6 | Hr/no | 6 | 1 | 7
| SH- DAVIT WELDING |  | STD | 12 |  |  |  | 1 | Nos | 4 | Hr/no | 4 | 1 | 5
| SH- all welding dress up |  | STD |  |  |  |  | 1 | Nos | 12 | Hr/no | 12 | 1 | 13
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
FL HEAD DISH | FL H DISH MARKING | CS |  | 35 | 1445 |  | 1 | 1.7051 | MTR | 0.1 |  | 0.17051 | 1 | 1.1705
| FL H DISH CUTTING | CS |  | 30 | 1445 |  | 1 | 1.7051 | MTR | 0.25 |  | 0.42627 | 1 | 1.4263
| FL H DISH GRINDING | CS |  | 30 | 1445 |  | 1 | 1.7051 | MTR | 0.15 |  | 0.25576 | 1 | 1.2558
| FL H DISH FORMING | CS | STD | 30 | 1445 |  | 1 | 1.7051 | NO | 10 | DAYS |  |  | 10 DAYS
| FL H DISH MKG AFTER FORM | CS |  | 30 | 1445 |  | 1 | 1.7051 | MTR | 0.1 |  | 0.17051 | 1 | 1.1705
| FL H DISH CUTTING | CS |  | 30 | 1445 |  | 1 | 4.5402 | MTR | 0.25 |  | 1.135 | 1 | 2.135
| FL H DISH BEVEL CUTTING | CS |  | 30 | 1445 | BOTH SIDE | 2 | 9.0804 | MTR | 0.5 |  | 4.5402 | 1 | 5.5402
| FL H DISH BEVEL GRINDING | CS |  | 30 | 1450 |  | 2 | 9.1118 | MTR | 1 |  | 9.1118 | 1 | 10.1118
| FL H DISH FIT UP | CS |  | 30 | 1450 | BOTH SIDE | 1 | 4.5559 | MTR | 1 |  | 4.5559 | 1 | 5.5559
| FL H DISH WELDING | CS |  | 16 | 1450 |  | 1 | 4.5559 | MTR | 5.6 |  | 25.513 | 1 | 26.513
| FH-PP PL MARKING | CS |  | 25 | 300 | 1450 | 1 | 3.5 | MTR | 0.1 | HR/MTR | 0.35 | 1 | 1.35
| FH-PP PL CUTTING | CS |  | 25 | 300 | 1450 | 1 | 3.5 | MTR | 0.25 | HR/MTR | 0.875 | 1 | 1.875
| FH-PP PL GRINDING | CS |  | 25 | 300 | 1450 | 1 | 3.5 | MTR | 0.15 | HR/MTR | 0.525 | 1 | 1.525
| FH-PP PL FIT UP | CS | STD | 25 |  |  |  | 1 | Nos | 4 | No | 4 | 1 | 5
| FH-PP PL WELDING | CS |  | 18 |  | 1450 | 2 | 2.9 | MTR | 3.4 | HR/MTR | 9.86 | 1 | 10.86
| FH GRINDING | [12 empty] | 12
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
TB ITEMS | SEAL ST-MARKING | CS
| SLAIDING ST-MARKING | CS |  | 20 | 70 | 8571 | 2 | 34.564 |  | 0.1 |  | 3.4564 | 1 | 4.4564
| IMP PL MARKING | CS
| IMP ROD MARKING |  |  |  | DIA 25.4 | ~ 1450 | 43 | 43 | No | 0.083333 | HR/ NO | 3.5833
| SEAL ROD MARKING |  |  |  | DIA 25.4 | ~7000 | 7 | 7 | No | 0.083333 | HR/ NO | 0.58333
| TIE ROD MARKING |  |  |  | DIA 12 | ~ 8000 | 14 | 14 | No | 0.083333 | HR/ NO | 1.1667
| SPACER MARKING |  |  |  | 21.8 d |  | 419 | 419 | No | 0.083333 | HR/ NO | 34.9167
| CON PIECE MARKING | CS |  | 24 | 100 | 500 | 2 | 2.4 |  | 0.1 |  | 0.24 | 1 | 1.24
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
TB ITEMS | SEAL ST-CUTTING | CS
| SLAIDING ST-CUTTING | CS |  | 20 | 70 | 8571 | 2 | 34.564 |  | 0.25 |  | 8.641 | 1 | 9.641
| IMP PL CUTTING | CS
| IMP ROD CUTTING |  |  |  | DIA 25.4 | ~ 1450 | 43 | 43 | No | 0.16667 | HR/ NO | 7.1667 |  | 7.1667
| SEAL ROD CUTTING |  |  |  | DIA 25.4 | ~7000 | 7 | 7 | No | 0.16667 | HR/ NO | 1.1667 |  | 1.1667
| TIE ROD CUTTING |  |  |  | DIA 12 | ~ 8000 | 14 | 14 | No | 0.16667 | HR/ NO | 2.3333 |  | 2.3333
| SPACER CUTTING |  |  |  | 21.8 d |  | 419 | 419 | No | 0.083333 | HR/ NO | 34.9167 |  | 34.9167
| CON PIECE CUTTING | CS |  | 24 | 100 | 500 | 2 | 2.4 |  | 0.25 |  | 0.6 | 1 | 1.6
| ACTIVITY J 4220 B | MOC |  | THK | ID-MM | LONG-MM | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
TB ITEMS | SEAL ST-GRINDING | CS
| SLAIDING ST-GRINDING | CS |  | 20 | 70 | 8571 | 2 | 2 |  | 8 |  | 16 | 1 | 17
| IMP PL GRININD | CS
| IMP ROD M/C |  |  |  | DIA 25.4 | ~ 1450 | 43 | 43 | No | 0.5 | HR/ NO | 21.5 |  | 21.5
| SEAL ROD M/C |  |  |  | DIA 25.4 | ~7000 | 7 | 7 | No | 0.5 | HR/ NO | 3.5 |  | 3.5
| TIE ROD M/C |  |  |  | DIA 12 | ~ 8000 | 14 | 14 | No | 0.5 | HR/ NO | 7 |  | 7
| SPACER M/C |  |  |  | 21.8 d |  | 419 | 419 | No | 0.16667 | HR/ NO | 69.8333 |  | 69.8333
| CON PIECE DRILLING | CS |  | 24 | 100 | 500 | 2 | 1 |  | 6 |  | 6 | 1 | 7
TUBE BUNDLE ASSY | FRAME SET UP |  |  | 1000 |  |  | 1 | 1 |  | 12 |  | 12 | 1 | 13
| TS ASSY |  |  | 1000 |  |  | 1 | 1 | Nos | 4 |  | 4 | 1 | 5
| TIE ROD ASSY |  |  | 1000 |  |  | 17 | 17 | Nos | 0.15 |  | 2.55 | 1 | 3.55
| BAFFLE ASSY |  |  | 1000 |  |  | 22 | 22 | Nos | 0.5 |  | 11 | 1 | 12
| TUBE INSERT |  |  | 1000 |  |  | 500 | 500 | Nos | 0.083333 |  | 41.6667 | 1 | 42.6667
| SEAL ROD ASSY |  |  | 1000 |  |  | 10 | 10 | Nos | 0.25 |  | 2.5 | 1 | 3.5
| TUBE INSERT |  |  | 1000 |  |  | 550 | 550 | Nos | 0.083333 |  | 45.8333 | 1 | 46.8333
| SEAL STRIP FITUP |  |  | 1000 |  |  | 0 | 0 | Nos | 2 |  | 0 | 1 | 1
| SLIDING STRIP FIT UP |  |  | 1000 |  |  | 2 | 2 | Nos | 2 |  | 4 | 1 | 5
| WELDING |  |  | 1000 |  |  | 60 | 60 | Nos | 0.25 |  | 15 | 1 | 16
| GRINDING |  |  | 1000 |  |  | 60 | 60 | Nos | 0.15 |  | 9 | 1 | 10
| BUNDLE INDERT |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
| FLH TUBE SHEET ASSY |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
| GLAND & TEST RING ASSY |  |  | 1000 |  |  | 56 | 56 | Nos | 0.5 |  | 28 | 1 | 29
| TUBE EXP ST SIDE STG1 |  |  | 1000 |  |  | 1050 | 1050 | Nos | 0.05 |  | 52.5 | 1 | 53.5
| TUBE EXP FL SIDE STG1 |  |  | 1000 |  |  | 1050 | 1050 | Nos | 0.05 |  | 52.5 | 1 | 53.5
| TUBE TRIMMING |  |  | 1000 |  |  | 1461 | 1461 | Nos | 0.05 |  | 73.05 | 1 | 74.05
| TUBE EXPANSION BOTH SIDE |  |  | 1000 |  |  | 2100 | 2100 | Nos | 0.05 |  | 105 | 1 | 106
| AIR LEAK TEST |  |  | STD |  |  | 1 | 1 | Nos | 10 |  | 10 | 1 | 11
| SHELL SIDE HYDRO |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
| DISMANTLE TEST RING |  |  | 1000 |  |  | 55 | 55 | BOLT | 0.16667 |  | 9.1667 | 1 | 10.1667
| ASSY OF CH & FL HEAD |  |  | 1000 |  |  | 55 | 55 | BOLT | 0.5 |  | 27.5 | 1 | 28.5
| CH SIDE HYDRO |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
| ASSY OF BARREL |  |  | 1000 |  |  | 55 | 55 | Nos | 0.5 |  | 27.5 | 1 | 28.5
| SHELL SIDE HYDRO |  |  | 1000 |  |  | 1 | 1 | Nos | 16 |  | 16 | 1 | 17
| NOZ PIPE-MARKING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE-MARKING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE-CUTTING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE-CUTTING |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE-EP |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE-EP |  |  | 400NB |  |  |  | 1 | No | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE+FIT UP |  |  | 400NB |  |  |  | 1 |  | #N/A |  | #N/A | 1 | #N/A
| NOZ PIPE+FIT UP |  |  | 400NB |  |  |  | 1 |  | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| NOZ PIPE + FLG WELD |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 4.02 |  | 5.1332 | 1 | 6.1332
| NOZ PIPE + FLG WELD |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 4.02 |  | 5.1332 | 1 | 6.1332
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| NOZ BORE FLUSH GRIND |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 0.5 |  | 0.63845 | 1 | 1.6385
| NOZ BORE FLUSH GRIND |  |  | 16 | 400NB | 406.4 | 1 | 1.2769 |  | 0.5 |  | 0.63845 | 1 | 1.6385
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| NOZ PROFILE MARKING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
| NOZ PROFILE MARKING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| NOZ PROFILE CUTTING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
| NOZ PROFILE CUTTING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| NOZ PROFILE GRINDING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
| NOZ PROFILE GRINDING |  |  | 400NB |  |  | 1 | 1 |  | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | NB | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| RF PAD MARKING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| RF PAD MARKING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| RF PAD CUTTING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| RF PAD CUTTING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| RF PAD EP |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| RF PAD EP |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| RF PAD FORMING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| RF PAD FORMING |  |  | 400NB |  |  | 1 | 1 | NO | #N/A |  | #N/A | 1 | #N/A
| ACTIVITY J 4220 B | MOC |  | THK | WIDTH | LENGTH | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SAD PAD- TOP-MARKING | CS |  | 25 | 320 | 1736 | 0 | 0 |  | 0.1 |  | 0 | 1 | 1
| SAD PAD- BOT-MARKING | CS |  | 25 | 320 | 4904 | 2 | 20.896 |  | 0.1 |  | 2.0896 | 1 | 3.0896
| SAD BASE- TOP-MARKING | CS |  | 30 | 320 | 1890 | 0 | 0 |  | 0.1 |  | 0 | 1 | 1
| SAD BASE- BOT-MARKING | CS |  | 30 | 320 | 1890 | 4 | 17.68 |  | 0.1 |  | 1.768 | 1 | 2.768
| SAD WEB- TOP-MARKING | CS |  | 25 | 2336 | 1890 | 0 | 0 |  | 0.1 |  | 0 | 1 | 1
| SAD RIB-MARKING | CS |  | 30 | 135 | 400 | 16 | 17.12 |  | 0.1 |  | 1.712 | 1 | 2.712
11.5696
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SAD PAD- TOP-CUTTING | CS |  | 25 | 320 | 1736 | 0 | 0 |  | 0.25 |  | 0 | 1 | 1
| SAD PAD- BOT-CUTTING | CS |  | 25 | 320 | 4904 | 2 | 20.896 |  | 0.25 |  | 5.224 | 1 | 6.224
| SAD BASE- TOP-CUTTING | CS |  | 30 | 320 | 1890 | 0 | 0 |  | 0.25 |  | 0 | 1 | 1
| SAD BASE- BOT-CUTTING | CS |  | 30 | 320 | 1890 | 4 | 17.68 |  | 0.25 |  | 4.42 | 1 | 5.42
| SAD WEB- TOP-CUTTING | CS |  | 25 | 2336 | 1890 | 0 | 0 |  | 0.25 |  | 0 | 1 | 1
| SAD RIB-CUTTING | CS |  | 30 | 135 | 400 | 16 | 17.12 |  | 0.25 |  | 4.28 | 1 | 5.28
19.924
| ACTIVITY J 4220 B | MOC |  | THK | PIPE NB | PIPE OD | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SAD PAD- TOP-CUTTING | CS |  | 25 | 320 | 1736 | 0 | 0 |  | 0.15 |  | 0 | 1 | 1
| SAD PAD- BOT-CUTTING | CS |  | 25 | 320 | 4904 | 2 | 20.896 |  | 0.15 |  | 3.1344 | 1 | 4.1344
| SAD BASE- TOP-CUTTING | CS |  | 30 | 320 | 1890 | 0 | 0 |  | 0.15 |  | 0 | 1 | 1
| SAD BASE- BOT-CUTTING | CS |  | 30 | 320 | 1890 | 4 | 17.68 |  | 0.15 |  | 2.652 | 1 | 3.652
| SAD WEB- TOP-CUTTING | CS |  | 25 | 2336 | 1890 | 0 | 0 |  | 0.15 |  | 0 | 1 | 1
| SAD RIB-CUTTING | CS |  | 30 | 135 | 400 | 16 | 17.12 |  | 0.15 |  | 2.568 | 1 | 3.568
14.3544
| ACTIVITY J 4220 B | MOC |  | THK |  |  | QTY | WORK | UOM | BENCH MARK TIME | UOM | WORK | SETTING TIME | DURATION -HR
| SADDLE FIT UP | CS |  | 25 |  |  | 2 | 2 | Nos | 12 |  | 24 | 1 | 25
| SADDLE FIT WELDING | CS |  | 25 |  |  | 2 | 0 |  | 0.15 |  | 0 | 1 | 1
| vessel od | 1536
| Pad thk | 25
| Total OD | 1561
| Half Support |  | thk | fillet size | Long | Qty | Length of welding | welding hr | welding time - Hr
| Saddle base + Web |  |  | 18 | 1890 | 1 | 1890 | 3.4 | 6.426
| Web+Rib |  |  | 18 | 539 | 4 | 4312 | 3.4 | 14.6608
| Base to Rib |  |  | 18 | 138 | 4 | 1104 | 3.4 | 3.7536
24.8404
[7 empty] | No of Side | 4
[7 empty] | Tolal long |  | 99.3616 | Hrs
| vessel od | 1536
| Pad thk | 25
| Total OD | 1561
| FULL SUPPOR |  | thk | fillet size | Long | Qty | Length of welding | welding hr | welding time - Hr
| Base to Web- Bot & bot |  |  | 18 | 1890 | 2 | 1890 | 3.4 | 6.426
| Web to side |  |  | 18 | 2336 | 2 | 9344 | 3.4 | 31.7696
| Side to base |  |  | 18 | 320 | 1 | 640 | 3.4 | 2.176
| Rib to Web |  |  | 18 | 775 | 4 | 6200 | 3.4 | 38.1956
| Rib to base |  |  | 18 | 160 | 4 | 2560 | 3.4 | 33.9456
112.5128
[7 empty] | No of Side | 4 | 450.0512

## ESTIMATE (2) (hidden)
JOB NO | PART NO | ITEM | OPERATION |  | MOC | THK | DIAMETER | LONG | QTY | MARKING | CUTTING | GRINDING | EDGE PREPARATION | FIT UP | WELDING | BACK CHIP | INSIDE WELDING | FLUSH GRINDINH | MISC | TOTAL
4170A | 1 | SHELL |  | LS-1 | CS | 18 | 1200 | 2500 | 1 | [8 empty] | 1.875 |  | 1.875
4170A | 1 | SHELL |  | LS-2 | CS | 18 | 1200 | 2500 | 1 | [8 empty] | 1.875 |  | 1.875
4170A | 1 | SHELL |  | LS-2 | CS | 18 | 1200 | 2000 | 1 | [8 empty] | 1.5 |  | 1.5
4170A | 1 | SHELL | SH 1+SH 2 JONINIG | CS-1 | CS | 18 | 1200 |  | 1 | [8 empty] | 2.8278 |  | 2.8278
4170A | 1 | SHELL | SH 1+2+3 JOINING | CS-2 | CS | 18 | 1200 |  | 1 | [8 empty] | 2.8278 |  | 2.8278
4170A | 1 | SHELL | SH+ FLG JOINING | CS-3 | CS | 18 | 1200 |  | 1 | [8 empty] | 2.8278 |  | 2.8278
4170A | 1 | SHELL | LENGTH CORRECTION |  |  | 18 | 1200 |  |  | 2 | 2
[10 empty] | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7334

## Welding Qty Estimate
SHELL
[5 empty] | CUTTING | LS WELDING | CS WELDING
| T | ID | LONG | RMT | RMT | RMT | RMT
SH-1 | 12 | 625 | 2500 | 9.0029 | 9.0029 | 2.5 | 2.0015
SH-2 | 12 | 625 | 2000 | 8.0029 | 8.0029 | 2 | 2.0015
SH-3 | 12 | 625 | 1000 | 6.0029 | 6.0029 | 1 | 2.0015
SH-4 | [6 empty] | 0
CHANNEL
[5 empty] | CUTTING | LS WELDING | CS WELDING
| T | ID | LONG | RMT | RMT | RMT | RMT
SH-1 | 12 | 625 | 512 | 5.0269 | 5.0269 | 0.512 | 2.0015
BARREL
[5 empty] | CUTTING | LS WELDING | CS WELDING
| T | ID | LONG | RMT | RMT | RMT | RMT
SH-1 | 12 | 740 | 352 | 5.4296 | 5.4296 | 0.352 | 2.3628
DISH
|  |  |  | BLANK | CUTTING
| T | ID | TYPE | D- MTR | RMT
| 12 | 740 | 2:01 | 0.94 | 2.9535
Base - top
| thk | Width | Length | Qty | RMT-CUT | Welding
Base |  |  |  | 1 | 0 | 0 | 0
Web |  |  |  | 1 | 1.7344
Rib |  |  |  | 4 | 0 | 0 | 0
Rib |  |  |  | 4 | 0 | 0
[5 empty] | 1.7344 |  | 0
|  |  | No Saddle | 2 | 3.4688 |  | 0
Base- Bot
| thk | Width | Length | Qty | RMT-CUT | WELDING
Base | 16 | 150 | 510 | 1 | 1.32 | 4.08
Web | 12 | 234 | 490 | 1 | 1.448
Side |  |  |  | 1 | 0
Rib | 12 | 122 | 172 | 4 | 2.352 | 9.408
Rib | 12 | 122 | 172 | 4 | 2.352
Rib |  |  |  | 4 | 0
Rib |  |  |  | 4 | 0
7.472
|  |  | No Saddle | 2 | 14.944 | 13.488