## 23.11.2017
TITANIUM EQUIPMENT AND ANODE MANUFACTURING COMPANY LIMITED PENDING ORDERS / WORK IN PROGRESS
Sl. | PMO | PM | Job | Date of | Customer | Description | Qty | Delivery | DELAY/ AVL | LD | Drawing | Inspn | Remarks | ACTUAL DILIVERY DATE | DELIVERY TERMS
|  |  | No. | P.O./W.O |  |  |  | as per P.O. | 2017-11-23 |  | approval
1 |  |  | 4106 | 14.10.2016 | THERMAX | EC | 1 LOT | 2017-02-15 | -281 | .5% PER WEEK UPTO MAX 5% | THERMAX | THERMAX |  | 2017-02-28 | FOR GUJARAT
2 |  |  | 4107 | 13.10.2016 | BPCL | HASTELLOY COLUMN | 2 Nos | 2017-09-09 | -75 | .5% PER WEEK UPTO MAX 5% | EIL | TPIA/EIL |  | 2017-10-06 | FOR KOCHI KERALA
3 |  |  | 4147 | 2017-02-07 | DRDL | AIR FRAME | 24 NOS | 2017-07-15 | -131 | 0.5% PER WEEK UPTO MAX 5% | TEAM NEED TO SUBMIT THE DRAWINGS | DRDL |  | 2017-09-30 | FOR HYDERABAD
4 |  |  | 4156 | 2017-03-14 | ANDRITZ | TOTAL SKID | 1 LOT | 2017-10-15 | -39 | 2%PER WEEK UPTO MAX 15% | CLIENT/AI | CLIENT/AI |  | 2017-10-30 | EXWORKS VANDLAUR
5 |  |  | 4157 | 2017-03-22 | HYPER FILTRATION | ANODES | 30 NOS | 2017-04-30 | -207 | NA | CLIENT | CLIENT |  | 2017-04-30 | FOR UP
6 |  |  | 4158 | 2017-03-30 | HYPER FILTRATION | ANODES | 24 NOS | 2017-04-30 | -207 | NA | CLIENT | CLIENT |  | 2017-04-30 | FOR UP
7 |  |  | 4161 | 31.03.2017 | EIL - BPCL | HEAT EXCHANGTER | 3 NOS | 2017-11-22 | -1 | .5% PER WEEK UPTO MAX 5% | EIL | EIL |  | 2017-11-29 | FOR KOCHI KERALA
8 |  |  | 4166 | 18.04.2017 | PGAD | AIR BOTTLES | 10 NOS | 2018-02-05 | 74 | .5% PER WEEK UPTO MAX 10% | NA | CLIENT |  | 2018-03-13 | FOR HYDERABAD
9 |  |  | 4167 | 2017-04-20 | BORL, BINA | SUPPLY OF PRESSURE VESSEL | 1 NO | 2017-10-10 | -44 | .5% PER WEEK UPTO MAX 5% | EIL | TUV |  | 2017-10-17 | FOR MADHYAPRADESH
10 |  |  | 4169 | 14.04.2017 | ESSAR OIL LTD-GUJARAT | SUPPLY OF TITANIUM AND CS HEAT EXCHANGER | 1 NO EACH | 2017-11-20 | -3 | .5% PER WEEK UPTO MAX 5% | CLIENT | CLIENT/TPI |  | 2017-12-20 | FOR GUJARAT
11 |  |  | 4170 | 02.05.2017 | EIL/IOCL | SUPPLY OF HEAT EXCHANGERS | 21 NOS | 2017-11-30 | 7 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | EIL | TPIA |  | 2018-01-01 | FOR HARYANA, GUJARAT, KOLKATA, ASSAM
12 |  |  | 4171 | 05.05.2017 | L&T HYDROCARBON ENGINEERING LTD HAZIRA | SERVICE CHARGE FOR OFF SHORE PRECOMMISSIONING SUPERVISION | 1 LOT | 2017-05-30 | -177 | NA | NA | L&T | Work already completed, based on man days we need to raise the bill | 2017-09-30 | SITE WORK
13 |  |  | 4173 | 09.05.2017 | EIL/IOCL GUJARAT | SUPPLY OF HEAT EXCHANGERS | 5 NOS | 2018-03-09 | 106 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | EIL | TPIA - TEAM Scope |  | 2018-04-07 | FOR GUJARAT
14 |  |  | 4174 | 18.05.2017 | TKIS/IOCL-GUJARAT | SUPPLY OF HEAT EXCHANGERS | 1 NO | 2017-11-18 | -5 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | TKIS | TPIA |  | 2017-12-14 | FOR GUJARAT
15 |  |  | 4176 | 22.05.2017 | NPOL KERALA | SUPPLY OF ELIPTICAL BRIDLE ASSY & FULCRUM PIN | ELLIPTICAL BRIDLE ASSY-1 NOS | 2017-08-20 | -95 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | NA | CLIENT |  | 2017-11-10 | FOR KOCHI
16 |  |  | 4176 | 22.05.2017 | NPOL KERALA | SUPPLY OF ELIPTICAL BRIDLE ASSY & FULCRUM PIN | ELLIPTICAL BRIDLE ASSY-3 NOS | 2017-09-19 | -65 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | NA | CLIENT |  | 2017-11-10 | FOR KOCHI
17 |  |  | 4180 | 2017-06-02 | NIOT | TITANIUM PRESSURE CASE | 2 NOS | 2017-11-29 | 6 |  |  |  |  | 2017-12-29 | FOR CHENNAI
18 |  |  | 4182 | 2017-06-08 | UPL | NICKEL HEAT EXCHANGERS | 6 Nos | 2017-12-10 | 17 | WILL BE PROVIDED AFTER RECEIPT OF ORDER | CLIENT | UPL/CONSULTANT/TPI |  | 2018-01-10 | EXWORKS VANDLAUR
19 |  |  | 4183 | 2017-06-08 | IOCL-GUJARAT | SHELL & TUBE HEAT EXCHANGER | 1 NO | 2018-01-04 | 42 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | CLIENT | TPIA |  | 2018-01-04 | FOR GUJARAT
20 |  |  | 4184 | 2017-06-12 | ANDHRA SUGARS LTD | SUPPLY OF CHLORINE COOLER & RECUPERATOR | 1NO EACH | 2017-11-09 | -14 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | CLIENT | CLIENT |  | 2017-12-09 | FOR SAGGONDA AP
21 |  |  | 4186 | 2017-06-14 | SRF LIMITED | SUPPLY OF HASTELLOY HEAT EXCHANGERS, VESSELS, COLUMNS | 1 LOT | 2017-09-28 | -56 | 1% PER WEEK UPTO MAXIMUM OF 10% | CLIENT | TPIA |  | 2017-10-15 | FOR GUJARAT
22 |  |  | 4188 | 2017-06-18 | SRF LIMITED | REACTOR REPAIR | 1 NO |  |  |  |  | CLIENT
23 |  |  | 4191 | 2017-07-05 | KMML | TIGR7 EQUAL TEE | 10 NOS | 2017-11-02 | -21 | NA | NA | CLIENT |  | 2017-12-02 | FOR KERALA
24 | Yes | Srivaths | 4192 | 2017-07-05 | IGCAR MRPU | LABOUR CHARGES FOR SUPPLY OF SS TANK | 1 LOT (33 NOS) | 2018-12-07 | 379 | 2% PER MONTH UPTO MAX 5% | NA | CLIENT |  | 2019-01-07 | FOR KALPAKKAM
25 |  |  | 4193 | 2017-07-13 | SANDVIK ASIA PRIVATE LIMITED | U STAMP VESSEL | 1 NO | 2017-09-19 | -65 | 1% PER WEEK UPTO MAXIMUM OF 10% | SANDVIK | SANDVIK/TEAM(U STAMP) |  | 2017-10-19 | EXWORKS VANDLAUR
26 |  |  | 4195 | 2017-07-20 | ANDHRA SUGARS LTD | CELL RACK | 2 NOS | 2017-11-05 | -18 | 0.5%PER WEEK UPTO MAXIMUM OF 5% | NA | CLIENT |  | 2017-12-05 | FOR SAGGONDA AP
27 |  |  | 4196 | 2017-07-20 | NPOL KERALA | SUPPLY OF ELLIPTICAL SHELL ASSEMBLY | 1 LOT
28 |  |  | 4197 | 2017-07-26 | ANDHRA SUGARS LTD | SUPPLY OF PUMP | 8 NOS | 2017-12-06 | 13 | 0.5%PER WEEK UPTO MAXIMUM OF 5% | CLIENT | CLIENT |  | 2018-01-06 | FOR SAGGONDA AP
29 |  |  | 4198 | 2018-07-27 | BEL BANGALORE | CTD STRUCTURE ASSEMBLY | 2 NOS | 2017-11-15 | -8 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | NA | CLIENT |  | 2017-12-15 | FOR BANGALORE
30 |  |  | 4199 | 2017-07-28 | KMML KERALA | HYDROCYCLONE O-401 | 1 NO | 2017-11-28 | 5 | 1% PER MONTH UPTO MAXIMUM OF 5% | NA | CLIENT |  | 2017-12-25 | FOR KERALA
31 |  |  | 4200 | 2017-07-31 | TECHNIP CHENNAI | SEAL WELDING OF TI SPOOLS | 3 NOS | [7 empty] | SITE WORK
32 | Yes | Varun | 4201 | 2017-08-01 | EIL/DANGOTE | HEAT EXCHANGER-SS | 8 NOS | 2018-02-05 | 74 | 1% PER WEEK UPTO MAXIMUM OF 10% | EIL | TPIA |  | 2018-02-28 | FOB CHENNAI LOCATION
33 |  |  | 4202 | 2017-08-01 | TATA CHEMICALS LTD | COMPLETE PUMP | 1 NO | 2017-11-30 | 7 | 0.5%PER WEEK UPTO MAXIMUM OF 5% | CLIENT | CLIENT |  | 2017-12-31 | EXWORKS VANDLAUR
34 | Yes | Srivaths | 4203 | 2017-08-02 | IGCAR MRPU | LABOUR CHARGES FOR SUPPLY OF SS TANK | 1 LOT (330 NOS) | 2019-01-14 | 417 | 2% PER MONTH UPTO MAX 5% | CLIENT | TPIA/CLIENT |  | 2019-02-14 | FOR KALPAKKAM
35 |  |  | 4204 | 2017-08-04 | BEL BANGALORE | RJB SUPPORT PLATE STARBOARD ASSEMBLY | 3 NOS | 2017-11-27 | 4 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | NA | CLIENT |  | 2017-12-27 | FOR BANGALORE
36 | Yes | Ethiraj | 4209 | 2017-08-22 | EIL/DANGOTE | HEAT EXCHANGERS | 1 LOT (25 NOS) | 2018-06-22 | 211 | 1% PER WEEK UPTO MAXIMUM OF 10% | EIL | TPIA |  | 2018-07-22 | FOB CHENNAI LOCATION
37 |  |  | 4210 | 2017-08-28 | MCCPTA | ARC SITE JOB | 1 LOT
38 |  |  | 4211 | 2017-08-28 | ASL HYDERABAD | TI AIR BOTTLE | 25 NOS | 2017-11-28 | 5 | WILL BE PROVIDED AFTER RECEIPT OF ORDER | NA | CLIENT |  | 2017-12-28 | FOR HYDERABAD
39 |  |  | 4212 | 2017-08-30 | RCI HYDERABAD | AIR FRAME SECTIONS | 4 SETS | 2018-02-28 | 97 | WILL BE PROVIDED AFTER RECEIPT OF ORDER | NA | CLIENT |  | 2018-03-28 | FOR HYDERABAD
40 |  |  | 4213 | 2017-08-31 | SRF LIMITED | HEAT EXCHANGER | 1 NO | 2018-01-31 | 69 | 1% PER WEEK UPTO MAXIMUM OF 10% | CLIENT | CLIENT |  | 2018-02-27 | FOR BHIWADI
41 |  |  | 4214 | 2017-09-05 | CHEMFAB ALKALIS LTD | ALLOY PIPING SITE JOB | 1 LOT | [7 empty] | SITE WORK
42 |  |  | 4215 | 2017-09-06 | SRF LIMITED | SUPPLY OF SHELL FLANGE WITH SPOOL | 1 SET | 2017-10-30 | -24 | WILL BE PROVIDED AFTER RECEIPT OF ORDER | CLIENT | CLIENT |  | 2017-11-30 | FOR GURGAON
43 |  |  | 4216 | 2017-09-08 | BEML | ROLLING OF TI SHEETS | 50 NOS | 2017-11-01 | -22 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | NA | CLIENT |  | 2017-12-01 | FOR BEML
44 |  |  | 4217 | 2017-09-12 | RELIANCE INDUSTRIES LTD | PIPING MODIFICATION WORK DURING PRESHUT DOWN AND SHUTDOWN | 1 LOT | 2017-11-30 | 7 | 1% PER WEEK UPTO MAXIMUM OF 5% | NA | CLIENT |  | 2017-11-30 | SITE WORK
45 | Yes | Varun | 4218 | 2017-09-13 | CPCL CHENNAI | SUPPLY OF HEAT EXCHANGER(TAG NO: 031-E-10 C/D/E) | 3 NOS | 2018-08-11 | 261 | WILL BE PROVIDED AFTER RECEIPT OF ORDER | EIL | TPIA |  | 2018-09-11 | FOR CPCL CHENNAI
46 |  |  | 4219 | 2017-09-27 | CHEMFAB ALKALIS LTD | LABOUR CHARGES FOR ERECTION OF PIPES & FITTINGS FOR FLAKER PROJECT | 1 LOT | 3-4 WEEKS FROM DATE OF SITE CLEARANCE | - | NA | NA | CLIENT |  | 3-4 WEEKS FROM DATE OF SITE CLEARANCE | SITE WORK
47 | Yes | Sanjai | 4220 | 2017-10-03 | EIL/DANGOTE | HEAT EXCHANGERS | 1 LOT(28 NOS) | 2018-09-03 | 284 | 1% PER WEEK UPTO MAXIMUM OF 10% | EIL | TPIA |  | 2018-10-03 | FOB CHENNAI SEAPORT
48 | Yes | Elamaran | 4221 | 2017-10-04 | EIL/DANGOTE | DOUBLE PIPE HEAT EXCHANGERS | 3 NOS | GPC AWAITED |  |  | EIL | TPIA |  | 2018-09-01 | FOB CHENNAI SEAPORT
49 | Yes | Elamaran | 4224 | 2017-10-17 | EIL/ IOCL-PANIPAT | HEAT EXCHANGER | 2 NOS | 2018-05-11 | 169 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | EIL | TPIA |  | 2018-06-11 | DELIVERY@FOR-IOCL PANIPAT
49 |  |  | 4225 | 2017-10-24 | SRE SENTHIL ENGINEERING COMPANY | TITANIUM ANODE PLATE WITH MMO COATING | 10 SETS | 2017-11-24 | 1 | NA | NA | CLIENT |  | 2017-11-24 | DELIVERY@ EXW-VANDALUR CHENNAI
49 | Yes | Ethiraj | 4226 | 2017-10-27 | CHEMPLAST SANMAR LTD | SUPPLY OF VITON ORINGS | 16 NOS | 2018-02-15 | 84 | NA | NA | CLIENT |  | 2018-03-15 | DELIVERY@FOR-METTUR
49 |  |  | 4227 | 2017-10-30 | BHARAT DYNAMICS LTD | TI SHELL ROLLING | 100 NOS | 2018-11-30 | 372 | NA | NA | CLIENT |  | 2018-12-31 | DELIVERY@FOR BDL-KANCHANBAGH STORES
50 |  |  | 4228 | 2017-11-01 | EIL/IOCL | SUPPLY OF HEAT EXCHANGER | 5 NOS | 2018-06-30 | 219 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | EIL | TPIA |  | 2018-07-31 | DELIVERY@IOCL BONGAIGAON & HALDIA
51 |  |  | 4229 | 2017-11-02 | CHEMFAB ALKALIS LTD | SUPPLY OF SLEEVE | 1 NO | 2017-11-24 | 1 | NA | NA | CLENT |  | 2017-11-30 | DELIVERY@ EXW-VANDALUR CHENNAI
52 |  |  | 4230 | 2017-11-02 | ADVANCED SYSTEM LABORATORY | SUPPLY OF TITANIUM AIR BOTTLES | 10 NOS | 2018-04-02 | 130 | WILL BE PROVIDED AFTER RECEIPT OF ORDER |  |  |  | 2018-05-02 | DELIVERY@ FOR-HYDERABAD
53 |  |  | 4231 | 2017-11-07 | TECHNIP JBF | WELDING OF TITANIUM PIPES | 1 LOT | [7 empty] | SITE WORK
54 | Yes | Elamaran | 4232 | 2017-11-07 | TECHNIP IOCL | SUPPLY OF HEAT EXCHANGER | 1 NO | 2018-06-07 | 196 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | IOCL/TECHNIP | TPIA/TECHNIP/IOCL |  | 2018-07-07 | DELIVERY@IOCL BARASUNI
55 |  |  | 4233 | 2017-11-14 | KMML | SUPPLY OF STUD M16 X 150 MM LONG TITANIUM WITH 2 NUTS AND 2 WASHERS FULL THREADED | 22 NOS | 2018-01-01 | 39 | NA | NA | CLIENT |  | 2018-01-13 | DELIVERY@FOR KOLLAM
TOTAL
Equipment Ready For Despatch / Awaiting for client compliance & Team dispatch clearance
Sl. |  |  | Job | Date of | Customer | Description | Qty | Delivery |  | LD | DISPATCH CLEARANCE | PLANNED DISPATCH DATE | Remarks |  | DELIVERY TERMS
No. |  |  | No. | P.O./W.O |  |  |  | as per P.O.
1 |  |  | 4097 | 02.09.2017 | TNPL, KARUR | SITE WORK | 2 Man days |  |  | NA | NA | TNPL |  |  | SITE WORK
Total Value

## o2c_report (hidden)
Ordered Date | Order Type | Order Status | Customer Name | Customer Number | Customer Po Number | Project No | Ship Address | Bill Address | Price List | Price Date | Term Name | Schedule Date | Vat Tax Per | Vat Tax | Ed Per | Ed Value | Cst Tax Per | Cst Tax | Ser Per | Ser Value | Tcs | Fright Charges | Item Code | Item Desc | Qty | Assesable Value | Unit Price | Uom | Tax Category | Gl Code | Basic | Line Type | Line Status | Line DFF | LC Flag | LC Number | Amount | LC Description | Cust Po | Move Order | Transact Mv Order | Payment Check No | Advance Amt | Sales DFF | DC No | DC Date | Transporter Name | Vechicle No | LR No | Packing Detail | Dept | Area | Invoice Number | Invoice Date | Invoice Amount | Excise Invoice No | Excise Invoice Date | Rma Number | Rma Qty | Rma Value | Net Qty | Net Value | Receipt Method | Receipt Number | Gl Date | Receipt Amount | Credit Memo | Credit Memo Date | Credit Value | Master Price | Unit Delivery Price | Job Number
2016-04-01 | ENGG_INTER_LABOUR | CLOSED | MULTIMAX ENGINEERING WORKS PVT LTD | 3965 | AMMENDED PO NO: MM/JOB/15-16/G-95/632/1539 | 4007 | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | ENGG_PRICE_LIST | 2016-04-01 | MULTIMAXPT | 2016-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 63000 | 0 | 2250 | 40/07/LBFG/MME | J 4007 LABOUR WORK FOR TUBE BUNDLE FOR HEAT EXCHANGER | 1 | 0 | 450000 | Numbers | - | 310251 | 450000 | ENGG_INTER_LABOUR_LINE | CLOSED | (JOB NO: 632/1)- TUBE BUNDLE FABRICATION FOR HEAT EXCHANGER #E14968 | - | - | - | - | 2015-10-01 | 661994 | Y | - | - | (JOB NO: 632/1)- TUBE BUNDLE FABRICATION FOR HEAT EXCHANGER #E14968AS PER PO | 714447 | 2016-04-01 | GAUR LOGISTIC SOLUTIONS | HR 55 S 0973 | - | ONE EQPT, 2 LOOSE PLATE & 1 PVC BDLE. PARTY'S MATL RECD VIDE 4(5)a CHALLAN NO.44 DT.13.02.16 & 45 DT.19.02.16 AND BACK TO PARTY AFTER FABRICATION. NOT | - | - | 1617090001 | 2016-04-05 | 515250 | - | 2016-04-05 | - | 0 | 0 | 1 | 515250 | ENG. IDBI BANK | multimax eng. | 2016-04-05 | 65250 | - | - | - | 450000 | 450000 | -
2016-04-02 | ENGG_INTER_EQUIPMENT | CLOSED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | TECHNIP CENTRE, 19, VELACHERY MAIN ROAD, CHENNAI-600032, INDIA, PROJECT-2450, JBF PTA - | ENGG_PRICE_LIST | 2016-04-02 | TECHNIPFWPT | 2016-04-02 | 0 | 0 | 0 | 87500 | 2 | 15750 | - | 0 | 0 | 0 | 40/35/TIFW/320 | Titanium Gr.2 - dia 3.2 filler wire | 100 | 0 | 7000 | Numbers | - | 310101 | 700000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TITANIUM GR.2 FILLER WIRE OF DIA-3.2 | - | - | - | - | 2016-02-29 | 663002 | Y | - | - | SUPPLY OF TITANIUM GR.2 FILLER WIRE OF DIA-3.2AS PER SERVICE ORDER | 717464 | 2016-04-04 | COURIER | TCI XPS COURIER | LR NO.328391280 | PACKED IN ONE WOODEN BOX. GROSS WT : 175 KGS.SIZE : 1300 L X 340 W X 410 H. | - | - | 1617070001 | 2016-04-04 | 803250 | 9.9162e+35 | 04-APR-2016,04-APR-2016,04-APR-2016 | - | 0 | 0 | 100 | 803250 | ENG. IDBI BANK | TECHNIP,TECHNIP | 2017-03-04 | -260750 | - | - | - | 7000 | 7000 | -
2016-04-02 | ENGG_INTER_EQUIPMENT | CLOSED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | TECHNIP CENTRE, 19, VELACHERY MAIN ROAD, CHENNAI-600032, INDIA, PROJECT-2450, JBF PTA - | ENGG_PRICE_LIST | 2016-04-02 | TECHNIPFWPT | 2016-04-02 | 0 | 0 | 0 | 43750 | 2 | 7875 | - | 0 | 0 | 0 | 40/35/TIFW/200 | Titanium Gr.2 - dia 2 .0 filler wire | 50 | 0 | 7000 | Numbers | - | 310101 | 350000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR.2 FILLER WIRE OF DIA- 2.0 | - | - | - | - | 2016-02-29 | 663002 | Y | - | - | SUPPLY OF TIGR.2 FILLER WIRE OF DIA- 2.0AS PER YOUR SERVICE ORDER | 717464 | 2016-04-04 | COURIER | TCI XPS COURIER | LR NO.328391280 | PACKED IN ONE WOODEN BOX. GROSS WT : 175 KGS.SIZE : 1300 L X 340 W X 410 H. | - | - | 1617070001 | 2016-04-04 | 401625 | 9.9162e+35 | 04-APR-2016,04-APR-2016,04-APR-2016 | - | 0 | 0 | 50 | 401625 | ENG. IDBI BANK | TECHNIP,TECHNIP | 2017-03-04 | -662375 | - | - | - | 7000 | 7000 | -
2016-04-02 | ENGG_INTER_EQUIPMENT | CLOSED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | TECHNIP CENTRE, 19, VELACHERY MAIN ROAD, CHENNAI-600032, INDIA, PROJECT-2450, JBF PTA - | ENGG_PRICE_LIST | 2016-04-02 | TECHNIPFWPT | 2016-04-02 | 0 | 0 | 0 | 1750 | 2 | 315 | - | 0 | 0 | 0 | 40/35/TIFW/160 | Titanium Gr .2- dia 1.6 filler wire | 2 | 0 | 7000 | Numbers | - | 310101 | 14000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR.2 FILLER WIRE OF DIA-1.6 | - | - | - | - | 2016-02-29 | 663002 | Y | - | - | SUPPLY OF TIGR.2 FILLER WIRE OF DIA-1.6AS PER SERVICE ORDER | 717464 | 2016-04-04 | COURIER | TCI XPS COURIER | LR NO.328391280 | PACKED IN ONE WOODEN BOX. GROSS WT : 175 KGS.SIZE : 1300 L X 340 W X 410 H. | - | - | 1617070001 | 2016-04-04 | 16065 | 9.9162e+35 | 04-APR-2016,04-APR-2016,04-APR-2016 | - | 0 | 0 | 2 | 16065 | ENG. IDBI BANK | TECHNIP,TECHNIP | 2017-03-04 | -1047935 | - | - | - | 7000 | 7000 | -
2016-04-13 | ENGG_INTER_EQUIPMENT | CLOSED | SEC INDUSTRIES PRIVATE LIMITED | 1025 | SEC/A396/14-15/1066 | 3949 | 6-25, OPPOSITE IDPL WORKS, BALANAGAR, HYDERABAD- 500 037 - | 6-25, OPPOSITE IDPL WORKS, BALANAGAR, HYDERABAD- 500 037 - | ENGG_PRICE_LIST | 2015-10-31 | 100% Advance | 2016-04-13 | 0 | 0 | 0 | 333125 | 2 | 59962.5 | - | 0 | 0 | 0.5 | 39/49/ABFG/002 | J 3949 - TITANIUM AIRBOTTLE | 5 | 0 | 533000 | Numbers | - | 310101 | 2665000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 005)- TITANIUM AIR BOTTLE OF DIA 315MM | - | - | - | - | 2014-11-13 | 670134 | Y | - | - | (MATERIAL CODE: 005)- TITANIUM AIR BOTTLE OF DIA 315MMAS PER PO | 728573 | 2016-04-13 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | - | 5 WOODEN BOXES | - | - | 1617070002 | 2016-04-13 | 3058088 | 991617000002 | 2016-04-13 | - | 0 | 0 | 5 | 3058088 | ENG. IDBI BANK | sec industries | 2016-04-13 | 393088 | - | - | - | 533000 | 533000 | -
2016-04-27 | ENGG_INTER_EQUIPMENT | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4590000759 | 4030 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | 8-48/1, BACHUPALLY INDL AREA, QUTHUBULLAPUR MANDAL, ANDHRA PRADESH-500072 | ENGG_PRICE_LIST | 2016-04-27 | VEM PT | 2016-04-27 | 0 | 0 | 0 | 631250 | 2 | 113625 | - | 0 | 0 | 0 | 40/30/ABFG/001 | J 4030 TITANIUM AIR BOTTLE | 10 | 0 | 505000 | Numbers | - | 310101 | 5050000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSEMBLY AS PER DRG NO: 1712801000000 REV-01 | - | - | - | - | 2016-02-20 | 703124 | Y | - | - | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSEMBLY AS PER DRG NO: 1712801000000 REV-01AS PER PO | 766576 | 2016-04-27 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO. 104 | PACKED IN 10 WOODEN BOXES. SL NOS: 668, 670 TO 678 | - | - | 1617070003 | 2016-04-27 | 5794875 | 991617000003 | 2016-04-27 | - | 0 | 0 | 10 | 5794875 | ENG. IDBI BANK | VEM | 2016-04-27 | 744875 | - | - | - | 505000 | 505000 | -
2016-05-02 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | - | 100% Advance | 2016-05-02 | 5 | 188.6 | 0 | 0 | 0 | 0 | - | 0 | 40 | 0.4 | WS/MA/SCRP/LOT | WASTE SCRAP MATERIAL WITH LOT UOM | 1 | 0 | 3772 | LOT | - | 310701 | 3772 | ENGG_LOCAL_SCRAP_LINE | CLOSED | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD, PLASTIC ITEMS | - | - | - | - | - | 709148 | Y | - | - | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD, PLASTIC ITEMS | 774602 | 2016-05-02 | - | MDJ 5855 | - | - | - | - | 1617070004 | 2016-05-02 | 4001 | - | 2016-05-02 | - | 0 | 0 | 1 | 4001 | ENG. IDBI BANK | 776205 | 2016-05-02 | 229 | - | - | - | 3772 | 3772 | -
2016-05-12 | ENGG_INTER_EQUIPMENT | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4590000759 | 4030 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | 8-48/1, BACHUPALLY INDL AREA, QUTHUBULLAPUR MANDAL, ANDHRA PRADESH-500072 | ENGG_PRICE_LIST | 2016-04-27 | VEM PT | 2016-05-12 | 0 | 0 | 0 | 946875 | 2 | 170437.5 | - | 0 | 0 | 0.5 | 40/30/ABFG/001 | J 4030 TITANIUM AIR BOTTLE | 15 | 0 | 505000 | Numbers | - | 310101 | 7575000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSEMBLY AS PER DRG NO: 1712801000000 REV-01 | - | - | - | - | 2016-02-20 | 725138 | Y | - | - | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSEMBLY AS PER DRG NO: 1712801000000 REV-01AS PER PO | 797577 | 2016-05-12 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | - | PACKED IN 15 WOODEN BOXES. | - | - | 1617070005 | 2016-05-12 | 8692313 | 991617000005 | 2016-05-12 | - | 0 | 0 | 15 | 8692313 | ENG. IDBI BANK | VEM | 2016-05-12 | 1117313 | - | - | - | 505000 | 505000 | -
2016-07-15 | ENGG_EXPORT_EQUIPMENT | CLOSED | CCM CHEMICALS SDN BHD | 4099 | 4100091555/04.11.2015 | 4014 | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | ENGG_PRICE_LIST | 2016-07-15 | 50%ADV, BAL DOD | 2016-07-15 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 40/14/GCFG/CCM | 4014 D CHLORINE GAS COOLER | 1 | 0 | 2360511 | Numbers | - | 310451 | 2360511 | ENGG_EXPORT_EQUIPMENT_LINE | CLOSED | E420 NO 2 CL2 GAS COOLER (OP) | - | - | - | - | - | 823166 | Y | - | - | E420 NO 2 CL2 GAS COOLER (OP) | 854574 | 2016-07-15 | BY CHENNAI SEAPORT | THRO AP 24T 3798 | CONTAINER NO.MAEU 342584 0 45P3 | 5 EQUIPMENTS. | - | - | 1617080001 | 2016-07-15 | 2360511 | - | 15-JUL-2016,15-JUL-2016,15-JUL-2016,15-JUL-2016 | - | 0 | 0 | 1 | 2360511 | ENG. IDBI BANK | STATEMENT,CCM CHEMICALS | 2016-07-15 | -9388333.15 | - | - | - | 2360511 | 2360511 | -
2016-07-15 | ENGG_EXPORT_EQUIPMENT | CLOSED | CCM CHEMICALS SDN BHD | 4099 | 4100091555/04.11.2015 | 4014 | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | ENGG_PRICE_LIST | 2016-07-15 | 50%ADV, BAL DOD | 2016-07-15 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 40/14/HEFG/CCM | 4014 C CHLORINE GAS COOLER | 1 | 0 | 4553847 | Numbers | - | 310451 | 4553847 | ENGG_EXPORT_EQUIPMENT_LINE | CLOSED | E410 NO CL2 GAS COOLER (OP) | - | - | - | - | - | 823166 | Y | - | - | E410 NO CL2 GAS COOLER (OP) | 854574 | 2016-07-15 | BY CHENNAI SEAPORT | THRO AP 24T 3798 | CONTAINER NO.MAEU 342584 0 45P3 | 5 EQUIPMENTS. | - | - | 1617080001 | 2016-07-15 | 4553847 | - | 15-JUL-2016,15-JUL-2016,15-JUL-2016,15-JUL-2016 | - | 0 | 0 | 1 | 4553847 | ENG. IDBI BANK | STATEMENT,CCM CHEMICALS | 2016-07-15 | -7194997.15 | - | - | - | 4553847 | 4553847 | -
2016-07-15 | ENGG_EXPORT_EQUIPMENT | CLOSED | CCM CHEMICALS SDN BHD | 4099 | 4100091555/04.11.2015 | 4014 | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | ENGG_PRICE_LIST | 2016-07-15 | 50%ADV, BAL DOD | 2016-07-15 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 40/14/ASFG/CCM | 4014 B ANOLYTE SEPERATOR | 2 | 0 | 454716 | Numbers | - | 310451 | 909432 | ENGG_EXPORT_EQUIPMENT_LINE | CLOSED | D210 C/D ANOLYTE SEPARATOR (OP) | - | - | - | - | - | 823166 | Y | - | - | D210 C/D ANOLYTE SEPARATOR (OP) | 854574 | 2016-07-15 | BY CHENNAI SEAPORT | THRO AP 24T 3798 | CONTAINER NO.MAEU 342584 0 45P3 | 5 EQUIPMENTS. | - | - | 1617080001 | 2016-07-15 | 909432 | - | 15-JUL-2016,15-JUL-2016,15-JUL-2016,15-JUL-2016 | - | 0 | 0 | 2 | 909432 | ENG. IDBI BANK | STATEMENT,CCM CHEMICALS | 2016-07-15 | -10839412.15 | - | - | - | 454716 | 454716 | -
2016-07-15 | ENGG_EXPORT_EQUIPMENT | CLOSED | CCM CHEMICALS SDN BHD | 4099 | 4100091555/04.11.2015 | 4014 | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | ENGG_PRICE_LIST | 2016-07-15 | 50%ADV, BAL DOD | 2016-07-15 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 40/14/PVFG/CCM | 4014 A DEPLETED BRINE TANK | 1 | 0 | 5282730 | Numbers | - | 310451 | 5282730 | ENGG_EXPORT_EQUIPMENT_LINE | CLOSED | D240 DEPLETED BRINE TANK (OP) | - | - | - | - | - | 823166 | Y | - | - | D240 DEPLETED BRINE TANK (OP) | 854574 | 2016-07-15 | BY CHENNAI SEAPORT | THRO AP 24T 3798 | CONTAINER NO.MAEU 342584 0 45P3 | 5 EQUIPMENTS. | - | - | 1617080001 | 2016-07-15 | 5282730 | - | 15-JUL-2016,15-JUL-2016,15-JUL-2016,15-JUL-2016 | - | 0 | 0 | 1 | 5282730 | ENG. IDBI BANK | STATEMENT,CCM CHEMICALS | 2016-07-15 | -6466114.15 | - | - | - | 5282730 | 5282730 | -
2016-07-22 | ENGG_LOCAL_SCRAP | CLOSED | IMAC ALLOY CASTING PRIVATE LTD | 3758 | - | - | NO:877/2, THATTANKULAM ROAD TAMIL NADU-600060 | NO:877/2, THATTANKULAM ROAD TAMIL NADU-600060 | ENGG_PRICE_LIST | 2016-07-22 | IMMEDIATE | 2016-07-22 | 5 | 4980.94 | 0 | 11068.75 | 0 | 0 | - | 0 | 0 | 0.31 | TT/SC/SCRP/KG | TITANIUM SCRAP | 770 | 0 | 115 | kilogram | - | 310701 | 88550 | ENGG_LOCAL_SCRAP_LINE | CLOSED | TITANIUM BORING SCRAP | - | - | - | - | - | 829164 | Y | - | - | TITANIUM BORING SCRAP | 857573 | 2016-07-22 | - | TN 38 AC 1251 | - | - | - | - | 1617070016 | 2016-07-22 | 104600 | 991617000042 | 2016-07-22 | - | 0 | 0 | 770 | 104600 | ENG. IDBI BANK | SCBLR22013033000005335,168841,948110,948110,948110 | 2016-07-22 | 16050 | - | - | - | 115 | 115 | -
2016-08-11 | ENGG_INTER_EQUIPMENT | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4590000833 | 4046 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | 8-48/1, BACHUPALLY INDL AREA, QUTHUBULLAPUR MANDAL, ANDHRA PRADESH-500072 | ENGG_PRICE_LIST | 2016-07-26 | 45 NET | 2016-08-11 | 0 | 0 | 0 | 815625 | 2 | 146812.5 | - | 0 | 0 | 0.5 | 40/46/ABFG/VEM | 4046 TITANIUM ALLOY AIR BOTTLE ASSEMBLY | 15 | 0 | 435000 | Numbers | - | 310101 | 6525000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSY AS PER DRG NO: 1712801000000 REV.01 | - | - | - | - | 2016-05-18 | 844164 | Y | - | - | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSY AS PER DRG NO: 1712801000000 REV.01AS PER PO | 867573 | 2016-08-11 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.112 | PACKED IN 15 WOODEN BOXES. SL NOS: 731 TO 745 | - | - | 1617070113 | 2016-08-11 | 7487438 | 991617000061 | 2016-08-11 | - | 0 | 0 | 15 | 7487438 | ENG. IDBI BANK | vem | 2016-08-11 | 962438 | - | - | - | 435000 | 435000 | -
2016-10-12 | ENGG_INTER_EQUIPMENT | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700775 | 4093 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-10-12 | 100%PT45DAYS | 2016-10-12 | 0 | 0 | 0 | 1365.63 | 2 | 245.81 | - | 0 | 0 | 0.12 | 40/93/COFG/002 | J 4093 - SUPPLY OF SLEEVE | 1 | 0 | 10925 | Numbers | - | 310101 | 10925 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: RPMP120750537)- SLEEVE MOC: TITANIUM SB348 GR.2 FOR TEAM PUMP JOB NO. 3808-B | - | - | - | - | 2016-08-24 | 901168 | Y | - | - | (MATERIAL CODE: RPMP120750537)- SLEEVE MOC: TITANIUM SB348 GR.2 FOR TEAM PUMP JOB NO. 3808-BAS PER PO | 917574 | 2016-10-12 | - | TN 30 BB 6087 | - | PACKED IN ONE CARTON BOX. | - | - | 1617070130 | 2016-10-12 | 12536.56 | 9.9162e+23 | 12-OCT-2016,12-OCT-2016 | - | 0 | 0 | 1 | 12536.56 | ENG. IDBI BANK | 161670 | 2016-10-12 | -9313.44 | - | - | - | 10925 | 10925 | -
2016-10-12 | ENGG_INTER_EQUIPMENT | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700775 | 4093 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-10-12 | 100%PT45DAYS | 2016-10-12 | 0 | 0 | 0 | 1365.63 | 2 | 245.81 | - | 0 | 0 | 0 | 40/93/COFG/001 | J 4093 - SUPPLY OF TI SLEEVE | 1 | 0 | 10925 | Numbers | - | 310101 | 10925 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: RPMP120750536)- SLEEVE MOC: TITANIUM SB348GR.2 FOR TEAM PUMP JOB NO.3817 A | - | - | - | - | 2016-08-24 | 901168 | Y | - | - | (MATERIAL CODE: RPMP120750536)- SLEEVE MOC: TITANIUM SB348GR.2 FOR TEAM PUMP JOB NO.3817 AAS PER PO | 917574 | 2016-10-12 | - | TN 30 BB 6087 | - | PACKED IN ONE CARTON BOX. | - | - | 1617070130 | 2016-10-12 | 12536.44 | 9.9162e+23 | 12-OCT-2016,12-OCT-2016 | - | 0 | 0 | 1 | 12536.44 | ENG. IDBI BANK | 161670 | 2016-10-12 | -9313.56 | - | - | - | 10925 | 10925 | -
2016-12-01 | ENGG_INTER_RECOATING | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161701139 | 4117 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-11-29 | 100% PAYMENT | 2016-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14000 | 0 | 0 | 41/17/RCFG/CAL | J 4117 - RECOATING OF ANODE ELEMENT | 1 | 0 | 100000 | Numbers | - | 310252 | 100000 | ENGG_INTER_RECOATING_LINE | CLOSED | (MATERIAL CODE: WO12400012PRC)-RECOATING OF ANODE ELEMENT OF 4TH GENERATOR UHDE ELECTROLYSER | - | - | - | - | 2016-10-26 | 959173 | Y | - | - | (MATERIAL CODE: WO12400012PRC)-RECOATING OF ANODE ELEMENT OF 4TH GENERATOR UHDE ELECTROLYSERAS PER PO | 960575 | 2016-12-01 | PARTY VEHICLE | TN 30 BB 6087 | - | ONE WOODEN BOX.PARTY MATERIAL RETURNED AFTER REPAIR RECEIVED VIDE RGP NO/1617/0152 DT 20-OCT-2016 | - | - | 1617090021 | 2016-12-01 | 115000 | - | 2016-12-01 | - | 0 | 0 | 1 | 115000 | - | - | 2016-12-01 | - | - | - | - | 100000 | 100000 | -
2016-12-23 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100% PAYMENT | 2016-12-23 | 0 | 0 | 0 | 65531.25 | 2 | 11795.63 | - | 0 | 0 | 0.12 | 40/57/IPFG/001 | J 4057 - INTERMEDIATE PLATE | 1398 | 0 | 375 | Numbers | - | 310101 | 524250 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO:21258519010603)- INTERMEDIATE PLATE | - | - | - | - | 2016-06-13 | 979178 | Y | - | - | (BEL PART NO:21258519010603)- INTERMEDIATE PLATEAS PER PO | 978577 | 2016-12-23 | COURIER | TCI XPS | LR NO.329732211 | PACKED IN THREE WOODEN BOXES | - | - | 1617070170 | 2016-12-23 | 601577 | 9.9162e+23 | 23-DEC-2016,23-DEC-2016 | - | 0 | 0 | 1398 | 601577 | - | - | 2016-12-23 | - | - | - | - | 375 | 375 | -
2016-12-23 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100% PAYMENT | 2016-12-23 | 0 | 0 | 0 | 78750 | 2 | 14175 | - | 0 | 0 | 0 | 40/57/BPFG/001 | J 4057 - BOTTOM PLATE | 175 | 0 | 3600 | Numbers | - | 310101 | 630000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO:21258517012408)- BOTTOM PLATE | - | - | - | - | 2016-06-13 | 979178 | Y | - | - | (BEL PART NO:21258517012408)- BOTTOM PLATEAS PER PO | 978577 | 2016-12-23 | COURIER | TCI XPS | LR NO.329732211 | PACKED IN THREE WOODEN BOXES | - | - | 1617070170 | 2016-12-23 | 722925 | 9.9162e+23 | 23-DEC-2016,23-DEC-2016 | - | 0 | 0 | 175 | 722925 | - | - | 2016-12-23 | - | - | - | - | 3600 | 3600 | -
2016-12-23 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2014-05-31 | 100% Advance | 2016-12-23 | 5 | 188.6 | 0 | 0 | 0 | 0 | - | 0 | 40 | 0.4 | WS/PC/SCRP/WST | WASTE SCRAP CONSIST OF PAPER, DAMAGED CARTON BOX PLASTIC ITEM | 1 | 0 | 3772 | Numbers | - | 310701 | 3772 | ENGG_LOCAL_SCRAP_LINE | CLOSED | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD, PLASTIC ITEMS | - | - | - | - | - | 980177 | Y | - | - | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD, PLASTIC ITEMS | 981575 | 2016-12-23 | - | TAY 5767 | - | - | - | - | 1617070172 | 2016-12-23 | 4001 | - | 2016-12-23 | - | 0 | 0 | 1 | 4001 | ENG. IDBI BANK | 712761 | 2016-12-23 | 229 | - | - | - | 3772 | 3772 | -
2016-10-27 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/21/771/2016-2017 | 4062 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-10-27 | 100%PT30DAYS | 2016-10-27 | 0 | 0 | 0 | 70500 | 2 | 12690 | - | 0 | 0 | 0 | 40/62/ETFG/KMM | 4062 TITANIUM GR.7 EQUAL TEE | 6 | 0 | 94000 | Numbers | - | 310101 | 564000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO:614276760)- SUPPLY OF 100NB TIGR.7 EQUAL TEE MATERIAL OF CONTRUCTION: FLANGE SA105 WITH TIGR.7 LINING | - | - | - | - | 2016-06-20 | 923167 | Y | - | - | (MATERIAL CODE NO:614276760)- SUPPLY OF 100NB TIGR.7 EQUAL TEE MATERIAL OF CONTRUCTION: FLANGE SA105 WITH TIGR.7 LININGAS PER DRG. TP/MR/IBP/DIG-T/REV.0 MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH THE SUPPLY | 931573 | 2016-10-27 | COURIER | TCI XPS | LR NO.329246842 | PACKED IN TWO WOODEN BOXES. GR WT: 80 KGS ( EACH) | - | - | 1617070138 | 2016-10-27 | 647190 | 991617000174 | 2016-10-27 | - | 0 | 0 | 6 | 647190 | ENG. IDBI BANK | 795405 | 2016-10-27 | 83190 | - | - | - | 94000 | 94000 | -
2016-11-04 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2016-11-04 | 100% Advance | 2016-11-04 | 5 | 47.15 | 0 | 0 | 0 | 0 | - | 0 | 10 | -0.15 | WS/MA/SCRP/LOT | WASTE SCRAP MATERIAL WITH LOT UOM | 1 | 0 | 943 | LOT | - | 310701 | 943 | ENGG_LOCAL_SCRAP_LINE | CLOSED | DAMAGED WOODEN SCRAP | - | - | - | - | - | 933169 | Y | - | - | DAMAGED WOODEN SCRAP | 938574 | 2016-11-04 | - | TN 18 M 1773 | - | - | - | - | 1617070144 | 2016-11-04 | 1000 | - | 2016-11-04 | - | 0 | 0 | 1 | 1000 | ENG. IDBI BANK | 970531 | 2016-11-04 | 57 | - | - | - | 943 | 943 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210055016 | 4064 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 112.5 | 2 | 20.25 | - | 0 | 0 | 0.25 | 40/64/CMFG/TCL | J 4064 - SUPPLY OF O RING FOR DOME NUT | 1 | 0 | 900 | Numbers | - | 310101 | 900 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 109050102102)- O RING FOR DOME NUT NO 3550 6300 MAT:VI | - | - | - | - | 2016-06-22 | 937167 | Y | - | - | (MATERIAL CODE: 109050102102)- O RING FOR DOME NUT NO 3550 6300 MAT:VIAS PER PO | 940573 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED AND KEPT IN SHAFT WOODEN BOX VIDE DC NO.941574 | - | - | 1617070148 | 2016-11-09 | 1033 | 991617000189 | 2016-11-09 | - | 0 | 0 | 1 | 1033 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | 133 | - | - | - | 900 | 900 | -
2016-11-19 | ENGG_LOCAL_SCRAP | CLOSED | N.S.TRADERS | 6381 | - | - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | ENGG_PRICE_LIST | 2016-11-18 | 100% PAYMENT | 2016-11-19 | 5 | 12305.08 | 0 | 27344.63 | 0 | 0 | - | 0 | 2584 | 0.29 | SS/CB/SCRP/KG | STAINLESS STELL SCRAP | 3300 | 0 | 66.29 | kilogram | - | 310701 | 218757 | ENGG_LOCAL_SCRAP_LINE | CLOSED | S.S. CUT BITS SCRAP | - | - | - | - | - | 951167 | Y | - | - | S.S. CUT BITS SCRAP | 951574 | 2016-11-19 | - | TN 09 F 7439 | - | - | - | - | 1617070155 | 2016-11-19 | 260991 | 991617000211 | 2016-11-19 | - | 0 | 0 | 3300 | 260991 | ENG. IDBI BANK | N.S.TRADERS,046997,N.S.TRADERS | 2016-11-19 | 42234 | - | - | - | 66.29 | 66.29 | -
2016-09-26 | ENGG_INTER_EQUIPMENT | CLOSED | CHEMPLAST SANMAR LIMITED | 1023 | 3000044407 | 4045 | CC2 315, MELAVANJORE VILLAGE, NAGORE PO-611002, KARAIKAL,UNION TERRITORY OF PUDUCHERRY - | CC2 315, MELAVANJORE VILLAGE, NAGORE PO-611002, KARAIKAL,UNION TERRITORY OF PUDUCHERRY - | ENGG_PRICE_LIST | 2016-09-26 | 100% Advance | 2016-09-26 | 0 | 0 | 0 | 15187.5 | 2 | 2733.75 | - | 0 | 0 | 0 | 40/45/CBFG/CSL | 4045 ELECTROLYSER A/B COPPER CATHODE BUS BAR | 9 | 0 | 13500 | Numbers | - | 310101 | 121500 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 833804)-ELECTROLYSER A/B COPPER CATHODE BUS BAR-0222 | - | - | - | - | 2016-05-06 | 889166 | Y | - | - | (MATERIAL CODE: 833804)-ELECTROLYSER A/B COPPER CATHODE BUS BAR-0222AS PER PO | 906573 | 2016-09-26 | ASSOCIATED ROAD CARRIERS LTD | - | - | PACKED IN ONE WOODEN BOX | - | - | 1617070126 | 2016-09-26 | 139421.25 | 991617000126 | 2016-09-26 | - | 0 | 0 | 9 | 139421.25 | ENG. IDBI BANK | 36716 | 2016-09-26 | 17921.25 | - | - | - | 13500 | 13500 | -
2016-08-29 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT PETROLEUM CORPORATION LIMITED | 1045 | 4505513354 | 4022 | Mumbai refinery Mahul Maharastra-400074 | Mumbai refinery Mahul Maharastra-400074 | ENGG_PRICE_LIST | 2016-08-29 | 4022BPCLPT | 2016-08-29 | 0 | 0 | 0 | 1145254.25 | 2 | 206145.77 | - | 0 | 0 | -0.02 | 40/22/HEFG/BPC | J 4022- SPLITTER REBOILER | 1 | 0 | 9162034 | Numbers | - | 310101 | 9162034 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | LT KERO TRIPPER REBOILER (ITEM TAG NO: 131-E-126N) | - | - | - | - | 2016-03-19 | 864167 | Y | - | - | LT KERO TRIPPER REBOILER (ITEM TAG NO: 131-E-126N)AS PER PO | 886574 | 2016-08-29 | NTC LOGISTICS INDIA (P) LIMITED | MH 46 AF 4544 | LR NO. 000439 | PACKING DETAILS : ONE EQUIPMENT, THREE W/BOXES, ONE MS FRAME | - | - | 1617070119 | 2016-08-30 | 10513434 | 991617000089 | 2016-08-30 | - | 0 | 0 | 1 | 10513434 | Engg-CA(472) - BOB/MYL1 | BPCL,STATEMENT,STATEMENT,STATEMENT,BPCL,BPCL | 2016-08-30 | 1351400 | - | - | - | 9162034 | 9162034 | -
2016-05-12 | ENGG_LOCAL_SCRAP | CLOSED | IMAC ALLOY CASTING PRIVATE LTD | 3758 | - | - | NO:877/2, THATTANKULAM ROAD TAMIL NADU-600060 | NO:877/2, THATTANKULAM ROAD TAMIL NADU-600060 | ENGG_PRICE_LIST | 2016-03-30 | 100% Advance | 2016-05-12 | 5 | 3847.5 | 0 | 8550 | 0 | 0 | - | 0 | 0 | 0.5 | TT/SC/SCRP/KG | TITANIUM SCRAP | 570 | 0 | 120 | kilogram | - | 310701 | 68400 | ENGG_LOCAL_SCRAP_LINE | CLOSED | TITANIUM BORING SCRAP | - | - | - | - | - | 725142 | Y | - | - | TITANIUM BORING SCRAP | 797580 | 2016-05-12 | - | TN 05 D 2799 | - | - | - | - | 1617070006 | 2016-05-12 | 80798 | 991617000006 | 2016-05-12 | - | 0 | 0 | 570 | 80798 | ENG. IDBI BANK | SCBLR22013033000005335,948110 | 2016-05-12 | 12398 | - | - | - | 120 | 120 | -
2016-07-26 | ENGG_INTER_EQUIPMENT | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4590000893 | 4046 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | 8-48/1, BACHUPALLY INDL AREA, QUTHUBULLAPUR MANDAL, ANDHRA PRADESH-500072 | ENGG_PRICE_LIST | 2016-07-26 | 100% PAYMENT | 2016-07-27 | 0 | 0 | 0 | 543750 | 2 | 97875 | - | 0 | 0 | 0 | 40/46/ABFG/VEM | 4046 TITANIUM ALLOY AIR BOTTLE ASSEMBLY | 10 | 0 | 435000 | Numbers | - | 310101 | 4350000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSY AS PER DRG NO: 1712801000000 REV-01 | - | - | - | - | 2016-05-18 | 832164 | Y | - | - | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSY AS PER DRG NO: 1712801000000 REV-01AS PER PO | 860573 | 2016-07-26 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO. 111 | PACKED IN 10 WOODEN BOXES. SL NOS: 720 TO 726 & 728 TO 730 | - | - | 1617070017 | 2016-07-27 | 4991625 | 991617000047 | 2016-07-27 | - | 0 | 0 | 10 | 4991625 | ENG. IDBI BANK | VEM | 2016-07-27 | 641625 | - | - | - | 435000 | 435000 | -
2016-05-23 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/64/140/2478/2015-2016/600 | 4024 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-05-23 | 30 DAYS CREDIT | 2016-05-23 | 0 | 0 | 0 | 55000 | 2 | 9900 | - | 0 | 0 | 0 | 40/24/PIFG/KMM | J 4024 : SPRAY BOOM HEAD | 5 | 0 | 88000 | Numbers | - | 310101 | 440000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SPRAY BOOM HEAD MOC:TI Gr.2(Inner Boottom Pipe: SB 862 Gr. 2, Stub End: SB 265 Gr.2, Flanged Nipple: SB 265 Gr.2, | - | - | - | - | - | 739124 | Y | - | - | SPRAY BOOM HEAD MOC:TI Gr.2(Inner Boottom Pipe: SB 862 Gr. 2, Stub End: SB 265 Gr.2, Flanged Nipple: SB 265 Gr.2,Threaded Nipple: SB 348 Gr.2, Flanges:IS 2062, Gasket: PTFE, AS PER DRG. NO TP/MM/ARP/SBP/1261 REVE.0, NOTE: MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY | 815573 | 2016-05-23 | COURIER | TCI XPS | LR NO.328133805 | PACKED IN ONE WOODEN BOX AND ONE CARTON BOX | - | - | 1617070007 | 2016-05-23 | 504900 | 991617000008 | 2016-05-23 | - | 0 | 0 | 5 | 504900 | ENG. IDBI BANK | 529119 | 2016-05-23 | 64900 | - | - | - | 88000 | 88000 | -
2016-06-02 | ENGG_INTER_EQUIPMENT | CLOSED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | TECHNIP CENTRE, 19, VELACHERY MAIN ROAD, CHENNAI-600032, INDIA, PROJECT-2450, JBF PTA - | ENGG_PRICE_LIST | 2016-06-02 | TECHNIPFWPT | 2016-06-02 | 0 | 0 | 0 | 17500 | 2 | 3150 | - | 0 | 0 | 0 | 40/35/TIFG/320 | J 4035 - TITANIUM FILLER WIRE DIA 3.2 | 20 | 0 | 7000 | Numbers | - | 310101 | 140000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR2 FILLER WIRE OF DIAMETER- 3.2 | - | - | - | - | 2016-02-29 | 759124 | Y | - | - | SUPPLY OF TIGR2 FILLER WIRE OF DIAMETER- 3.2AS PER PO | 825573 | 2016-06-02 | COURIER | TCI XPS | LR NO. 328139825 | PACKED IN ONE WOODEN BOX. GR.WT: 100 KGS. SIZE : 116 X 58 X 40CMS | - | - | 1617070008 | 2016-06-02 | 160650 | 9.9162e+35 | 02-JUN-2016,02-JUN-2016,02-JUN-2016 | - | 0 | 0 | 20 | 160650 | ENG. IDBI BANK | technip,technip | 2016-06-02 | -399350 | - | - | - | 7000 | 7000 | -
2016-06-02 | ENGG_INTER_EQUIPMENT | CLOSED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | TECHNIP CENTRE, 19, VELACHERY MAIN ROAD, CHENNAI-600032, INDIA, PROJECT-2450, JBF PTA - | ENGG_PRICE_LIST | 2016-06-02 | TECHNIPFWPT | 2016-06-02 | 0 | 0 | 0 | 26250 | 2 | 4725 | - | 0 | 0 | 0 | 40/35/TIFG/240 | J 4035 - TITANIUM FILLER WIRE DIA 2.4 | 30 | 0 | 7000 | Numbers | - | 310101 | 210000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR2 FILLER WIRE OF DIAMETER- 2.4 | - | - | - | - | 2016-02-29 | 759124 | Y | - | - | SUPPLY OF TIGR2 FILLER WIRE OF DIAMETER- 2.4AS PER PO | 825573 | 2016-06-02 | COURIER | TCI XPS | LR NO. 328139825 | PACKED IN ONE WOODEN BOX. GR.WT: 100 KGS. SIZE : 116 X 58 X 40CMS | - | - | 1617070008 | 2016-06-02 | 240975 | 9.9162e+35 | 02-JUN-2016,02-JUN-2016,02-JUN-2016 | - | 0 | 0 | 30 | 240975 | ENG. IDBI BANK | technip,technip | 2016-06-02 | -319025 | - | - | - | 7000 | 7000 | -
2016-06-02 | ENGG_INTER_EQUIPMENT | CLOSED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | TECHNIP CENTRE, 19, VELACHERY MAIN ROAD, CHENNAI-600032, INDIA, PROJECT-2450, JBF PTA - | ENGG_PRICE_LIST | 2016-06-02 | TECHNIPFWPT | 2016-06-02 | 0 | 0 | 0 | 26250 | 2 | 4725 | - | 0 | 0 | 0 | 40/35/TIFG/200 | J 4035 - TITANIUM FILLER WIRE DIA 2.0 | 30 | 0 | 7000 | Numbers | - | 310101 | 210000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR2 FILLER WIRE OF DIAMETER- 2.0 | - | - | - | - | 2016-02-29 | 759124 | Y | - | - | SUPPLY OF TIGR2 FILLER WIRE OF DIAMETER- 2.0AS PER PO | 825573 | 2016-06-02 | COURIER | TCI XPS | LR NO. 328139825 | PACKED IN ONE WOODEN BOX. GR.WT: 100 KGS. SIZE : 116 X 58 X 40CMS | - | - | 1617070008 | 2016-06-02 | 240975 | 9.9162e+35 | 02-JUN-2016,02-JUN-2016,02-JUN-2016 | - | 0 | 0 | 30 | 240975 | ENG. IDBI BANK | technip,technip | 2016-06-02 | -319025 | - | - | - | 7000 | 7000 | -
2016-06-04 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/2653/2015-2016/727 | 4028 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-06-04 | 100% PAYMENT | 2016-06-04 | 0 | 0 | 0 | 5168 | 2 | 930.24 | - | 0 | 0 | 0 | 40/28/HNFG/KMM | J 4028 Ti Gr.2 M16 HEX NUT | 64 | 0 | 646 | Numbers | - | 310101 | 41344 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM CODE NO: 296052016)- NUT HEX. M16 TITANIUM GR2 | - | - | - | - | 2016-02-17 | 761124 | Y | - | - | (ITEM CODE NO: 296052016)- NUT HEX. M16 TITANIUM GR2AS PER PO | 828573 | 2016-06-04 | COURIER | FIRST FLIGHT | - | PACKED IN ONE CARTON BOX | - | - | 1617070009 | 2016-06-04 | 47442.24 | 991617000010 | 2016-06-04 | - | 0 | 0 | 64 | 47442.24 | ENG. IDBI BANK | 529278 | 2016-06-04 | 6098.24 | - | - | - | 646 | 646 | -
2016-06-04 | ENGG_INTER_LABOUR | CLOSED | MULTIMAX ENGINEERING WORKS PVT LTD | 3965 | AMMENDED ORDER NO:MM/JOB/ 15-16/G-95/632/1539 | 4007 | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | ENGG_PRICE_LIST | 2016-06-04 | 100% PAYMENT | 2016-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 51475 | 0 | 0 | 40/07/LBFG/MM3 | J 4007 C - LABOUR WORK FOR TUE BUNDLE | 1 | 0 | 355000 | Numbers | - | 310251 | 355000 | ENGG_INTER_LABOUR_LINE | CLOSED | (JOB NO: 632/3)- TUBE BUNDLE FABRICATION FOR HEAT EXCHANGER #E14970 | - | - | - | - | 2015-10-01 | 762131 | Y | - | - | (JOB NO: 632/3)- TUBE BUNDLE FABRICATION FOR HEAT EXCHANGER #E14970AS PER PO | 829574 | 2016-06-04 | ASSOCIATED ROAD CARRIERS LTD | RJ 14 GD 7693 | LR NO. M9000042815 | TWO EQUIPMENTS AND ONE WOODEN BOX. HEREWITH ENCLOSED 4(5)a CHALLAN NO.02 DT.4.5.16 AND SL NO.04 DT.7.5.16 | - | - | 1617090002 | 2016-06-04 | 408250 | - | 04-JUN-2016,04-JUN-2016 | - | 0 | 0 | 1 | 408250 | ENG. IDBI BANK | MULTIMAX,MULTIMAX,MULTIMAX | 2016-06-04 | -356793.48 | - | - | - | 355000 | 355000 | -
2016-06-04 | ENGG_INTER_LABOUR | CLOSED | MULTIMAX ENGINEERING WORKS PVT LTD | 3965 | AMMENDED ORDER NO:MM/JOB/ 15-16/G-95/632/1539 | 4007 | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | ENGG_PRICE_LIST | 2016-06-04 | 100% PAYMENT | 2016-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 61625 | 0 | 0 | 40/07/LBFG/MM2 | J 4007 LABOUR WORK FOR TUBE BUNDLE OF HEAT EXCHANGER | 1 | 0 | 425000 | Numbers | - | 310251 | 425000 | ENGG_INTER_LABOUR_LINE | CLOSED | (JOB NO: 632/2)- TUBE BUNDLE FABRICATION FOR HEAT EXCHANGER #E14969 | - | - | - | - | 2015-10-01 | 762131 | Y | - | - | (JOB NO: 632/2)- TUBE BUNDLE FABRICATION FOR HEAT EXCHANGER #E14969AS PER PO | 829574 | 2016-06-04 | ASSOCIATED ROAD CARRIERS LTD | RJ 14 GD 7693 | LR NO. M9000042815 | TWO EQUIPMENTS AND ONE WOODEN BOX. HEREWITH ENCLOSED 4(5)a CHALLAN NO.02 DT.4.5.16 AND SL NO.04 DT.7.5.16 | - | - | 1617090002 | 2016-06-04 | 488750 | - | 04-JUN-2016,04-JUN-2016 | - | 0 | 0 | 1 | 488750 | ENG. IDBI BANK | MULTIMAX,MULTIMAX,MULTIMAX | 2016-06-04 | -276293.48 | - | - | - | 425000 | 425000 | -
2016-06-14 | ENGG_INTER_EQUIPMENT | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4590000759 | 4030 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | 8-48/1, BACHUPALLY INDL AREA, QUTHUBULLAPUR MANDAL, ANDHRA PRADESH-500072 | ENGG_PRICE_LIST | 2016-06-04 | VEM PT | 2016-06-15 | 0 | 0 | 0 | 946875 | 2 | 170437.5 | - | 0 | 0 | 0.5 | 40/30/ABFG/002 | J 4030 TITANIUM AIR BOTTLE | 15 | 0 | 505000 | Numbers | - | 310101 | 7575000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSY AS PER DRG NO: 1712801000000 REV-01 | - | - | - | - | 2016-02-20 | 774124 | Y | - | - | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSY AS PER DRG NO: 1712801000000 REV-01AS PER PO | 834573 | 2016-06-14 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO. 109 | PACKED IN 15 WOODEN BOXES. SL NOS: 703 TO 707 & 709 TO 718 | - | - | 1617070011 | 2016-06-14 | 8692313 | 991617000012 | 2016-06-14 | - | 0 | 0 | 15 | 8692313 | ENG. IDBI BANK | VEM | 2016-06-14 | 1117313 | - | - | - | 505000 | 505000 | -
2016-06-16 | ENGG_INTER_EQUIPMENT | CLOSED | M/S.MEGHMANI LLP | 4400 | 593 | 4023 | CH-3,GIDC,DAHEJ, TALUKA-VAGRA, - | CH-3,GIDC,DAHEJ, TALUKA-VAGRA, - | ENGG_PRICE_LIST | 2016-06-16 | 100% PAYMENT | 2016-06-16 | 0 | 0 | 0 | 165625 | 2 | 29812.5 | - | 0 | 0 | 0 | 40/23/HEFG/MEG | J 4023 TITANIUM RE-BOILER | 1 | 0 | 1325000 | Numbers | - | 310101 | 1325000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (INDENT NO: IND/000379/1516) TITANIUM REBOILER (EQPT.NO EV-601A)-DESIGN, MANUFACTURE AND SUPPLY OF TITANIUM REBOILER , | - | - | - | - | 2016-02-06 | 780124 | Y | - | - | (INDENT NO: IND/000379/1516) TITANIUM REBOILER (EQPT.NO EV-601A)-DESIGN, MANUFACTURE AND SUPPLY OF TITANIUM REBOILER ,CAPACITY: 71.00 M2, MOC: TITANIUM GR.2 | 837573 | 2016-06-17 | TCI FREIGHT | GJ 06 AV 9501 | - | ONE EQUIPMENT. | - | - | 1617070012 | 2016-06-17 | 1520437.5 | 991617000013 | 2016-06-17 | - | 0 | 0 | 1 | 1520437.5 | ENG. IDBI BANK | 810001608000885 | 2016-06-17 | 195437.5 | - | - | - | 1325000 | 1325000 | -
2016-07-05 | ENGG_INTER_EQUIPMENT | CLOSED | SHRIRAM ALKALIS AND CHEMICALS LIMITED | 1604 | SAC/AMG/913734 | 4040 | 749 GIDC INDUSTRIAL ESTATE GUJARAT-393110 | 749 GIDC INDUSTRIAL ESTATE GUJARAT-393110 | ENGG_PRICE_LIST | 2016-07-05 | 100% PAYMENT | 2016-07-06 | 0 | 0 | 0 | 197500 | 2 | 35550 | - | 0 | 0 | 0 | 40/40/PUFG/DCM | 4040 DEPLETED BRINE PUMP | 2 | 0 | 790000 | Numbers | - | 310101 | 1580000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM CODE NO: 227479)- PUMP CENTRIFUGAL 120M3/HR 30M DEPLETED BRINE PUMP WITHOUT MOTOR AND MECHANICAL SEAL(TAG NO: P244X AB) | - | - | - | - | 2016-03-23 | 814124 | Y | - | - | (ITEM CODE NO: 227479)- PUMP CENTRIFUGAL 120M3/HR 30M DEPLETED BRINE PUMP WITHOUT MOTOR AND MECHANICAL SEAL(TAG NO: P244X AB)AS PER PO | 848573 | 2016-07-05 | TCI FREIGHT | RJ 27 GA 7558 | - | TWO WOODEN BOXES | - | - | 1617070013 | 2016-07-05 | 1813050 | 991617000017 | 2016-07-05 | - | 0 | 0 | 2 | 1813050 | ENG. IDBI BANK | DCM SHRIRAM,SHRIRAM ALKALIS | 2016-07-05 | 390410.35 | - | - | - | 790000 | 790000 | -
2016-07-05 | ENGG_INTER_EQUIPMENT | CLOSED | HINDUSTAN PETROLEUM CORPORATION LIMITED | 1504 | 15001151-OP-46002/VSK | 4021 | VISAKH REFINERY,MALKAPURAM PB No.15 - | VISAKH REFINERY,MALKAPURAM PB No.15 - | ENGG_PRICE_LIST | 2016-07-05 | 100% PAYMENT | 2016-07-06 | 0 | 0 | 0 | 475000 | 2 | 85500 | - | 0 | 0 | 0 | 40/21/TBFG/001 | 4021 B TUBE BUNDLE ASSEMBLY | 1 | 0 | 3800000 | Numbers | - | 310101 | 3800000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM NUMBER- 225153364)- SUPPLY OF 12-E-07D TUBE BUNDLE | - | - | - | - | 2016-01-27 | 814128 | Y | - | - | (ITEM NUMBER- 225153364)- SUPPLY OF 12-E-07D TUBE BUNDLEAS PER PO | 849573 | 2016-07-05 | TCI FREIGHT | AP 03 T 3902 | - | TWO TUBE BUNDLES AND ONE WOODEN BOX | - | - | 1617070014 | 2016-07-07 | 4360500 | 9.9162e+23 | 07-JUL-2016,07-JUL-2016 | - | 0 | 0 | 1 | 4360500 | Engg-CA(472) - BOB/MYL1 | STATEMENT | 2016-07-07 | -1772833.33 | - | - | - | 3800000 | 3800000 | -
2016-07-05 | ENGG_INTER_EQUIPMENT | CLOSED | HINDUSTAN PETROLEUM CORPORATION LIMITED | 1504 | 15001151-OP-46002/VSK | 4021 | VISAKH REFINERY,MALKAPURAM PB No.15 - | VISAKH REFINERY,MALKAPURAM PB No.15 - | ENGG_PRICE_LIST | 2016-07-05 | 100% PAYMENT | 2016-07-06 | 0 | 0 | 0 | 425000 | 2 | 76500 | - | 0 | 0 | 0 | 40/21/TBFG/HPC | 4021 A TUBE BUNDLE ASSEMBLY | 1 | 0 | 3400000 | Numbers | - | 310101 | 3400000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM NUMBER- 225153362)- SUPPLY OF 11-E-17A TUBE BUNDLE | - | - | - | - | 2016-01-27 | 814128 | Y | - | - | (ITEM NUMBER- 225153362)- SUPPLY OF 11-E-17A TUBE BUNDLEAS PER PO | 849573 | 2016-07-05 | TCI FREIGHT | AP 03 T 3902 | - | TWO TUBE BUNDLES AND ONE WOODEN BOX | - | - | 1617070014 | 2016-07-07 | 3901500 | 9.9162e+23 | 07-JUL-2016,07-JUL-2016 | - | 0 | 0 | 1 | 3901500 | Engg-CA(472) - BOB/MYL1 | STATEMENT | 2016-07-07 | -2231833.33 | - | - | - | 3400000 | 3400000 | -
2016-06-04 | ENGG_INTER_EQUIPMENT | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4590000759 | 4030 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | 8-48/1, BACHUPALLY INDL AREA, QUTHUBULLAPUR MANDAL, ANDHRA PRADESH-500072 | ENGG_PRICE_LIST | 2016-06-04 | VEM PT | 2016-06-04 | 0 | 0 | 0 | 631250 | 2 | 113625 | - | 0 | 0 | 0 | 40/30/ABFG/002 | J 4030 TITANIUM AIR BOTTLE | 10 | 0 | 505000 | Numbers | - | 310101 | 5050000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSEMBLY AS PER DRG NO: 1712801000000 REV-01 | - | - | - | - | 2016-02-20 | 762124 | Y | - | - | (MATERIAL CODE: 1712801000000)- TITANIUM ALLOY AIR BOTTLE ASSEMBLY AS PER DRG NO: 1712801000000 REV-01AS PER PO | 829573 | 2016-06-04 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO. 108 | PACKED IN 10 WOODEN BOXES. | - | - | 1617070010 | 2016-06-04 | 5794875 | 991617000011 | 2016-06-04 | - | 0 | 0 | 10 | 5794875 | ENG. IDBI BANK | VEM | 2016-06-04 | 744875 | - | - | - | 505000 | 505000 | -
2016-07-13 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | - | 100% Advance | 2016-07-13 | 5 | 188.6 | 0 | 0 | 0 | 0 | - | 0 | 40 | 0.4 | WS/MA/SCRP/LOT | WASTE SCRAP MATERIAL WITH LOT UOM | 1 | 0 | 3772 | LOT | - | 310701 | 3772 | ENGG_LOCAL_SCRAP_LINE | CLOSED | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD, PLASTIC ITEMS | - | - | - | - | - | 821164 | Y | - | - | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD, PLASTIC ITEMS | 852573 | 2016-07-13 | - | TN 33 Z 1686 | - | - | - | - | 1617070015 | 2016-07-13 | 4001 | - | 2016-07-13 | - | 0 | 0 | 1 | 4001 | - | - | 2016-07-13 | - | - | - | - | 3772 | 3772 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 450 | 2 | 81 | - | 0 | 0 | 0 | 40/52/COFG/003 | J 4052 - SUPPLY OF O RINGS | 2 | 0 | 1800 | Numbers | - | 310101 | 3600 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:109050102104)-COVER O RING NO.5301 8000 MAT:VITON | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE:109050102104)-COVER O RING NO.5301 8000 MAT:VITONAS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 4131 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 2 | 4131 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | -130869 | - | - | - | 1800 | 1800 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 225 | 2 | 40.5 | - | 0 | 0 | 0 | 40/52/COFG/002 | J 4052 - SUPPLY OF O RINGS | 2 | 0 | 900 | Numbers | - | 310101 | 1800 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 109050102103)-O RING FOR SLEEVE-3550 6500 MAT: VITON | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE: 109050102103)-O RING FOR SLEEVE-3550 6500 MAT: VITONAS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 2065.5 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 2 | 2065.5 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | -132934.5 | - | - | - | 900 | 900 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 225 | 2 | 40.5 | - | 0 | 0 | 0 | 40/52/COFG/001 | J 4052- SUPPLY OF ORINGS | 2 | 0 | 900 | Numbers | - | 310101 | 1800 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:109050102102)- O RING FOR DOME NUT NO 3550 6300 MAT:VI | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE:109050102102)- O RING FOR DOME NUT NO 3550 6300 MAT:VIAS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 2065.5 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 2 | 2065.5 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | -132934.5 | - | - | - | 900 | 900 | -
2016-12-02 | ENGG_INTER_EQUIPMENT | CLOSED | ANDHRA SUGARS LIMITED | 2104 | 51/52016/0189/M2/1A/0154/00177 | 4088 | CHEMICAL AND FERTILIZERS DIVISION, KOVVUR-534350, WEST GODAVARI DISTRICT, ANDHRA PRADESH - | CHEMICAL AND FERTILIZERS DIVISION, SAGGONDA-534318, WEST GODAVARI DISTRICT - | ENGG_PRICE_LIST | 2016-12-02 | 100% PAYMENT | 2016-12-02 | 0 | 0 | 0 | 23562.5 | 2 | 4241.25 | - | 0 | 0 | 0.25 | 40/88/COFG/ASL | J 4088 - SUPPLY OF EARTHING CONNECTIONS | 1 | 0 | 188500 | SET | - | 310101 | 188500 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF EARTHING CONNECTIONS(MATERIAL OF CONSTRUCTION: TITANIUM GR.2 WITH ACTIVATED | - | - | - | - | 2016-08-05 | 961173 | Y | - | - | SUPPLY OF EARTHING CONNECTIONS(MATERIAL OF CONSTRUCTION: TITANIUM GR.2 WITH ACTIVATEDRAW MATERIAL ORIGIN: EUROPEAN AS PER PO | 961575 | 2016-12-02 | COURIER | TCI XPS | LR NO.329352516 | PACKED IN ONE GUNNY CARTON BOX. | - | - | 1617070159 | 2016-12-02 | 216304 | 991617000228 | 2016-12-02 | - | 0 | 0 | 1 | 216304 | ENG. IDBI BANK | 10150 | 2016-12-02 | 27804 | - | - | - | 188500 | 188500 | -
2016-12-08 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/64/50/910/2016-2017 | 4074 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 30 NET | 2016-12-08 | 0 | 0 | 0 | 20000 | 2 | 3600 | - | 0 | 0 | 0 | 40/74/COFG/001 | J 4074- SUPPLY OF TUBES | 32 | 0 | 5000 | Numbers | - | 310101 | 160000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | TIE ROD | - | - | - | - | - | 968175 | Y | - | - | TIE ROD | 968576 | 2016-12-08 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.131 | PACKED IN ONE WOODEN BOX.GR.WT: 62 KGS. SIZE: 750 L X 510 W X 280MM H | - | - | 1617070163 | 2016-12-08 | 183600 | 9.9162e+23 | 08-DEC-2016,08-DEC-2016 | - | 0 | 0 | 32 | 183600 | - | - | 2016-12-08 | - | - | - | - | 5000 | 5000 | -
2016-12-08 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/64/50/910/2016-2017 | 4074 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 30 NET | 2016-12-08 | 0 | 0 | 0 | 32500 | 2 | 5850 | - | 0 | 0 | 0 | 40/74/COFG/KMM | J 4074 - SUPPLY OF TIE ROD & SAPCER | 8 | 0 | 32500 | Numbers | - | 310101 | 260000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPORT TUBE | - | - | - | - | - | 968175 | Y | - | - | SUPPORT TUBE | 968576 | 2016-12-08 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.131 | PACKED IN ONE WOODEN BOX.GR.WT: 62 KGS. SIZE: 750 L X 510 W X 280MM H | - | - | 1617070163 | 2016-12-08 | 298350 | 9.9162e+23 | 08-DEC-2016,08-DEC-2016 | - | 0 | 0 | 8 | 298350 | - | - | 2016-12-08 | - | - | - | - | 32500 | 32500 | -
2016-08-11 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2016-08-11 | 100% Advance | 2016-08-11 | 5 | 1732.73 | 0 | 3850.5 | 0 | 0 | - | 0 | 364 | -0.23 | SS/CB/SCRP/KG | STAINLESS STELL SCRAP | 510 | 0 | 60.4 | kilogram | - | 310701 | 30804 | ENGG_LOCAL_SCRAP_LINE | CLOSED | S.S.CUT BITS SCRAP | - | - | - | - | - | 845164 | Y | - | - | S.S.CUT BITS SCRAP | 868573 | 2016-08-11 | - | TN 09 AX 2733 | - | - | - | - | 1617070111 | 2016-08-11 | 36751 | 991617000068 | 2016-08-11 | - | 0 | 0 | 510 | 36751 | ENG. IDBI BANK | 971848 | 2016-08-11 | 5947 | - | - | - | 60.4 | 60.4 | -
2016-08-24 | ENGG_LOCAL_LABOUR | CLOSED | TAMILNADU PETROPRODUCTS LTD | 3598 | SERVICE ORDER NO: ME/4900068756 | 4071 | MANALI EXPRESS HIGHWAY, MANALI, CHENNAI-600068 - | MANALI EXPRESS HIGHWAY, MANALI, CHENNAI-600068 - | ENGG_PRICE_LIST | 2016-08-24 | 100% PAYMENT | 2016-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 110600 | 0 | 0 | 40/71/ANFG/001 | J 4071- ANODE CELL RECOATING | 1 | 0 | 790000 | LOT | - | 310251 | 790000 | ENGG_LOCAL_LABOUR_LINE | CLOSED | ER-205 ANODE ELEMENT REPAIR AND RECOATING AS PER PO | - | - | - | - | 2016-07-18 | 858164 | Y | - | - | ER-205 ANODE ELEMENT REPAIR AND RECOATING AS PER PO | 880573 | 2016-08-24 | - | TN 07 J 3399 | - | PACKED IN TWO W/BOXES. MATLS RECD VIDE RGP NO.HMEC0066 DT.8-7-16 & 4(5)a CHALLAN NO.09 DT.8-7-16 AND BEING RETURNED BACK TO PARTY AFTER JOB WORK. | - | - | 1617090009 | 2016-08-24 | 908500 | - | 2016-08-24 | - | 0 | 0 | 1 | 908500 | ENG. IDBI BANK | 575093 | 2016-08-24 | 118500 | - | - | - | 790000 | 790000 | -
2016-11-05 | ENGG_INTER_EQUIPMENT | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700775 | 4093 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-11-05 | 100%PT45DAYS | 2016-11-05 | 0 | 0 | 0 | 3250 | 2 | 585 | - | 0 | 0 | 0 | 40/93/COFG/003 | J 4093 - SUPPLY OF SHAFT | 1 | 0 | 26000 | Numbers | - | 310101 | 26000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: RPMP120100634)- SHAFT MOC: SS316(SA479GR316) FOR UF CHEMICAL CLEANING PUMP(JOB NO:2885) | - | - | - | - | 2016-08-24 | 935167 | Y | - | - | (MATERIAL CODE: RPMP120100634)- SHAFT MOC: SS316(SA479GR316) FOR UF CHEMICAL CLEANING PUMP(JOB NO:2885)AS PER PO | 939573 | 2016-11-05 | COURIER | PROFESSIONAL | - | PACKED IN ONE CARTON BOX. | - | - | 1617070145 | 2016-11-09 | 29835 | 991617000186 | 2016-11-09 | - | 0 | 0 | 1 | 29835 | ENG. IDBI BANK | 345579/31-DEC-2016 | 2016-11-09 | 3835 | - | - | - | 26000 | 26000 | -
2016-11-19 | ENGG_LOCAL_SCRAP | CLOSED | GAS TECH ENGINEERING SERVICE | 6400 | - | - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | ENGG_PRICE_LIST | 2016-11-19 | 100% PAYMENT | 2016-11-21 | 5 | 3218.25 | 0 | 0 | 0 | 0 | - | 0 | 676 | -0.25 | BR/EM/SCRP/PVC | OLD PVC EMPTY BARREL | 21 | 0 | 3065 | Numbers | - | 310701 | 64365 | ENGG_LOCAL_SCRAP_LINE | CLOSED | OLD EMPTY ARGON CYLINDER-7.00CUM | - | - | - | - | - | 952169 | Y | - | - | OLD EMPTY ARGON CYLINDER-7.00CUM | 952574 | 2016-11-21 | - | TN 20 AR 9600 | - | - | - | - | 1617070156 | 2016-11-21 | 68259 | - | 2016-11-21 | - | 0 | 0 | 21 | 68259 | ENG. IDBI BANK | GAS TECH | 2016-11-21 | 3894 | - | - | - | 3065 | 3065 | -
2016-11-21 | ENGG_LOCAL_SCRAP | CLOSED | N.S.TRADERS | 6381 | - | - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | ENGG_PRICE_LIST | 2016-11-18 | 100% PAYMENT | 2016-11-21 | 5 | 9195.53 | 0 | 20434.5 | 0 | 0 | - | 0 | 1931 | -0.03 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 11400 | 0 | 14.34 | kilogram | - | 310701 | 163476 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S. CUT BITS SCRAP | - | - | - | - | - | 953168 | Y | - | - | M.S. CUT BITS SCRAP | 953573 | 2016-11-21 | - | TN 50 H 9051 | - | - | - | - | 1617070158 | 2016-11-21 | 195037 | 991617000212 | 2016-11-21 | - | 0 | 0 | 11400 | 195037 | ENG. IDBI BANK | N.S.TRADERS,N.S.TRADERS,N.S.TRADERS,N.S.TRADERS | 2016-11-21 | 31561 | - | - | - | 14.34 | 14.34 | -
2016-12-07 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237774 | 4053 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-07 | 100%30DAYS | 2016-12-07 | 0 | 0 | 0 | 28050 | 2 | 5049 | - | 0 | 0 | 0 | 40/53/MTPL/001 | J 4053 - MOUNTING PLATE | 48 | 0 | 4675 | Numbers | - | 310101 | 224400 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | MOUNTING PLATE FOR JUNCTION BO(BEL PART NO: 21258766011404) | - | - | - | - | 2016-06-09 | 966173 | Y | - | - | MOUNTING PLATE FOR JUNCTION BO(BEL PART NO: 21258766011404)AS PER PO | 965575 | 2016-12-07 | SRI LAKSHMI TRANSPORT | TN 11 T 3875 | - | PACKED IN ONE WOODEN BOX | - | - | 1617070161 | 2016-12-07 | 257499 | 991617000233 | 2016-12-07 | - | 0 | 0 | 48 | 257499 | - | - | 2016-12-07 | - | - | - | - | 4675 | 4675 | -
2016-12-23 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237774 | 4053 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-23 | 100% PAYMENT | 2016-12-23 | 0 | 0 | 0 | 71875 | 2 | 12937.5 | - | 0 | 0 | 0.5 | 40/53/BSPL/001 | J 4053 - BASE PLATE | 200 | 0 | 2875 | Numbers | - | 310101 | 575000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO:212587140194)- BASE PLATE | - | - | - | - | 2016-06-09 | 979173 | Y | - | - | (BEL PART NO:212587140194)- BASE PLATEAS PER PO | 978575 | 2016-12-23 | COURIER | TCI XPS | LR NO.329732211 | PACKED IN TWO WOODEN BOXES. | - | - | 1617070169 | 2016-12-23 | 659813 | 991617000255 | 2016-12-23 | - | 0 | 0 | 200 | 659813 | - | - | 2016-12-23 | - | - | - | - | 2875 | 2875 | -
2016-12-27 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT OMAN REFINERIES LIMITED | 4660 | RCEP/PUR/13/4500025204 | 4032 | POST BORL RESIDENTIAL COMPLEX, REVAMP AND CAPACITY ENHANCEMENT PROJECT, - | POST BORL RESIDENTIAL COMPLEX, REVAMP AND CAPACITY ENHANCEMENT PROJECT, - | ENGG_PRICE_LIST | 2016-12-27 | 5%10%15%50%20% | 2016-12-28 | 0 | 0 | 0 | 1091944 | 2 | 196549.92 | - | 0 | 0 | 87356.08 | 40/32/HEFG/001 | J 4032 -SUPPLY OF SS DUPLEX HEAT EXCHANGER | 1 | 0 | 8735552 | Numbers | - | 310101 | 8735552 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM CODE:11-EE-00-1005B)- DESALTING WATER/ EFFLUENT EXCHANGER-2 | - | - | - | - | 2016-04-28 | 983173 | Y | - | - | (ITEM CODE:11-EE-00-1005B)- DESALTING WATER/ EFFLUENT EXCHANGER-2AS PER PO | 985575 | 2016-12-28 | TCI FREIGHT | RJ 26 GA 1088 | LR NO.309388321 | 2 EQUIPMENTS AND 8 WOODEN BOXES | - | - | 1617070173 | 2016-12-28 | 10111402 | 9.9162e+23 | 28-DEC-2016,28-DEC-2016 | - | 0 | 0 | 1 | 10111402 | - | - | 2016-12-28 | - | 16171007 | 2016-12-28 | 10024047 | 8735552 | 8735552 | -
2016-12-27 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT OMAN REFINERIES LIMITED | 4660 | RCEP/PUR/13/4500025204 | 4032 | POST BORL RESIDENTIAL COMPLEX, REVAMP AND CAPACITY ENHANCEMENT PROJECT, - | POST BORL RESIDENTIAL COMPLEX, REVAMP AND CAPACITY ENHANCEMENT PROJECT, - | ENGG_PRICE_LIST | 2016-12-27 | 5%10%15%50%20% | 2016-12-28 | 0 | 0 | 0 | 1091944 | 2 | 196549.92 | - | 0 | 0 | 87356.08 | 40/32/HEFG/BOR | J 4032- SUPPLY SS DUPLEX HEAT EXCHANGER | 1 | 0 | 8735552 | Numbers | - | 310101 | 8735552 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM CODE:11-EE-00-1005A)- DESALTING WATER/ EFFLUENT EXCHANGER-2 | - | - | - | - | 2016-04-28 | 983173 | Y | - | - | (ITEM CODE:11-EE-00-1005A)- DESALTING WATER/ EFFLUENT EXCHANGER-2AS PER PO | 985575 | 2016-12-28 | TCI FREIGHT | RJ 26 GA 1088 | LR NO.309388321 | 2 EQUIPMENTS AND 8 WOODEN BOXES | - | - | 1617070173 | 2016-12-28 | 10111402 | 9.9162e+23 | 28-DEC-2016,28-DEC-2016 | - | 0 | 0 | 1 | 10111402 | - | - | 2016-12-28 | - | 16171007 | 2016-12-28 | 10024047 | 8735552 | 8735552 | -
2016-10-03 | ENGG_INTER_LABOUR | CLOSED | BHARAT DYNAMICS LIMITED | 1024 | 40701684 | 3905 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | ENGG_PRICE_LIST | 2016-10-03 | 3905BDLPT | 2016-10-03 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 21000 | 0 | 0 | 39/05/ROFG/3RD | J 3905- TI SHELL ROOLING | 10 | 0 | 15000 | Numbers | - | 310251 | 150000 | ENGG_INTER_LABOUR_LINE | CLOSED | - | - | - | - | - | 2014-03-05 | 895170 | Y | - | - | - | 911575 | 2016-10-03 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO: 118 | PACKED IN 12 C / BOXES. MATLS RECD VIDE GATE PASS NO:201660659 & 4(5)a CHALLAN NO.5751000021 DT.27-08-16 AND RETURNED BACK TO PARTY AFTER JOB WORK. | - | - | 1617090014 | 2016-10-03 | 172500 | - | 2016-10-03 | 151600000006 | 10 | 150000 | 0 | 22500 | - | - | 2016-10-03 | - | 1617050001 | 2016-10-27 | 0 | 15000 | 15000 | -
2016-10-03 | ENGG_INTER_LABOUR | CLOSED | BHARAT DYNAMICS LIMITED | 1024 | 40701684 | 3905 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | ENGG_PRICE_LIST | 2016-10-03 | 3905BDLPT | 2016-10-03 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 21000 | 0 | 0 | 39/05/ROFG/3RD | J 3905- TI SHELL ROOLING | 10 | 0 | 15000 | Numbers | - | 310251 | 150000 | ENGG_INTER_LABOUR_LINE | CLOSED | - | - | - | - | - | 2014-03-05 | 895170 | Y | - | - | - | 911575 | 2016-10-03 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO: 118 | PACKED IN 12 C / BOXES. MATLS RECD VIDE GATE PASS NO:201660659 & 4(5)a CHALLAN NO.5751000021 DT.27-08-16 AND RETURNED BACK TO PARTY AFTER JOB WORK. | - | - | 1617090014 | 2016-10-03 | 172500 | - | 2016-10-03 | 151600000006 | 10 | 150000 | 0 | 22500 | - | - | 2016-10-03 | - | 1617050001 | 2016-10-27 | 172500 | 15000 | 15000 | -
2016-10-12 | ENGG_INTER_RECOATING | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700799 | 4095 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-10-12 | 100%PT45DAYS | 2016-10-12 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 84700 | 0 | 0 | 40/95/REFG/CAT | J 4095 - RECOATING OF CATHODE | 11 | 0 | 55000 | Numbers | - | 310252 | 605000 | ENGG_INTER_RECOATING_LINE | CLOSED | (MATERIAL CODE: WO12140012PRC)- RECOATING OF CATHODE ELEMENTS OF UHDE ELECTROLYSER | - | - | - | - | 2016-08-27 | 901166 | Y | - | - | (MATERIAL CODE: WO12140012PRC)- RECOATING OF CATHODE ELEMENTS OF UHDE ELECTROLYSERAS PER PO | 917573 | 2016-10-12 | - | TN 30 BB 6087 | - | PACKED IN TWO W/BOXES. PARTY'S MATERIALS RECD VIDE RGP NO.1617/109 DT.19-08-16 AND 4(5)A CHALLAN & RETURNED BACK TO PARTY AFTER JOB WORK.NOT FOR SALE | - | - | 1617090016 | 2016-10-12 | 695750 | - | 12-OCT-2016,12-OCT-2016 | - | 0 | 0 | 11 | 695750 | ENG. IDBI BANK | 1.6152e+17 | 2016-10-12 | -509250 | - | - | - | 55000 | 55000 | -
2016-10-12 | ENGG_INTER_RECOATING | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700799 | 4095 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-10-12 | 100%PT45DAYS | 2016-10-12 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 84000 | 0 | 0 | 40/95/REFG/AND | J 4095 - RECOATING OF ANODE | 6 | 0 | 100000 | Numbers | - | 310252 | 600000 | ENGG_INTER_RECOATING_LINE | CLOSED | (MATERIAL CODE:WO12400012PRC)-RECOATING OF ANODE ELEMENTS OF UHDE ELECTROLYSER | - | - | - | - | 2016-08-27 | 901166 | Y | - | - | (MATERIAL CODE:WO12400012PRC)-RECOATING OF ANODE ELEMENTS OF UHDE ELECTROLYSERAS PER PO | 917573 | 2016-10-12 | - | TN 30 BB 6087 | - | PACKED IN TWO W/BOXES. PARTY'S MATERIALS RECD VIDE RGP NO.1617/109 DT.19-08-16 AND 4(5)A CHALLAN & RETURNED BACK TO PARTY AFTER JOB WORK.NOT FOR SALE | - | - | 1617090016 | 2016-10-12 | 690000 | - | 12-OCT-2016,12-OCT-2016 | - | 0 | 0 | 6 | 690000 | ENG. IDBI BANK | 1.6152e+17 | 2016-10-12 | -515000 | - | - | - | 100000 | 100000 | -
2016-11-02 | ENGG_INTER_EQUIPMENT | CLOSED | TEAMEC CHLORATES LIMITED | 1044 | TM/16-17/0124 | 4101 | PLOT NO. 558 & 559,APIIC GROWTH CENTRE GUNDLAPALLI VILLAGE ANDHRA PRADESH-523211 | PLOT NO. 558 & 559,APIIC GROWTH CENTRE GUNDLAPALLI VILLAGE ANDHRA PRADESH-523211 | ENGG_PRICE_LIST | 2016-11-02 | 100%30 DAYS | 2016-11-02 | 0 | 0 | 0 | 2625 | 2 | 472.5 | - | 0 | 0 | 0.5 | 41/01/COFG/002 | J 4101 - BURNER DISTRIBUTER SS 316 L | 1 | 0 | 21000 | Numbers | - | 310101 | 21000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | BURNER DISTRIBUTOR SS316L | - | - | - | - | 2016-09-17 | 930167 | Y | - | - | BURNER DISTRIBUTOR SS316LAS PER PO | 936573 | 2016-11-02 | - | TN 11 D 7697 | - | - | - | - | 1617070142 | 2016-11-03 | 24098 | 9.9162e+23 | 03-NOV-2016,03-NOV-2016 | - | 0 | 0 | 1 | 24098 | - | - | 2016-11-03 | - | - | - | - | 21000 | 21000 | -
2016-11-02 | ENGG_INTER_EQUIPMENT | CLOSED | TEAMEC CHLORATES LIMITED | 1044 | TM/16-17/0124 | 4101 | PLOT NO. 558 & 559,APIIC GROWTH CENTRE GUNDLAPALLI VILLAGE ANDHRA PRADESH-523211 | PLOT NO. 558 & 559,APIIC GROWTH CENTRE GUNDLAPALLI VILLAGE ANDHRA PRADESH-523211 | ENGG_PRICE_LIST | 2016-11-02 | 100%30 DAYS | 2016-11-02 | 0 | 0 | 0 | 1500 | 2 | 270 | - | 0 | 0 | 0 | 41/01/COFG/TCL | J 4101 - TI SLEEVE | 1 | 0 | 12000 | Numbers | - | 310101 | 12000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | TI SLEEVE-55 MM-180MM LONG | - | - | - | - | 2016-09-17 | 930167 | Y | - | - | TI SLEEVE-55 MM-180MM LONGAS PER PO | 936573 | 2016-11-02 | - | TN 11 D 7697 | - | - | - | - | 1617070142 | 2016-11-03 | 13770 | 9.9162e+23 | 03-NOV-2016,03-NOV-2016 | - | 0 | 0 | 1 | 13770 | - | - | 2016-11-03 | - | - | - | - | 12000 | 12000 | -
2016-11-21 | ENGG_LOCAL_SCRAP | CLOSED | GAS TECH ENGINEERING SERVICE | 6400 | - | - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | ENGG_PRICE_LIST | 2016-11-19 | 100% PAYMENT | 2016-11-21 | 5 | 396.15 | 0 | 0 | 0 | 0 | - | 0 | 83 | 0 | WS/MA/SCRP/LOT | WASTE SCRAP MATERIAL WITH LOT UOM | 3 | 0 | 2641 | LOT | - | 310701 | 7923 | ENGG_LOCAL_SCRAP_LINE | CLOSED | OLD EMPTY SCRAP ARGON CYLINDER -7.30CUM | - | - | - | - | - | 952171 | Y | - | - | OLD EMPTY SCRAP ARGON CYLINDER -7.30CUM | 952575 | 2016-11-21 | - | TN 19 X 8481 | - | - | - | - | 1617070157 | 2016-11-21 | 8402.15 | - | 21-NOV-2016,21-NOV-2016,21-NOV-2016 | - | 0 | 0 | 3 | 8402.15 | ENG. IDBI BANK | GAS TECH | 2016-11-21 | -278010.24 | - | - | - | 2641 | 2641 | -
2016-11-21 | ENGG_LOCAL_SCRAP | CLOSED | GAS TECH ENGINEERING SERVICE | 6400 | - | - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | ENGG_PRICE_LIST | 2016-11-19 | 100% PAYMENT | 2016-11-21 | 5 | 6721.75 | 0 | 0 | 0 | 0 | - | 0 | 1412 | 0 | MS/BR/SCRP/NO | OLD MS EMPTY BARREL | 46 | 0 | 2922.5 | Numbers | - | 310701 | 134435 | ENGG_LOCAL_SCRAP_LINE | CLOSED | OLD EMPTY SCRAP ARGON CYLINDER -6.00CUM | - | - | - | - | - | 952171 | Y | - | - | OLD EMPTY SCRAP ARGON CYLINDER -6.00CUM | 952575 | 2016-11-21 | - | TN 19 X 8481 | - | - | - | - | 1617070157 | 2016-11-21 | 142568.75 | - | 21-NOV-2016,21-NOV-2016,21-NOV-2016 | - | 0 | 0 | 46 | 142568.75 | ENG. IDBI BANK | GAS TECH | 2016-11-21 | -143843.64 | - | - | - | 2922.5 | 2922.5 | -
2016-11-21 | ENGG_LOCAL_SCRAP | CLOSED | GAS TECH ENGINEERING SERVICE | 6400 | - | - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | 2/36A PERUMAL KOIL STREET NEW GUMMUDIPONDI - | ENGG_PRICE_LIST | 2016-11-19 | 100% PAYMENT | 2016-11-21 | 5 | 7202.75 | 0 | 0 | 0 | 0 | - | 0 | 1513 | 0 | BR/EM/SCRP/PVC | OLD PVC EMPTY BARREL | 47 | 0 | 3065 | Numbers | - | 310701 | 144055 | ENGG_LOCAL_SCRAP_LINE | CLOSED | OLD EMPTY SCRAP ARGON CYLINDER-7.00CUM | - | - | - | - | - | 952171 | Y | - | - | OLD EMPTY SCRAP ARGON CYLINDER-7.00CUM | 952575 | 2016-11-21 | - | TN 19 X 8481 | - | - | - | - | 1617070157 | 2016-11-21 | 152770.75 | - | 21-NOV-2016,21-NOV-2016,21-NOV-2016 | - | 0 | 0 | 47 | 152770.75 | ENG. IDBI BANK | GAS TECH | 2016-11-21 | -133641.64 | - | - | - | 3065 | 3065 | -
2017-01-16 | ENGG_INTER_EQUIPMENT | BOOKED | INDIAN OIL CORPORATION LIMITED | 2867 | 1048/065/24785288 | 4056 | SR.PROJECT MANAGER BS IV PROJECT, PO BARAUNI REFINERY, - | SR.PROJECT MANAGER BS IV PROJECT, PO BARAUNI REFINERY, - | ENGG_PRICE_LIST | 2017-01-16 | 5%5%75%5%10% | 2017-01-16 | 0 | 0 | 0 | 484125 | 2 | 87142.5 | - | 0 | 0 | 116190.5 | 40/56/HEFG/IOC | J 4056 - SUPPLY OF SHELL & TUBE HEAT EXCHANGER | 1 | 0 | 3873000 | Numbers | - | 310101 | 3873000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:2956030013)-SHELL AND TUBE HEAT EXCHANGER 803-E-017 | - | - | - | - | 2016-06-14 | 1000177 | Y | - | - | (MATERIAL CODE:2956030013)-SHELL AND TUBE HEAT EXCHANGER 803-E-017AS PER PO | 1001575 | 2017-01-16 | ASSOCIATED ROAD CARRIERS LTD | UP 71 T 2889 | LR NO.M9000010429 | ONE EQUIPMENT AND 2 WOODEN BOXES | - | - | 1617070178 | 2017-01-16 | 4560458 | 991617000287 | 2017-01-16 | - | 0 | 0 | 1 | 4560458 | - | - | 2017-01-16 | - | - | - | - | 3873000 | 3873000 | -
2016-08-22 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2016-08-18 | 100% Advance | 2016-08-22 | 5 | 864.7 | 0 | 1921.56 | 0 | 0 | - | 0 | 182 | 0.24 | MS/SS/SCRP/MIX | MS AND SS MIXED BORING SCRAP | 1430 | 0 | 10.75 | kilogram | - | 310701 | 15372.5 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S. AND S.S. MIXED BORING SCRAP | - | - | - | - | - | 855166 | Y | - | - | M.S. AND S.S. MIXED BORING SCRAP | 878574 | 2016-08-22 | - | TN 04 M 1702 | - | - | - | - | 1617070117 | 2016-08-22 | 18341 | 991617000079 | 2016-08-22 | - | 0 | 0 | 1430 | 18341 | ENG. IDBI BANK | 7.7673e+23 | 2016-08-22 | 2968.5 | - | - | - | 10.75 | 10.75 | -
2016-09-30 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/ASD/488/2016-2017 | 4049 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-09-30 | 4049PTKMML | 2016-09-30 | 0 | 0 | 0 | 136500 | 2 | 24570 | - | 0 | 0 | 0 | 40/49/COFG/KMM | J 4049 - Ti Gr 7 EMICO FILTER | 1 | 0 | 1092000 | Numbers | - | 310101 | 1092000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (CODE NO: 615246762)- GR.7 TRAY TITANIUM FOR EMICO FILTER (WITH SS316 TI STIFFNER) AS PER DRG NO TP/MR/IBP/O-201 REV 0 | - | - | - | - | 2016-05-23 | 893170 | Y | - | - | (CODE NO: 615246762)- GR.7 TRAY TITANIUM FOR EMICO FILTER (WITH SS316 TI STIFFNER) AS PER DRG NO TP/MR/IBP/O-201 REV 0(MTC OF TITANIUM GR.7 SHOULD BE SUBMITTED ALONG WITH THE SUPPLY) | 910575 | 2016-09-30 | COURIER | TCI XPS | LR NO. 329498610 | PACKED IN ONE WOODEN BOX. | - | - | 1617070128 | 2016-09-30 | 1253070 | 991617000136 | 2016-09-30 | - | 0 | 0 | 1 | 1253070 | ENG. IDBI BANK | 795123 | 2016-09-30 | 161070 | - | - | - | 1092000 | 1092000 | -
2016-10-24 | ENGG_INTER_EQUIPMENT | CLOSED | HYPER FILTRATION PVT LTD | 5380 | HFPL/TEAM/PO/16/15716 | 4078 | 16/1 , A-4, SITE IV, SAHIBABAD INDUSTRIAL AREA, DIST. GHAZIABAD - 201010, UTTAR PRADESH, - | 16/1 , A-4, SITE IV, SAHIBABAD INDUSTRIAL AREA, DIST. GHAZIABAD - 201010, UTTAR PRADESH, - | ENGG_PRICE_LIST | 2016-10-24 | 50%ADV50%DESP | 2016-10-24 | 0 | 0 | 0 | 105000 | 2 | 18900 | - | 0 | 0 | 0 | 40/78/COFG/HFP | 4078 TI Gr.2 PLATE WITH MMO COATING | 35 | 0 | 24000 | Numbers | - | 310101 | 840000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TITANIUM GR.2 PLATE WITH MMO COATING (5 MICRON THICKNESS), ANODE PLATE-SB265GR.2 | - | - | - | - | 2016-07-15 | 916171 | Y | - | - | SUPPLY OF TITANIUM GR.2 PLATE WITH MMO COATING (5 MICRON THICKNESS), ANODE PLATE-SB265GR.2AS PER PO | 925575 | 2016-10-24 | COURIER | TCI XPS | LR NO. 329246794 | PACKED IN ONE WOODEN BOX. | - | - | 1617070136 | 2016-10-24 | 963900 | 991617000166 | 2016-10-24 | - | 0 | 0 | 35 | 963900 | ENG. IDBI BANK | HYPER,HYPER | 2016-10-24 | 123900 | - | - | - | 24000 | 24000 | -
2016-11-17 | ENGG_LOCAL_SCRAP | CLOSED | AVM ENTERPRISES | 6340 | - | - | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-11-17 | 5 | 2823.23 | 0 | 6273.85 | 0 | 0 | - | 0 | 593 | 0.12 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 3740 | 0 | 13.42 | kilogram | - | 310701 | 50190.8 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S.CUT BITS SCRAP | - | - | - | - | - | 946169 | Y | - | - | M.S.CUT BITS SCRAP | 947574 | 2016-11-17 | - | TN 20 AW 3552 | - | - | - | - | 1617070152 | 2016-11-17 | 59881 | 991617000208 | 2016-11-17 | - | 0 | 0 | 3740 | 59881 | ENG. IDBI BANK | AVM-SCRAP | 2016-11-17 | 9690.2 | - | - | - | - | 13.42 | -
2016-12-05 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%30DAYS | 2016-12-05 | 0 | 0 | 0 | 210937.5 | 2 | 37968.75 | - | 0 | 0 | -0.25 | 40/57/IPFG/001 | J 4057 - INTERMEDIATE PLATE | 4500 | 0 | 375 | Numbers | - | 310101 | 1687500 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | INTERMEDIATE PLATE(BEL PART NO: 21258519010603) | - | - | - | - | 2016-06-13 | 965173 | Y | - | - | INTERMEDIATE PLATE(BEL PART NO: 21258519010603)AS PER PO | 964575 | 2016-12-07 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.130 | PACKED IN 14 WOODEN BOXES AND ONE CARTON BOX. | - | - | 1617070160 | 2016-12-07 | 1936406 | 9.9162e+35 | 07-DEC-2016,07-DEC-2016,07-DEC-2016 | - | 0 | 0 | 4500 | 1936406 | - | - | 2016-12-07 | - | - | - | - | 375 | 375 | -
2016-12-05 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%30DAYS | 2016-12-05 | 0 | 0 | 0 | 143859.38 | 2 | 25894.69 | - | 0 | 0 | -0.07 | 40/57/TPFG/001 | J 4057 - TOP PLATE | 155 | 0 | 7425 | Numbers | - | 310101 | 1150875 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | TOP PLATE(BEL PART NO: 21258518011505) | - | - | - | - | 2016-06-13 | 965173 | Y | - | - | TOP PLATE(BEL PART NO: 21258518011505)AS PER PO | 964575 | 2016-12-07 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.130 | PACKED IN 14 WOODEN BOXES AND ONE CARTON BOX. | - | - | 1617070160 | 2016-12-07 | 1320629 | 9.9162e+35 | 07-DEC-2016,07-DEC-2016,07-DEC-2016 | - | 0 | 0 | 155 | 1320629 | - | - | 2016-12-07 | - | - | - | - | 7425 | 7425 | -
2016-12-05 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%30DAYS | 2016-12-05 | 0 | 0 | 0 | 292500 | 2 | 52650 | - | 0 | 0 | 0 | 40/57/BPFG/001 | J 4057 - BOTTOM PLATE | 650 | 0 | 3600 | Numbers | - | 310101 | 2340000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | BOTTOM PLATE(BEL PART NO: 21258517012408) | - | - | - | - | 2016-06-13 | 965173 | Y | - | - | BOTTOM PLATE(BEL PART NO: 21258517012408)AS PER PO | 964575 | 2016-12-07 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.130 | PACKED IN 14 WOODEN BOXES AND ONE CARTON BOX. | - | - | 1617070160 | 2016-12-07 | 2685150 | 9.9162e+35 | 07-DEC-2016,07-DEC-2016,07-DEC-2016 | - | 0 | 0 | 650 | 2685150 | - | - | 2016-12-07 | - | - | - | - | 3600 | 3600 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 208828.13 | 2 | 37589.06 | - | 0 | 0 | -0.19 | 40/57/TPFG/001 | J 4057 - TOP PLATE | 225 | 0 | 7425 | Numbers | - | 310101 | 1670625 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | TOP PLATE(BEL PART NO: 21258518011505) | - | - | - | - | 2016-06-13 | 996177 | Y | - | - | TOP PLATE(BEL PART NO: 21258518011505)AS PER PO | 997576 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 6 WOODEN BOXES | - | - | 1617070176 | 2017-01-10 | 1917042 | 9.9162e+23 | 10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 225 | 1917042 | - | - | 2017-01-10 | - | - | - | - | 7425 | 7425 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 45000 | 2 | 8100 | - | 0 | 0 | 0 | 40/57/BPFG/001 | J 4057 - BOTTOM PLATE | 100 | 0 | 3600 | Numbers | - | 310101 | 360000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | BOTTOM PLATE (BEL PART NO: 21258517012408) | - | - | - | - | 2016-06-13 | 996177 | Y | - | - | BOTTOM PLATE (BEL PART NO: 21258517012408)AS PER PO | 997576 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 6 WOODEN BOXES | - | - | 1617070176 | 2017-01-10 | 413100 | 9.9162e+23 | 10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 100 | 413100 | - | - | 2017-01-10 | - | - | - | - | 3600 | 3600 | -
2016-09-29 | ENGG_INTER_EQUIPMENT | CLOSED | ADVANCE NAVAL SYSTEM PROGRAMME | 5920 | DRDL/21/15(SV)/2015/013/027 | 4039 | K-15, RCI CAMPUS, PB NO.1, VIGNYANKANCHAA, HYDERABAD-500069 - | K-15, RCI CAMPUS, PB NO.1, VIGNYANKANCHAA, HYDERABAD-500069 - | ENGG_PRICE_LIST | 2016-09-08 | 4039PTANSP | 2016-09-29 | 0 | 0 | 0 | 698250 | 14.5 | 911216.25 | - | 0 | 0 | -0.25 | 40/39/ABFG/ANS | 4039 SPHERICAL AIR BOTTLE | 7 | 0 | 798000 | Numbers | - | 310101 | 5586000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SPHERICAL AIR BOTTLE | - | - | - | - | 2016-05-03 | 892166 | Y | - | - | SPHERICAL AIR BOTTLEAS PER PO | 909573 | 2016-09-29 | OUR OWN VECHILE | TN 11 D 7697 | - | PACKED IN 7 WOODEN BOXES. | - | - | 1617070127 | 2016-09-29 | 7195466 | 991617000133 | 2016-09-29 | - | 0 | 0 | 7 | 7195466 | ENG. IDBI BANK | ANSP | 2016-09-29 | 1609466 | - | - | - | 798000 | 798000 | -
2016-10-21 | ENGG_INTER_LABOUR | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700799 | 4095 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | 2016-10-21 | 30 NET | 2016-10-21 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 84000 | 0 | 0 | 40/95/REFG/002 | J 4095 - ANODE RECOATING | 6 | 0 | 100000 | Numbers | - | 310251 | 600000 | ENGG_INTER_LABOUR_LINE | CLOSED | (MATERIAL CODE: WO12400012PRC)- RECOATING OF ANODE ELEMENTS OF UHDE ELECTROLYSER | - | - | - | - | 2016-08-21 | 915167 | Y | - | - | (MATERIAL CODE: WO12400012PRC)- RECOATING OF ANODE ELEMENTS OF UHDE ELECTROLYSERAS PER PO | 924573 | 2016-10-21 | TN 16 C7477 | - | - | ONE WOODEN BOX.PARTYS MATERIAL RECD VIDE RGP NO:RGP/1617/109 DT 19-AUG-2016 & RGP 1617/152 DT 20-OCT-2016 AND 4(5) A CHALAN.JOB WORK DONE AND RETURN.N | - | - | 1617090017 | 2016-10-21 | 690000 | - | 2016-10-21 | - | 0 | 0 | 6 | 690000 | ENG. IDBI BANK | 161670 | 2016-10-21 | 90000 | - | - | - | 100000 | 100000 | -
2016-10-27 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/40/1122/2016-2017 | 4085 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-10-27 | 100%PT30DAYS | 2016-10-27 | 0 | 0 | 0 | 36375 | 2 | 6547.5 | - | 0 | 0 | 0 | 40/85/COFG/KML | J 4085 - Ti Gr 7 - EQUAL TEE | 3 | 0 | 97000 | Numbers | - | 310101 | 291000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO:614276760)- SUPPLY OF 100 MM NB TIGR.7 EQUAL TEE AS PER DRG. TP/MR/IBP/DIG-T/REV.0 | - | - | - | - | 2016-07-28 | 923171 | Y | - | - | (MATERIAL CODE NO:614276760)- SUPPLY OF 100 MM NB TIGR.7 EQUAL TEE AS PER DRG. TP/MR/IBP/DIG-T/REV.0MATERIAL OF CONTRUCTION: FLANGE SA105 WITH TIGR.7 LINING MATERIAL TEST CERTIFICATE FOR TITANIUM GR.7 SHOULD BE SUBMITTED ALONG WITH THE SUPPLY | 931575 | 2016-10-27 | COURIER | TCI XPS | LR NO.329246842 | PACKED IN ONE WOODEN BOX. GR.WT: 80 KGS | - | - | 1617070140 | 2016-10-27 | 333922.5 | 991617000176 | 2016-10-27 | - | 0 | 0 | 3 | 333922.5 | ENG. IDBI BANK | 795405 | 2016-10-27 | 42922.5 | - | - | - | 97000 | 97000 | -
2016-11-18 | ENGG_LOCAL_SCRAP | CLOSED | N.S.TRADERS | 6381 | - | - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | ENGG_PRICE_LIST | 2016-11-18 | 100% PAYMENT | 2016-11-18 | 5 | 8526.03 | 0 | 18946.73 | 0 | 0 | - | 0 | 1790 | 0.44 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 10570 | 0 | 14.34 | kilogram | - | 310701 | 151573.8 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S.CUT BITS SCRAP | - | - | - | - | - | 948169 | Y | - | - | M.S.CUT BITS SCRAP | 949573 | 2016-11-18 | - | TN 50 H 9051 | - | - | - | - | 1617070153 | 2016-11-18 | 180837 | 991617000209 | 2016-11-18 | - | 0 | 0 | 10570 | 180837 | ENG. IDBI BANK | 46997 | 2016-11-18 | 29263.2 | - | - | - | 14.34 | 14.34 | -
2016-12-09 | ENGG_LOCAL_SCRAP | CLOSED | N.S.TRADERS | 6381 | - | - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | ENGG_PRICE_LIST | 2016-12-09 | 100% PAYMENT | 2016-12-09 | 5 | 70.75 | 0 | 0 | 0 | 0 | - | 0 | 15 | 0 | WS/MA/SCRP/LOT | WASTE SCRAP MATERIAL WITH LOT UOM | 1 | 0 | 1415 | LOT | - | 310701 | 1415 | ENGG_LOCAL_SCRAP_LINE | CLOSED | WASTE WOODEN SCRAP | - | - | - | - | - | 973174 | Y | - | - | WASTE WOODEN SCRAP | 972575 | 2016-12-09 | - | TN 50 H 9051 | - | - | - | - | 1617070166 | 2016-12-09 | 1500.75 | 991617000242 | 09-DEC-2016,09-DEC-2016 | - | 0 | 0 | 1 | 1500.75 | ENG. IDBI BANK | N.S.TRADERS | 2016-12-09 | -45042.95 | - | - | - | 1415 | 1415 | -
2016-12-09 | ENGG_LOCAL_SCRAP | CLOSED | N.S.TRADERS | 6381 | - | - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | ENGG_PRICE_LIST | 2016-12-09 | 100% PAYMENT | 2016-12-09 | 5 | 2538.49 | 0 | 5641.09 | 0 | 0 | - | 0 | 533 | 0 | BR/SC/SCRP/KGS | BRASS SCRAP | 244.6 | 0 | 184.5 | kilogram | - | 310701 | 45128.7 | ENGG_LOCAL_SCRAP_LINE | CLOSED | ALUMINUM BRANZ SCRAP | - | - | - | - | - | 973174 | Y | - | - | ALUMINUM BRANZ SCRAP | 972575 | 2016-12-09 | - | TN 50 H 9051 | - | - | - | - | 1617070166 | 2016-12-09 | 53841.28 | 991617000242 | 09-DEC-2016,09-DEC-2016 | - | 0 | 0 | 244.6 | 53841.28 | ENG. IDBI BANK | N.S.TRADERS | 2016-12-09 | 7297.58 | - | - | - | 184.5 | 184.5 | -
2016-08-18 | ENGG_LOCAL_EQUIPMENT | CLOSED | TAMILNADU NEWSPRINTAND PAPERS LIMITED | 4500 | FAC-MAT-PUR/161715001697 | 4050 | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | ENGG_PRICE_LIST | 2016-08-18 | TNPL4050PT | 2016-08-18 | 5 | 5622.75 | 0 | 12495 | 0 | 0 | - | 0 | 0 | 0.25 | 40/50/TPFG/TNP | 4050 TI GR.2 PIPE SUPPLY | 12 | 0 | 8330 | Numbers | - | 310201 | 99960 | ENGG_LOCAL_EQUIPMENT_LINE | CLOSED | TITANIUM PIPE 40NB SCH40 GR.2 (TNPL CODE: 2652000161) | - | - | - | - | 2016-05-30 | 850165 | Y | - | - | TITANIUM PIPE 40NB SCH40 GR.2 (TNPL CODE: 2652000161)AS PER PO | 873573 | 2016-08-18 | COURIER | TCI XPS | LR NO. 328690121 | PACKED IN ONE WOODEN BOX | - | - | 1617070114 | 2016-08-18 | 118078 | 991617000074 | 2016-08-18 | - | 0 | 0 | 12 | 118078 | ENG. IDBI BANK | TNPL | 2016-08-18 | 18118 | - | - | - | 8330 | 8330 | -
2017-01-09 | ENGG_INTER_EQUIPMENT | BOOKED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | ENGG_PRICE_LIST | 2017-01-09 | 20%70%10% | 2017-01-09 | 0 | 0 | 0 | 4781.25 | 2 | 860.63 | - | 0 | 0 | 0.12 | 40/35/COFG/032 | J 4035 - TITANIUM FILLER WIRE | 4.5 | 0 | 8500 | Numbers | - | 310101 | 38250 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR.2 FILLER WIRE 3.2MM DIA | - | - | - | - | 2016-10-26 | 996173 | Y | - | - | SUPPLY OF TIGR.2 FILLER WIRE 3.2MM DIAAS PER PO | 996575 | 2017-01-09 | COURIER | PROFESSIONAL | - | PACKED IN ONE CARTON BOX | - | - | 1617070174 | 2017-01-10 | 43892 | 9.9162e+23 | 10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 4.5 | 43892 | - | - | 2017-01-10 | - | - | - | - | 8500 | 8500 | -
2017-01-09 | ENGG_INTER_EQUIPMENT | BOOKED | TECHNIP INDIA LIMITED | 4600 | PO-6311-01 | 4035 | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | C/o M/S. JBF PETROCHEMICALS LTD, #4-214,PB NO.001, INDUSTRIAL PLOT NO.09,MANGALORE SEZ LTD, BAJPE VILLAGE, MANGALORE, - | ENGG_PRICE_LIST | 2017-01-09 | 20%70%10% | 2017-01-09 | 0 | 0 | 0 | 14875 | 2 | 2677.5 | - | 0 | 0 | 0.5 | 40/35/COFG/200 | J 4035 - TITANIUM FILLER WIRE - DIA 2.0 MM | 14 | 0 | 8500 | Numbers | - | 310101 | 119000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TIGR.2 FILLER WIRE 2MM DIA | - | - | - | - | 2016-10-26 | 996173 | Y | - | - | SUPPLY OF TIGR.2 FILLER WIRE 2MM DIAAS PER PO | 996575 | 2017-01-09 | COURIER | PROFESSIONAL | - | PACKED IN ONE CARTON BOX | - | - | 1617070174 | 2017-01-10 | 136553 | 9.9162e+23 | 10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 14 | 136553 | - | - | 2017-01-10 | - | - | - | - | 8500 | 8500 | -
2016-08-31 | ENGG_LOCAL_LABOUR | CLOSED | TAMILNADU PETROPRODUCTS LTD | 3598 | ME/4900069129/30-SEP-2016 | 4096 | MANALI EXPRESS HIGHWAY, MANALI, CHENNAI-600068 - | MANALI EXPRESS HIGHWAY, MANALI, CHENNAI-600068 - | ENGG_PRICE_LIST | 2016-08-31 | 100%-ON COD | 2016-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 3500 | 0 | 0 | FG/LB/4096/TPL | TPL IMPELLER REPAIR | 1 | 0 | 25000 | Numbers | - | 310251 | 25000 | ENGG_LOCAL_LABOUR_LINE | CLOSED | Labourcharges for impeller reconditioning | - | - | - | - | - | 868164 | Y | - | - | Labourcharges for impeller reconditioning | 889573 | 2016-08-31 | BY PARTY | HAND CARRY | - | PARTY'S MATERIAL RECD VIDE RGP NO.HMEC0127 DT.24-AUG-2016 AND BEING RETURNED BACK TO PARTY AFTER REPAIR. NO SALES INVOLVED IN THIS TRANSACTION. | - | - | 1617090010 | 2016-08-31 | 28750 | - | 2016-08-31 | - | 0 | 0 | 1 | 28750 | ENG. IDBI BANK | 575265 | 2016-08-31 | 3750 | - | - | - | 25000 | 25000 | -
2016-09-19 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/9/647/2016-2017 | 4058 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-09-19 | 100% PAYMENT | 2016-09-19 | 0 | 0 | 0 | 7881.25 | 2 | 1418.63 | - | 0 | 0 | 0 | 40/58/COFG/KMM | J 4058 - SUPPLY OF M16 STUD WITH 2 NUTS & 2 WASHERS | 20 | 0 | 3152.5 | Numbers | - | 310101 | 63050 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO: 614276210)-SUPPLY OF STUD WITH 2 NUTS AND 2 WASHER, FULL THREADED SIZE: M16 X 150MM LONG | - | - | - | - | 2016-06-10 | 884168 | Y | - | - | (MATERIAL CODE NO: 614276210)-SUPPLY OF STUD WITH 2 NUTS AND 2 WASHER, FULL THREADED SIZE: M16 X 150MM LONGMOC: TiGr.2 AS PER PO | 902574 | 2016-09-19 | COURIER | FIRST FLIGHT | - | PACKED IN ONE CARTON BOX | - | - | 1617070124 | 2016-09-19 | 72349.88 | 991617000116 | 2016-09-19 | - | 0 | 0 | 20 | 72349.88 | ENG. IDBI BANK | 794555 | 2016-09-19 | 9299.88 | - | - | - | 3152.5 | 3152.5 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237775 | 4054 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2017-01-10 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 37950 | 2 | 6831 | - | 0 | 0 | 0 | 40/54/COVR/TOP | J 4054 - TOP COVER | 1012 | 0 | 300 | Numbers | - | 310101 | 303600 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | COVER TOP (BEL PART NO: 21258069017903) | - | - | - | - | 2016-06-09 | 997175 | Y | - | - | COVER TOP (BEL PART NO: 21258069017903)AS PER PO | 998575 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 5 CARTON BOXES | - | - | 1617070177 | 2017-01-10 | 348381 | 9.9162e+47 | 10-JAN-2017,10-JAN-2017,10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 1012 | 348381 | - | - | 2017-01-10 | - | - | - | - | 300 | 300 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237775 | 4054 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2017-01-10 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 37950 | 2 | 6831 | - | 0 | 0 | 0 | 40/54/COVR/BTM | J 4054 - BOTTOM COVER | 1012 | 0 | 300 | Numbers | - | 310101 | 303600 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | COVER BOTTOM ( BEL PART NO: 21257110017703) | - | - | - | - | 2016-06-09 | 997175 | Y | - | - | COVER BOTTOM ( BEL PART NO: 21257110017703)AS PER PO | 998575 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 5 CARTON BOXES | - | - | 1617070177 | 2017-01-10 | 348381 | 9.9162e+47 | 10-JAN-2017,10-JAN-2017,10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 1012 | 348381 | - | - | 2017-01-10 | - | - | - | - | 300 | 300 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237775 | 4054 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-23 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 65312.5 | 2 | 11756.25 | - | 0 | 0 | 0.25 | 40/54/BKTW/001 | J 4054 - BRACKET WELDED | 550 | 0 | 950 | Numbers | - | 310101 | 522500 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | BRACKET WELDED(BEL PART NO: 11200330699603) | - | - | - | - | 2016-06-09 | 997175 | Y | - | - | BRACKET WELDED(BEL PART NO: 11200330699603)AS PER PO | 998575 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 5 CARTON BOXES | - | - | 1617070177 | 2017-01-10 | 599569 | 9.9162e+47 | 10-JAN-2017,10-JAN-2017,10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 550 | 599569 | - | - | 2017-01-10 | - | - | - | - | 950 | 950 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237775 | 4054 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-23 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 12800 | 2 | 2304 | - | 0 | 0 | 0 | 40/54/EDSP/001 | J 4054 - END SUPPORT | 1024 | 0 | 100 | Numbers | - | 310101 | 102400 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | END SUPPORT WELDED (BEL PART NO:11200125680403) | - | - | - | - | 2016-06-09 | 997175 | Y | - | - | END SUPPORT WELDED (BEL PART NO:11200125680403)AS PER PO | 998575 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 5 CARTON BOXES | - | - | 1617070177 | 2017-01-10 | 117504 | 9.9162e+47 | 10-JAN-2017,10-JAN-2017,10-JAN-2017,10-JAN-2017 | - | 0 | 0 | 1024 | 117504 | - | - | 2017-01-10 | - | - | - | - | 100 | 100 | -
2016-08-11 | ENGG_EXPORT_EQUIPMENT | CLOSED | CCM CHEMICALS SDN BHD | 4099 | 4100106690 | 4036 | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | PASIR GUDANG WORKS(PGW1) PLOT 411, KAWASAN 4, JALAN PERAK 1, PASIR GUDANG INDUSTRIAL ESTATE, - | ENGG_PRICE_LIST | 2016-08-11 | 100% PAYMENT | 2016-08-11 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 40/36/PIFG/CCM | J 4036 TI GR.2 PIPE SPOOLS | 2 | 0 | 166075 | Numbers | - | 310451 | 332150 | ENGG_EXPORT_EQUIPMENT_LINE | CLOSED | TITANIUM GR.2 PIPE SPOOLS(OP) | - | - | - | - | 2016-03-07 | 843164 | Y | - | - | TITANIUM GR.2 PIPE SPOOLS(OP)AS PER PO | 866573 | 2016-08-11 | CHENNAI AIR CARGO | THRO PHOENIX TRANS LOGISTICS | TN 22 CX 1923 | PACKED IN ONE WOODEN BOX. GR WT: 181.5 KGS, NETT WT: 104.0 KGS | - | - | 1617080002 | 2016-08-11 | 332150 | - | 2016-08-11 | - | 0 | 0 | 2 | 332150 | ENG. IDBI BANK | CCM CHEMICALS | 2016-08-11 | 0 | - | - | - | 166075 | 166075 | -
2016-08-18 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2016-08-18 | 100% Advance | 2016-08-18 | 5 | 1838.25 | 0 | 4085 | 0 | 0 | - | 0 | 386 | -0.25 | MS/SS/SCRP/MIX | MS AND SS MIXED BORING SCRAP | 3040 | 0 | 10.75 | kilogram | - | 310701 | 32680 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S. AND S.S.MIXED BORING SCRAP | - | - | - | - | - | 852164 | Y | - | - | M.S. AND S.S.MIXED BORING SCRAP | 875573 | 2016-08-18 | - | TN 22 BF 8464 | - | - | - | - | 1617070115 | 2016-08-18 | 38989 | 991617000078 | 2016-08-18 | - | 0 | 0 | 3040 | 38989 | ENG. IDBI BANK | 971863 | 2016-08-18 | 6309 | - | - | - | 10.75 | 10.75 | -
2016-08-29 | ENGG_INTER_EQUIPMENT | CLOSED | GUJARAT ALKALIES AND CHEMICALS LIMITED | 4720 | MTL-P/20162017/633/2 | 4033 | P.O.PETROCHEMICALS-391346, DISTRICT VADODARA(GUJARAT), INDIA - | P.O.PETROCHEMICALS-391346, DISTRICT VADODARA(GUJARAT), INDIA - | ENGG_PRICE_LIST | 2016-08-29 | 4033GACLPT | 2016-08-29 | 0 | 0 | 0 | 190978.75 | 2 | 34376.18 | - | 0 | 0 | 0.07 | 40/33/HEFG/002 | J 4033 - TITANIUM HEAT EXCHANGER | 1 | 0 | 1527830 | Numbers | - | 310101 | 1527830 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (HE-2902)- WCS STRIPPER PRECONDENSER AS PER PO | - | - | - | - | 2016-04-02 | 863165 | Y | - | - | (HE-2902)- WCS STRIPPER PRECONDENSER AS PER PO | 885573 | 2016-08-29 | ASSOCIATED ROAD CARRIERS LTD | UP 70 AT 6220 | LR NO. M900042672 | LOOSE TWO EQUIPMENTS & SPARES PACKED IN ONE WOODEN BOX | - | - | 1617070118 | 2016-08-29 | 1753185 | 9.9162e+23 | 29-AUG-2016,29-AUG-2016 | - | 0 | 0 | 1 | 1753185 | ENG. IDBI BANK | 6.476e+23 | 2016-08-29 | -940213.5 | - | - | - | 1527830 | 1527830 | -
2016-08-29 | ENGG_INTER_EQUIPMENT | CLOSED | GUJARAT ALKALIES AND CHEMICALS LIMITED | 4720 | MTL-P/20162017/633/2 | 4033 | P.O.PETROCHEMICALS-391346, DISTRICT VADODARA(GUJARAT), INDIA - | P.O.PETROCHEMICALS-391346, DISTRICT VADODARA(GUJARAT), INDIA - | ENGG_PRICE_LIST | 2016-08-29 | 4033GACLPT | 2016-08-29 | 0 | 0 | 0 | 183104.38 | 2 | 32958.79 | - | 0 | 0 | -0.17 | 40/33/HEFG/GAC | 4033 TITANIUM HEAT EXCHANGER | 1 | 0 | 1464835 | Numbers | - | 310101 | 1464835 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (HE-2901)- WCS STRIPPER PREHEATER AS PER PO | - | - | - | - | 2016-04-02 | 863165 | Y | - | - | (HE-2901)- WCS STRIPPER PREHEATER AS PER PO | 885573 | 2016-08-29 | ASSOCIATED ROAD CARRIERS LTD | UP 70 AT 6220 | LR NO. M900042672 | LOOSE TWO EQUIPMENTS & SPARES PACKED IN ONE WOODEN BOX | - | - | 1617070118 | 2016-08-29 | 1680898 | 9.9162e+23 | 29-AUG-2016,29-AUG-2016 | - | 0 | 0 | 1 | 1680898 | ENG. IDBI BANK | 6.476e+23 | 2016-08-29 | -1012500.5 | - | - | - | 1464835 | 1464835 | -
2016-08-31 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/IBP/34/2016-2017, 02/04/2016 | 4042 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-08-31 | 30 DAYS CREDIT | 2016-08-31 | 0 | 0 | 0 | 50250 | 2 | 9045 | - | 0 | 0 | 0 | 40/42/LSFG/KMM | 4042 TITANIUM GR.2 LINED SCREW | 1 | 0 | 402000 | Numbers | - | 310101 | 402000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TITANIUM Gr 2 LINED SCREW FOR C-301 | - | - | - | - | - | 869164 | Y | - | - | SUPPLY OF TITANIUM Gr 2 LINED SCREW FOR C-301 | 890573 | 2016-08-31 | COURIER | TCI XPS | LR NO.329498562 | PACKED IN ONE WOODEN BOX | - | - | 1617070121 | 2016-08-31 | 461295 | 991617000091 | 2016-08-31 | - | 0 | 0 | 1 | 461295 | ENG. IDBI BANK | 795096 | 2016-08-31 | 59295 | - | - | - | 402000 | 402000 | -
2016-10-07 | ENGG_INTER_LABOUR | CLOSED | SAURASHTRA CHEMICALS | 2264 | M\8001096PO140900179 | 3934 | DIVISION OF NIRMA LIMITED BIRLA SAGAR - | DIVISION OF NIRMA LIMITED BIRLA SAGAR - | ENGG_PRICE_LIST | 2016-10-07 | 10%PO 90%INV | 2016-10-07 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 112000 | 0 | 0 | 39/34/LBFG/SAU | J 3934 - LABOUR CHARES FOR RETUBING | 1 | 0 | 800000 | Numbers | - | 310251 | 800000 | ENGG_INTER_LABOUR_LINE | CLOSED | (ITEM CODE: WMCHRPUN0366)- REPAIR OF HEAT EXCHANGER , REPLACEMENT OF TUBES IN HEAT EXCHANGER OF RGRH1 TEAM COOLER | - | - | - | - | 2016-09-10 | 899166 | Y | - | - | (ITEM CODE: WMCHRPUN0366)- REPAIR OF HEAT EXCHANGER , REPLACEMENT OF TUBES IN HEAT EXCHANGER OF RGRH1 TEAM COOLERAS PER PO | 914573 | 2016-10-07 | TCI FREIGHT | RJ 19 GD 6871 | LR NO.309387186 | ONE EQPT | - | - | 1617090015 | 2016-10-07 | 920000 | - | 2016-10-07 | - | 0 | 0 | 1 | 920000 | Engg-CA(472) - BOB/MYL1 | 013098 / 25-SEP-2014,600418 | 2016-10-07 | 120000 | - | - | - | 800000 | 800000 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEP0/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%PT30DAYS | 2016-11-09 | 0 | 0 | 0 | 7031.25 | 2 | 1265.63 | - | 0 | 0 | 0.43 | 40/57/IPFG/001 | J 4057 - INTERMEDIATE PLATE | 150 | 0 | 375 | Numbers | - | 310101 | 56250 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO: 21258519010603)- INTERMEDIATE PLATE | - | - | - | - | 2016-06-13 | 938167 | Y | - | - | (BEL PART NO: 21258519010603)- INTERMEDIATE PLATEAS PER PO | 941573 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246864 | PACKED IN ONE WOODEN BOX | - | - | 1617070146 | 2016-11-09 | 64547.31 | 9.9162e+35 | 09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 150 | 64547.31 | - | - | 2016-11-09 | - | - | - | - | 375 | 375 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEP0/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%PT30DAYS | 2016-11-09 | 0 | 0 | 0 | 23203.13 | 2 | 4176.56 | - | 0 | 0 | 0 | 40/57/TPFG/001 | J 4057 - TOP PLATE | 25 | 0 | 7425 | Numbers | - | 310101 | 185625 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO: 21258518011505)- TOP PLATE | - | - | - | - | 2016-06-13 | 938167 | Y | - | - | (BEL PART NO: 21258518011505)- TOP PLATEAS PER PO | 941573 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246864 | PACKED IN ONE WOODEN BOX | - | - | 1617070146 | 2016-11-09 | 213004.69 | 9.9162e+35 | 09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 25 | 213004.69 | - | - | 2016-11-09 | - | - | - | - | 7425 | 7425 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEP0/S20/4900237776 | 4057 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-11-08 | 100%PT30DAYS | 2016-11-09 | 0 | 0 | 0 | 11250 | 2 | 2025 | - | 0 | 0 | 0 | 40/57/BPFG/001 | J 4057 - BOTTOM PLATE | 25 | 0 | 3600 | Numbers | - | 310101 | 90000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO:21258517012408)- BOTTOM PLATE | - | - | - | - | 2016-06-13 | 938167 | Y | - | - | (BEL PART NO:21258517012408)- BOTTOM PLATEAS PER PO | 941573 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246864 | PACKED IN ONE WOODEN BOX | - | - | 1617070146 | 2016-11-09 | 103275 | 9.9162e+35 | 09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 25 | 103275 | - | - | 2016-11-09 | - | - | - | - | 3600 | 3600 | -
2016-11-16 | ENGG_LOCAL_SCRAP | CLOSED | AVM ENTERPRISES | 6340 | - | - | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | ENGG_PRICE_LIST | 2016-11-16 | 100% PAYMENT | 2016-11-16 | 5 | 3457.33 | 0 | 7682.95 | 0 | 0 | - | 0 | 726 | 0 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 4580 | 0 | 13.42 | kilogram | - | 310701 | 61463.6 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S.CUTBITS SCRAP | - | - | - | - | - | 945167 | Y | - | - | M.S.CUTBITS SCRAP | 946573 | 2016-11-16 | - | TN 65B 0617 | - | - | - | - | 1617070149 | 2016-11-16 | 73329.88 | 991617000199 | 2016-11-16 | - | 0 | 0 | 4580 | 73329.88 | ENG. IDBI BANK | AVM-SCRAP | 2016-11-16 | 11866.28 | - | - | - | 13.42 | 13.42 | -
2016-11-16 | ENGG_LOCAL_SCRAP | CLOSED | AVM ENTERPRISES | 6340 | - | - | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | ENGG_PRICE_LIST | 2016-11-16 | 100% PAYMENT | 2016-11-16 | 5 | 7745.02 | 0 | 17211.15 | 0 | 0 | - | 0 | 1626 | 0 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 10260 | 0 | 13.42 | kilogram | - | 310701 | 137689.2 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S.CUT BITS SCRAP | - | - | - | - | - | 945169 | Y | - | - | M.S.CUT BITS SCRAP | 946574 | 2016-11-16 | - | TN 85 8883 | - | - | - | - | 1617070150 | 2016-11-16 | 164271.37 | 991617000200 | 2016-11-16 | - | 0 | 0 | 10260 | 164271.37 | ENG. IDBI BANK | AVM-SCRAP | 2016-11-16 | 26582.17 | - | - | - | 13.42 | 13.42 | -
2016-10-13 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/ASD/293/2016-2017/1647 | 4044 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-10-13 | 100%RCPTACCEPT | 2016-10-13 | 0 | 0 | 0 | 4243.75 | 2 | 763.88 | - | 0 | 0 | 0 | 40/44/COFG/KMM | J 4044 - TI HEX BOLT & NUT | 25 | 0 | 1358 | SET | - | 310101 | 33950 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 292252168)- BOLT HEX TITANIUM 1/2" X 2" LONG WITH NUT | - | - | - | - | 2016-05-02 | 902167 | Y | - | - | (MATERIAL CODE: 292252168)- BOLT HEX TITANIUM 1/2" X 2" LONG WITH NUTAS PER PO | 918573 | 2016-10-13 | COURIER | PROFESSIONAL | - | PACKED IN ONE CARTON BOX | - | - | 1617070131 | 2016-10-13 | 38957.63 | 9.9162e+35 | 13-OCT-2016,13-OCT-2016,13-OCT-2016 | - | 0 | 0 | 25 | 38957.63 | ENG. IDBI BANK | 795197 | 2016-10-13 | -70652.37 | - | - | - | 1358 | 1358 | -
2016-10-13 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/ASD/293/2016-2017/1647 | 4044 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-10-13 | 100%RCPTACCEPT | 2016-10-13 | 0 | 0 | 0 | 6111 | 2 | 1099.98 | - | 0 | 0 | 0 | 40/44/COFG/002 | J 044- TI HEXAGONAL BOLT & NUT | 24 | 0 | 2037 | SET | - | 310101 | 48888 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 292252184)- BOLT HEX TITANIUM 5/8" X 21/2" LONG WITH NUT | - | - | - | - | 2016-05-02 | 902167 | Y | - | - | (MATERIAL CODE: 292252184)- BOLT HEX TITANIUM 5/8" X 21/2" LONG WITH NUTAS PER PO | 918573 | 2016-10-13 | COURIER | PROFESSIONAL | - | PACKED IN ONE CARTON BOX | - | - | 1617070131 | 2016-10-13 | 56098.98 | 9.9162e+35 | 13-OCT-2016,13-OCT-2016,13-OCT-2016 | - | 0 | 0 | 24 | 56098.98 | ENG. IDBI BANK | 795197 | 2016-10-13 | -53511.02 | - | - | - | 2037 | 2037 | -
2016-10-13 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/ASD/293/2016-2017/1647 | 4044 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-10-13 | 100%RCPTACCEPT | 2016-10-13 | 0 | 0 | 0 | 3346.5 | 2 | 602.37 | - | 0 | 0 | 0 | 40/44/COFG/001 | J 4044 - TI HEXAGONAL BOLT & NUT | 24 | 0 | 1115.5 | SET | - | 310101 | 26772 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 292252140)- BOLT HEX TITANIUM 3/8" X 11/2" LONG WITH NUT | - | - | - | - | 2016-05-02 | 902167 | Y | - | - | (MATERIAL CODE: 292252140)- BOLT HEX TITANIUM 3/8" X 11/2" LONG WITH NUTAS PER PO | 918573 | 2016-10-13 | COURIER | PROFESSIONAL | - | PACKED IN ONE CARTON BOX | - | - | 1617070131 | 2016-10-13 | 30720.87 | 9.9162e+35 | 13-OCT-2016,13-OCT-2016,13-OCT-2016 | - | 0 | 0 | 24 | 30720.87 | ENG. IDBI BANK | 795197 | 2016-10-13 | -78889.13 | - | - | - | 1115.5 | 1115.5 | -
2016-10-14 | ENGG_INTER_EQUIPMENT | CLOSED | INDIAN OIL CORPORATION LIMITED | 2867 | BSIVBR003/24804346 | 4026 | SR.PROJECT MANAGER BS IV PROJECT, PO BARAUNI REFINERY, - | SR.PROJECT MANAGER BS IV PROJECT, PO BARAUNI REFINERY, - | ENGG_PRICE_LIST | 2016-10-14 | 5%15%65%5%10% | 2016-10-14 | 0 | 0 | 0 | 1116275.63 | 2 | 200929.61 | - | 0 | 0 | -0.24 | 40/26/HEFG/IOC | J 4026 - SUPPLY OF LAS HEAT EXCHANGER | 1 | 0 | 8930205 | Numbers | - | 310101 | 8930205 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 2956010013)- LOW ALLOY STEEL HEAT EXCHANGER TAG NO: 702-E-51 A | - | - | - | - | 2016-07-06 | 905167 | Y | - | - | (MATERIAL CODE: 2956010013)- LOW ALLOY STEEL HEAT EXCHANGER TAG NO: 702-E-51 AAS PER PO | 920574 | 2016-10-14 | TCI FREIGHT | NL 01 D 7864 | LR NO: 309387304 | ONE EQUIPMENT AND ONE MS FRAME | - | - | 1617070134 | 2016-10-14 | 10247410 | 9.9162e+23 | 14-OCT-2016,14-OCT-2016 | - | 0 | 0 | 1 | 10247410 | - | - | 2016-10-14 | - | - | - | - | 8930205 | 8930205 | -
2016-10-27 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT DYNAMICS LIMITED | 1024 | 40701684 | 3905 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | ENGG_PRICE_LIST | 2016-10-27 | 100%PT30DAYS | 2016-10-27 | 0 | 0 | 0 | 18750 | 2 | 3375 | - | 0 | 0 | 0 | 39/05/ROFG/4TH | J 3905- Ti SHELL ROLLING | 10 | 0 | 15000 | Numbers | - | 310101 | 150000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO:540001000001)-SHELL ROLLING AS PER DRG. PD40-014 | - | - | - | - | 2014-03-05 | 924167 | Y | - | - | (MATERIAL CODE NO:540001000001)-SHELL ROLLING AS PER DRG. PD40-014AS PER PO | 932573 | 2016-10-27 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.120 | PACKED IN 12 CARTON BOXES. | - | - | 1617070141 | 2016-10-27 | 172125 | 991617000177 | 2016-10-27 | - | 0 | 0 | 10 | 172125 | - | - | 2016-10-27 | - | - | - | - | 15000 | 15000 | -
2016-08-22 | ENGG_INTER_EQUIPMENT | CLOSED | NAVAL PHYSICAL AND OCEANOGRAPHIC LABORATORY | 3398 | NPOL/17SO0040/UTS/GLF | 4025 | GOVERNMENT OF INDIA, MINISTRY OF DEFENCE, DEFENCE RESEARCH AND DEVELOPMENT ORGANISATION - | GOVERNMENT OF INDIA, MINISTRY OF DEFENCE, DEFENCE RESEARCH AND DEVELOPMENT ORGANISATION - | ENGG_PRICE_LIST | 2016-08-22 | NPOLPT4025 | 2016-08-22 | 0 | 0 | 0 | 0 | 14.5 | 348145 | - | 0 | 0 | 0 | 40/25/ASFG/NPO | 4025 OAS ARRAY STRUCTURE | 1 | 0 | 2401000 | Numbers | - | 310101 | 2401000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF OAS ARRAY STRUCTURE ASSEMBLY | - | - | - | - | 2016-05-27 | 855164 | Y | - | - | SUPPLY OF OAS ARRAY STRUCTURE ASSEMBLYAS PER PO | 878573 | 2016-08-22 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO. 113 | PACKED IN ONE WOODEN BOX | - | - | 1617070116 | 2016-08-22 | 2749145 | - | 2016-08-22 | - | 0 | 0 | 1 | 2749145 | ENG. IDBI BANK | NPOL | 2016-08-22 | 588245 | - | - | - | 2401000 | 2401000 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 14775 | 2 | 2659.5 | - | 0 | 0 | 0.5 | 40/52/COFG/TCL | J 4052 - SUPPLY OF SHAFT & O- RING | 1 | 0 | 118200 | Numbers | - | 310101 | 118200 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:108491290022)-SHAFT PART NO.6, REF NO. 863-04/13 | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE:108491290022)-SHAFT PART NO.6, REF NO. 863-04/13AS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 135635 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 1 | 135635 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | 635 | - | - | - | 118200 | 118200 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 450 | 2 | 81 | - | 0 | 0 | 0 | 40/52/COFG/006 | J 4052- SUPPLY OF O RINGS | 2 | 0 | 1800 | Numbers | - | 310101 | 3600 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:109050102106)- O RING FOR BRG.COVERS NO.3551 6000 MAT | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE:109050102106)- O RING FOR BRG.COVERS NO.3551 6000 MATAS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 4131 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 2 | 4131 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | -130869 | - | - | - | 1800 | 1800 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 300 | 2 | 54 | - | 0 | 0 | 0 | 40/52/COFG/005 | J 4052 - SUPPLY OF O RINGS | 2 | 0 | 1200 | Numbers | - | 310101 | 2400 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:109050102105)-SEAL O RING NO.3551 1500 MAT:VITON | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE:109050102105)-SEAL O RING NO.3551 1500 MAT:VITONAS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 2754 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 2 | 2754 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | -132246 | - | - | - | 1200 | 1200 | -
2016-11-08 | ENGG_INTER_EQUIPMENT | CLOSED | TATA CHEMICALS LMITED | 1043 | 4210054711 | 4052 | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | Mithapur - 361 345 Okhamandal, jamnagar State-Postal Code | ENGG_PRICE_LIST | 2016-11-08 | 100% Advance | 2016-11-09 | 0 | 0 | 0 | 450 | 2 | 81 | - | 0 | 0 | 0 | 40/52/COFG/004 | J 4052 - SUPPLY OD O RINGS | 2 | 0 | 1800 | Numbers | - | 310101 | 3600 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE:109050102104)-COVER O RING NO.5301 8000 MAT:VITON | - | - | - | - | 2016-06-07 | 938169 | Y | - | - | (MATERIAL CODE:109050102104)-COVER O RING NO.5301 8000 MAT:VITONAS PER PO | 941574 | 2016-11-08 | COURIER | TCI XPS | LR NO.329246875 | PACKED IN ONE WOODEN BOX. | - | - | 1617070147 | 2016-11-09 | 4131 | 9.9162e+83 | 09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016,09-NOV-2016 | - | 0 | 0 | 2 | 4131 | Engg-CA(472) - BOB/MYL1 | TATA CHEMICALS | 2016-11-09 | -130869 | - | - | - | 1800 | 1800 | -
2016-09-08 | ENGG_LOCAL_LABOUR | CLOSED | TAMILNADU NEWSPRINTAND PAPERS LIMITED | 4500 | FAC-PRO-TOS/161715003812 | 4082 | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | ENGG_PRICE_LIST | - | 4082PTTNPL | 2016-09-08 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 3360 | 0 | 0 | LS/AT/SIT1/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 2 | 0 | 12000 | Numbers | - | 310251 | 24000 | ENGG_LOCAL_PURE_LABOUR_LINE | CLOSED | FABRICATION AND ERECTION OF TITANIUM PIPES & FITTINGS- FITTER(TNPL CODE: 8351100045) | - | - | - | - | 2016-07-28 | - | N | - | - | FABRICATION AND ERECTION OF TITANIUM PIPES & FITTINGS- FITTER(TNPL CODE: 8351100045)AS PER PO | - | - | - | - | - | - | - | - | 1617090011 | 2016-09-08 | 27600 | - | 12-SEP-2016,12-SEP-2016 | - | 0 | 0 | 2 | 27600 | ENG. IDBI BANK | tnpl | 2016-09-08 | -20400 | - | - | - | - | 12000 | -
2016-09-13 | ENGG_INTER_LABOUR | CLOSED | MCC PTA INDIA CORP PVT LTD | 1033 | WO-M-10046109 | 4076 | Viii & p.o - bhuniaraichak, Via sutahata,haldia, Kolkata-721635 | Viii & p.o - bhuniaraichak, Via sutahata,haldia, Kolkata-721635 | ENGG_PRICE_LIST | - | 4076PTMCCPTA | 2016-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 58275.8 | 0 | -0.06 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 416255.7 | LOT | - | 310251 | 416255.7 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | ANNUAL RATE CONTRACT FOR VARIOUS TITANIUM TUBE TO TUBESHEET WORK AT MCPI PLANT SITE | - | - | - | - | 2015-11-20 | - | N | - | - | ANNUAL RATE CONTRACT FOR VARIOUS TITANIUM TUBE TO TUBESHEET WORK AT MCPI PLANT SITEAS PER PO | - | - | - | - | - | - | - | - | 1617090012 | 2016-09-13 | 478694 | - | 2016-09-13 | - | 0 | 0 | 1 | 478694 | - | - | 2016-09-13 | - | - | - | - | - | 416255.7 | -
2016-06-04 | ENGG_LOCAL_LABOUR | CLOSED | TAMILNADU NEWSPRINTAND PAPERS LIMITED | 4500 | FAC-PRO-TOS/151615009139 | 4027 | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | ENGG_PRICE_LIST | 2016-06-04 | 100% PAYMENT | 2016-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 13920 | 0 | 0 | LS/AT/SIT1/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 8 | 0 | 12000 | Numbers | - | 310251 | 96000 | ENGG_LOCAL_PURE_LABOUR_LINE | CLOSED | (TNPL CODE- 8351100045)- FABRICATION AND ERECTION OF TITANIUM PIPES & FITTINGS- FITTER AT SITE | - | - | - | - | 2016-02-06 | - | N | - | - | (TNPL CODE- 8351100045)- FABRICATION AND ERECTION OF TITANIUM PIPES & FITTINGS- FITTER AT SITEAS PER PO | - | - | - | - | - | - | - | - | 1617090004 | 2016-06-04 | 110400 | - | 04-JUN-2016,04-JUN-2016 | - | 0 | 0 | 8 | 110400 | ENG. IDBI BANK | TNPC | 2016-06-04 | -77252.17 | - | - | - | 12000 | 12000 | -
2016-09-08 | ENGG_LOCAL_LABOUR | CLOSED | TAMILNADU NEWSPRINTAND PAPERS LIMITED | 4500 | FAC-PRO-TOS/161715003812 | 4082 | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | ENGG_PRICE_LIST | - | 4082PTTNPL | 2016-09-08 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 3360 | 0 | 0 | LS/AT/SIT1/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 2 | 0 | 12000 | Numbers | - | 310251 | 24000 | ENGG_LOCAL_PURE_LABOUR_LINE | CLOSED | FABRICATION AND ERECTION OF TITANIUM PIPES & FITTINGS-WELDER (TNPL CODE: 8351100046) | - | - | - | - | 2016-07-28 | - | N | - | - | FABRICATION AND ERECTION OF TITANIUM PIPES & FITTINGS-WELDER (TNPL CODE: 8351100046)AS PER PO | - | - | - | - | - | - | - | - | 1617090011 | 2016-09-08 | 27600 | - | 12-SEP-2016,12-SEP-2016 | - | 0 | 0 | 2 | 27600 | ENG. IDBI BANK | tnpl | 2016-09-08 | -20400 | - | - | - | - | 12000 | -
2016-08-11 | ENGG_INTER_LABOUR | CLOSED | MULTIMAX ENGINEERING WORKS PVT LTD | 3965 | JOB ORDER NO:MM/JOB/16-17/G-95/632/1870 | 4087 | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | ENGG_PRICE_LIST | - | MULTIMAXPT4087 | 2016-08-11 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 3822 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 27300 | Numbers | - | 310251 | 27300 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | (JOB NO:632/2)- TUBE BUNDLE REPAIR FOR HEAT EXCHANGER #E14969 ALONG WITH REIMBURSEMENT OF | - | - | - | - | 2016-07-02 | - | N | - | - | (JOB NO:632/2)- TUBE BUNDLE REPAIR FOR HEAT EXCHANGER #E14969 ALONG WITH REIMBURSEMENT OFINCIDENTAL EXPENSES | - | - | - | - | - | - | - | - | 1617090007 | 2016-08-11 | 31395 | - | 2016-08-11 | - | 0 | 0 | 1 | 31395 | - | - | 2016-08-11 | - | - | - | - | - | 27300 | -
2016-06-04 | ENGG_LOCAL_LABOUR | CLOSED | TAMILNADU NEWSPRINTAND PAPERS LIMITED | 4500 | FAC-PRO-TOS/151615009139 | 4027 | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | KAGITHAPURAM-639136, KARUR DISTRICT, TAMILNADU, INDIA - | ENGG_PRICE_LIST | 2015-03-27 | 100% PAYMENT | 2016-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 13920 | 0 | 0 | LS/AT/SIT2/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 8 | 0 | 12000 | Numbers | - | 310251 | 96000 | ENGG_LOCAL_PURE_LABOUR_LINE | CLOSED | (TNPL CODE- 8351100046)- FABRICATION AND ERECTION OF TITANIUM PIPES AND FITTINGS-WELDER AT SITE | - | - | - | - | 2016-02-06 | - | N | - | - | (TNPL CODE- 8351100046)- FABRICATION AND ERECTION OF TITANIUM PIPES AND FITTINGS-WELDER AT SITEAS PER PO | - | - | - | - | - | - | - | - | 1617090004 | 2016-06-04 | 110400 | - | 04-JUN-2016,04-JUN-2016 | - | 0 | 0 | 8 | 110400 | ENG. IDBI BANK | TNPC | 2016-06-04 | -77252.17 | - | - | - | 200000 | 12000 | -
2016-12-23 | ENGG_INTER_LABOUR | CLOSED | MATERIALS CHEMICALS AND PERFORMANCE INTERMEDIARIES PRIVATE LIMITED | 6260 | WO-M-10046109 | 4115 | VILLAGE & P.O BHUNIARAICHAK, VIA: SUTAHATA(HALDIA), PURBA MIDNAPORE, - | VILLAGE & P.O BHUNIARAICHAK, VIA: SUTAHATA(HALDIA), PURBA MIDNAPORE, - | ENGG_PRICE_LIST | - | 100%PAYMENTINV | 2016-12-23 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 80591 | 0 | 0.5 | LS/AT/SIT1/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 575650 | LOT | - | 310251 | 575650 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | ANNUAL RATE CONTRACT FOR 2S-1411D N7 nozole/crack repar( Titanium) | - | - | - | - | 2015-11-02 | - | N | - | - | ANNUAL RATE CONTRACT FOR 2S-1411D N7 nozole/crack repar( Titanium)AS PER PO | - | - | - | - | - | - | - | - | 1617090025 | 2016-12-23 | 661998 | - | 2016-12-23 | - | 0 | 0 | 1 | 661998 | - | - | 2016-12-23 | - | - | - | - | - | 575650 | -
2016-07-08 | ENGG_INTER_LABOUR | CLOSED | TEAMEC CHLORATES LIMITED | 1044 | WO NO: TM/16-17/0012 | 4048 | PLOT NO. 558 & 559,APIIC GROWTH CENTRE GUNDLAPALLI VILLAGE ANDHRA PRADESH-523211 | PLOT NO. 558 & 559,APIIC GROWTH CENTRE GUNDLAPALLI VILLAGE ANDHRA PRADESH-523211 | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-07-08 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 15500.5 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 106900 | LOT | - | 310251 | 106900 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | DEPUTATION OF MANPOWER FOR CARRYING OUT REPAIR WORKS ON CRYSTALLIZER BODY AND NOZZLE AT ONGOLE FACTORY | - | - | - | - | 2016-06-01 | - | N | - | - | DEPUTATION OF MANPOWER FOR CARRYING OUT REPAIR WORKS ON CRYSTALLIZER BODY AND NOZZLE AT ONGOLE FACTORYAS PER PO | - | - | - | - | - | - | - | - | 1617090006 | 2016-07-08 | 122935 | - | 2016-07-08 | - | 0 | 0 | 1 | 122935 | - | - | 2016-07-08 | - | - | - | - | - | 106900 | -
2016-10-20 | ENGG_EXPORT_EQUIPMENT | CLOSED | M/S. SEA HORSE SERVICES SDN.BHD | 5540 | SHS/PO/07/2016/1043 | 4080 | NO. 82, JALAN S2C2, GREEN TECHNOLOGY PARK, SEREMBAN 2, 70300 SEREMBAN, NEGERI SEMBILAN - | NO. 82, JALAN S2C2, GREEN TECHNOLOGY PARK, SEREMBAN 2, 70300 SEREMBAN, NEGERI SEMBILAN - | ENGG_PRICE_LIST | 2016-10-20 | 30%ADV70%DESP | 2016-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 40/80/ECFG/SHS | J 4080 - ELECTROFLUCULATION SYSTEM | 1 | 0 | 213232 | Numbers | - | 310451 | 213232 | ENGG_EXPORT_EQUIPMENT_LINE | CLOSED | ELECTROFLUCULATION SYSTEM HAVING AN INSTALLED CAPACITY OF 100 LITRES PER HOUR WITH A GENERATION OF 15 GRAMS/HR HYDROXYL IONS | - | - | - | - | 2016-07-09 | 911167 | Y | - | - | ELECTROFLUCULATION SYSTEM HAVING AN INSTALLED CAPACITY OF 100 LITRES PER HOUR WITH A GENERATION OF 15 GRAMS/HR HYDROXYL IONSAS PER PO | 922573 | 2016-10-20 | CHENNAI-SEA | TN 05 AP 9920 | THRO FLYCON LOGISTICS | PACKED IN ONE WOODEN BOX.GR WT: 164 KGS, TARE WT: 85.0 KGS, NET WT: 79.0 KGS.ENCLOSED A.R.E.1 FORM | - | - | 1617080003 | 2016-10-20 | 213232 | - | 2016-10-20 | - | 0 | 0 | 1 | 213232 | ENG. IDBI BANK | SEA HORSE,SEA HORSE,SEA HORSE | 2016-10-20 | 0 | - | - | - | 213232 | 213232 | -
2016-10-27 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/45/1021/2016-2017 | 4079 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-10-27 | 100%PT30DAYS | 2016-10-27 | 0 | 0 | 0 | 36375 | 2 | 6547.5 | - | 0 | 0 | 0 | 40/79/COFG/KML | J 4079 - Ti Gr 7 EQUEEL TEE | 3 | 0 | 97000 | Numbers | - | 310101 | 291000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO: 614276760)- SUPPLY OF 100 NB TITANIUM GR.7 EQUAL TEE MATERIAL OF CONSTRUCTION: FALNGE SA105 WITH TIGR.7 LINING | - | - | - | - | 2016-07-19 | 923169 | Y | - | - | (MATERIAL CODE NO: 614276760)- SUPPLY OF 100 NB TITANIUM GR.7 EQUAL TEE MATERIAL OF CONSTRUCTION: FALNGE SA105 WITH TIGR.7 LININGAS PER DRG. TP/MR/IBP/DIG-T/REV0 MATERIAL TEST CERTIFICATE FOR TITANIUM GR7 SHOULD BE SUBMITTED ALONG WITH THE SUPPLY | 931574 | 2016-10-27 | COURIER | TCI XPS | LR NO.329246842 | PACKED IN ONE WOODEN BOX. GR WT: 80 KGS | - | - | 1617070139 | 2016-10-27 | 333922.5 | 991617000175 | 2016-10-27 | - | 0 | 0 | 3 | 333922.5 | ENG. IDBI BANK | 795405 | 2016-10-27 | 42922.5 | - | - | - | 97000 | 97000 | -
2016-12-07 | ENGG_LOCAL_RECOATING | CLOSED | TAMILNADU PETROPRODUCTS LTD | 3598 | ME/4900069424 | 4104 | MANALI EXPRESS HIGHWAY, MANALI, CHENNAI-600068 - | MANALI EXPRESS HIGHWAY, MANALI, CHENNAI-600068 - | ENGG_PRICE_LIST | 2016-12-07 | 100% PAYMENT | 2016-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 110600 | 0 | 0 | 41/04/COFG/TPL | J4104 RECOATING OF ANODE | 1 | 0 | 790000 | Numbers | - | 310252 | 790000 | ENGG_LOCAL_RECOATING_LINE | CLOSED | ER-216 ANODE ELEMENT REPAIR AND RECOATING | - | - | - | - | 2016-10-18 | 966175 | Y | - | - | ER-216 ANODE ELEMENT REPAIR AND RECOATINGAS PER PO | 966575 | 2016-12-07 | - | TN 09 AH 4647 | - | PACKED IN ONE WOODEN BOX | - | - | 1617090023 | 2016-12-07 | 908500 | - | 2016-12-07 | - | 0 | 0 | 1 | 908500 | - | - | 2016-12-07 | - | - | - | - | 790000 | 790000 | -
2016-12-08 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/64/25/782/2016-2017 | 4063 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 30 DAYS CREDIT | 2016-12-08 | 0 | 0 | 0 | 58375 | 2 | 10507.5 | - | 0 | 0 | 0 | 40/63/COFG/KMM | J 4063 - TIE ROD & SPACER | 28 | 0 | 16678.57 | Numbers | - | 310101 | 466999.96 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | TIE ROD MATERIAL:TITANIUM GR.7 | - | - | - | - | - | 968173 | Y | - | - | TIE ROD MATERIAL:TITANIUM GR.7 | 968575 | 2016-12-08 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.131 | MATL KEPT IN VIDE DC NO.968576 MATL WOODEN BOX.GR.WT: 62 KGS. SIZE: 750 L X 510 W X 280MM H | - | - | 1617070162 | 2016-12-08 | 535882.46 | 9.9162e+23 | 08-DEC-2016,08-DEC-2016 | - | 0 | 0 | 28 | 535882.46 | - | - | 2016-12-08 | - | - | - | - | 16678.57 | 16678.57 | -
2016-12-08 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/64/25/782/2016-2017 | 4063 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 30 DAYS CREDIT | 2016-12-08 | 0 | 0 | 0 | 45000 | 2 | 8100 | - | 0 | 0 | 0 | 40/63/COFG/001 | J 4063- SUPPLY OF TUBES | 128 | 0 | 2812.5 | Numbers | - | 310101 | 360000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPORT TUBE MATERIAL: TITANIUM-GR-7 | - | - | - | - | - | 968173 | Y | - | - | SUPPORT TUBE MATERIAL: TITANIUM-GR-7 | 968575 | 2016-12-08 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.131 | MATL KEPT IN VIDE DC NO.968576 MATL WOODEN BOX.GR.WT: 62 KGS. SIZE: 750 L X 510 W X 280MM H | - | - | 1617070162 | 2016-12-08 | 413100 | 9.9162e+23 | 08-DEC-2016,08-DEC-2016 | - | 0 | 0 | 128 | 413100 | - | - | 2016-12-08 | - | - | - | - | 2812.5 | 2812.5 | -
2016-08-30 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/181/2016-2017/154/ | 4043 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-08-30 | 100% PAYMENT | 2016-08-31 | 0 | 0 | 0 | 2250 | 2 | 405 | - | 0 | 0 | 0 | 40/43/COFG/003 | 4043 SUPPLY OF TI WASHER FLAT ROUND | 100 | 0 | 180 | Numbers | - | 310101 | 18000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | WASHER TITANIUM FLAT ROUND 1/2" (MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY) | - | - | - | - | 2016-04-25 | 866164 | Y | - | - | WASHER TITANIUM FLAT ROUND 1/2" (MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY)AS PER PO | 887573 | 2016-08-30 | COURIER | TCI XPS | LR NO. 329498562 | PACKED IN ONE CARTON BOX KEPT IN SCREW CONVEYOR WOODEN BOX | - | - | 1617070120 | 2016-08-31 | 20655 | 9.9162e+35 | 31-AUG-2016,31-AUG-2016,31-AUG-2016 | - | 0 | 0 | 100 | 20655 | ENG. IDBI BANK | 795096 | 2016-08-31 | -78345 | - | - | - | 180 | 180 | -
2016-08-30 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/181/2016-2017/154/ | 4043 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-08-30 | 100% PAYMENT | 2016-08-31 | 0 | 0 | 0 | 2625 | 2 | 472.5 | - | 0 | 0 | 0 | 40/43/COFG/002 | 4043 SUPPLY OF TI HEXAGONAL NUT | 50 | 0 | 420 | Numbers | - | 310101 | 21000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | NUT HEX. TITANIUM 1/2" (MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY) | - | - | - | - | 2016-04-25 | 866164 | Y | - | - | NUT HEX. TITANIUM 1/2" (MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY)AS PER PO | 887573 | 2016-08-30 | COURIER | TCI XPS | LR NO. 329498562 | PACKED IN ONE CARTON BOX KEPT IN SCREW CONVEYOR WOODEN BOX | - | - | 1617070120 | 2016-08-31 | 24097.5 | 9.9162e+35 | 31-AUG-2016,31-AUG-2016,31-AUG-2016 | - | 0 | 0 | 50 | 24097.5 | ENG. IDBI BANK | 795096 | 2016-08-31 | -74902.5 | - | - | - | 420 | 420 | -
2016-08-30 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/181/2016-2017/154/ | 4043 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-08-30 | 100% PAYMENT | 2016-08-31 | 0 | 0 | 0 | 7500 | 2 | 1350 | - | 0 | 0 | 0 | 40/43/COFG/KML | J 4043 - SUPPLY OF TI HEXAGONAL BOLT | 50 | 0 | 1200 | Numbers | - | 310101 | 60000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | BOLT HEX.TITANIUM FULL THREADED 1/2" X 3" (MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY) | - | - | - | - | 2016-04-25 | 866164 | Y | - | - | BOLT HEX.TITANIUM FULL THREADED 1/2" X 3" (MATERIAL TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH SUPPLY)AS PER PO | 887573 | 2016-08-30 | COURIER | TCI XPS | LR NO. 329498562 | PACKED IN ONE CARTON BOX KEPT IN SCREW CONVEYOR WOODEN BOX | - | - | 1617070120 | 2016-08-31 | 68850 | 9.9162e+35 | 31-AUG-2016,31-AUG-2016,31-AUG-2016 | - | 0 | 0 | 50 | 68850 | ENG. IDBI BANK | 795096 | 2016-08-31 | -30150 | - | - | - | 1200 | 1200 | -
2016-09-07 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | - | 100% Advance | 2016-09-07 | 5 | 188.6 | 0 | 0 | 0 | 0 | - | 0 | 40 | 0.4 | WS/MA/SCRP/LOT | WASTE SCRAP MATERIAL WITH LOT UOM | 1 | 0 | 3772 | LOT | - | 310701 | 3772 | ENGG_LOCAL_SCRAP_LINE | CLOSED | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD , PLASTIC ITEMS | - | - | - | - | - | 873164 | Y | - | - | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD , PLASTIC ITEMS | 892573 | 2016-09-07 | - | TAY 5767 | - | - | - | - | 1617070122 | 2016-09-07 | 4001 | - | 2016-09-07 | - | 0 | 0 | 1 | 4001 | ENG. IDBI BANK | 971863 | 2016-09-07 | 229 | - | - | - | 3772 | 3772 | -
2016-11-04 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2014-05-31 | 100% Advance | 2016-11-04 | 5 | 188.6 | 0 | 0 | 0 | 0 | - | 0 | 40 | 0.4 | WS/PC/SCRP/WST | WASTE SCRAP CONSIST OF PAPER, DAMAGED CARTON BOX PLASTIC ITEM | 1 | 0 | 3772 | Numbers | - | 310701 | 3772 | ENGG_LOCAL_SCRAP_LINE | CLOSED | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD PLASTIC ITEMS | - | - | - | - | - | 933167 | Y | - | - | WASTE SCRAP CONSIST OF PAPER DAMAGED WOOD PLASTIC ITEMS | 938573 | 2016-11-04 | - | TN 28 F 6933 | - | - | - | - | 1617070143 | 2016-11-04 | 4001 | - | 2016-11-04 | - | 0 | 0 | 1 | 4001 | ENG. IDBI BANK | 970531971863 | 2016-11-04 | 229 | - | - | - | 3772 | 3772 | -
2016-11-25 | ENGG_INTER_LABOUR | CLOSED | DEFENCE RESEARCH AND DEVELOPMENT LABORATORY | 2345 | DRDL/24/55P/15/0297/42445 | 4037 | GOVERNMENT OF INDIA MISNISTRY OF DEFENCE, KANCHANBAGH P.O,HYDERABAD-500058 - | GOVERNMENT OF INDIA MISNISTRY OF DEFENCE, KANCHANBAGH P.O,HYDERABAD-500058 - | ENGG_PRICE_LIST | 2016-11-25 | 100% PAYMENT | 2016-11-25 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 481600 | 0 | 0 | 40/37/ABFG/HEL | J 4037 - TITANIUM AIR BOTTLE | 20 | 0 | 172000 | Numbers | - | 310251 | 3440000 | ENGG_INTER_LABOUR_LINE | CLOSED | FABRICATION AND TESTING OF TITANIUM ALLOY CYLINDRICAL AIR BOTTLE FOR MISSILE COOLING | - | - | - | - | 2016-04-19 | 955168 | Y | - | - | FABRICATION AND TESTING OF TITANIUM ALLOY CYLINDRICAL AIR BOTTLE FOR MISSILE COOLINGSYSTEM AS PER PO | 954573 | 2016-11-25 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.127 | PACKED IN 6 WOODEN BOXES AND ONE CARTON BOX. PARTY'S MATERIAL RECD VIDE PASS NO.12597 AND BOOK NO.126 DT.19-05-2016 AND BEING RETURNED BACK TO PARTY. | - | - | 1617090019 | 2016-11-25 | 3956000 | - | 2016-11-25 | - | 0 | 0 | 20 | 3956000 | - | - | 2016-11-25 | - | - | - | - | 172000 | 172000 | -
2017-01-10 | ENGG_INTER_EQUIPMENT | BOOKED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237774 | 4053 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-23 | 100%30DAYS | 2017-01-11 | 0 | 0 | 0 | 215625 | 2 | 38812.5 | - | 0 | 0 | 0.5 | 40/53/BSPL/001 | J 4053 - BASE PLATE | 600 | 0 | 2875 | Numbers | - | 310101 | 1725000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | BASE PLATE (BEL PART NO: 21258714019403) | - | - | - | - | 2016-06-09 | 996175 | Y | - | - | BASE PLATE (BEL PART NO: 21258714019403)AS PER PO | 997575 | 2017-01-10 | SRI LAKSHMI TRANSPORT | TN 11 T 3975 | LR NO.133 | PACKED IN 6 WOODEN BOXES | - | - | 1617070175 | 2017-01-10 | 1979438 | 991617000274 | 2017-01-10 | - | 0 | 0 | 600 | 1979438 | - | - | 2017-01-10 | - | - | - | - | 2875 | 2875 | -
2017-01-17 | ENGG_INTER_EQUIPMENT | BOOKED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/51/1012/2016-2017 | 4084 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 100%30DAYS | 2017-01-18 | 0 | 0 | 0 | 68750 | 2 | 12375 | - | 0 | 0 | 0 | 40/84/COFG/KMM | J 4084 - SUPPLY OF HYDROCYCLONE | 1 | 0 | 550000 | Numbers | - | 310101 | 550000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO: 616001001)- HYDROCYCLONE O-401 | - | - | - | - | 2016-07-19 | 1002175 | Y | - | - | (MATERIAL CODE NO: 616001001)- HYDROCYCLONE O-401AS PER PO | 1002575 | 2017-01-17 | COURIER | TCI XPS | LR NO.329732292 | PACKED IN ONE WOODEN BOX | - | - | 1617070179 | 2017-01-18 | 631125 | 991617000288 | 2017-01-18 | - | 0 | 0 | 1 | 631125 | - | - | 2017-01-18 | - | - | - | - | 550000 | 550000 | -
2016-08-11 | ENGG_LOCAL_SCRAP | CLOSED | N.S.N.STEELS | 1048 | - | - | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | #30/6, anna street, T.m.p.nagar, Tamil nadu-600057 | ENGG_PRICE_LIST | 2015-12-17 | 100% Advance | 2016-08-11 | 5 | 6226.59 | 0 | 13836.88 | 0 | 0 | - | 0 | 1308 | -0.47 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 8450 | 0 | 13.1 | kilogram | - | 310701 | 110695 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S.CUTBITS SCRAP | - | - | - | - | - | 845167 | Y | - | - | M.S.CUTBITS SCRAP | 869573 | 2016-08-11 | - | TN 18 M 1773 | - | - | - | - | 1617070112 | 2016-08-11 | 132066 | 991617000069 | 2016-08-11 | - | 0 | 0 | 8450 | 132066 | ENG. IDBI BANK | 971848 | 2016-08-11 | 21371 | - | - | - | 13.1 | 13.1 | -
2016-09-09 | ENGG_LOCAL_EQUIPMENT | CLOSED | ARJATI FOUNDATION | 5780 | 001/2016-2017 | 4092 | 9, BHASKARAPURAM, CHENNAI-600004 - | 9, BHASKARAPURAM, CHENNAI-600004 - | ENGG_PRICE_LIST | 2016-09-09 | 4092PTARJ | 2016-09-09 | 5 | 843.75 | 0 | 1875 | 0 | 0 | - | 0 | 0 | 0.25 | 40/92/COFG/ARJ | J 4092 - SUPPLY OF TI GR 2 ANODES | 10 | 0 | 1500 | Numbers | - | 310201 | 15000 | ENGG_LOCAL_EQUIPMENT_LINE | CLOSED | SUPPLY OF ANODES | - | - | - | - | 2016-08-23 | 878165 | Y | - | - | SUPPLY OF ANODESAS PER PO | 896573 | 2016-09-09 | HAND CARRY | - | - | PACKED IN TWO CARTON BOX | - | - | 1617070123 | 2016-09-09 | 17719 | 991617000107 | 2016-09-09 | - | 0 | 0 | 10 | 17719 | ENG. IDBI BANK | STATEMENT | 2016-09-09 | 2719 | - | - | - | 1500 | 1500 | -
2016-09-17 | ENGG_INTER_EQUIPMENT | CLOSED | ISGEC HEAVY ENGINEERING LIMITED | 5200 | C04/4500182631 | 4055 | RADAUR ROAD, YAMUNANAGAR-135001, HARYANA - | RADAUR ROAD, YAMUNANAGAR-135001, HARYANA - | ENGG_PRICE_LIST | 2016-09-17 | 100% PAYMENT | 2016-09-17 | 0 | 0 | 0 | 6562.5 | 2 | 1181.25 | - | 0 | 0 | 0 | 40/55/COFG/ISG | J- SUPPLY OF TI SLEEVE | 3 | 0 | 17500 | Numbers | - | 310101 | 52500 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: CF012377TS2)- TITANIUM SLEEVE(MK-47) FOR TOP COVER(N5) | - | - | - | - | 2016-06-10 | 883168 | Y | - | - | (MATERIAL CODE: CF012377TS2)- TITANIUM SLEEVE(MK-47) FOR TOP COVER(N5)AS PER PO | 901574 | 2016-09-17 | COURIER | TCI XPS | LR NO. 329498595 | PACKED IN TWO GUNNY BUNDLES | - | - | 1617070125 | 2016-09-26 | 60243.75 | 9.9162e+35 | 26-SEP-2016,26-SEP-2016,26-SEP-2016 | - | 0 | 0 | 3 | 60243.75 | ENG. IDBI BANK | 134670 | 2016-09-26 | -140756.25 | - | - | - | 16000 | 17500 | -
2016-09-17 | ENGG_INTER_EQUIPMENT | CLOSED | ISGEC HEAVY ENGINEERING LIMITED | 5200 | C04/4500182631 | 4055 | RADAUR ROAD, YAMUNANAGAR-135001, HARYANA - | RADAUR ROAD, YAMUNANAGAR-135001, HARYANA - | ENGG_PRICE_LIST | 2016-09-17 | 100% PAYMENT | 2016-09-17 | 0 | 0 | 0 | 12562.5 | 2 | 2261.25 | - | 0 | 0 | 0 | 40/55/COFG/ISG | J- SUPPLY OF TI SLEEVE | 3 | 0 | 33500 | Numbers | - | 310101 | 100500 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: CF012377TS1)- TITANIUM SLEEVE(MK-46) FOR TOP COVER(N1) | - | - | - | - | 2016-06-10 | 883168 | Y | - | - | (MATERIAL CODE: CF012377TS1)- TITANIUM SLEEVE(MK-46) FOR TOP COVER(N1)AS PER PO | 901574 | 2016-09-17 | COURIER | TCI XPS | LR NO. 329498595 | PACKED IN TWO GUNNY BUNDLES | - | - | 1617070125 | 2016-09-26 | 115323.75 | 9.9162e+35 | 26-SEP-2016,26-SEP-2016,26-SEP-2016 | - | 0 | 0 | 3 | 115323.75 | ENG. IDBI BANK | 134670 | 2016-09-26 | -85676.25 | - | - | - | 16000 | 33500 | -
2016-09-17 | ENGG_INTER_EQUIPMENT | CLOSED | ISGEC HEAVY ENGINEERING LIMITED | 5200 | C04/4500182631 | 4055 | RADAUR ROAD, YAMUNANAGAR-135001, HARYANA - | RADAUR ROAD, YAMUNANAGAR-135001, HARYANA - | ENGG_PRICE_LIST | 2016-09-17 | 100% PAYMENT | 2016-09-17 | 0 | 0 | 0 | 6000 | 2 | 1080 | - | 0 | 0 | 0 | 40/55/COFG/ISG | J- SUPPLY OF TI SLEEVE | 3 | 0 | 16000 | Numbers | - | 310101 | 48000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: CF012377TS)- TITANIUM SLEEVE(MK-45) FOR TOP COVER(N6) | - | - | - | - | 2016-06-10 | 883168 | Y | - | - | (MATERIAL CODE: CF012377TS)- TITANIUM SLEEVE(MK-45) FOR TOP COVER(N6)AS PER PO | 901574 | 2016-09-17 | COURIER | TCI XPS | LR NO. 329498595 | PACKED IN TWO GUNNY BUNDLES | - | - | 1617070125 | 2016-09-26 | 55080 | 9.9162e+35 | 26-SEP-2016,26-SEP-2016,26-SEP-2016 | - | 0 | 0 | 3 | 55080 | ENG. IDBI BANK | 134670 | 2016-09-26 | -145920 | - | - | - | 16000 | 16000 | -
2016-10-07 | ENGG_INTER_EQUIPMENT | CLOSED | SAURASHTRA CHEMICALS | 2264 | M\8001096PO140900180 | 3935 | DIVISION OF NIRMA LIMITED BIRLA SAGAR - | DIVISION OF NIRMA LIMITED BIRLA SAGAR - | ENGG_PRICE_LIST | 2016-10-07 | 10%PO 90%INV | 2016-10-07 | 0 | 0 | 0 | 78750 | 2 | 14175 | - | 0 | 0 | 0 | 39/35/PIFG/SCL | J 3935 - SUPPLY OF TUBES | 1 | 0 | 630000 | Numbers | - | 310101 | 630000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (ITEM CODE: MTUBCCKD9903)-TITANIUM TUBE: OD-25.4 MM X 1.2 MM THK X 4020 MM LONG AS PER IS: 226,SB338 GR.2 | - | - | - | - | 2016-09-10 | 899168 | Y | - | - | (ITEM CODE: MTUBCCKD9903)-TITANIUM TUBE: OD-25.4 MM X 1.2 MM THK X 4020 MM LONG AS PER IS: 226,SB338 GR.2AS PER PO | 914574 | 2016-10-07 | TCI FREIGHT | RJ 19 GD 6871 | LR NO.309387186 | 104 PIPES FITTED WITH EQUPTMENT AND 01 PIPE LOOSE ITEM | - | - | 1617070129 | 2016-10-07 | 722925 | 991617000144 | 2016-10-07 | - | 0 | 0 | 1 | 722925 | Engg-CA(472) - BOB/MYL1 | 013097 / 25-SEP-2014,600417 | 2016-10-07 | 92925 | - | - | - | 630000 | 630000 | -
2016-10-14 | ENGG_INTER_EQUIPMENT | CLOSED | INDIAN OIL CORPORATION LIMITED | 2867 | BSIVBR003/24804346 | 4026 | SR.PROJECT MANAGER BS IV PROJECT, PO BARAUNI REFINERY, - | SR.PROJECT MANAGER BS IV PROJECT, PO BARAUNI REFINERY, - | ENGG_PRICE_LIST | 2016-10-14 | 5%15%65%5%10% | 2016-10-14 | 0 | 0 | 0 | 1116275.63 | 2 | 200929.61 | - | 0 | 0 | -0.24 | 40/26/HEFG/IOC | J 4026 - SUPPLY OF LAS HEAT EXCHANGER | 1 | 0 | 8930205 | Numbers | - | 310101 | 8930205 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 2956010013)- LOW ALLOY STEEL HEAT EXCHANGER TAG NO: 702-E-51 B | - | - | - | - | 2016-07-06 | 905169 | Y | - | - | (MATERIAL CODE: 2956010013)- LOW ALLOY STEEL HEAT EXCHANGER TAG NO: 702-E-51 BAS PER PO | 920575 | 2016-10-14 | TCI FREIGHT | NL 01 D 7224 | LR NO. 309387293 | ONE EQUIPMENT AND FOUR WOODEN BOXES | - | - | 1617070133 | 2016-10-14 | 10247410 | 9.9162e+23 | 14-OCT-2016,14-OCT-2016 | - | 0 | 0 | 1 | 10247410 | - | - | 2016-10-14 | - | - | - | - | 8930205 | 8930205 | -
2016-10-24 | ENGG_INTER_EQUIPMENT | CLOSED | HYPER FILTRATION PVT LTD | 5380 | HFPL/TEAM/PO/16/12716 | 4075 | 16/1 , A-4, SITE IV, SAHIBABAD INDUSTRIAL AREA, DIST. GHAZIABAD - 201010, UTTAR PRADESH, - | 16/1 , A-4, SITE IV, SAHIBABAD INDUSTRIAL AREA, DIST. GHAZIABAD - 201010, UTTAR PRADESH, - | ENGG_PRICE_LIST | 2016-10-24 | 50%ADV50%DESP | 2016-10-24 | 0 | 0 | 0 | 75000 | 2 | 13500 | - | 0 | 0 | 0 | 40/75/COFG/HFP | 4075 TI Gr.2 PLATE WITH MMO COATING | 25 | 0 | 24000 | Numbers | - | 310101 | 600000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | SUPPLY OF TITANIUM GR.2 PLATE WITH MMO COATING(5 MICRON THICKNESS), ANODE PLATE-SB265GR.2 | - | - | - | - | 2016-07-12 | 916169 | Y | - | - | SUPPLY OF TITANIUM GR.2 PLATE WITH MMO COATING(5 MICRON THICKNESS), ANODE PLATE-SB265GR.2(3 NOS FEED PUMPS TO MF+1 NO RO CIP) AS PER PO | 925574 | 2016-10-24 | COURIER | TCI XPS | LR NO. 329246794 | MATL KEPT INSIDE VIDE DC NO.925575 MATL WOODEN BOX | - | - | 1617070135 | 2016-10-24 | 688500 | 991617000165 | 2016-10-24 | - | 0 | 0 | 25 | 688500 | ENG. IDBI BANK | HYPER,HYPER | 2016-10-24 | 88500 | - | - | - | 24000 | 24000 | -
2016-10-27 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT DYNAMICS LIMITED | 1024 | 40701684 | 3905 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | ENGG_PRICE_LIST | 2016-10-03 | 100% PAYMENT | 2016-10-27 | 0 | 0 | 0 | 18750 | 2 | 3375 | - | 0 | 0 | 0 | 39/05/ROFG/3RD | J 3905- TI SHELL ROOLING | 10 | 0 | 15000 | Numbers | - | 310101 | 150000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 540001000001)- SHELL ROLLING AS PER DRG.PD40-014 | - | - | - | - | 2014-03-05 | 922167 | Y | - | - | (MATERIAL CODE: 540001000001)- SHELL ROLLING AS PER DRG.PD40-014AS PER PO | 930573 | 2016-10-27 | - | - | - | - | - | - | 1617070137 | 2016-10-27 | 172125 | 991617000173 | 2016-10-27 | - | 0 | 0 | 10 | 172125 | - | - | 2016-10-27 | - | - | - | - | 15000 | 15000 | -
2016-11-29 | ENGG_INTER_LABOUR | CLOSED | VEM TECHNOLOGIES PVT LTD | 1049 | 4550001781 | 4119 | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | UNIT -II , SURVEY NO 1/1 IMARATH KANCH, RAVIRALA VILLAGE, MAHESHWARAM MANDAL - | ENGG_PRICE_LIST | 2016-11-29 | 100% PAYMENT | 2016-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 12600 | 0 | 15000 | 41/19/COFG/001 | J 4119 - Ti SHELL ROLLING | 5 | 0 | 18000 | Numbers | - | 310251 | 90000 | ENGG_INTER_LABOUR_LINE | CLOSED | LABOUR CHARGES FOR TITANIUM SHELL ROLLING MOC: Ti6AL4V | - | - | - | - | 2016-03-25 | 957167 | Y | - | - | LABOUR CHARGES FOR TITANIUM SHELL ROLLING MOC: Ti6AL4VAS PER PO | 956573 | 2016-11-29 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | - | 5 WOODEN BOX,1 PLASTIC BUNDLE.PARTY MATERIAL RECEIVED RGP CHALLAN NO 4(5) A NO:2016200963 | - | - | 1617090020 | 2016-11-29 | 118500 | - | 2016-11-29 | - | 0 | 0 | 5 | 118500 | ENG. IDBI BANK | 4119 | 2016-11-29 | 28500 | - | - | - | 18000 | 18000 | -
2017-01-17 | ENGG_INTER_EQUIPMENT | BOOKED | THE KERALA MINERALS & METALS LTD | 1404 | TP/29/1571/2016-2017/5022 | 4105 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2017-01-17 | 100%30DAYS | 2017-01-18 | 0 | 0 | 0 | 4680 | 2 | 842.4 | - | 0 | 0 | 0 | 41/05/COFG/KMM | J 4105 -Titanium M8 HEXAGONAL BOLT , NUT & WASHER | 8 | 0 | 4680 | SET | - | 310101 | 37440 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO:292252130)- 3/8" X 1 1/4" LONG HEX. HEADED BOLT AND NUT WITH 2 PLAIN WASHERS EACH IN TITANIUM GR.7 | - | - | - | - | 2016-09-23 | 1002177 | Y | - | - | (MATERIAL CODE NO:292252130)- 3/8" X 1 1/4" LONG HEX. HEADED BOLT AND NUT WITH 2 PLAIN WASHERS EACH IN TITANIUM GR.7MATERIAL TEST CERTIFICATE SHOULD BE PRODUCED ALONG WITH THE SUPPLY AS PER PO | 1002576 | 2017-01-17 | COURIER | TCI XPS | LR NO.329732292 | PACKED IN ONE CARTON BOX. CARTON BOX KEPT IN WOODEN BOX VIDE DC NO.1002575 | - | - | 1617070180 | 2017-01-18 | 42962.4 | 991617000289 | 2017-01-18 | - | 0 | 0 | 8 | 42962.4 | - | - | 2017-01-18 | - | - | - | - | 4680 | 4680 | -
2016-10-13 | ENGG_INTER_EQUIPMENT | CLOSED | ESSAR OIL LIMITED | 5260 | 4500022627 | 4060 | EOL-WAREHOUSE, 39TH KM. STONE, JAMNAGAR-OKHA HIGHWAY, TALUKA: KHAMBALIA, - | POST BOX NO:24, JAMNAGAR-KHAMBALIA ROAD, JHAKAR, KHAMBALIA HEAD OFFICE, JAMNAGAR-361305 , - | ENGG_PRICE_LIST | 2016-10-13 | 100%15DAYS | 2016-10-13 | 0 | 0 | 0 | 210000 | 2 | 37800 | - | 0 | 0 | 0 | 40/60/HEFG/ESR | J 4060 - SUPPLY TUBE BUNDLE | 1 | 0 | 1680000 | Numbers | - | 310101 | 1680000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 2457630414)- TUBE BUNDLE TAG NO: 121-E-113 (19.05 X 2.11 X 6000) | - | - | - | - | 2016-06-16 | 902169 | Y | - | - | (MATERIAL CODE: 2457630414)- TUBE BUNDLE TAG NO: 121-E-113 (19.05 X 2.11 X 6000)AS PER PO | 918574 | 2016-10-13 | TCI FREIGHT | TN 28 AF 1669 | - | ONE EQUIPMENT | - | - | 1617070132 | 2016-10-13 | 1927800 | 991617000153 | 2016-10-13 | - | 0 | 0 | 1 | 1927800 | ENG. IDBI BANK | essar oil ltd | 2016-10-13 | 394205.23 | - | - | - | 1680000 | 1680000 | -
2016-11-16 | ENGG_LOCAL_SCRAP | CLOSED | AVM ENTERPRISES | 6340 | - | - | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | 106-50, JEEVA NAGAR, TAMILNADU-600 021 | ENGG_PRICE_LIST | 2016-11-16 | 100% PAYMENT | 2016-11-16 | 5 | 6137.13 | 0 | 13638.08 | 0 | 0 | - | 0 | 1289 | 0 | MS/CB/SCRP/KG | MS CUTBITS SCRAP | 8130 | 0 | 13.42 | kilogram | - | 310701 | 109104.6 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S.CUT BITS SCRAP | - | - | - | - | - | 945171 | Y | - | - | M.S.CUT BITS SCRAP | 946575 | 2016-11-16 | - | TN 20 BR 4066 | - | - | - | - | 1617070151 | 2016-11-16 | 130168.81 | 991617000201 | 2016-11-16 | - | 0 | 0 | 8130 | 130168.81 | ENG. IDBI BANK | AVM-SCRAP | 2016-11-16 | 21064.21 | - | - | - | 13.42 | 13.42 | -
2016-11-19 | ENGG_LOCAL_SCRAP | CLOSED | N.S.TRADERS | 6381 | - | - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | 5/1-A, AYYAPAKKAM MAIN ROAD M.G.R.PURAM - | ENGG_PRICE_LIST | 2016-11-18 | 100% PAYMENT | 2016-11-19 | 5 | 991.5 | 0 | 2203.34 | 0 | 0 | - | 0 | 208 | 0.46 | MS/SS/SCRP/MIX | MS AND SS MIXED BORING SCRAP | 1490 | 0 | 11.83 | kilogram | - | 310701 | 17626.7 | ENGG_LOCAL_SCRAP_LINE | CLOSED | M.S. AND S.S. MIXED BORING SCRAP | - | - | - | - | - | 950169 | Y | - | - | M.S. AND S.S. MIXED BORING SCRAP | 951573 | 2016-11-19 | - | TN 09 F 7439 | - | - | - | - | 1617070154 | 2016-11-19 | 21030 | 991617000210 | 2016-11-19 | - | 0 | 0 | 1490 | 21030 | ENG. IDBI BANK | 46997 | 2016-11-19 | 3403.3 | - | - | - | 11.83 | 11.83 | -
2016-12-08 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/51/1012/2016-2017 | 4084 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 100%PT30DAYS | 2016-12-08 | 0 | 0 | 0 | 68750 | 2 | 12375 | - | 0 | 0 | 0 | 40/84/COFG/KMM | J 4084 - SUPPLY OF HYDROCYCLONE | 1 | 0 | 550000 | Numbers | - | 310101 | 550000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO: 616001001)- HYDROCYCLONE O-401 AS PER DRAWING NO: TP/MM/IBP/O-401/1057 | - | - | - | - | 2016-07-19 | 969176 | Y | - | - | (MATERIAL CODE NO: 616001001)- HYDROCYCLONE O-401 AS PER DRAWING NO: TP/MM/IBP/O-401/1057TEST CERTIFICATE SHOULD BE SUBMITTED ALONG WITH THE SUPPLY FOR THE TITANIUM MATERIAL | 969576 | 2016-12-08 | SRI LAKSHMI TRANSPORT | TN 11 R 3994 | LR NO.131 | PACKED IN ONE WOODEN BOX. SIZE: 870 L X 430 W X 475 H. GR WT: 40 KGS | - | - | 1617070164 | 2016-12-08 | 631125 | 991617000236 | 2016-12-08 | - | 0 | 0 | 1 | 631125 | - | - | 2016-12-08 | - | - | - | - | 550000 | 550000 | -
2016-12-08 | ENGG_INTER_EQUIPMENT | CLOSED | THE KERALA MINERALS & METALS LTD | 1404 | TP/61/31/853/2016-2017 | 4067 | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | (A GOVERNMENT OF KERALA UNDERTAKING) SANKARAMANGALAM,CHAVARA-691583, - | ENGG_PRICE_LIST | 2016-12-08 | 100%30DAYS | 2016-12-08 | 0 | 0 | 0 | 135750 | 2 | 24435 | - | 0 | 0 | 0 | 40/67/COFG/KML | J 4067 - Ti Gr 7- Grid Pot | 4 | 0 | 271500 | Numbers | - | 310101 | 1086000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE NO: 616001040)- SUPPLY OF TITANIUM GRIT POT FOR HYDROCYCLONE MATERIAL: TIGR.7 | - | - | - | - | 2016-06-28 | 970173 | Y | - | - | (MATERIAL CODE NO: 616001040)- SUPPLY OF TITANIUM GRIT POT FOR HYDROCYCLONE MATERIAL: TIGR.7FLANGE: SS316 AS PER DRAWING NO: TP/MM/IBP/O401/1123 REV0 | 970575 | 2016-12-08 | SRI LAKSHMI TRANPORT | TN 11 R 3994 | LR NO.131 | PACKED IN ONE WOODEN BOX. GR WT: 93 KGS. SIZE: 1400 L X 825 W X 460 H. | - | - | 1617070165 | 2016-12-08 | 1246185 | 991617000237 | 2016-12-08 | - | 0 | 0 | 4 | 1246185 | - | - | 2016-12-08 | - | - | - | - | 271500 | 271500 | -
2016-12-16 | ENGG_INTER_EQUIPMENT | CLOSED | L&T HYDROCARBON ENGINEERING LIMITED | 4380 | EA172PO6001138 | 4128 | SITE1: ISBL COMPOSITE WORKS, PTA-1, C/O. JBF PETROCHEMICALS LIMITED, D.NO.4-214, - | SITE1: ISBL COMPOSITE WORKS, PTA-1, C/O. JBF PETROCHEMICALS LIMITED, D.NO.4-214, - | ENGG_PRICE_LIST | 2016-12-16 | 100% PAYMENT | 2016-12-16 | 0 | 0 | 0 | 4881.25 | 2 | 878.63 | - | 0 | 0 | 0 | 41/28/COFG/003 | J-4128 FILLER WIRE 3.00 MM | 5.5 | 0 | 7100 | Numbers | - | 310101 | 39050 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 358199959)-FILLER WIRE ERTI-2 3.2MM | - | - | - | - | 2016-07-22 | 974173 | Y | - | - | (MATERIAL CODE: 358199959)-FILLER WIRE ERTI-2 3.2MMAS PER PO | 973575 | 2016-12-16 | TCI XPS COURIER | - | 329352531 | PACKED IN ONE BUBBLE PACKAGE | - | - | 1617070167 | 2016-12-16 | 44809.88 | 9.9162e+23 | 16-DEC-2016,16-DEC-2016 | - | 0 | 0 | 5.5 | 44809.88 | - | - | 2016-12-16 | - | - | - | - | 7100 | 7100 | -
2016-12-16 | ENGG_INTER_EQUIPMENT | CLOSED | L&T HYDROCARBON ENGINEERING LIMITED | 4380 | EA172PO6001138 | 4128 | SITE1: ISBL COMPOSITE WORKS, PTA-1, C/O. JBF PETROCHEMICALS LIMITED, D.NO.4-214, - | SITE1: ISBL COMPOSITE WORKS, PTA-1, C/O. JBF PETROCHEMICALS LIMITED, D.NO.4-214, - | ENGG_PRICE_LIST | 2016-12-16 | 100% PAYMENT | 2016-12-16 | 0 | 0 | 0 | 5325 | 2 | 958.5 | - | 0 | 0 | 0 | 41/28/COFG/002 | J- 4128 FILLER WIRE 2.0 MM | 6 | 0 | 7100 | Numbers | - | 310101 | 42600 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (MATERIAL CODE: 358199958)- FILLER WIRE ERTI-2 2MM | - | - | - | - | 2016-07-22 | 974173 | Y | - | - | (MATERIAL CODE: 358199958)- FILLER WIRE ERTI-2 2MMAS PER PO | 973575 | 2016-12-16 | TCI XPS COURIER | - | 329352531 | PACKED IN ONE BUBBLE PACKAGE | - | - | 1617070167 | 2016-12-16 | 48883.5 | 9.9162e+23 | 16-DEC-2016,16-DEC-2016 | - | 0 | 0 | 6 | 48883.5 | - | - | 2016-12-16 | - | - | - | - | 7100 | 7100 | -
2016-12-20 | ENGG_INTER_EQUIPMENT | CLOSED | LORDS CHLORO ALKALI LTD | 1029 | LCAL/PUR/133 | 4070 | Sp-460, desula (m.i.a) Alwar - 301030 Rajasthan-301030 | Sp-460, desula (m.i.a) Alwar - 301030 Rajasthan-301030 | ENGG_PRICE_LIST | 2016-12-20 | 100% Advance | 2016-12-21 | 0 | 0 | 0 | 12150 | 2 | 2187 | - | 0 | 0 | 0 | 40/70/COFG/LRD | J 4070 - SUPPLY OF SS SHAFT | 3 | 0 | 32400 | Numbers | - | 310101 | 97200 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | P 84/284 PUMP MAKE- TEAM, MODEL-TF-BP-1, Q=40 M3/Hr, H=20mtr Temp=80dc, P=7.5KW, Shaft-MOC-SA479TP304 | - | - | - | - | - | 976182 | Y | - | - | P 84/284 PUMP MAKE- TEAM, MODEL-TF-BP-1, Q=40 M3/Hr, H=20mtr Temp=80dc, P=7.5KW, Shaft-MOC-SA479TP304 | 975577 | 2016-12-20 | COURIER | TCI XPS | COURIER | PACKED IN ONE WOODEN BOX | - | - | 1617070168 | 2016-12-21 | 111537 | 991617000251 | 2016-12-21 | - | 0 | 0 | 3 | 111537 | ENG. IDBI BANK | 38022 | 2016-12-21 | 14337 | - | - | - | 32400 | 32400 | -
2016-12-23 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237775 | 4054 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-23 | 100% PAYMENT | 2016-12-23 | 0 | 0 | 0 | 11875 | 2 | 2137.5 | - | 0 | 0 | 0.5 | 40/54/BKTW/001 | J 4054 - BRACKET WELDED | 100 | 0 | 950 | Numbers | - | 310101 | 95000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO:112003306996)- BRACKET WELDED | - | - | - | - | 2016-06-09 | 979175 | Y | - | - | (BEL PART NO:112003306996)- BRACKET WELDEDAS PER PO | 978576 | 2016-12-23 | COURIER | TCI XPS | LR NO.329732211 | PACKED IN ONE CARTON BOX | - | - | 1617070171 | 2016-12-23 | 109013 | 9.9162e+23 | 23-DEC-2016,23-DEC-2016 | - | 0 | 0 | 100 | 109013 | - | - | 2016-12-23 | - | - | - | - | 950 | 950 | -
2016-12-23 | ENGG_INTER_EQUIPMENT | CLOSED | BHARAT ELECTRONICS LTD | 2804 | BEPO/S20/4900237775 | 4054 | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | (A GOVERNMENT OF INDIA ENTERPRISE) JALAHALLI P.O, BANGALORE- 560013 - | ENGG_PRICE_LIST | 2016-12-23 | 100% PAYMENT | 2016-12-23 | 0 | 0 | 0 | 12500 | 2 | 2250 | - | 0 | 0 | 0 | 40/54/EDSP/001 | J 4054 - END SUPPORT | 1000 | 0 | 100 | Numbers | - | 310101 | 100000 | ENGG_INTER_EQUIPMENT_LINE | CLOSED | (BEL PART NO: 112001256804)- END SUPPORT WELDED | - | - | - | - | 2016-06-09 | 979175 | Y | - | - | (BEL PART NO: 112001256804)- END SUPPORT WELDEDAS PER PO | 978576 | 2016-12-23 | COURIER | TCI XPS | LR NO.329732211 | PACKED IN ONE CARTON BOX | - | - | 1617070171 | 2016-12-23 | 114750 | 9.9162e+23 | 23-DEC-2016,23-DEC-2016 | - | 0 | 0 | 1000 | 114750 | - | - | 2016-12-23 | - | - | - | - | 100 | 100 | -
2016-10-27 | ENG_RETURN_SALES_ORDER | BOOKED | BHARAT DYNAMICS LIMITED | 1024 | - | 3905 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | A govt. Of india enterprise Kanchanbagh Andhra pradesh-500058 | ENGG_PRICE_LIST | 2016-10-03 | 30 NET | - | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 39/05/ROFG/3RD | J 3905- TI SHELL ROOLING | 10 | 0 | - | Numbers | - | 310251 | - | ENG_RETURNS_LINE | CLOSED | - | - | - | - | - | - | - | N | - | - | - | - | - | - | - | - | - | - | - | 1617050001 | 2016-10-27 | -172500 | - | - | - | 0 | 0 | 10 | -172500 | - | - | 2016-10-27 | - | - | - | - | 15000 | 15000 | -
2016-06-20 | ENGG_INTER_LABOUR | CLOSED | L&T HYDROCARBON ENGINEERING LIMITED | 4380 | LOA :LTHE/JBFPL/PTA-1/ISBL/TITANIUM PIPING/LOA/001 | 4038 | SITE1: ISBL COMPOSITE WORKS, PTA-1, C/O. JBF PETROCHEMICALS LIMITED, D.NO.4-214, - | SITE1: ISBL COMPOSITE WORKS, PTA-1, C/O. JBF PETROCHEMICALS LIMITED, D.NO.4-214, - | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-06-20 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 368706 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 2542800 | LOT | - | 310251 | 2542800 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | FIELD WELDING OF PIPES/PIPE SPOOLS/PIPE FITTINGS INCLUDING FIXING AND REMOVAL OF BOOTH AND SAFETY NET, CUTTING, BEVELLING,EDGE PREPARATION, FUITUP INCLUSIVE OF THE EDGES OF PIPES, FITTINGS, FLANGES, TO MATCH MATING EDGES OF UNEVEN/DIFFERENT | - | - | - | - | 2016-04-02 | - | N | - | - | FIELD WELDING OF PIPES/PIPE SPOOLS/PIPE FITTINGS INCLUDING FIXING AND REMOVAL OF BOOTH AND SAFETY NET, CUTTING, BEVELLING,EDGE PREPARATION, FUITUP INCLUSIVE OF THE EDGES OF PIPES, FITTINGS, FLANGES, TO MATCH MATING EDGES OF UNEVEN/DIFFERENTTHICKNESS(BACKCHIPPING), NORMAL PREHEATING, WELDING OF PIPES OF ALL THICKNESS AT ALL HEIGHTS INCLUDING ALL TYPES OF FITTINGS LIKE ELBOWS, TEES, MITRES, BENDS, FORGED/FABRICATED REDUCERS, CROSS, CAPS AND STUB ENDS, WELDING AND ERECTION OF | - | - | - | - | - | - | - | - | 1617090005 | 2016-06-20 | 2924220 | - | 2016-06-20 | - | 0 | 0 | 1 | 2924220 | ENG. IDBI BANK | L&amp;T | 2016-06-20 | 750306.96 | - | - | - | - | 2542800 | -
2016-11-02 | ENGG_INTER_LABOUR | CLOSED | MATERIALS CHEMICALS AND PERFORMANCE INTERMEDIARIES PRIVATE LIMITED | 6260 | WORK ORDER NO: WO-M-10046109 | 4091 | VILLAGE & P.O BHUNIARAICHAK, VIA: SUTAHATA(HALDIA), PURBA MIDNAPORE, - | VILLAGE & P.O BHUNIARAICHAK, VIA: SUTAHATA(HALDIA), PURBA MIDNAPORE, - | ENGG_PRICE_LIST | - | 100%30 DAYS | 2016-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 46823.62 | 0 | 0.44 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 334454.4 | LOT | - | 310251 | 334454.4 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | ANNUAL RATE CONTRACT FOR VARIOUS TI FABRICATION AND MAINTENANCE JOBS AT MCPI PLANT SITE, HALDIA | - | - | - | - | 2015-11-02 | - | N | - | - | ANNUAL RATE CONTRACT FOR VARIOUS TI FABRICATION AND MAINTENANCE JOBS AT MCPI PLANT SITE, HALDIAAS PER PO | - | - | - | - | - | - | - | - | 1617090018 | 2016-11-02 | 384623 | - | 2016-11-02 | - | 0 | 0 | 1 | 384623 | - | - | 2016-11-02 | - | - | - | - | - | 334454.4 | -
2016-12-23 | ENGG_INTER_LABOUR | CLOSED | MATERIALS CHEMICALS AND PERFORMANCE INTERMEDIARIES PRIVATE LIMITED | 6260 | WO-M-10046109 | 4115 | VILLAGE & P.O BHUNIARAICHAK, VIA: SUTAHATA(HALDIA), PURBA MIDNAPORE, - | VILLAGE & P.O BHUNIARAICHAK, VIA: SUTAHATA(HALDIA), PURBA MIDNAPORE, - | ENGG_PRICE_LIST | - | 100%PAYMENTINV | 2016-12-23 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 260275.05 | 0 | 0.37 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 1859107.5 | LOT | - | 310251 | 1859107.5 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | ANNUAL RATE CONTRACT FOR 2S-1411A inside casing damage (Titanium clad/C.S) | - | - | - | - | 2015-11-02 | - | N | - | - | ANNUAL RATE CONTRACT FOR 2S-1411A inside casing damage (Titanium clad/C.S)AS PER PO | - | - | - | - | - | - | - | - | 1617090024 | 2016-12-23 | 2137974 | - | 2016-12-23 | - | 0 | 0 | 1 | 2137974 | - | - | 2016-12-23 | - | - | - | - | - | 1859107.5 | -
2016-06-04 | ENGG_INTER_LABOUR | CLOSED | MULTIMAX ENGINEERING WORKS PVT LTD | 3965 | AMMENDED ORDER NO:MM/JOB/15-16/G-95/632/1539 | 4007 | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | A-6 INDUSTRIAL ESTATE , PARTAPUR, MEERUT(U.P)-250103 - | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 14.075 | 11600 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 80000 | LOT | - | 310251 | 80000 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | (JOB NO: 632)- INSPECTION CHARGES (LUMPSUM) | - | - | - | - | 2015-10-01 | - | N | - | - | (JOB NO: 632)- INSPECTION CHARGES (LUMPSUM)AS PER PO | - | - | - | - | - | - | - | - | 1617090003 | 2016-06-04 | 92000 | - | 2016-06-04 | - | 0 | 0 | 1 | 92000 | ENG. IDBI BANK | MULTIMAX | 2016-06-04 | 12000 | - | - | - | - | 80000 | -
2016-08-11 | ENGG_INTER_LABOUR | CLOSED | L&T HEAVY ENGINEERING DIVISION | 5640 | 01L003254/SACHIN TIWARI | 4066 | LARSEN AND TOURBO LIMITED, SURAT HAZIRA ROAD P.O. BHATA SURAT DISTRICT, GUJARAT-394510,INDIA - | LARSEN AND TOURBO LIMITED, SURAT HAZIRA ROAD P.O. BHATA SURAT DISTRICT, GUJARAT-394510,INDIA - | ENGG_PRICE_LIST | - | L&TPT4066 | 2016-08-11 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 64400 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 460000 | LOT | - | 310251 | 460000 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | (ITEM: SRVSHPFABRN)- CHARGES FOR TITANIUM SHIM SIZING, SETUP AND WELDING ON TRAY SUPPORT RINGS INSIDE THE EQUIPMENT AT REQUIRED | - | - | - | - | 2016-07-09 | - | N | - | - | (ITEM: SRVSHPFABRN)- CHARGES FOR TITANIUM SHIM SIZING, SETUP AND WELDING ON TRAY SUPPORT RINGS INSIDE THE EQUIPMENT AT REQUIREDLOCATION | - | - | - | - | - | - | - | - | 1617090008 | 2016-08-11 | 529000 | - | 2016-08-11 | - | 0 | 0 | 1 | 529000 | - | - | 2016-08-11 | - | - | - | - | - | 460000 | -
2016-12-26 | ENGG_INTER_LABOUR | CLOSED | L&T HEAVY ENGINEERING DIVISION | 5640 | 01L004144 | 4126 | LARSEN AND TOURBO LIMITED, SURAT HAZIRA ROAD P.O. BHATA SURAT DISTRICT, GUJARAT-394510,INDIA - | LARSEN AND TOURBO LIMITED, SURAT HAZIRA ROAD P.O. BHATA SURAT DISTRICT, GUJARAT-394510,INDIA - | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-12-26 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 62002.5 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 442875 | LOT | - | 310251 | 442875 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | (ITEM: SRVSHPFABRN)-CHARGES FOR MANPOWER SUPPLY TO CARRY OUT TITANIUM WELDING FOR 11938-2ND DEHYDRATION TOWER(SHIM WELDING) AT | - | - | - | - | 2016-11-28 | - | N | - | - | (ITEM: SRVSHPFABRN)-CHARGES FOR MANPOWER SUPPLY TO CARRY OUT TITANIUM WELDING FOR 11938-2ND DEHYDRATION TOWER(SHIM WELDING) ATTECHNIP SITE MANGALORE AS PER PO | - | - | - | - | - | - | - | - | 1617090026 | 2016-12-26 | 509306.26 | - | 2016-12-26 | - | 0 | 0 | 1 | 509306.26 | - | - | 2016-12-26 | - | - | - | - | - | 442875 | -
2016-12-03 | ENGG_INTER_LABOUR | CLOSED | CHEMFAB ALKALIS LIMITED | 1050 | 104161700799 | 4095 | Gnanananda place Kalapet, Puducherry 605014 - | Gnanananda place Kalapet, Puducherry 605014 - | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-12-03 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1120 | 0 | 0 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 8000 | Numbers | - | 310251 | 8000 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | (MATERIAL CODE: WO12500012PRC)-REPAIR OF ANODE ELEMENT OF UHDE ELECTROLYSER | - | - | - | - | 2016-08-27 | - | N | - | - | (MATERIAL CODE: WO12500012PRC)-REPAIR OF ANODE ELEMENT OF UHDE ELECTROLYSERAS PER PO | - | - | - | - | - | - | - | - | 1617090022 | 2016-12-03 | 9200 | - | 2016-12-03 | - | 0 | 0 | 1 | 9200 | ENG. IDBI BANK | 161670 | 2016-12-03 | 1200 | - | - | - | - | 8000 | -
2016-09-27 | ENGG_INTER_LABOUR | CLOSED | MCC PTA INDIA CORP PVT LTD | 1033 | WO NO: WO-M-10046109 | 4065 | Viii & p.o - bhuniaraichak, Via sutahata,haldia, Kolkata-721635 | Viii & p.o - bhuniaraichak, Via sutahata,haldia, Kolkata-721635 | ENGG_PRICE_LIST | - | 100% PAYMENT | 2016-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 46779.01 | 0 | -0.17 | LS/AT/SITE/REP | LABOUR CHARGES FOR DEPUTATION OF OUR CREW TO CARRY REPAIR WORK AT YOUR SITE | 1 | 0 | 334135.8 | LOT | - | 310251 | 334135.8 | ENGG_INTER_LABOUR_LINE_WITH_S | CLOSED | ANNUAL RATE CONTRACT FOR VARIOUS TI FABRICATION AND MAINTENANCE JOBS AT MCPI SITE, HALDIA | - | - | - | - | 2015-11-02 | - | N | - | - | ANNUAL RATE CONTRACT FOR VARIOUS TI FABRICATION AND MAINTENANCE JOBS AT MCPI SITE, HALDIA(2S-1411D INSIDE REPAIR ( LOWER HOPPER PORTION WELDING) | - | - | - | - | - | - | - | - | 1617090013 | 2016-09-27 | 384256 | - | 2016-09-27 | - | 0 | 0 | 1 | 384256 | - | - | 2016-09-27 | - | - | - | - | - | 334135.8 | -

## BILLING DETAILS
BILLING DETAILS FROM APRIL 1 2017 TO TILL DATE
S.NO | JOB NO | CLIENT | DESCRIPTION | QTY | CDD | DISPATCH DATE | LD CLAUSE | DELAY IN DAYS | LD AMOUNT IN INR
1 | 4150 | FIELD FRESH FOODS | TITANIUM FORCER DISC AND SEAL | 1 LOT | 2017-04-15 | 2017-04-10 | NA | 5 | 0
2 | 4163 | FLAIR STRAINER AND FILTERS | SUPPLY OF DUPLEX & Ti MATERIALS | 1 LOT | 2017-04-19 | 2017-04-21 | NA | -2 | 0
3 | 4098 | TECHNIP INDIA LTD | SUPPLY OF TITANIUM FABRICATED SPOOL | 1 LOT | 2017-04-19 | 2017-04-21 | NA | -2 | 0
4 | 4152 | MODERN ENGINEERING PLASTICS PRIVATE LTD | SUPPLY OF END AND MIDDLE ELECTRODES | END ELECTRODES-12 NOS MIDDLE ELECTRODE-18 NOS | 2017-04-16 | 2017-04-28 | NA | -12 | 0
5 | 4072B | INDIAN OIL CORPORATION LIMITED | SUPPLY OF HEAT EXCHANGER | 1 NO | 2017-03-07 | 2017-05-07 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -61 | 450267.14
6 | 4123 | TAMILNADUNEWSPRINT AND PAPERS LIMITED | HYDROGEN SCRUBBER BOTTOM VESSEL | 1 NO | 2017-03-21 | 2017-05-08 | NA | -48 | 0
7 | 4155 | HYPERFILTRATION PVT LTD | SUPPLY OF TIGR.2 PLATE WITH MMO COATING (5 MICRON THICKNESS), ANODE PLATE- SB265GR.2 | 6 NOS | 2017-05-12 | 2017-05-12 | NA | 0 | 0
8 | 4145 | KERALA MINERALS AND MINERALS LTD | STUD M16 X 150 MM LG P/N.707 TITANIUM WITH 2 NUTS (P/N.704) AND 2 WASHERS (P/N.706)FULL THREADED TITANIUM GR.2 MATERIAL | 15 NO | 2017-05-20 | 2017-05-12 | 1% PER MONTH UPTO MAXIMUM OF 5% | 8 | 0
9 | 4131 | ORIENT PAPER MILLS | SUPPLY OF TIGR.2 BLOWER WITHOUT MOTOR ALONG WITH 2 YEARS CONSUMABLE SPARES | 1 NO | 2017-04-20 | 2017-05-17 | 1% PER WEEK UPTO MAXIMUM OF 5% | -27 | 69042.86
10 | 4153 | MATERIALS CHEMICALS AND PERFORMANCE INTERMEDIARIES PRIVATE LIMITED | ANNUAL RATE CONTRACT FOR TI FABRICATION JOBS AT MCPI SITE | 1 LOT | 2017-05-20 | 2017-05-20 | NA | 0 | 0
11 | 4120 | UPL LIMITED | SHELL & TUBE HEAT EXCHANGER | 1 NO | 2017-02-01 | 2017-05-24 | 1% PER WEEK UPTO MAXIMUM OF 10% | -112 | 420000
12 | 4072 | IOCL GUJARAT | 4072- TOTAL FREIGHT BILL | 1 LOT | - | 2017-05-24 | NA | 0 | 0
13 | 4077 | IOCL HALDIA | HEAT EXCHANGERS(4077-A)-2NOS | 2 NOS | 2017-05-11 | 2017-05-31 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -20 | 112828.57
14 | 4111 | SRF LIMITED | SUPPLY OF MONEL PRESSURE VESSEL(4111B-1NO)& MONEL COLUMN(4111C-1NO) | 2 NOS | 2017-05-27 | 2017-05-31 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -4 | 18342.86
15 | 4111 | SRF LIMITED | SUPPLY OF MONEL DISTILLATION COLUMN (4111F-1NO) | 1 NO | 2017-05-27 | 2017-06-03 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -7 | 60000
16 | 4111 | SRF LIMITED | SUPPLY OF MONEL COLUMN LENGTH 15.8 MTR (4111G) | 0.81 NOS | 2017-05-27 | 2017-06-09 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -13 | 94393.93
17 | 4111 | SRF LIMITED | SUPPLY OF MONEL HEAT EXCHANGER (4111D) | 1 NO | 2017-05-27 | 2017-06-13 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -17 | 18821.43
18 | 4111 | SRF LIMITED | SUPPLY OF HEAT EXCHANGER (4111A) | 1 NO | 2017-05-27 | 2017-06-13 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -17 | 32421.43
19 | 4094 | BHARAT ELECTRONICS LIMITED | SUPPLY OF ARRAY STRUCTURE | 2 NOS | 2017-01-22 | 2017-06-15 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -144 | 437142.86
20 | 4175 | RELIANCE INDUSTRIES LIMITED | 3107471 MISCELLANEOUS WORK REIMBURSEMENT OF EXPENSES TOWARDS MOBILIZATIONAS PER WO | 1 LOT | NA | 2017-06-15 | NA | 0 | 0
21 | 4111 | SRF LIMITED | (ITEM CODE-P014000000377)- HEAT EXCHANGER SHELL AND TUBE METALLIC, SIZE: 21.1 M2, NT91, OD 25.4, THK-2.11, LEN.3000MM, NP 1:1, MOC: TUBE-MONEL, SHELL-CS, TUBE SHEET-CLADDED,E-524 THERMAL RECOV., SHELL ID 387MM,DP-(16.5 S.SIDE),(16.5 T.SIDE0, DT-(-46/100 S.SIDE, 93 T.SIDE) AS PER PO-(4111 I) | 1 NO | 2017-05-27 | 2017-06-16 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -20 | 32142.86
22 | 4111 | SRF LIMITED | (ITEM CODE: P014000000378)-HEAT EXCHANGER SHELL AND TUBE METALLIC, SIZE: 92.8 M2, NT-182U, OD-25.4, THK-2.11, LEN-3000 MM, NP 1:4,MOC: TUBE-MONEL, TUBE SHEET-MONEL, E-542 CONDEN., SHELL ID 750MM,DP-(12/FV S.SIDE), (7 T.SIDE), DT-(100 S.SIDE,65 T.SIDE) AS PER PO-(4111H) | 1 NO | 2017-05-27 | 2017-06-16 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -20 | 117142.86
23 | 4111 | SRF LIMITED | (ITEM CODE: P004200000116)- COLUMN DISTILLATION, SIZE: DIA 750MM, TOTAL LENGTH-19.5 MTR, SUPPLY -3.7 MTR, MOC: MONEL, T-541 1ST C1DISTILLATION COLUMN AS PER PO-(4111G) | 0.19 NO | 2017-05-27 | 2017-06-16 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -20 | 34064.29
24 | 4133 | DCW LIMITED | (MATERIAL CODE: 3009195)- RECOATING WORK OF ANODE HALF SHELLSAS PER PO | 10 NOS | 2017-06-30 | 2017-06-16 | NA | 14 | 0
25 | 4134 | DCW LIMITED | (MATERIAL CODE: 3012419)- RECOATING OF CATHODE HALF SHELLSAS PER PO | 8 NOS | 2017-06-30 | 2017-06-16 | NA | 14 | 0
26 | 4111 | SRF LIMITED | (ITEM CODE: P022000000045)- REACTOR STATIONARY , SIZE: 960 I.D AND LENGTH: 12633 TAG NO: R-500AS PER PO-(4111E) | 0.46 NOS | 2017-05-27 | 2017-06-17 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -21 | 302634
27 | 4111 | SRF LIMITED | (ITEM CODE: P022000000045)- REACTOR STATIONARY , SIZE: 960 I.D AND LENGTH:4353 MM TAG NO: R-500 WITH COOLER TAG NO: E-500 SHELL ID: 1250MM LENGTH: 5008MM TUBE DIA 50.8MM, THK 2.77MM, LENGTH: 5000MM AND NO OF TUBES- 304, MOC: MONELAS PER PO-(4111E) | 0.54 NOS | 2017-05-27 | 2017-06-17 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -21 | 355266
28 | 4142 | YUSUF BIN AHMED KANOO W.L.L | SUPPLY OF SPARES FOR ELECTROCHLORINATION UNIT INCLUDING PACKING, FORWARDING AND FREIGHT CHARGESAS PER PO | 1 SET | 2017-04-20 | 2017-06-19 | NA | -60 | 0
29 | 3905 | BHARAT DYNAMICS LIMITED | (MATERIAL CODE: 540001000001)- SHELL ROLLING AS PER DRG.PD40-014 | 15 NOS | 1ST BATCH OF 15 NOS TO BE DELIVERED WITHIN 45 DAYS FROM THE DATE OF RECEIPT OF FIM | 2017-06-22 | NA | 0 | 0
32 | 4106 | THERMAX LIMITED | SUPPLY OF ITEMS FROM TEAM TO RSPL | 1 LOT | 2017-02-28 | 2017-06-23 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -115 | 446200
33 | 4164 | TEAMEC CHLORATES LIMITED | RECOATING OF SPARE ELECTROLYSER WITH NEW CATHODE PLATES | 1 SET | 2018-03-31 | 2017-06-26 | NA | 278 | 0
34 | 4154 | SRF LIMITED | (ITEM CODE: S001400000323)- LABOUR SUPPLY,HIGH SKILLED MANPOWER SUPPLY FOR HASTELLOYCLADED EQUIPMENT REPAIRING AS PER PO | 775.5 HRS | 2017-06-19 | 2017-06-26 | NA | -7 | 0
35 | 4154 | SRF LIMITED | (ITEM CODE: S001400000323)- LABOUR SUPPLY,HIGH SKILLED MANPOWER SUPPLY FOR HASTELLOYCLADED EQUIPMENT REPAIRING AS PER PO | 100 HRS | 2017-06-19 | 2017-06-26 | NA | -7 | 0
36 | 4165 | SRF LIMITED | (ITEM CODE: S006300000108)- EQUIPMENT INSPECTION SERVICE,EQUIPMENT INSTALLATION CHARGESAS PER PO | 1 NO | 2017-06-30 | 2017-06-26 | NA | 4 | 0
38 | 4146 | TECHNIP INDIA LIMITED | LABOUR CHARGES FOR SUPPLY OF MANPOWER FOR CARRYING OUT TITANIUM WORKS AT SITE | 1 LOT | NA | 2017-06-27 | NA | 0 | 0
39 | 4038 | L&T HYDROCARBON ENGINEERING LIMITED | LABOUR CHARGES FOR FIELD WELDING OF PIPES/PIPE SPOOLS/PIPE FITTINGS INCLUDING FIXING AND REMOVAL OF BOOTH AND SAFETY NET , CUTTING, ETC ALONG WITH WELDING OFPIPES OF ALL THICKNESS AT ALL HEIGHTS INCLUDING ALL TYPES OF FITTINGS | 1 LOT | NA | 2017-06-27 | NA | 0 | 0
40 | 4038 | L&T HYDROCARBON ENGINEERING LIMITED | LABOUR CHARGES FOR FIELD WELDING OF PIPES/PIPE SPOOLS/PIPE FITTINGS INCLUDING FIXING AND REMOVAL OF BOOTH AND SAFETY NET , CUTTING, ETC ALONG WITH WELDING OFPIPES OF ALL THICKNESS AT ALL HEIGHTS INCLUDING ALL TYPES OF FITTINGS | 1 LOT | NA | 2017-06-27 | NA | 0 | 0
41 | 4148 | KERALA MINERALS AND MINERALS LTD | SUPPLY OF SPRAY BOOM PIPE | 5 SET | 2017-05-16 | 2017-06-29 | 1% PER MONTH UPTO MAXIMUM OF 5% | -44 | 6899.93
42 | 4149 | HINDUSTAN PETROLEUM CORPORATION LIMITED , VAIZAKH | SUPPLY OF LAS TUBE BUNDLE | 1 NO | 2017-05-30 | 2017-06-30 | NA | -31 | 0
43 | 4187 | TECHNIP INDIA LIMITED | MODIFICATION OF STRAINER BASKET BY CUTTING, GRINDING, ROLLING AND WELDING OF 8MM THICK | 1 NO | 2017-07-08 | 2017-07-07 | NA | 1 | 0
44 | 4106 | THERMAX LIMITED | (PART CODE: WQDBLA1294/00/NA)- TRANSFORMER RECTIFIER FOR ELECTROCHLORINATION PACKAGE | 2 NOS | 2017-02-28 | 2017-07-13 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -135 | 94692.86
45 | 4137 | ORIENT PAPER MILLS | DESIGN, ENGINEERING, FABRICATION, TESTING, SUPPLY OF TIGR.2 BRINE PUMP WITHOUT MOTOR(ITEM NO: P-102A&B) & P-103 A & B | 4 NOS | 2017-05-04 | 2017-07-13 | 1% PER WEEK UPTO MAXIMUM OF 5% | -70 | 270000
46 | 4106 | THERMAX LIMITED | (PART CODE: WQDBLA1275/00/NA)- HYDROGEN GAS DILUTION BLOWER FOR ELECTROCHLORINATION | 2 NOS | 2017-02-28 | 2017-07-13 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -135 | 11089.29
37 | 4106 | THERMAX LIMITED | FRP TANKS FOR ELECTROCHLORINATION SYSTEM | 4 NOS | 2017-02-28 | 2017-07-13 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -135 | 45098.49
47 | 4121 | SANDVIK ASIA PRIVATE LIMITED | (ITEM NO: HRP126468)- VESSEL WITH FASTENER & GASKET 78KW | 1 NO | 2017-03-31 | 2017-07-19 | 1% PER WEEK UPTO MAXIMUM OF 10% | -110 | 121314.29
48 | 4124 | ESSAR OIL LIMITED | (MATERIAL CODE: 2457646194)- TUBE BUNDLE 5714-01/5714-02 35E121 | 1 NO | 2017-05-15 | 2017-07-21 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -67 | 514464.29
49 | 4190 | MATERIALS CHEMICALS AND PERFORMANCE INTERMEDIARIES PRIVATE LIMITED | ANNUAL RATE CONTRACT FOR VARIOUS TI FABRICATION AND MAINTENANCE JOBS AT MCPI PLANT SITE, HALDIA | 1 LOT | NA | 2017-07-21 | NA | 0 | 0
50 | 4159 A | SRF LIMITED | (ITEM CODE: S009500000322)- MECHANICAL MISCELLANEOUS WORK,MECHANICAL MISCELLANEOUS WORK, CHARGES FOR EQUIPMENT SPARES PARTS | 1 SET | 2017-03-30 | 2017-07-22 | NA | -114 | 0
51 | 4159 B | SRF LIMITED | (ITEM CODE: P022000100043)- BELLOW FOR REACTOR STATIONARY R- 33111A/B - P3 PLANT ,MOC:SA 240GR.304,MAKE:TEAMCO,REF:REACTOR | 1 NO | 2017-05-06 | 2017-07-22 | NA | -77 | 0
52 | 4143 | SRF LIMITED | (ITEM NAME: P004200000138)- COLUMN DISTILLATION HASTALLOY,SIZE:I/D:500I/D,TLTO TL: 21122.5MM, :1ELLI MOC:SHL:SB575N102766MMTHK ,DISH ENDS:2,FASTNERS:SA193GRB7/SA194GR2H,BF:SA240GR.304+HC-276 10MM WELD O/L,GSKT:HC-276 SPWD | 1 NO | 2017-06-15 | 2017-07-22 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -37 | 356785.71
53 | 4168 | SRF LIMITED | (ITEM CODE: S006600000212)- EQUIPMENT REPAIR METALLIC HEAT EXCHANGER ,MOC:SB 163N006600(INCONEL-600),RETUBING OF HE E-11633 WITH SUPPLY OFINCONEL TUBE(SIZE:25.4ODX2.11THKX1500LENGTH-23NOS,8NOS.TOBE USED AFTER ECT,HYDRO TESTING) AS PER DWG.NO.TEAMCO-3673/E REV.3 | 1 NO | 2017-08-19 | 2017-07-25 | NA | 25 | 0
54 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-07-27 | 0.5% PER WEEK UPTO 5% | 35 | 0
55 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-07-27 | 0.5% PER WEEK UPTO 5% | 35 | 0
56 | 4077 | INDIAN OIL CORPORATION LIMITED | J 4077 B - SUPPLY OF HEAT EXCHANGER | 1 NO | 2017-05-11 | 2017-07-28 | 0.5% PER WEEK UPTO 5% | -78 | 657400.71
57 | 4051 | BHARAT EARTH MOVERS LIMITED | J 4051- TI SHELL ROLLING | 5 NO | 2017-07-01 | 2017-07-28 | 0.5% PER WEEK UPTO 5% | -27 | 1446.43
58 | 4077 | INDIAN OIL CORPORATION LIMITED | J 4077 B - SUPPLY OF HEAT EXCHANGER | 1 NO | 2017-05-11 | 2017-07-28 | 0.5% PER WEEK UPTO 5% | -78 | 657400.71
59 | 4106 | THERMAX LIMITED | J 4106 - RSPL-FIRST CONSIGMENT | 9 NO | 2017-02-28 | 2017-07-29 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -151 | 33975
60 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-07-29 | 0.5% PER WEEK UPTO 5% | 33 | 0
61 | 4172 | CHEMFAB ALKALIS LIMITED | J 4172 - CATHODE RECOATING | 10 NOS | 2017-07-31 | 2017-07-31 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | 0 | 0
62 | 4172 | CHEMFAB ALKALIS LIMITED | J 4172 - ANODE RECOATING | 10 NOS | 2017-07-31 | 2017-07-31 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | 0 | 0
63 | 4130 | ESSAR OIL LIMITED | HEAT EXCHANGER | 1 NO | 2017-07-10 | 2017-08-03 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -24 | 363428.57
64 | 4051 | BHARAT EARTH MOVERS LIMITED | J 4051- TI SHELL ROLLING | 15 NOS | 2017-07-01 | 2017-08-07 | 0.5% PER WEEK UPTO 5% | -37 | 5946.43
65 | 4113 | IGCAR/MRPU | FABRICATION OF TI-SS 304L DISSIMILAR PIPE INSERT 8NB (HIGHER WALL THICKNESS PIPE) | 25 NOS | 2017-04-03 | 2017-08-08 | 2% PER MONTH UPTO MAXIMUM OF 5% | -127 | 24341.67
66 | 4113 | IGCAR/MRPU | FABRICATION OF TI-SS 304L DISSIMILAR PIPE INSERT 15NB (HIGHER WALL THICKNESS PIPE) | 59 NOS | 2017-04-03 | 2017-08-08 | 2% PER MONTH UPTO MAXIMUM OF 5% | -127 | 87418.33
67 | 4113 | IGCAR/MRPU | FABRICATION OF TI-SS 304L DISSIMILAR PIPE INSERT 25NB | 3 NOS | 2017-04-03 | 2017-08-08 | 2% PER MONTH UPTO MAXIMUM OF 5% | -127 | 5969
68 | 4113 | IGCAR/MRPU | FABRICATION OF TI-SS 304L DISSIMILAR PIPE INSERT 100NB | 1 NO | 2017-04-03 | 2017-08-08 | 2% PER MONTH UPTO MAXIMUM OF 5% | -127 | 2963
69 | 4138 | ORIENT PAPER MILLS | SITE SUPERVISION FOR PUMP AND BLOWER | 1 LOT | NA | 2017-08-09 | NA | 0 | 0
70 | 4166 | PROGRAMME AD | TITANIUM AIR BOTTLE | 20 NOS | 2017-07-30 | 2017-08-10 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | -11 | 139857.14
71 | 4086 | HINDUSTAN PETROLEUM CORPORATION LIMITED , VAIZAKH | SUPPLY OF 14-E-91A FIXED TUBESHEET TITANIUM TUBE BUNDLE | 1 NO | 2017-01-23 | 2017-08-16 | 1% PER WEEK UPTO MAXIMUM OF 5% | -205 | 542957.14
72 | 4208 | SANDVIK ASIA PRIVATE LIMITED | SUPPLY OF FLANGE BLRF 50THK TESTING | 1 NO | 2017-08-16 | 2017-08-16 | NA | 0 | 0
73 | 4189 | CHEMFAB ALKALIS LIMITED | NRV WAFER TYPE MOC: NICKEL ANSI.B.16.5 300# 40 NB | 1 NO | 2017-09-18 | 2017-08-17 | NA | 32 | 0
74 | 4129 | SRF LIMITED | HEAT EXCHANGER SHELL AND TUBE NOS METALLIC RETUBING OF ,SIZE:SURF AREA:11.41, TUBE SIZE: 25.4 OD X 2.11 THICK X 1000 LNG.,MOC:SB 622 (UNS N10276),REF:AS PER E- 12510 DRAWING,TUBES IN VENDORS SCOPE | 1 NO | 2017-06-15 | 2017-08-22 | NA | -68 | 0
75 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-08-22 | 0.5% PER WEEK UPTO 5% | 9 | 0
76 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-08-22 | 0.5% PER WEEK UPTO 5% | 9 | 0
78 | 4086 | HINDUSTAN PETROLEUM CORPORATION LIMITED , VAIZAKH | SUPPLY OF 14-E-91B FIXED TUBESHEET TITANIUM TUBE BUNDLE | 1 NO | 2017-01-23 | 2017-08-24 | 1% PER WEEK UPTO MAXIMUM OF 5% | -213 | 564145.71
79 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-08-24 | 0.5% PER WEEK UPTO 5% | 7 | 0
80 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-08-31 | 0.5% PER WEEK UPTO 5% | 0 | 0
81 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-09-01 | 0.5% PER WEEK UPTO 5% | -1 | 1475.71
82 | 4103 | HINDUSTAN PETROLEUM CORPORATION LIMITED , MUMBAI | SUPPLY OF SDSS TUBE BUNDLE | 1 NO | 2017-01-27 | 2017-09-02 | 0.5% PER WEEK UPTO 5% | -218 | 270406.27
83 | 4118 | GRASIM INDUSTRIES LIMITED | J 4118 - SUPPLY OF CELL RACK | 2 NOS | 2017-08-31 | 2017-09-02 | 0.5% PER WEEK UPTO 5% | -2 | 2951.43
84 | 4144 | ESSAR OIL LIMITED | SUPPLY OF FLOATING HEAD COVER 32E-002A/B | 2 NOS | 2017-05-15 | 2017-09-05 | 0.5% PER WEEK UPTO 5% | -113 | 201785.71
85 | 4106 | THERMAX LIMITED | SUPPLY OF SEAWATER BOOSTER PUMP WITH MOTOR | 2 NOS | 2017-02-28 | 2017-09-05 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -189 | 13202.6
86 | 4106 | THERMAX LIMITED | SUPPLY OF CONTINOUS DOSING PUMP WITH MOTOR | 2 NOS | 2017-02-28 | 2017-09-05 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -189 | 13770
87 | 4207 | DCW LIMITED | RECOATING OF ANODE HALF SHELLS | 8 NOS | 2017-08-30 | 2017-09-05 | NA | -6 | 0
88 | 4106 | THERMAX LIMITED | (PART NO: WQDBLA1280/00/NA)- JUNCTION BOX FOR ELECTROCHLORINATION PACKAGE | 4 NOS | 2017-02-28 | 2017-09-07 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -191 | 5388.79
89 | 4106 | THERMAX LIMITED | (PART NO: WQDBLA1277/00/NA)- CABLE TRAY FOR ELECTROCHLORINATION PACKAGE | 1 LOT | 2017-02-28 | 2017-09-07 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -191 | 18726.6
90 | 4179 | SANDVIK ASIA PRIVATE LIMITED | SUPPLY OF VESSEL WITH FASTENERS & GASKET | 1 NO | 2017-09-03 | 2017-09-09 | 1% PER WEEK UPTO MAXIMUM OF 10% | -6 | 18985.71
91 | 4194 | SRF LIMITED | SUPPLY OF FABRICATION TEAM FOR REACTOR TUBE TO TUBE SHEET WELDING WORK | 1 LOT | 2017-09-30 | 2017-09-11 | NA | 19 | 0
92 | 4109 | BHARAT OMAN REFINERIES LTD | SUPPLY OF HEAT EXCHANGER 16-EE-00-103 | 1 NO | 2017-07-23 | 2017-09-12 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -51 | 49251.43
93 | 4109 | BHARAT OMAN REFINERIES LTD | SUPPLY OF HEAT EXCHANGER 16-EE-00-1101 | 1 NO | 2017-07-23 | 2017-09-12 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -51 | 17074.29
94 | 4177 | CHEMPLAST SANMAR | SUPPLY OF TIGR2 SLEEVE | 2 NOS | 2017-09-30 | 2017-09-12 | NA | 18 | 0
95 | 4108 | RAMAGUNADAM FERTILIZERS LTD | SUPPLY OF HEAT EXCHNAGERS | 1 NO | 2017-09-20 | 2017-09-13 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | 7 | 0
96 | 4160 A | KERALA MINERALS AND MINERALS LTD | SUPPLY OF HYDROCYCLONE | 1 NO | 2017-08-15 | 2017-09-16 | 1% PER MONTH UPTO MAXIMUM OF 5% | -32 | 6080
97 | 4160 B | KERALA MINERALS AND MINERALS LTD | SUPPLY OF GRIT POT | 1 NO | 2017-08-15 | 2017-09-16 | 1% PER MONTH UPTO MAXIMUM OF 5% | -32 | 3136
98 | 4162 | KERALA MINERALS AND MINERALS LTD | SUPPLY OF IMPELLER | 2 NOS | 2017-08-24 | 2017-09-16 | 1% PER MONTH UPTO MAXIMUM OF 5% | -23 | 6900 |  |  |  | 0.76667
99 | 4181 A | KERALA MINERALS AND MINERALS LTD | SUPPLY OF FASTENERS | 24 SET | 2017-09-20 | 2017-09-16 | 1% PER MONTH UPTO MAXIMUM OF 5% | 4 | 0
100 | 4181 B | KERALA MINERALS AND MINERALS LTD | SUPPLY OF FASTENERS | 24 SET | 2017-09-20 | 2017-09-16 | 1% PER MONTH UPTO MAXIMUM OF 5% | 4 | 0
101 | 4106 | THERMAX LIMITED | SUPPLY OF CONSIGNMENT FROM TEAM TO RSPL | 1 LOT | 2017-02-28 | 2017-09-18 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -202 | 372072.87
102 | 4205 | MCCPTA | CTA DECABTER FEED LINE 6" PS-1322A-BN3B & GEAR BOX TOP COVER REPAIR WORK | 1 LOT | - | 2017-09-28 | NA | 0 | 0
103 | 4069 | CHENNAI PETROLEUM CORPORATION LTD | SUPPLY FOR STEAM TRACING -EXCHANGERS FOR COKER BLOCK OF RESID UPGRADATION PROJECTFOR CPCL REFINERY CHENNAI | 1 NO | 2016-10-12 | 2017-09-16 | NA | -339 | 0
104 | 4069 | CHENNAI PETROLEUM CORPORATION LTD | LABOUR WORK FOR STEAM TRACING -EXCHANGERS FOR COKER BLOCK OF RESID UPGRADATION PROJECTFOR CPCL REFINERY CHENNAI | 1 LOT | 2016-10-12 | 2017-09-16 | NA | -339 | 0
105 | 4139 | SAURASHTRA CHEMICALS | TITANIUM TUBE | 50 NOS | 2017-09-25 | 2017-10-04 | NA | -9 | 0
106 | 4140 | SAURASHTRA CHEMICALS | REPAIR OF HEAT EXCHANGER | 1 NO | 2017-09-25 | 2017-10-04 | NA | -9 | 0
107 | 4151 | SAURASHTRA CHEMICALS | RHCD-RGRH CHANNEL COVER REPAIRING | 1 NO | 2017-09-25 | 2017-10-04 | NA | -9 | 0
108 | 4216 | BHARAT EARTH MOVERS LIMITED | TITANIUM CASING- ROLLED | 25 NOS | 2017-10-22 | 2017-10-09 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | 13 | 0
109 | 4206 | SRF LIMITED | DOM FOR HEAT EXCHANGER | 1 NO | 2017-10-03 | 2017-10-12 | NA | -9 | 0
110 | 4178 | KERALA MINERALS AND MINERALS LTD | TITANIUM LINED SCREW | 1 NO | 2017-10-27 | 2017-10-20 | 1% PER MONTH UPTO MAXIMUM OF 5% | 7 | 0
111 | 4223 | BHARAT ELECTRONICS LIMITED | SUPPLY OF CLAMP ASSY FOR UCS JB | 2 NOS | 2017-10-19 | 2017-10-21 | NA | -2 | 0
112 | 4176 | NAVAL PHYSICAL AND OCEANOGRAPHIC LABORATORY | SUPPLY OF ELLIPTICAL BRIDLE ASSY-1NO & FULCRUM PIN-6 NOS | 1 LOT | 2017-11-10 | 2017-10-25 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | 16 | 0
113 | 3905 | BHARAT DYNAMICS LIMITED | TITANIUM SHELL ROLLING | 19 NOS | 2017-10-31 | 2017-10-26 | NA | 5 | 0
114 | 4185 | SRF LIMITED | SUPPLY OF TOP MANHOLE WITH SPARGER, BOTTOM CONE, HAND HOLE COVER AND DISTRIBUTOR PLATE | 1 LOT | 2017-09-28 | 2017-11-02 | 0.5% PER WEEK UPTO MAXIMUM OF 5% | -35 | 57500 | 5 | 2.5 | #REF!
115 | 4166 | PROGRAMME AD | TITANIUM AIR BOTTLE | 20 NOS | 2018-03-13 | 2017-11-14 | 0.5% PER WEEK UPTO MAXIMUM OF 10% | 119 | 0
116 | 4210 | MATERIALS CHEMICALS AND PERFORMANCE INTERMEDIARIES PRIVATE LIMITED | ANNUAL RATE CONTRACT FOR VARIOUS TI FABRICATION AND MAINTENANCE JOBS AT MCPI PLANT SITE, HALDIA | 1 LOT | NA | 2017-11-18 | NA | 0 | 0
TOTAL BILLING

## PMO-Projects
# | Project | Client | PM Name | Short Name | New Schedule Date | Status
1 | 4224 | IOCL-Panipat | Elamaran | EM |  | Done
2 | 4173 | EIL-IOCL Gujrat | Ethiraj | ER
3 | 4232 | IOCL-Technip | Elamaran | EM |  | Done
4 | 4228 | EIL-IOCL-Haldiya | Ethiraj | ER
5 | 4209 | EIL-Dangote | PT Sanjai | PTS
6 | 4218 | CPCL-Chennai | Varun | VG |  | Done
7 | 4201 | EIL Dangote | PT Sanjai | PTS
8 | 4221 | EIL-Dangote | PT Sanjai | PTS
9 | 4235 | MCPI | Vasudevan | VD |  | Done
10 | 4203 | IGCAR | Srivaths Sampath | SS
11 | 4192 | IGCAR | Srivaths Sampath | SS
| 4220 | EIL-Dangote | PT Sanjai | PTS
| 4233 | KMML | Nanda Kumar | NK
| 4230 | Advance System Lab | Nanda Kumar | NK
| 4215 | SRF | Nanda Kumar | NK
| 4213 | SRF | Nanda Kumar | NK
| 4211 | Advance System Lab | Nanda Kumar | NK
| 4236 | SRF | Ethiraj | ER |  | Done