## Sheet1
This is suggested frequency. It can be different. Slowly when people start following the SOPs and they have have challenge with input, output, steps, frequencies we need to refine these further, bring new, retire existing and merge existing SOPs. It is work culture change initiative so it will be slow. But the starting point is when ask people to follow SOP and insist that they either follow and tell the challenges in following. Final audit the implementation.
SOP & Frequencies
# | SOP Name | Frequency
1 | 01-Kanban Board Updation | Daily
2 | 02-Daily Standup Meeting | Daily
3 | 03-Weekly Task-Card Printing | Weekly
4 | 04-Action Register Maintenance | Daily
5 | 05-Project Schedule Creation | Project Planning
6 | 06-Project Schedule Updation | Daily
7 | 07-Issue Management | Daily
8 | 08-Risk Management | Daily
9 | 09-MPR (Monday Project Review) Meetings | Weekly
10 | 10-Project Startup | CRM
11 | 11-Project Output Dispatch | Before and During Despatch
12 | 12-Oracle/MSP Data Sync In Power BI | Weekly
13 | 13-Project Creation In PWA | Post CRM
14 | 14-MSP Licensing And Payment To Microsoft | Monthly
15 | 15-Tonnage Report Based On BOM | Monthly
16 | 16- PM Assignment To a Project | Before CRM
17 | 17-Project Site Creation | Post Project Creation in PWA
18 | 18-Negotiating Duration, Time with Departments Before Schedule Baseline | Before Baseline
19 | 19-Configuration Management, Backup And Restore | Whenever Project Document Created/ Modified
20 | 20-Project Schedule Review | When Project Plan is Ready or Major Changes are incorporated
21 | 21-Project Retrospective Meeting – Not being done. | Project Milestone, Project Closure, Major Event, Monthly (whatever early)
22 | 22-Assign licenses to a new user/existing user | Need Basis