## Sheet1
ROLES & RESPONSIBILITIES OF MR. HARI TAPLIYAL
| OBJECTIVES: | Status | Remarks
1 | To deliver specific PMO services in line with minimum standards, policies and methodologies, focusing on continuously improving processes to optimise operational efficiency.
2 | Delivering best practice project management tools and templates, providing subject matter expertise around project and programme governance.
3 | Developing reporting frameworks, producing standard project reporting templates, reviewing and challenging the content with PMs.
4 | Focusing and entail collaboration with Business, Operations, Finance, Compliance, IT and other functions.
5 | Driving forward improvements in Project quality and ensuring a joined-up approach to PMO and Project Management between the Business and other areas.
6 | Data Analysis and Interpretation - providing reporting and analysis statistics of delivery during the project lifecycle.
7 | You will guide the internal team to manage and maintain resourcing plans, tracking resource availability, managing Dashboard Reporting and be liaison point between Finance, Business and Project Managers.
OTHER ACTIVITIES:
1 | Gap Analysis by review of existing facility/systems, which includes Processes, Systems, Tools and People. |  | Purchase, PPC, Design department and their oracle system integration into EPM still untouched
2 | Planning (estimation, scheduling, budgeting, baseline, who does what and when and how)
3 | Decide PMO head, Project Managers, Project Management Team members from various departments (TEAM)
4 | Conduct workshops (3 days) on fundamental of project management. |  | Because of full availability of resources for full 3 days, small workshop related to the work has been done. More based on the need can be conducted
5 | Conduct workshops (3 days) on MS-EPM enterprise project management & MSP (Microsoft Project) tools. |  | Handson training done for PMs & some PMTs
6 | Refine roles, responsibilities & accountabilities of all. |  | A workshop was conducted on this. R&R document has been shared. It need to be further emphasised.
7 | Train all PMO team Sit with each project manager & PMT and understand what they understood, what they are doing and what they are supposed to do.
8 | Install MS / EPM tools. Recommend for apt tool for TEAM requirement and train the people.
9 | To start with, select 20-30 critical projects and distribute those among existing project managers. |  | All projects are taken
10 | Oversee the plans prepared by Project Managers for these projects and help upload in EPM.
11 | To ensure PM & PMT start using the tool on regular basis.
12 | Design Project Management Dashboard for Senior Management. |  | For CEO & Project Managers some dashboard has been designed
13 | Project Management Process Design. |  | No formal documentation. Planning level system is agreed & implemented. Initiation, Governance & Closure level system will be discussed
14 | Implement the processes in the tool.
KEY DELIVERABLES:
1 | To establish a fully functional PMO on or before 31st January 2018, that covers all the projects effectively and efficiently. |  | PMO is in place with PMO basic dashboard. PMO Head doing weekly reviews with PM and managing projects. PMO dashboard will be refined in coming weeks.
2 | All jobs as per CDD with ZERO LD in the most efficient manner with OPTIMUM use of resources. |  | System is there in place which tells PM & PMO Head the bottleneck in real time so they can take timely action to achieve Zero LD.
3 | Make it clear with the existing Team and framework how many projects max they are capable of handling. |  | It should be based on manhour work of the project. By the end of EPMO implementation project we will know some reasonable number.
4 | Creating the dashboard that must highlight every deviation so that the corrective action can be real time. Dashboard format to be shared with the Management prior to implementing. Dashboard access must be management decision. |  | CEO Level dashboard need to be developed
5 | Guide and ensure proper preparation of Schedules, data capturing, monitoring and job analysis after completion, Job completion meeting to discuss best practices, mistakes, action to be taken to avoid mistakes etc. |  | Integration of actual production timesheet into EPM need to planned.
6 | Hand hold the PMO team at least for 6 months.