## Sheet1
Project Schedule Review Checklist
| Template Version | v0.1
Project Manager Name
Reviewer Name
Project Code
Review Date
|  | Answer | Remarks
Project Level
1 | Team_Stand_Calendar is set at project level. | Not Checked
2 | Start date of project is set correctly. | Not Checked
3 | Project summary task turned on and check project name is correct. | Not Checked
In Project Organizer
1 | No extra/local fields for Task & Resource | Not Checked
2 | No local table | Not Checked
3 | No local view | Not Checked
4 | No local filter | Not Checked
5 | Only these Calendar Team_Stand_Calendar, Team_2Shift_Calendar, TEAM_Night_Calendar | Not Checked
| Resource Level | Not Checked
1 | No local resource in the project schedule | Not Checked
2 | Name of resources should be same as in global checklist | Not Checked
Task level
1 | Check calendar of the tasks (If production task then 2shift calendar else stand calendar) | Not Checked
2 | Check task type (it should be fixed duration mostly) | Not Checked
3 | Project should have marked some activities as milestone (Ticked) | Not Checked
4 | Check dependency are correctly defined (FS, SS, FF, SF should be correctly set) | Not Checked
5 | No dependency should be assigned to a summary task. | Not Checked
6 | Summary task should not have any resources assigned. | Not Checked
7 | Every activity should have resource. | Not Checked
8 | Check number of resources required for an activity correctly assigned. | Not Checked
9 | Lead & Lag is wait / overlap time and it is not estimate of duration. Ensure this is NOT part of the duration/work estimate | Not Checked
10 | Lead & Lag time is correctly set to an activity. | Not Checked
11 | Duration of every activities are correctly estimated and assigned. Use the benckmark estimate provided by Production. | Not Checked
12 | Unit number of resources assigned to a task multiplied by the duration should be tallied to the work. | Not Checked
13 | If required estimate the "work" column again. | Not Checked
14 | No task should have constraint other than ASAP (As Soon As Possible), unless there is some genuine reason | Not Checked
15 | No task should have estimated work / duration with question mark (?), unless there is some reason. | Not Checked
During Project Lifecycle
1. ABG PBG Information is correctly updated. Date, Amount, Remaining Work.
2. MilestoneName should be selected for all the milestone in the project
3. Actual of work, remaining work, duration, finish date, start date is correctly updated
4. Never ever overwrite any baseline information
5. If any commitment change happens then record that information in "EarlierCommitment" column then only update the date in finish date. Use this only for task finish date and nothing else. If commitment change more than once use comma ",". For example 2 times commitment change can be written like this 1-Apr-17, 12-Apr-17. Do not write anything else in this column. Write the date in this format only.