## Datewise Job Despatch-31-Dec-18
Project | Despatch Name | CDD | BL FD | New FinishDate | ClientName | Des.Qty | Des.Val (Lakhs) | Pr.%WC | Task%WC | Pr.Qty | Pr.Val (Lakhs) | Project Budget (Hrs) | CompletionStatus | PM
4106 | Finished goods - Spares | 2018-09-01 08:00 |  | 2018-09-27 17:00 | Thermax | 1 | 5 | 11 | 0 | 1 | 5 |  | 8-Project Completed | Viswanathan
4161 | DESPATCH TO SITE | 2018-01-03 08:00 | 2017-10-09 12:00 | 2018-03-06 12:30 | BPCL | 3 | 39.16 | 100 | 100 | 3 | 41.2 | 2622 | 8-Project Completed | Anand
4166 | Despatch | 2018-03-31 08:00 |  | 2017-04-13 16:30 | Programme AD | 10 | 89 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4166 | Despatch | 2018-03-31 08:00 |  | 2017-04-13 16:30 | Programme AD | 20 | 178 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4166 | Despatch | 2018-03-31 08:00 |  | 2017-12-12 09:59 | Programme AD | 20 | 178 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4167 | DESPATCH TO SITE | 2017-10-07 08:00 | 2017-10-17 17:00 | 2017-12-22 17:00 | BORL | 1 | 67.21 | 100 | 100 | 1 | 67.2 | 2772 | 8-Project Completed | Anand
4169 | DESPATCH | 2017-12-20 08:00 | 2017-09-29 14:42 | 2017-09-29 14:44 | Essar | 1 | 15.29 | 100 | 100 | 2 | 214 | 8777 | 8-Project Completed | Varun
4169 | Despatch | 2017-12-20 08:00 | 2017-10-27 13:09 | 2018-03-16 14:00 | Essar | 1 | 198.71 | 100 | 100 | 2 | 214 | 8777 | 8-Project Completed | Varun
4170 | Depatch 4170F | 2018-01-01 06:00 | 2018-03-26 21:30 | 2018-03-26 21:30 | IOCL-EIL | 1 | 80.05 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170A1 | 2018-01-01 06:00 | 2018-02-16 20:30 | 2018-02-16 20:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170A2 | 2018-01-01 06:00 | 2018-02-16 20:30 | 2018-02-16 20:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170B1 | 2018-01-01 06:00 | 2018-01-30 20:30 | 2018-01-30 20:30 | IOCL-EIL | 1 | 62.03 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170B2 | 2018-01-01 06:00 | 2018-01-30 20:30 | 2018-01-30 20:30 | IOCL-EIL | 1 | 62.03 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170C1 | 2018-01-01 06:00 | 2018-02-16 21:30 | 2018-02-16 21:30 | IOCL-EIL | 1 | 19.76 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170C2 | 2018-01-01 06:00 | 2018-02-16 21:30 | 2018-02-16 21:30 | IOCL-EIL | 1 | 19.76 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170D1 | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 27.7 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170D2 | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 27.7 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170E | 2018-01-01 06:00 | 2018-03-16 21:30 | 2018-03-16 21:30 | IOCL-EIL | 1 | 30.92 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170G1 | 2018-01-01 06:00 | 2018-02-28 21:30 | 2018-02-28 21:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170G2 | 2018-01-01 06:00 | 2018-02-28 21:30 | 2018-02-28 21:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170H | 2018-01-01 06:00 | 2018-03-28 20:30 | 2018-03-28 20:30 | IOCL-EIL | 1 | 118.32 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170I1 | 2018-01-01 06:00 | 2018-03-16 21:30 | 2018-03-16 21:30 | IOCL-EIL | 1 | 32.63 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170I2 | 2018-01-01 06:00 | 2018-03-13 20:30 | 2018-03-13 20:30 | IOCL-EIL | 1 | 32.63 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J1 | 2018-01-01 06:00 | 2018-02-23 21:30 | 2018-02-23 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J2A | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J2B | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170K1 | 2018-01-01 06:00 | 2018-03-24 20:30 | 2018-03-24 20:30 | IOCL-EIL | 1 | 13.4 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170K2 | 2018-01-01 06:00 | 2018-03-24 21:30 | 2018-03-24 21:30 | IOCL-EIL | 1 | 13.4 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170L | 2018-01-01 06:00 | 2018-03-14 20:30 | 2018-03-14 20:30 | IOCL-EIL | 1 | 32.72 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4174 | DESPATCH | 2017-12-14 08:00 | 2017-12-30 17:10 | 2018-02-05 17:00 | IOCL | 1 | 57.79 | 100 | 100 | 1 | 59.4 | 4688 | 8-Project Completed | Elamaran
4180 | Despatch | 2017-12-29 08:00 | 2018-01-22 21:30 | 2018-01-22 21:30 | NIOT | 1 | 43.08 | 100 | 100 | 2 | 86.2 | 1696 | 8-Project Completed | Varun
4180 | Despatch | 2017-12-29 08:00 | 2018-01-23 12:30 | 2018-01-23 12:30 | NIOT | 1 | 43.08 | 100 | 100 | 2 | 86.2 | 1696 | 8-Project Completed | Varun
4182 | DESPATCH | 2018-01-10 08:00 | 2017-09-05 12:21 | 2018-02-05 17:00 | UPL | 6 | 144 | 100 | 100 | 6 | 144 | 4812 | 8-Project Completed | Ethiraj
4183 | Despatch | 2018-01-04 08:00 | 2018-02-27 20:22 | 2018-03-31 10:00 | IOCL | 1 | 113.14 | 100 | 100 | 1 | 115.4 | 11102 | 8-Project Completed | Ethiraj
4197 | Despatch | 2018-01-06 08:00 | 2018-01-05 09:50 | 2018-02-03 08:36 | ASL | 8 | 92.1 | 100 | 100 | 8 | 92.1 | 13200 | 8-Project Completed | Anand
4211 | Despatch | 2018-07-17 08:00 | 2018-04-30 07:50 | 2018-04-30 14:47 | Advanced System Laboratory | 25 | 142.5 | 100 | 100 | 25 | 142.5 | 4450 | 8-Project Completed | Varun
4213 | Despatch | 2018-02-27 08:00 | 2018-01-30 16:00 | 2018-03-03 09:00 | SRF | 1 | 28.75 | 100 | 100 | 1 | 28.8 | 1220 | 8-Project Completed | Elamaran
4215 | Despatch | 2017-11-30 08:00 | 2018-01-19 15:30 | 2018-02-17 18:00 | SRF | 1 | 10.5 | 100 | 100 | 1 | 10.5 | 336 | 8-Project Completed | Varun
4216 | Product Transportation to Site | 2018-07-31 08:30 | 2018-06-16 17:30 | 2019-02-15 17:30 | BEML | 5 | 0.8 | 20 | 0 | 75 | 12 | 1800 | 9-On Hold | Varun
4218 | Despatch | 2018-08-11 08:00 | 2018-07-20 21:54 | 2018-08-30 14:00 | CPCL | 1 | 79.07 | 100 | 100 | 1 | 80.3 | 7383 | 8-Project Completed | Varun
4227 | Despatch | 2018-08-10 08:30 | 2018-03-17 14:30 | 2018-03-17 14:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 2018-05-19 11:30 | 2018-05-11 09:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 2018-05-19 11:30 | 2018-06-06 12:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 |  | 2018-07-20 12:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4230 | Despatch | 2018-06-30 08:00 | 2018-03-31 18:30 | 2018-03-31 18:30 | ASL | 7 | 36.4 | 100 | 100 | 10 | 52 | 1600 | 8-Project Completed | Varun
4230 | Despatch | 2018-06-30 08:00 | 2018-04-26 18:00 | 2018-04-30 20:22 | ASL | 3 | 15.6 | 100 | 100 | 10 | 52 | 1600 | 8-Project Completed | Varun
4232 | Despatch | 2018-07-07 08:00 | 2018-06-16 10:30 | 2018-07-05 17:00 | IOCL-TECHNIP | 1 | 52.48 | 100 | 100 | 1 | 52.5 | 4245 | 8-Project Completed | Elamaran
4233 | Despatch | 2018-01-22 08:00 | 2017-12-30 17:30 | 2018-01-23 17:30 | KMML | 22 | 0.81 | 100 | 100 | 22 | 1 | 12 | 8-Project Completed | Varun
4239 | Invoice to Customer | 2018-02-03 08:30 | 2018-03-16 12:30 | 2018-03-17 12:30 | IGCAR | 1 | 9.47 | 100 | 100 | 1 | 9.5 | 260 | 8-Project Completed
4240 | Despatch | 2018-07-20 08:30 | 2018-05-22 19:30 | 2019-03-26 19:30 | RCI | 2 | 19.4 | 18 | 0 | 2 | 19.4 | 840 | 9-On Hold | Varun
4240 | Final Inspection & Dispatch | 2018-07-20 08:30 | 2018-05-22 19:30 | 2019-03-26 19:30 | RCI |  |  | 18 | 0 | 2 | 19.4 | 840 | 9-On Hold | Varun
4241 | Despatch - 4241 | 2018-08-21 08:00 | 2018-08-10 09:30 | 2019-01-11 21:30 | IOCL-EIL | 1 | 5 | 63 | 0 | 1 | 5 | 2059 | B-Production in Progress | Elamaran
4242 | Despatched | 2018-03-10 08:00 | 2018-03-13 17:00 | 2018-03-13 17:00 | KMML | 1 | 2.52 | 100 | 100 | 1 | 2.5 | 50 | 8-Project Completed | PMO
4243 | despatch through courier | 2018-03-10 08:00 | 2018-03-05 17:30 | 2018-03-05 17:30 | Apid Engineer | 1 | 0.3 | 100 | 100 | 1 | 0.3 | 6 | 8-Project Completed | PMO
4245 | Finished good - Pump spares | 2018-03-31 08:30 | 2018-03-17 09:30 | 2018-08-27 17:30 | Grasim | 1 | 1.73 | 100 | 100 | 1 | 1.7 | 280 | 8-Project Completed | Viswanathan
4246 | Despatch-4246 | 2018-11-15 08:00 | 2018-11-13 16:41 | 2018-12-31 17:00 | SRF | 1 | 96 | 99 | 0 | 1 | 96 | 2955 | 6-QC Completed | Ethiraj
4247 | Despatch | 2018-06-30 08:00 |  | 2018-12-29 19:29 | SSIS |  |  | 99 | 0 | 2 | 20.9 | 2043 | 5-Production Completed | Varun
4247 | Payment followup and despatch | 2018-06-30 08:00 |  | 2018-12-29 19:29 | SSIS | 2 | 20.93 | 99 | 0 | 2 | 20.9 | 2043 | 5-Production Completed | Varun
4248 | Product Transportation to Site | 2018-06-18 08:30 | 2018-04-19 16:30 | 2018-06-27 15:30 | KMML | 3 | 1.32 | 100 | 100 | 3 | 1.3 | 70 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-07-02 14:30 | 2018-07-24 11:00 | SVCI | 2 | 21.76 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-06-22 20:30 | 2018-07-24 13:00 | SVCI | 2 | 21.76 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-06-27 12:30 | 2018-07-27 12:30 | SVCI | 2 | 22.26 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4250 | Finished good - Pump spares | 2018-03-31 08:30 | 2018-05-04 08:31 | 2018-08-21 17:30 | Grasim | 3 | 3.06 | 100 | 100 | 3 | 3.1 | 312 | 8-Project Completed | Viswanathan
4251 | Final Assembly & Machining | 2018-08-05 08:30 |  | 2018-11-28 16:30 | NPOL | 1 | 37.34 | 100 | 100 | 1 | 37.3 | 1330 | 8-Project Completed | Varun
4252 | Despatch | 2018-12-31 08:30 |  | 2019-01-02 19:30 | NPOL | 1 | 76 | 83 | 0 | 1 | 76 | 3130 | B-Production in Progress | Varun
4253 | Despatch | 2018-06-14 08:30 | 2018-06-13 09:30 | 2018-06-26 09:30 | KMML | 4 | 3.99 | 100 | 100 | 4 | 4 | 400 | 8-Project Completed | Elamaran
4254 | Despatch | 2018-10-21 08:30 | 2018-10-01 14:30 | 2018-10-23 18:30 | IOCL | 1 | 31.7 | 100 | 100 | 1 | 33 | 2957 | 8-Project Completed | Varun
4257 | Despatch | 2018-09-10 08:00 | 2018-08-21 09:30 | 2018-11-10 17:00 | Keltron | 1 | 43 | 100 | 100 | 1 | 43 | 2370 | 8-Project Completed | Elamaran
4258 | Despatch | 2018-10-13 08:00 | 2018-10-03 21:00 | 2018-09-29 19:30 | RRCAT | 5 | 13.5 | 100 | 100 | 5 | 13.5 | 530 | 8-Project Completed | Elamaran
4259 | Despatch | 2018-10-04 08:00 | 2018-09-17 12:30 | 2018-09-29 16:00 | Orient Paper Mills | 1 | 20.3 | 100 | 100 | 1 | 20.3 | 2720 | 8-Project Completed | Ethiraj
4260 | Despatch-4260-No1 No2 | 2018-10-04 08:00 | 2018-10-04 16:30 | 2019-01-03 08:00 | CCM CHEMICALS SDN BHD | 2 | 43.47 | 99 | 0 | 2 | 43.5 | 4780 | 6-QC Completed | Ethiraj
4261 | Finished good despatch | 2018-05-15 08:00 | 2018-03-05 17:30 | 2018-05-04 15:30 | DCW Limited | 1 | 9 | 41 | 0 | 1 | 9 | 400 | 8-Project Completed | Viswanathan
4262 | Despatch | 2018-09-15 08:00 | 2018-03-05 17:30 | 2018-09-01 17:00 | Tata Chemicals Ltd, Mithapur | 4 | 0.79 | 100 | 100 | 4 | 0.8 | 100 | 8-Project Completed | Ethiraj
4263 | Product Transportation to Site - 1st lot | 2018-10-17 08:00 | 2018-10-15 07:30 | 2018-09-27 08:00 | Kutch Chemical Industries Limited | 6 | 92.4 | 95 | 100 | 12 | 189.8 | 4320 | 7-Despatched | Ethiraj
4263 | Product Transportation to Site - 2nd lot | 2018-10-17 08:00 |  | 2018-10-26 16:00 | Kutch Chemical Industries Limited | 6 | 97.4 | 95 | 100 | 12 | 189.8 | 4320 | 7-Despatched | Ethiraj
4264 | Finished goods | 2018-07-15 08:00 | 2018-05-31 17:30 | 2018-05-31 17:30 | CAL, TEAM's Group company | 20 | 18.3 | 100 | 100 | 20 | 18.3 | 680 | 8-Project Completed | Viswanathan
4265 | Finished goods | 2018-10-14 08:00 |  | 2018-09-29 20:30 | The Kerala Minerals & Metals Ltd | 1 | 5.3 | 100 | 100 | 1 | 5.3 | 925 | 8-Project Completed | Elamaran
4268 | Despatch-4268 | 2018-12-24 08:30 | 2018-12-20 12:30 | 2019-01-15 09:30 | Technip Mumbai | 1 | 253.11 | 81 | 0 | 1 | 253.1 | 17360 | B-Production in Progress | Ethiraj
4269 | Despatch-4269 | 2018-12-25 08:30 | 2018-11-03 17:30 | 2018-12-31 14:30 | SPX FLOW | 2 | 69 | 96 | 0 | 2 | 69 | 1560 | B-Production in Progress | Ethiraj
4270 | Finished good - Anode | 2018-07-03 08:30 |  | 2018-05-02 17:30 | VXL Life sceinces, Mumbai | 1 | 0.8 | 0 | 0 | 2 | 1.6 | 300 | 8-Project Completed | Viswanathan
4270 | Finished good - Cathode | 2018-07-03 08:30 |  | 2018-06-11 17:30 | VXL Life sceinces, Mumbai | 1 | 0.9 | 0 | 0 | 2 | 1.6 | 300 | 8-Project Completed | Viswanathan
4271 | Finished goods | 2018-07-10 08:00 | 2018-07-05 17:30 | 2018-09-28 08:00 | KMML | 1 | 0.34 | 100 | 100 | 1 | 0.3 | 4 | 8-Project Completed | Elamaran
4273 | Despatch | 2018-09-27 08:00 | 2018-08-23 09:30 | 2018-09-25 09:30 | KMML, Kochi | 60 | 0.86 | 100 | 100 | 60 | 0.9 | 100 | 8-Project Completed | Varun
4274 | Despatch | 2019-03-30 08:00 |  | 2018-07-27 17:30 | NIOT | 4 | 0.46 | 100 | 100 | 10 | 1.2 | 100 | 5-Production Completed | Varun
4274 | Despatch | 2019-03-30 08:00 |  | 2018-08-24 17:30 | NIOT | 1 | 0.12 | 100 | 100 | 10 | 1.2 | 100 | 5-Production Completed | Varun
4276 | Finished good | 2018-06-30 08:00 |  | 2018-06-25 12:00 | Praxair | 1 | 0.89 | 20 | 0 | 1 | 0.9 |  | 8-Project Completed | Viswanathan
4279 | Finished goods | 2018-10-30 08:00 |  | 2018-10-29 17:00 | CCAL | 1 | 0.65 | 100 | 100 | 1 | 0.7 | 100 | 8-Project Completed | Hariprasath
4280 | Despatch | 2018-12-12 08:00 | 2018-10-03 09:30 | 2018-09-29 13:30 | NSTL, Vizag | 6 | 30 | 100 | 100 | 6 | 30 | 1650 | 8-Project Completed | Elamaran
4282 | Finished goods | 2018-10-30 08:00 |  | 2018-10-29 17:00 | CCAL | 1 | 0.32 | 100 | 100 | 1 | 0.3 | 3 | 8-Project Completed | Hariprasath
4283 | Finished goods - 1st Lot | 2018-07-15 08:00 | 2018-05-31 17:30 | 2018-07-30 14:30 | CAL, TEAM's Group company | 22 | 23.68 | 100 | 100 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 2nd Lot | 2018-07-15 08:00 |  | 2018-08-18 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 3rd Lot | 2018-07-15 08:00 |  | 2018-08-29 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 4th Lot | 2018-07-15 08:00 |  | 2018-09-26 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 5th Lot | 2018-07-15 08:00 |  | 2018-10-23 14:30 | CAL, TEAM's Group company | 47 | 49.77 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4284 | Despatch-4284-2Nos | 2019-03-25 08:00 | 2019-03-15 13:30 | 2019-02-27 08:30 | Larsen & Toubro | 2 | 49.6 | 11 | 0 | 2 | 49.6 | 1640 | 4-Purchase Completed | Hariprasath
4285 | Finished goods | 2018-10-30 08:00 |  | 2018-10-29 17:00 | Tata Chemicals Limited | 1 | 0.3 | 100 | 100 | 1 | 0.3 |  | 8-Project Completed | Hariprasath
4286 | Despatch | 2019-02-15 08:30 | 2019-02-08 17:00 | 2019-02-08 17:00 | TVG SRAAC, Kurnool |  |  | 60 | 0 | 10 | 98.5 | 16300 | B-Production in Progress | Hariprasath
4286 | Despatch-4286-10Nos | 2019-02-15 08:30 | 2019-02-08 17:00 | 2019-02-08 17:00 | TVG SRAAC, Kurnool | 10 | 98.5 | 60 | 0 | 10 | 98.5 | 16300 | B-Production in Progress | Hariprasath
4287 | Inspection & dispatch | 2018-12-30 08:00 |  | 2018-10-26 17:00 | VEM Technologies, Hyd | 24 | 5.23 | 100 | 100 | 24 | 5.2 |  | 7-Despatched | Hariprasath
4288 | Finished goods | 2018-11-21 08:00 |  | 2018-10-23 17:00 | Lords Chloro Alkalies | 2 | 0.55 | 100 | 100 | 1 | 0.6 | 14 | 8-Project Completed | Hariprasath
4290 | Delivery - 10 nos | 2018-10-06 08:00 |  | 2018-09-17 17:30 | NIOT | 10 | 0.1 | 100 | 100 | 10 | 0.1 | 100 | 8-Project Completed | Hariprasath
4294 | Finished good | 2018-10-18 08:00 |  | 2018-10-18 17:00 | Kavinaya (Praxair) | 1 | 0.89 | 0 | 0 | 1 | 0.9 |  | 8-Project Completed | Hariprasath
4295 | Despatch-4295-2Nos | 2019-01-18 08:30 |  | 2019-01-15 17:30 | KMML | 2 | 10.68 | 82 | 0 | 2 | 10.7 | 860 | B-Production in Progress | Hariprasath
4296 | Despatch 4256-A | 2019-08-16 08:30 | 2019-01-08 10:30 | 2019-06-10 15:30 | Technimont | 1 | 200.78 | 3 | 0 | 20 | 1390 | 5282 | 2-Design Completed | Elamaran
4297 | Despatch-4297 | 2019-04-16 08:30 |  | 2019-03-29 17:30 | CCM | 4 | 16.66 | 45 | 0 | 4 | 16.7 | 700 | 2-Design Completed | Vinothkumar
4298 | Inspection & dispatch | 2018-12-30 08:00 |  | 2018-11-28 17:00 | BDL | 12 | 1.92 | 100 | 100 | 12 | 1.9 |  | 8-Project Completed | Hariprasath
4300 | Despatch-4300 | 2019-03-31 08:30 | 2019-03-28 17:30 | 2019-03-26 17:30 | YUSUF BIN AHMED KANOO W.L.L., | 64 | 15.67 | 22 | 0 | 64 | 15.7 | 448 | 3-PPC Completed | Vinothkumar
4301 | Despatch | 2019-04-03 08:30 |  | 2019-03-18 17:30 | MCCPTA | 1 | 2.53 | 14 | 0 | 1 | 2.5 | 8 | 3-PPC Completed | Hariprasath
4302 | Despatch-4302 | 2019-05-08 08:00 |  | 2019-05-04 09:30 | Sirpur Paper Mills | 1 | 10.07 | 39 | 0 | 1 | 10.1 | 1430 | 2-Design Completed | Vinothkumar
4303 | Inspection & dispatch | 2018-12-30 08:00 |  | 2018-11-15 17:00 | BDL | 1 | 0.05 | 0 | 0 | 1 | 0.1 |  | 8-Project Completed | Hariprasath
4305 | Despatch-4295-30Nos | 2019-01-03 08:30 | 2019-01-23 17:30 | 2019-01-25 12:30 | Modern Engineering & Plastics | 30 | 0.74 | 2 | 0 | 30 | 0.7 | 280 | 3-PPC Completed | Hariprasath
4309 | Despatch | 2019-03-23 08:00 | 2019-02-20 09:00 | 2019-02-20 09:00 | KMML | 40 | 0.51 | 8 | 0 | 40 | 0.5 | 8 | 3-PPC Completed | Hariprasath
4173-02 | DESPATCH | 2018-04-07 06:00 | 2018-01-09 06:04 | 2018-03-31 18:00 | IOCL-EIL | 2 | 111.72 | 100 | 100 | 2 | 111.7 | 9702 | 8-Project Completed | Ethiraj
4173-108 | Despatch | 2018-04-07 06:00 | 2018-03-31 13:30 | 2018-03-31 13:30 | IOCL-EIL | 1 | 65.62 | 100 | 100 | 1 | 65.6 | 5579 | 8-Project Completed | Ethiraj
4173-126 | DESPATCH | 2018-04-07 06:00 | 2018-03-30 08:40 | 2018-03-30 08:40 | IOCL-EIL | 2 | 43.75 | 100 | 100 | 2 | 43.8 | 4352 | 8-Project Completed | Ethiraj
4192-HC 150-1 | Despatch | 2019-01-07 08:00 | 2018-05-14 13:12 | 2018-09-05 17:00 | IGCAR | 1 | 66.77 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-2 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2018-12-27 09:30 | IGCAR | 1 | 66.77 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-2 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2018-12-27 09:30 | IGCAR |  |  | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-3 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-04-30 12:30 | IGCAR | 1 | 66.77 | 66 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-3 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-04-30 12:30 | IGCAR |  |  | 66 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-4 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-4 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR |  |  | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-5 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-5 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR |  |  | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-6 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-6 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR |  |  | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-VC-100 | Despatch | 2019-01-07 08:30 | 2018-10-09 08:30 | 2018-11-30 08:30 | IGCAR | 1 | 2.07 | 100 | 100 | 1 | 2.1 | 80 | 8-Project Completed | Varun
4192-VC-600 | Despatch | 2019-01-07 08:30 | 2018-10-09 08:30 | 2018-11-30 08:30 | IGCAR | 1 | 2.55 | 100 | 100 | 1 | 2.6 | 200 | 8-Project Completed | Varun
4201-0004 | Despatch | 2018-08-06 08:00 |  | 2018-09-29 14:00 | Dangote | 4 | 386.56 | 100 | 0 | 4 | 386.6 | 33620 | 6-QC Completed | Anand
4201-0005 | Despatch | 2018-08-31 08:00 |  | 2018-09-29 15:30 | Dangote | 4 | 301.44 | 100 | 0 | 4 | 301.4 | 26218 | 6-QC Completed | Anand
4203-AT 630-2 | Despatch | 2019-02-14 08:30 | 2018-07-27 22:00 | 2018-08-23 22:00 | IGCAR | 1 | 2.91 | 100 | 100 | 1 | 2.9 | 575 | 8-Project Completed | Varun
4203-AT 630-4,5,6 | Despatch | 2019-02-14 08:30 | 2018-07-27 22:00 | 2018-11-30 22:00 | IGCAR | 1 | 2.91 | 100 | 100 | 1 | 8.7 | 1725 | 8-Project Completed | Varun
4203-AT-400 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 22 | 50.6 | 0 | 0 | 22 | 50.6 | 8074 | 9-On Hold | Varun
4203-AT-400N | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 7 | 16.31 | 0 | 0 | 7 | 16.3 | 2628 | 9-On Hold | Varun
4203-AT-500 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 14 | 38.78 | 0 | 0 | 14 | 38.8 | 7393 | 9-On Hold | Varun
4203-AT-630 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 20 | 58.2 | 0 | 0 | 20 | 58.2 | 11523 | 9-On Hold | Varun
4203-AT-630-10 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-03 08:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 575 | B-Production in Progress | Varun
4203-AT-630-3 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-05 08:30 | IGCAR | 1 | 2.91 | 91 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-7 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2018-12-31 08:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-8 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2018-12-31 20:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-9 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-03 08:30 | IGCAR | 1 | 2.91 | 98 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630N | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 2 | 6.02 | 0 | 0 | 2 | 6 | 1155 | 9-On Hold | Varun
4203-AT-720 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 11 | 33.99 | 0 | 0 | 11 | 34 | 7070 | 9-On Hold | Varun
4203-RCAT-125 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 16 | 25.12 | 0 | 0 | 16 | 25.1 | 3057 | 9-On Hold | Varun
4203-RCAT-500 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 6 | 15.96 | 0 | 0 | 6 | 16 | 3528 | 9-On Hold | Varun
4203-RCAT-90 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 16 | 20.96 | 0 | 0 | 16 | 21 | 2165 | 9-On Hold | Varun
4203-RCVC-50-1 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 20:30 | IGCAR | 1 | 1.04 | 74 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-2 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 16:30 | IGCAR | 1 | 1.04 | 71 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-3 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 14:00 | IGCAR | 1 | 1.04 | 75 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-4 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 14:00 | IGCAR | 1 | 1.04 | 75 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4209-A&F | Despatch | 2018-10-01 06:00 |  | 2019-02-05 16:57 | Dangote | 2 | 88.35 | 51 | 0 | 2 | 88.4 | 9336 | B-Production in Progress | Anand
4209-B&G | Despatch | 2018-10-01 06:00 |  | 2018-11-20 17:30 | Dangote | 2 | 34.89 | 100 | 0 | 2 | 34.9 | 2086 | 6-QC Completed | Anand
4209-C&H | Despatch | 2018-10-01 06:00 |  | 2019-03-20 10:30 | Dangote | 2 | 221.48 | 46 | 0 | 2 | 221.5 | 22160 | B-Production in Progress | Anand
4209-D&I | Despatch | 2018-10-01 06:00 |  | 2018-12-28 11:00 | Dangote | 2 | 25.54 | 100 | 0 | 2 | 25.5 | 1450 | 6-QC Completed | Anand
4209-E&J | Despatch | 2018-10-01 06:00 |  | 2018-12-15 17:30 | Dangote | 2 | 10.37 | 99 | 0 | 2 | 10.4 | 570 | 6-QC Completed | Anand
4209-K&L | Despatch | 2018-10-01 06:00 |  | 2018-12-18 17:30 | Dangote | 4 | 21.82 | 100 | 0 | 4 | 21.8 | 1176 | 6-QC Completed | Anand
4209-M | Despatch | 2018-10-01 06:00 |  | 2019-01-08 12:03 | Dangote | 2 | 29.2 | 91 | 0 | 2 | 29.2 | 1560 | B-Production in Progress | Anand
4209-N | Despatch | 2018-10-01 06:00 |  | 2019-01-08 10:45 | Dangote | 1 | 17.01 | 91 | 0 | 1 | 17 | 1080 | B-Production in Progress | Anand
4209-O | Despatch | 2018-10-01 06:00 |  | 2018-12-14 17:30 | Dangote | 2 | 15.99 | 100 | 0 | 2 | 16 | 952 | 6-QC Completed | Anand
4209-P | Despatch | 2018-10-01 06:00 |  | 2019-01-08 14:02 | Dangote | 2 | 27.34 | 91 | 0 | 2 | 27.3 | 1502 | B-Production in Progress | Anand
4209-Q | Despatch | 2018-10-01 06:00 |  | 2018-12-15 12:30 | Dangote | 2 | 21.04 | 100 | 0 | 2 | 21 | 1142 | 6-QC Completed | Anand
4209-R&S | Despatch | 2018-10-01 06:00 |  | 2018-11-17 17:30 | Dangote | 2 | 11.79 | 100 | 0 | 2 | 11.8 | 518 | 6-QC Completed | Anand
4220-A1001 | Despatch 4220 A - AB | 2019-05-26 08:00 |  | 2019-01-18 17:30 | Dangote | 2 | 302.87 | 95 | 0 | 4 | 605.7 | 57103 | B-Production in Progress | Anand
4220-A1001 | Despatch 4220 A - CD | 2019-05-26 08:00 |  | 2019-02-11 17:30 | Dangote | 2 | 302.87 | 95 | 0 | 4 | 605.7 | 57103 | B-Production in Progress | Anand
4220-B1003 | Despatch | 2019-05-26 06:00 |  | 2019-12-31 17:30 | Dangote | 2 | 204.5 | 0 | 0 | 2 | 204.5 | 20354 | 2-Design Completed | Anand
4220-D1006 | Despatch | 2019-05-26 08:00 |  | 2020-01-27 08:44 | Dangote | 2 | 199.53 | 3 | 0 | 2 | 199.5 | 20080 | 4-Purchase Completed | Anand
4220-E1007 | Despatch | 2019-05-26 08:00 |  | 2019-03-28 17:30 | Dangote | 2 | 304.81 | 0 | 0 | 2 | 304.8 | 24348 | 4-Purchase Completed | Anand
4220-F1008 | Despatch | 2019-05-26 08:00 |  | 2019-06-29 17:30 | Dangote | 1 | 16.83 | 0 | 0 | 1 | 16.8 | 2053 | 4-Purchase Completed | Anand
4220-G1009-1 | Despatch | 2019-05-26 08:00 |  | 2019-07-17 17:30 | Dangote | 2 | 92.59 | 0 | 0 | 2 | 92.6 | 9310 | 4-Purchase Completed | Anand
4220-H1010 | Despatch | 2019-05-26 08:00 |  | 2019-03-27 17:30 | Dangote | 1 | 14.16 | 13 | 0 | 1 | 14.2 | 13494 | 4-Purchase Completed | Anand
4220-I1011 | Despatch | 2018-10-02 08:00 |  | 2019-05-28 15:00 | Dangote | 4 | 799.3 | 0 | 0 | 4 | 799.3 | 82197 | 4-Purchase Completed | Anand
4220-J1012 | Despatch | 2019-05-26 06:00 |  | 2019-07-12 17:00 | Dangote | 4 | 600.48 | 1 | 0 | 4 | 600.5 | 77331 | 4-Purchase Completed | Anand
4220-K1013 | Despatch | 2019-05-26 08:00 |  | 2019-08-23 11:00 | Dangote | 2 | 1057.37 | 0 | 0 | 2 | 1057.4 | 65261 | 4-Purchase Completed | Anand
4220-L1014 | Despatch | 2019-05-26 08:00 |  | 2019-07-18 10:28 | Dangote | 1 | 6.4 | 6 | 0 | 1 | 6.4 | 983 | 4-Purchase Completed | Anand
4220-N1011 | Despatch | 2019-05-26 08:00 |  | 2019-07-20 08:44 | Dangote | 1 | 38.85 | 0 | 0 | 1 | 38.9 | 7561 | 4-Purchase Completed | Anand
4220-O1011 | Despatch | 2019-05-26 08:00 |  | 2019-09-24 10:44 | Dangote | 1 | 38.26 | 0 | 0 | 1 | 38.3 | 13116 | 3-PPC Completed | Anand
4221-2403 | Despatch | 2018-09-01 08:00 |  | 2019-10-31 17:30 | Dangote | 1 | 10.66 | 3 | 0 | 1 | 10.7 | 517 | 2-Design Completed | Anand
4221-7001 | Despatch | 2018-09-01 08:00 |  | 2019-10-31 17:30 | Dangote | 1 | 31.08 | 29 | 0 | 1 | 31.1 | 872 | 2-Design Completed | Anand
4221-9101 | Despatch | 2018-09-01 08:00 | 2018-10-06 09:58 | 2019-11-05 17:58 | Dangote | 1 | 48.85 | 1 | 0 | 1 | 48.9 | 425 | 2-Design Completed | Anand
4224-103 | Despatch 4224-A | 2018-06-11 08:00 | 2018-05-31 20:30 | 2018-06-08 20:30 | IOCL-EIL | 1 | 33.03 | 100 | 100 | 1 | 35.5 | 3066 | 8-Project Completed | Elamaran
4224-309 | Despatch 4224-B | 2018-06-11 08:00 | 2018-06-06 17:40 | 2018-06-08 20:40 | IOCL-EIL | 1 | 16.98 | 100 | 100 | 1 | 17 | 739 | 8-Project Completed | Elamaran
4228-010 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-06-30 13:01 | 2017-11-09 17:00 | IOCL-EIL | 1 | 39.79 | 97 | 100 | 2 | 79.6 | 5040 | 8-Project Completed | Ethiraj
4228-010 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-07-20 07:41 | 2018-11-09 15:30 | IOCL-EIL | 1 | 39.79 | 97 | 100 | 2 | 79.6 | 5040 | 8-Project Completed | Ethiraj
4228-014 | Clearance By TPI | 2018-07-31 08:00 | 2018-07-02 09:52 | 2018-11-05 18:30 | IOCL-EIL | 1 | 11.57 | 100 | 100 | 2 | 23.1 | 1736 | 8-Project Completed | Ethiraj
4228-014 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-06-30 13:01 | 2018-11-05 17:00 | IOCL-EIL | 1 | 11.57 | 100 | 100 | 2 | 23.1 | 1736 | 8-Project Completed | Ethiraj
4228-102 | Shipping | 2018-07-31 08:00 | 2018-07-17 09:00 | 2018-11-10 17:00 | IOCL-EIL | 1 | 7.24 | 100 | 100 | 1 | 7.2 | 814 | 8-Project Completed | Ethiraj
4237-A | Despatch | 2018-09-08 08:00 | 2018-11-08 18:30 | 2019-01-30 10:50 | IOCL-EIL | 1 | 102.51 | 85 | 0 | 1 | 102.5 | 5670 | B-Production in Progress | Ethiraj
4237-B | Despatch | 2018-09-08 08:00 | 2018-08-09 19:02 | 2019-01-21 12:00 | IOCL-EIL | 1 | 63.87 | 88 | 0 | 1 | 63.9 | 3100 | B-Production in Progress | Ethiraj
4237-C | Despatch | 2018-09-08 08:00 | 2018-12-05 07:05 | 2019-01-21 21:24 | IOCL-EIL | 1 | 85.17 | 88 | 0 | 1 | 85.2 | 5070 | B-Production in Progress | Ethiraj
4237-D | Despatch | 2018-09-08 08:00 | 2018-08-08 18:30 | 2019-01-14 18:30 | IOCL-EIL | 4 | 48.45 | 85 | 0 | 1 | 48.5 | 2320 | B-Production in Progress | Ethiraj
4238-49 | Despatch-4238(A) | 2018-10-12 08:30 | 2018-09-24 17:30 | 2018-10-12 17:30 | HPCL | 1 | 57.65 | 100 | 100 | 1 | 57.7 | 5267 | 8-Project Completed | Elamaran
4238-7001 | Despatch-4238(B) | 2018-10-12 08:30 | 2018-09-18 13:31 | 2018-10-12 18:31 | HPCL | 2 | 20 | 100 | 100 | 2 | 20 | 1234 | 8-Project Completed | Elamaran
4256-1002 | Despatch 4256-A | 2019-03-12 08:00 | 2019-01-08 10:30 | 2019-03-09 18:30 | EIL-HPCL | 1 | 200.78 | 20 | 0 | 1 | 200.8 | 10920 | B-Production in Progress | Elamaran
4256-1007 | Despatch 4256-B | 2019-03-12 08:00 | 2018-12-29 21:30 | 2019-03-09 14:30 | EIL-HPCL | 1 | 84.72 | 17 | 0 | 1 | 84.7 | 4340 | B-Production in Progress | Elamaran
4256-1008 | Despatch 4256-C | 2019-03-12 08:00 | 2019-01-14 21:30 | 2019-03-11 13:30 | EIL-HPCL | 1 | 104.05 | 41 | 0 | 1 | 104.1 | 5450 | B-Production in Progress | Elamaran
4256-1009 | Despatch 4256 D | 2019-03-12 08:00 | 2019-01-31 19:30 | 2019-03-14 11:30 | EIL-HPCL | 1 | 267.21 | 28 | 0 | 1 | 267.2 | 14880 | B-Production in Progress | Elamaran
4256-1013 | Despatch 4256-N | 2019-03-12 08:00 | 2019-02-02 18:12 | 2019-03-07 09:30 | EIL-HPCL | 1 | 20.27 | 27 | 0 | 1 | 20.3 | 680 | B-Production in Progress | Elamaran
4256-102C | Despatch 4256-L | 2019-03-12 08:00 | 2019-01-31 07:30 | 2019-02-18 20:00 | EIL-HPCL | 1 | 58.96 | 26 | 0 | 1 | 59 | 2690 | B-Production in Progress | Elamaran
4256-2003 | Despatch 4256-E | 2019-03-12 08:00 | 2019-01-23 07:30 | 2019-03-16 19:30 | EIL-HPCL | 2 | 113.89 | 30 | 0 | 2 | 113.9 | 5240 | B-Production in Progress | Elamaran
4256-2004 | Despatch 4256-F | 2019-03-12 08:00 | 2019-02-01 07:30 | 2019-03-09 15:30 | EIL-HPCL | 2 | 96.31 | 19 | 0 | 2 | 96.3 | 4680 | B-Production in Progress | Elamaran
4256-2005 | Despatch 4256-G | 2019-03-12 08:00 | 2019-02-05 11:30 | 2019-03-11 13:42 | EIL-HPCL | 2 | 180.95 | 38 | 0 | 2 | 181 | 9140 | B-Production in Progress | Elamaran
4256-2009 | Despatch 4256-H | 2019-03-12 08:00 | 2019-02-05 11:30 | 2019-03-06 09:30 | EIL-HPCL | 2 | 110.79 | 14 | 0 | 2 | 110.8 | 5580 | B-Production in Progress | Elamaran
4256-2011 | Despatch 4256-I | 2019-03-12 08:00 | 2019-02-07 15:00 | 2019-02-27 12:00 | EIL-HPCL | 1 | 68.48 | 20 | 0 | 1 | 68.5 | 3420 | B-Production in Progress | Elamaran
4256-5001 | Despatch 4256-J | 2019-03-12 08:00 | 2019-02-12 11:30 | 2019-03-01 09:30 | EIL-HPCL | 2 | 88.68 | 41 | 0 | 2 | 88.7 | 4100 | B-Production in Progress | Elamaran
4256-6002 | Despatch 4256-K | 2019-03-12 08:00 | 2019-02-05 18:00 | 2019-02-16 18:00 | EIL-HPCL | 2 | 88.12 | 28 | 0 | 2 | 88.1 | 4000 | B-Production in Progress | Elamaran
4256-700-2003 | Despatch 4256-M | 2019-03-12 08:00 | 2019-01-19 08:30 | 2019-03-15 15:30 | EIL-HPCL | 2 | 95.4 | 22 | 0 | 2 | 95.4 | 4400 | B-Production in Progress | Elamaran
4266-72-E-51 | Despatch-4266C | 2019-02-24 08:30 | 2019-02-01 15:30 | 2019-03-14 17:30 | TECHNIP | 1 | 116.86 | 12 | 0 | 1 | 116.9 | 7160 | 2-Design Completed | Viswanathan
4266-74-E-04 | Despatch-4266E | 2019-02-24 08:30 | 2019-02-08 12:30 | 2019-03-16 17:30 | TECHNIP | 2 | 242.98 | 11 | 0 | 2 | 243 | 14425 | 2-Design Completed | Viswanathan
4266-74-E-106 | Despatch-4266F | 2019-02-24 08:30 | 2019-01-30 15:30 | 2019-02-18 17:30 | TECHNIP | 2 | 56.59 | 8 | 0 | 2 | 56.6 | 3000 | 2-Design Completed | Viswanathan
4266-74-E-51 | Despatch-4266D | 2019-02-24 08:30 | 2019-02-12 15:30 | 2019-02-20 17:30 | TECHNIP | 1 | 67.84 | 12 | 0 | 1 | 67.8 | 3950 | 2-Design Completed | Viswanathan
4266-75-E-12 | Despatch-4266G | 2019-02-24 08:30 | 2019-02-12 17:30 | 2019-03-20 06:30 | TECHNIP | 2 | 192.26 | 19 | 0 | 2 | 192.3 | 8113 | 2-Design Completed | Viswanathan
4266-75-E-56 A&B | Despatch-4266H | 2019-02-24 08:30 | 2019-04-02 11:30 | 2019-03-27 15:30 | TECHNIP | 2 | 110 | 5 | 0 | 2 | 110 | 6596 | 2-Design Completed | Viswanathan
4266-90-E-09 | Despatch-4266B | 2019-02-24 08:30 | 2019-02-19 10:30 | 2019-02-20 17:30 | TECHNIP | 2 | 157.71 | 18 | 0 | 2 | 157.7 | 10150 | 2-Design Completed | Viswanathan
4266-90-E-13C | Despatch-4266A | 2019-02-24 08:30 | 2019-02-16 14:30 | 2019-02-21 14:00 | TECHNIP | 1 | 199.89 | 14 | 0 | 1 | 199.9 | 10675 | 2-Design Completed | Viswanathan
4267-502-E-101 | Despatch-4267A | 2019-04-30 08:30 | 2019-03-02 12:30 | 2019-04-06 15:30 | TECHNIP-HPCL | 2 | 47.26 | 8 | 0 | 2 | 47.3 | 1850 | 2-Design Completed | Viswanathan
4267-502-E-104 | Despatch-4267B | 2019-04-30 08:30 | 2019-03-11 17:30 | 2019-03-13 12:30 | TECHNIP-HPCL | 2 | 35.88 | 2 | 0 | 2 | 35.9 | 1425 | 2-Design Completed | Viswanathan
4267-502-E-105 | Despatch-4267C | 2019-04-30 08:30 | 2019-02-28 15:30 | 2019-03-05 14:00 | TECHNIP-HPCL | 2 | 139.31 | 14 | 0 | 2 | 139.3 | 5375 | 2-Design Completed | Viswanathan
4267-502-E-108 | Despatch-4267D | 2019-04-30 08:30 | 2019-03-21 14:30 | 2019-03-19 12:30 | TECHNIP-HPCL | 2 | 33.99 | 7 | 0 | 2 | 34 | 1300 | 2-Design Completed | Viswanathan
4267-502-E-114 | Despatch-4267E | 2019-04-30 08:30 | 2019-03-07 17:30 | 2019-03-08 15:06 | TECHNIP-HPCL | 2 | 360.9 | 14 | 0 | 2 | 360.9 | 17860 | 2-Design Completed | Viswanathan
4267-502-E-119 | Despatch-4267F | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 35.28 | 4 | 0 | 2 | 35.3 | 1350 | 2-Design Completed | Viswanathan
4267-502-E-120 | Despatch-4267K | 2019-04-30 08:30 | 2019-03-21 17:30 | 2019-04-04 17:30 | TECHNIP-HPCL | 1 | 20 | 10 | 0 | 1 | 811.5 | 552 | 2-Design Completed | Viswanathan
4267-502-E-123 | Despatch-4267G | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 55.35 | 5 | 0 | 2 | 55.4 | 2570 | 2-Design Completed | Viswanathan
4267-502-E-123-1 | Despatch-4267G | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 55.35 | 5 | 0 | 2 | 55.4 | 2570 | 2-Design Completed | Viswanathan
4267-502-E-124 | Despatch-4267H | 2019-04-30 08:30 | 2019-03-08 11:42 | 2019-03-19 14:30 | TECHNIP-HPCL | 2 | 56.97 | 7 | 0 | 2 | 57 | 2710 | 2-Design Completed | Viswanathan
4267-502-E-129 | Despatch-4267I | 2019-04-30 08:30 | 2019-03-21 17:30 | 2019-03-20 09:30 | TECHNIP-HPCL | 2 | 26.95 | 9 | 0 | 2 | 27 | 1060 | 2-Design Completed | Viswanathan
4267-502-E-130 | Despatch-4267J | 2019-04-30 08:30 | 2019-04-04 17:30 | 2019-03-25 16:42 | TECHNIP-HPCL | 2 | 52.11 | 4 | 0 | 2 | 52.1 | 2300 | 2-Design Completed | Viswanathan
Site jobs | 4106 - Thermax site | 2018-04-18 08:30 |  | 2018-08-23 17:30 | All clients |  | 3.79 | 100 | 0 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4255 - MCCPTA site work | 2018-04-18 08:30 | 2018-05-02 12:30 | 2018-05-10 17:30 | All clients | 1 | 39.14 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4272 -RIL site work | 2018-04-18 08:30 |  | 2018-06-11 17:30 | All clients |  | 14.96 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4275 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-06-12 17:30 | All clients | 1 | 3.8 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4281 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-08-17 17:30 | All clients | 1 | 5.67 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4289 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-09-17 17:30 | All clients | 1 | 7.6 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4299 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-12-18 17:30 | All clients | 1 | 2.59 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4306 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-12-18 17:30 | All clients | 1 | 3.16 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Work to done | In your Project Plan suffix despatch with Job+Tag . Make the same change in this excel file | I hope the CDD is correct | Please write BL date of the despatch and correct the same in your plan | Nothing | I hope client name is correct | Check Dispatch Qty. If not correct then correct in this file and then in Project Plan | Check Dispatch Value. If not correct then correct in this file and then in Project Plan | Nothing | Nothing | Check Project Qty. If not correct then correct in this file and then in Project Plan | Check Project Value. If not correct then correct in this file and then in Project Plan |  | Nothing | Nothing

## Today
Project | Despatch Name | CDD | BL FD | New FinishDate | ClientName | Des.Qty | Des.Val (Lakhs) | Pr.%WC | Task%WC | Pr.Qty | Pr.Val (Lakhs) | Project Budget (Hrs) | CompletionStatus | PM
4106 | Finished goods - Spares | 2018-09-01 08:00 |  | 2018-09-27 17:00 | Thermax | 1 | 5 | 11 | 0 | 1 | 5 |  | 8-Project Completed | Viswanathan
4161 | DESPATCH TO SITE | 2018-01-03 08:00 | 2017-10-09 12:00 | 2018-03-06 12:30 | BPCL | 3 | 39.16 | 100 | 100 | 3 | 41.2 | 2622 | 8-Project Completed | Anand
4166 | Despatch | 2018-03-31 08:00 |  | 2017-04-13 16:30 | Programme AD | 10 | 89 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4166 | Despatch | 2018-03-31 08:00 |  | 2017-04-13 16:30 | Programme AD | 20 | 178 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4166 | Despatch | 2018-03-31 08:00 |  | 2017-12-12 09:59 | Programme AD | 20 | 178 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4167 | DESPATCH TO SITE | 2017-10-07 08:00 | 2017-10-17 17:00 | 2017-12-22 17:00 | BORL | 1 | 67.21 | 100 | 100 | 1 | 67.2 | 2772 | 8-Project Completed | Anand
4169 | DESPATCH | 2017-12-20 08:00 | 2017-09-29 14:42 | 2017-09-29 14:44 | Essar | 1 | 15.29 | 100 | 100 | 2 | 214 | 8777 | 8-Project Completed | Varun
4169 | Despatch | 2017-12-20 08:00 | 2017-10-27 13:09 | 2018-03-16 14:00 | Essar | 1 | 198.71 | 100 | 100 | 2 | 214 | 8777 | 8-Project Completed | Varun
4170 | Depatch 4170F | 2018-01-01 06:00 | 2018-03-26 21:30 | 2018-03-26 21:30 | IOCL-EIL | 1 | 80.05 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170A1 | 2018-01-01 06:00 | 2018-02-16 20:30 | 2018-02-16 20:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170A2 | 2018-01-01 06:00 | 2018-02-16 20:30 | 2018-02-16 20:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170B1 | 2018-01-01 06:00 | 2018-01-30 20:30 | 2018-01-30 20:30 | IOCL-EIL | 1 | 62.03 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170B2 | 2018-01-01 06:00 | 2018-01-30 20:30 | 2018-01-30 20:30 | IOCL-EIL | 1 | 62.03 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170C1 | 2018-01-01 06:00 | 2018-02-16 21:30 | 2018-02-16 21:30 | IOCL-EIL | 1 | 19.76 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170C2 | 2018-01-01 06:00 | 2018-02-16 21:30 | 2018-02-16 21:30 | IOCL-EIL | 1 | 19.76 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170D1 | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 27.7 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170D2 | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 27.7 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170E | 2018-01-01 06:00 | 2018-03-16 21:30 | 2018-03-16 21:30 | IOCL-EIL | 1 | 30.92 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170G1 | 2018-01-01 06:00 | 2018-02-28 21:30 | 2018-02-28 21:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170G2 | 2018-01-01 06:00 | 2018-02-28 21:30 | 2018-02-28 21:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170H | 2018-01-01 06:00 | 2018-03-28 20:30 | 2018-03-28 20:30 | IOCL-EIL | 1 | 118.32 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170I1 | 2018-01-01 06:00 | 2018-03-16 21:30 | 2018-03-16 21:30 | IOCL-EIL | 1 | 32.63 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170I2 | 2018-01-01 06:00 | 2018-03-13 20:30 | 2018-03-13 20:30 | IOCL-EIL | 1 | 32.63 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J1 | 2018-01-01 06:00 | 2018-02-23 21:30 | 2018-02-23 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J2A | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J2B | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170K1 | 2018-01-01 06:00 | 2018-03-24 20:30 | 2018-03-24 20:30 | IOCL-EIL | 1 | 13.4 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170K2 | 2018-01-01 06:00 | 2018-03-24 21:30 | 2018-03-24 21:30 | IOCL-EIL | 1 | 13.4 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170L | 2018-01-01 06:00 | 2018-03-14 20:30 | 2018-03-14 20:30 | IOCL-EIL | 1 | 32.72 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4174 | DESPATCH | 2017-12-14 08:00 | 2017-12-30 17:10 | 2018-02-05 17:00 | IOCL | 1 | 57.79 | 100 | 100 | 1 | 59.4 | 4688 | 8-Project Completed | Elamaran
4180 | Despatch | 2017-12-29 08:00 | 2018-01-22 21:30 | 2018-01-22 21:30 | NIOT | 1 | 43.08 | 100 | 100 | 2 | 86.2 | 1696 | 8-Project Completed | Varun
4180 | Despatch | 2017-12-29 08:00 | 2018-01-23 12:30 | 2018-01-23 12:30 | NIOT | 1 | 43.08 | 100 | 100 | 2 | 86.2 | 1696 | 8-Project Completed | Varun
4182 | DESPATCH | 2018-01-10 08:00 | 2017-09-05 12:21 | 2018-02-05 17:00 | UPL | 6 | 144 | 100 | 100 | 6 | 144 | 4812 | 8-Project Completed | Ethiraj
4183 | Despatch | 2018-01-04 08:00 | 2018-02-27 20:22 | 2018-03-31 10:00 | IOCL | 1 | 113.14 | 100 | 100 | 1 | 115.4 | 11102 | 8-Project Completed | Ethiraj
4197 | Despatch | 2018-01-06 08:00 | 2018-01-05 09:50 | 2018-02-03 08:36 | ASL | 8 | 92.1 | 100 | 100 | 8 | 92.1 | 13200 | 8-Project Completed | Anand
4211 | Despatch | 2018-07-17 08:00 | 2018-04-30 07:50 | 2018-04-30 14:47 | Advanced System Laboratory | 25 | 142.5 | 100 | 100 | 25 | 142.5 | 4450 | 8-Project Completed | Varun
4213 | Despatch | 2018-02-27 08:00 | 2018-01-30 16:00 | 2018-03-03 09:00 | SRF | 1 | 28.75 | 100 | 100 | 1 | 28.8 | 1220 | 8-Project Completed | Elamaran
4215 | Despatch | 2017-11-30 08:00 | 2018-01-19 15:30 | 2018-02-17 18:00 | SRF | 1 | 10.5 | 100 | 100 | 1 | 10.5 | 336 | 8-Project Completed | Varun
4216 | Product Transportation to Site | 2018-07-31 08:30 | 2018-06-16 17:30 | 2019-02-15 17:30 | BEML | 5 | 0.8 | 20 | 0 | 75 | 12 | 1800 | 9-On Hold | Varun
4218 | Despatch | 2018-08-11 08:00 | 2018-07-20 21:54 | 2018-08-30 14:00 | CPCL | 1 | 79.07 | 100 | 100 | 1 | 80.3 | 7383 | 8-Project Completed | Varun
4227 | Despatch | 2018-08-10 08:30 | 2018-03-17 14:30 | 2018-03-17 14:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 2018-05-19 11:30 | 2018-05-11 09:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 2018-05-19 11:30 | 2018-06-06 12:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 |  | 2018-07-20 12:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4230 | Despatch | 2018-06-30 08:00 | 2018-03-31 18:30 | 2018-03-31 18:30 | ASL | 7 | 36.4 | 100 | 100 | 10 | 52 | 1600 | 8-Project Completed | Varun
4230 | Despatch | 2018-06-30 08:00 | 2018-04-26 18:00 | 2018-04-30 20:22 | ASL | 3 | 15.6 | 100 | 100 | 10 | 52 | 1600 | 8-Project Completed | Varun
4232 | Despatch | 2018-07-07 08:00 | 2018-06-16 10:30 | 2018-07-05 17:00 | IOCL-TECHNIP | 1 | 52.48 | 100 | 100 | 1 | 52.5 | 4245 | 8-Project Completed | Elamaran
4233 | Despatch | 2018-01-22 08:00 | 2017-12-30 17:30 | 2018-01-23 17:30 | KMML | 22 | 0.81 | 100 | 100 | 22 | 1 | 12 | 8-Project Completed | Varun
4239 | Invoice to Customer | 2018-02-03 08:30 | 2018-03-16 12:30 | 2018-03-17 12:30 | IGCAR | 1 | 9.47 | 100 | 100 | 1 | 9.5 | 260 | 8-Project Completed
4240 | Despatch | 2018-07-20 08:30 | 2018-05-22 19:30 | 2019-03-26 19:30 | RCI | 2 | 19.4 | 18 | 0 | 2 | 19.4 | 840 | 9-On Hold | Varun
4240 | Final Inspection & Dispatch | 2018-07-20 08:30 | 2018-05-22 19:30 | 2019-03-26 19:30 | RCI |  |  | 18 | 0 | 2 | 19.4 | 840 | 9-On Hold | Varun
4241 | Despatch - 4241 | 2018-08-21 08:00 | 2018-08-10 09:30 | 2019-01-11 21:30 | IOCL-EIL | 1 | 5 | 63 | 0 | 1 | 5 | 2059 | B-Production in Progress | Elamaran
4242 | Despatched | 2018-03-10 08:00 | 2018-03-13 17:00 | 2018-03-13 17:00 | KMML | 1 | 2.52 | 100 | 100 | 1 | 2.5 | 50 | 8-Project Completed | PMO
4243 | despatch through courier | 2018-03-10 08:00 | 2018-03-05 17:30 | 2018-03-05 17:30 | Apid Engineer | 1 | 0.3 | 100 | 100 | 1 | 0.3 | 6 | 8-Project Completed | PMO
4245 | Finished good - Pump spares | 2018-03-31 08:30 | 2018-03-17 09:30 | 2018-08-27 17:30 | Grasim | 1 | 1.73 | 100 | 100 | 1 | 1.7 | 280 | 8-Project Completed | Viswanathan
4246 | Despatch-4246 | 2018-11-15 08:00 | 2018-11-13 16:41 | 2018-12-31 17:00 | SRF | 1 | 96 | 99 | 0 | 1 | 96 | 2955 | 6-QC Completed | Ethiraj
4247 | Despatch | 2018-06-30 08:00 |  | 2018-12-29 19:29 | SSIS |  |  | 99 | 0 | 2 | 20.9 | 2043 | 5-Production Completed | Varun
4247 | Payment followup and despatch | 2018-06-30 08:00 |  | 2018-12-29 19:29 | SSIS | 2 | 20.93 | 99 | 0 | 2 | 20.9 | 2043 | 5-Production Completed | Varun
4248 | Product Transportation to Site | 2018-06-18 08:30 | 2018-04-19 16:30 | 2018-06-27 15:30 | KMML | 3 | 1.32 | 100 | 100 | 3 | 1.3 | 70 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-07-02 14:30 | 2018-07-24 11:00 | SVCI | 2 | 21.76 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-06-22 20:30 | 2018-07-24 13:00 | SVCI | 2 | 21.76 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-06-27 12:30 | 2018-07-27 12:30 | SVCI | 2 | 22.26 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4250 | Finished good - Pump spares | 2018-03-31 08:30 | 2018-05-04 08:31 | 2018-08-21 17:30 | Grasim | 3 | 3.06 | 100 | 100 | 3 | 3.1 | 312 | 8-Project Completed | Viswanathan
4251 | Final Assembly & Machining | 2018-08-05 08:30 |  | 2018-11-28 16:30 | NPOL | 1 | 37.34 | 100 | 100 | 1 | 37.3 | 1330 | 8-Project Completed | Varun
4252 | Despatch | 2018-12-31 08:30 |  | 2019-01-02 19:30 | NPOL | 1 | 76 | 83 | 0 | 1 | 76 | 3130 | B-Production in Progress | Varun
4253 | Despatch | 2018-06-14 08:30 | 2018-06-13 09:30 | 2018-06-26 09:30 | KMML | 4 | 3.99 | 100 | 100 | 4 | 4 | 400 | 8-Project Completed | Elamaran
4254 | Despatch | 2018-10-21 08:30 | 2018-10-01 14:30 | 2018-10-23 18:30 | IOCL | 1 | 31.7 | 100 | 100 | 1 | 33 | 2957 | 8-Project Completed | Varun
4257 | Despatch | 2018-09-10 08:00 | 2018-08-21 09:30 | 2018-11-10 17:00 | Keltron | 1 | 43 | 100 | 100 | 1 | 43 | 2370 | 8-Project Completed | Elamaran
4258 | Despatch | 2018-10-13 08:00 | 2018-10-03 21:00 | 2018-09-29 19:30 | RRCAT | 5 | 13.5 | 100 | 100 | 5 | 13.5 | 530 | 8-Project Completed | Elamaran
4259 | Despatch | 2018-10-04 08:00 | 2018-09-17 12:30 | 2018-09-29 16:00 | Orient Paper Mills | 1 | 20.3 | 100 | 100 | 1 | 20.3 | 2720 | 8-Project Completed | Ethiraj
4260 | Despatch-4260-No1 No2 | 2018-10-04 08:00 | 2018-10-04 16:30 | 2019-01-03 08:00 | CCM CHEMICALS SDN BHD | 2 | 43.47 | 99 | 0 | 2 | 43.5 | 4780 | 6-QC Completed | Ethiraj
4261 | Finished good despatch | 2018-05-15 08:00 | 2018-03-05 17:30 | 2018-05-04 15:30 | DCW Limited | 1 | 9 | 41 | 0 | 1 | 9 | 400 | 8-Project Completed | Viswanathan
4262 | Despatch | 2018-09-15 08:00 | 2018-03-05 17:30 | 2018-09-01 17:00 | Tata Chemicals Ltd, Mithapur | 4 | 0.79 | 100 | 100 | 4 | 0.8 | 100 | 8-Project Completed | Ethiraj
4263 | Product Transportation to Site - 1st lot | 2018-10-17 08:00 | 2018-10-15 07:30 | 2018-09-27 08:00 | Kutch Chemical Industries Limited | 6 | 92.4 | 95 | 100 | 12 | 189.8 | 4320 | 7-Despatched | Ethiraj
4263 | Product Transportation to Site - 2nd lot | 2018-10-17 08:00 |  | 2018-10-26 16:00 | Kutch Chemical Industries Limited | 6 | 97.4 | 95 | 100 | 12 | 189.8 | 4320 | 7-Despatched | Ethiraj
4264 | Finished goods | 2018-07-15 08:00 | 2018-05-31 17:30 | 2018-05-31 17:30 | CAL, TEAM's Group company | 20 | 18.3 | 100 | 100 | 20 | 18.3 | 680 | 8-Project Completed | Viswanathan
4265 | Finished goods | 2018-10-14 08:00 |  | 2018-09-29 20:30 | The Kerala Minerals & Metals Ltd | 1 | 5.3 | 100 | 100 | 1 | 5.3 | 925 | 8-Project Completed | Elamaran
4268 | Despatch-4268 | 2018-12-24 08:30 | 2018-12-20 12:30 | 2019-01-15 09:30 | Technip Mumbai | 1 | 253.11 | 81 | 0 | 1 | 253.1 | 17360 | B-Production in Progress | Ethiraj
4269 | Despatch-4269 | 2018-12-25 08:30 | 2018-11-03 17:30 | 2018-12-31 14:30 | SPX FLOW | 2 | 69 | 96 | 0 | 2 | 69 | 1560 | B-Production in Progress | Ethiraj
4270 | Finished good - Anode | 2018-07-03 08:30 |  | 2018-05-02 17:30 | VXL Life sceinces, Mumbai | 1 | 0.8 | 0 | 0 | 2 | 1.6 | 300 | 8-Project Completed | Viswanathan
4270 | Finished good - Cathode | 2018-07-03 08:30 |  | 2018-06-11 17:30 | VXL Life sceinces, Mumbai | 1 | 0.9 | 0 | 0 | 2 | 1.6 | 300 | 8-Project Completed | Viswanathan
4271 | Finished goods | 2018-07-10 08:00 | 2018-07-05 17:30 | 2018-09-28 08:00 | KMML | 1 | 0.34 | 100 | 100 | 1 | 0.3 | 4 | 8-Project Completed | Elamaran
4273 | Despatch | 2018-09-27 08:00 | 2018-08-23 09:30 | 2018-09-25 09:30 | KMML, Kochi | 60 | 0.86 | 100 | 100 | 60 | 0.9 | 100 | 8-Project Completed | Varun
4274 | Despatch | 2019-03-30 08:00 |  | 2018-07-27 17:30 | NIOT | 4 | 0.46 | 100 | 100 | 10 | 1.2 | 100 | 5-Production Completed | Varun
4274 | Despatch | 2019-03-30 08:00 |  | 2018-08-24 17:30 | NIOT | 1 | 0.12 | 100 | 100 | 10 | 1.2 | 100 | 5-Production Completed | Varun
4276 | Finished good | 2018-06-30 08:00 |  | 2018-06-25 12:00 | Praxair | 1 | 0.89 | 20 | 0 | 1 | 0.9 |  | 8-Project Completed | Viswanathan
4279 | Finished goods | 2018-10-30 08:00 |  | 2018-10-29 17:00 | CCAL | 1 | 0.65 | 100 | 100 | 1 | 0.7 | 100 | 8-Project Completed | Hariprasath
4280 | Despatch | 2018-12-12 08:00 | 2018-10-03 09:30 | 2018-09-29 13:30 | NSTL, Vizag | 6 | 30 | 100 | 100 | 6 | 30 | 1650 | 8-Project Completed | Elamaran
4282 | Finished goods | 2018-10-30 08:00 |  | 2018-10-29 17:00 | CCAL | 1 | 0.32 | 100 | 100 | 1 | 0.3 | 3 | 8-Project Completed | Hariprasath
4283 | Finished goods - 1st Lot | 2018-07-15 08:00 | 2018-05-31 17:30 | 2018-07-30 14:30 | CAL, TEAM's Group company | 22 | 23.68 | 100 | 100 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 2nd Lot | 2018-07-15 08:00 |  | 2018-08-18 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 3rd Lot | 2018-07-15 08:00 |  | 2018-08-29 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 4th Lot | 2018-07-15 08:00 |  | 2018-09-26 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 5th Lot | 2018-07-15 08:00 |  | 2018-10-23 14:30 | CAL, TEAM's Group company | 47 | 49.77 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4284 | Despatch-4284-2Nos | 2019-03-25 08:00 | 2019-03-15 13:30 | 2019-02-27 08:30 | Larsen & Toubro | 2 | 49.6 | 11 | 0 | 2 | 49.6 | 1640 | 4-Purchase Completed | Hariprasath
4285 | Finished goods | 2018-10-30 08:00 |  | 2018-10-29 17:00 | Tata Chemicals Limited | 1 | 0.3 | 100 | 100 | 1 | 0.3 |  | 8-Project Completed | Hariprasath
4286 | Despatch | 2019-02-15 08:30 | 2019-02-08 17:00 | 2019-02-08 17:00 | TVG SRAAC, Kurnool |  |  | 60 | 0 | 10 | 98.5 | 16300 | B-Production in Progress | Hariprasath
4286 | Despatch-4286-10Nos | 2019-02-15 08:30 | 2019-02-08 17:00 | 2019-02-08 17:00 | TVG SRAAC, Kurnool | 10 | 98.5 | 60 | 0 | 10 | 98.5 | 16300 | B-Production in Progress | Hariprasath
4287 | Inspection & dispatch | 2018-12-30 08:00 |  | 2018-10-26 17:00 | VEM Technologies, Hyd | 24 | 5.23 | 100 | 100 | 24 | 5.2 |  | 7-Despatched | Hariprasath
4288 | Finished goods | 2018-11-21 08:00 |  | 2018-10-23 17:00 | Lords Chloro Alkalies | 2 | 0.55 | 100 | 100 | 1 | 0.6 | 14 | 8-Project Completed | Hariprasath
4290 | Delivery - 10 nos | 2018-10-06 08:00 |  | 2018-09-17 17:30 | NIOT | 10 | 0.1 | 100 | 100 | 10 | 0.1 | 100 | 8-Project Completed | Hariprasath
4294 | Finished good | 2018-10-18 08:00 |  | 2018-10-18 17:00 | Kavinaya (Praxair) | 1 | 0.89 | 0 | 0 | 1 | 0.9 |  | 8-Project Completed | Hariprasath
4295 | Despatch-4295-2Nos | 2019-01-18 08:30 |  | 2019-01-15 17:30 | KMML | 2 | 10.68 | 82 | 0 | 2 | 10.7 | 860 | B-Production in Progress | Hariprasath
4296 | Despatch 4256-A | 2019-08-16 08:30 | 2019-01-08 10:30 | 2019-06-10 15:30 | Technimont | 1 | 200.78 | 3 | 0 | 20 | 1390 | 5282 | 2-Design Completed | Elamaran
4297 | Despatch-4297 | 2019-04-16 08:30 |  | 2019-03-29 17:30 | CCM | 4 | 16.66 | 45 | 0 | 4 | 16.7 | 700 | 2-Design Completed | Vinothkumar
4298 | Inspection & dispatch | 2018-12-30 08:00 |  | 2018-11-28 17:00 | BDL | 12 | 1.92 | 100 | 100 | 12 | 1.9 |  | 8-Project Completed | Hariprasath
4300 | Despatch-4300 | 2019-03-31 08:30 | 2019-03-28 17:30 | 2019-03-26 17:30 | YUSUF BIN AHMED KANOO W.L.L., | 64 | 15.67 | 22 | 0 | 64 | 15.7 | 448 | 3-PPC Completed | Vinothkumar
4301 | Despatch | 2019-04-03 08:30 |  | 2019-03-18 17:30 | MCCPTA | 1 | 2.53 | 14 | 0 | 1 | 2.5 | 8 | 3-PPC Completed | Hariprasath
4302 | Despatch-4302 | 2019-05-08 08:00 |  | 2019-05-04 09:30 | Sirpur Paper Mills | 1 | 10.07 | 39 | 0 | 1 | 10.1 | 1430 | 2-Design Completed | Vinothkumar
4303 | Inspection & dispatch | 2018-12-30 08:00 |  | 2018-11-15 17:00 | BDL | 1 | 0.05 | 0 | 0 | 1 | 0.1 |  | 8-Project Completed | Hariprasath
4305 | Despatch-4295-30Nos | 2019-01-03 08:30 | 2019-01-23 17:30 | 2019-01-25 12:30 | Modern Engineering & Plastics | 30 | 0.74 | 2 | 0 | 30 | 0.7 | 280 | 3-PPC Completed | Hariprasath
4309 | Despatch | 2019-03-23 08:00 | 2019-02-20 09:00 | 2019-02-20 09:00 | KMML | 40 | 0.51 | 8 | 0 | 40 | 0.5 | 8 | 3-PPC Completed | Hariprasath
4173-02 | DESPATCH | 2018-04-07 06:00 | 2018-01-09 06:04 | 2018-03-31 18:00 | IOCL-EIL | 2 | 111.72 | 100 | 100 | 2 | 111.7 | 9702 | 8-Project Completed | Ethiraj
4173-108 | Despatch | 2018-04-07 06:00 | 2018-03-31 13:30 | 2018-03-31 13:30 | IOCL-EIL | 1 | 65.62 | 100 | 100 | 1 | 65.6 | 5579 | 8-Project Completed | Ethiraj
4173-126 | DESPATCH | 2018-04-07 06:00 | 2018-03-30 08:40 | 2018-03-30 08:40 | IOCL-EIL | 2 | 43.75 | 100 | 100 | 2 | 43.8 | 4352 | 8-Project Completed | Ethiraj
4192-HC 150-1 | Despatch | 2019-01-07 08:00 | 2018-05-14 13:12 | 2018-09-05 17:00 | IGCAR | 1 | 66.77 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-2 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2018-12-27 09:30 | IGCAR | 1 | 66.77 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-2 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2018-12-27 09:30 | IGCAR |  |  | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-3 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-04-30 12:30 | IGCAR | 1 | 66.77 | 66 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-3 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-04-30 12:30 | IGCAR |  |  | 66 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-4 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-4 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR |  |  | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-5 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-5 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR |  |  | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-6 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-6 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR |  |  | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-VC-100 | Despatch | 2019-01-07 08:30 | 2018-10-09 08:30 | 2018-11-30 08:30 | IGCAR | 1 | 2.07 | 100 | 100 | 1 | 2.1 | 80 | 8-Project Completed | Varun
4192-VC-600 | Despatch | 2019-01-07 08:30 | 2018-10-09 08:30 | 2018-11-30 08:30 | IGCAR | 1 | 2.55 | 100 | 100 | 1 | 2.6 | 200 | 8-Project Completed | Varun
4201-0004 | Despatch | 2018-08-06 08:00 |  | 2018-09-29 14:00 | Dangote | 4 | 386.56 | 100 | 0 | 4 | 386.6 | 33620 | 6-QC Completed | Anand
4201-0005 | Despatch | 2018-08-31 08:00 |  | 2018-09-29 15:30 | Dangote | 4 | 301.44 | 100 | 0 | 4 | 301.4 | 26218 | 6-QC Completed | Anand
4203-AT 630-2 | Despatch | 2019-02-14 08:30 | 2018-07-27 22:00 | 2018-08-23 22:00 | IGCAR | 1 | 2.91 | 100 | 100 | 1 | 2.9 | 575 | 8-Project Completed | Varun
4203-AT 630-4,5,6 | Despatch | 2019-02-14 08:30 | 2018-07-27 22:00 | 2018-11-30 22:00 | IGCAR | 1 | 2.91 | 100 | 100 | 1 | 8.7 | 1725 | 8-Project Completed | Varun
4203-AT-400 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 22 | 50.6 | 0 | 0 | 22 | 50.6 | 8074 | 9-On Hold | Varun
4203-AT-400N | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 7 | 16.31 | 0 | 0 | 7 | 16.3 | 2628 | 9-On Hold | Varun
4203-AT-500 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 14 | 38.78 | 0 | 0 | 14 | 38.8 | 7393 | 9-On Hold | Varun
4203-AT-630 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 20 | 58.2 | 0 | 0 | 20 | 58.2 | 11523 | 9-On Hold | Varun
4203-AT-630-10 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-03 08:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 575 | B-Production in Progress | Varun
4203-AT-630-3 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-05 08:30 | IGCAR | 1 | 2.91 | 91 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-7 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2018-12-31 08:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-8 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2018-12-31 20:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-9 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-03 08:30 | IGCAR | 1 | 2.91 | 98 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630N | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 2 | 6.02 | 0 | 0 | 2 | 6 | 1155 | 9-On Hold | Varun
4203-AT-720 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 11 | 33.99 | 0 | 0 | 11 | 34 | 7070 | 9-On Hold | Varun
4203-RCAT-125 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 16 | 25.12 | 0 | 0 | 16 | 25.1 | 3057 | 9-On Hold | Varun
4203-RCAT-500 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 6 | 15.96 | 0 | 0 | 6 | 16 | 3528 | 9-On Hold | Varun
4203-RCAT-90 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 16 | 20.96 | 0 | 0 | 16 | 21 | 2165 | 9-On Hold | Varun
4203-RCVC-50-1 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 20:30 | IGCAR | 1 | 1.04 | 74 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-2 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 16:30 | IGCAR | 1 | 1.04 | 71 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-3 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 14:00 | IGCAR | 1 | 1.04 | 75 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-4 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 14:00 | IGCAR | 1 | 1.04 | 75 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4209-A&F | Despatch | 2018-10-01 06:00 |  | 2019-02-05 16:57 | Dangote | 2 | 88.35 | 51 | 0 | 2 | 88.4 | 9336 | B-Production in Progress | Anand
4209-B&G | Despatch | 2018-10-01 06:00 |  | 2018-11-20 17:30 | Dangote | 2 | 34.89 | 100 | 0 | 2 | 34.9 | 2086 | 6-QC Completed | Anand
4209-C&H | Despatch | 2018-10-01 06:00 |  | 2019-03-20 10:30 | Dangote | 2 | 221.48 | 46 | 0 | 2 | 221.5 | 22160 | B-Production in Progress | Anand
4209-D&I | Despatch | 2018-10-01 06:00 |  | 2018-12-28 11:00 | Dangote | 2 | 25.54 | 100 | 0 | 2 | 25.5 | 1450 | 6-QC Completed | Anand
4209-E&J | Despatch | 2018-10-01 06:00 |  | 2018-12-15 17:30 | Dangote | 2 | 10.37 | 99 | 0 | 2 | 10.4 | 570 | 6-QC Completed | Anand
4209-K&L | Despatch | 2018-10-01 06:00 |  | 2018-12-18 17:30 | Dangote | 4 | 21.82 | 100 | 0 | 4 | 21.8 | 1176 | 6-QC Completed | Anand
4209-M | Despatch | 2018-10-01 06:00 |  | 2019-01-08 12:03 | Dangote | 2 | 29.2 | 91 | 0 | 2 | 29.2 | 1560 | B-Production in Progress | Anand
4209-N | Despatch | 2018-10-01 06:00 |  | 2019-01-08 10:45 | Dangote | 1 | 17.01 | 91 | 0 | 1 | 17 | 1080 | B-Production in Progress | Anand
4209-O | Despatch | 2018-10-01 06:00 |  | 2018-12-14 17:30 | Dangote | 2 | 15.99 | 100 | 0 | 2 | 16 | 952 | 6-QC Completed | Anand
4209-P | Despatch | 2018-10-01 06:00 |  | 2019-01-08 14:02 | Dangote | 2 | 27.34 | 91 | 0 | 2 | 27.3 | 1502 | B-Production in Progress | Anand
4209-Q | Despatch | 2018-10-01 06:00 |  | 2018-12-15 12:30 | Dangote | 2 | 21.04 | 100 | 0 | 2 | 21 | 1142 | 6-QC Completed | Anand
4209-R&S | Despatch | 2018-10-01 06:00 |  | 2018-11-17 17:30 | Dangote | 2 | 11.79 | 100 | 0 | 2 | 11.8 | 518 | 6-QC Completed | Anand
4220-A1001 | Despatch 4220 A - AB | 2019-05-26 08:00 |  | 2019-01-18 17:30 | Dangote | 2 | 302.87 | 95 | 0 | 4 | 605.7 | 57103 | B-Production in Progress | Anand
4220-A1001 | Despatch 4220 A - CD | 2019-05-26 08:00 |  | 2019-02-11 17:30 | Dangote | 2 | 302.87 | 95 | 0 | 4 | 605.7 | 57103 | B-Production in Progress | Anand
4220-B1003 | Despatch | 2019-05-26 06:00 |  | 2019-12-31 17:30 | Dangote | 2 | 204.5 | 0 | 0 | 2 | 204.5 | 20354 | 2-Design Completed | Anand
4220-D1006 | Despatch | 2019-05-26 08:00 |  | 2020-01-27 08:44 | Dangote | 2 | 199.53 | 3 | 0 | 2 | 199.5 | 20080 | 4-Purchase Completed | Anand
4220-E1007 | Despatch | 2019-05-26 08:00 |  | 2019-03-28 17:30 | Dangote | 2 | 304.81 | 0 | 0 | 2 | 304.8 | 24348 | 4-Purchase Completed | Anand
4220-F1008 | Despatch | 2019-05-26 08:00 |  | 2019-06-29 17:30 | Dangote | 1 | 16.83 | 0 | 0 | 1 | 16.8 | 2053 | 4-Purchase Completed | Anand
4220-G1009-1 | Despatch | 2019-05-26 08:00 |  | 2019-07-17 17:30 | Dangote | 2 | 92.59 | 0 | 0 | 2 | 92.6 | 9310 | 4-Purchase Completed | Anand
4220-H1010 | Despatch | 2019-05-26 08:00 |  | 2019-03-27 17:30 | Dangote | 1 | 14.16 | 13 | 0 | 1 | 14.2 | 13494 | 4-Purchase Completed | Anand
4220-I1011 | Despatch | 2018-10-02 08:00 |  | 2019-05-28 15:00 | Dangote | 4 | 799.3 | 0 | 0 | 4 | 799.3 | 82197 | 4-Purchase Completed | Anand
4220-J1012 | Despatch | 2019-05-26 06:00 |  | 2019-07-12 17:00 | Dangote | 4 | 600.48 | 1 | 0 | 4 | 600.5 | 77331 | 4-Purchase Completed | Anand
4220-K1013 | Despatch | 2019-05-26 08:00 |  | 2019-08-23 11:00 | Dangote | 2 | 1057.37 | 0 | 0 | 2 | 1057.4 | 65261 | 4-Purchase Completed | Anand
4220-L1014 | Despatch | 2019-05-26 08:00 |  | 2019-07-18 10:28 | Dangote | 1 | 6.4 | 6 | 0 | 1 | 6.4 | 983 | 4-Purchase Completed | Anand
4220-N1011 | Despatch | 2019-05-26 08:00 |  | 2019-07-20 08:44 | Dangote | 1 | 38.85 | 0 | 0 | 1 | 38.9 | 7561 | 4-Purchase Completed | Anand
4220-O1011 | Despatch | 2019-05-26 08:00 |  | 2019-09-24 10:44 | Dangote | 1 | 38.26 | 0 | 0 | 1 | 38.3 | 13116 | 3-PPC Completed | Anand
4221-2403 | Despatch | 2018-09-01 08:00 |  | 2019-10-31 17:30 | Dangote | 1 | 10.66 | 3 | 0 | 1 | 10.7 | 517 | 2-Design Completed | Anand
4221-7001 | Despatch | 2018-09-01 08:00 |  | 2019-10-31 17:30 | Dangote | 1 | 31.08 | 29 | 0 | 1 | 31.1 | 872 | 2-Design Completed | Anand
4221-9101 | Despatch | 2018-09-01 08:00 | 2018-10-06 09:58 | 2019-11-05 17:58 | Dangote | 1 | 48.85 | 1 | 0 | 1 | 48.9 | 425 | 2-Design Completed | Anand
4224-103 | Despatch 4224-A | 2018-06-11 08:00 | 2018-05-31 20:30 | 2018-06-08 20:30 | IOCL-EIL | 1 | 33.03 | 100 | 100 | 1 | 35.5 | 3066 | 8-Project Completed | Elamaran
4224-309 | Despatch 4224-B | 2018-06-11 08:00 | 2018-06-06 17:40 | 2018-06-08 20:40 | IOCL-EIL | 1 | 16.98 | 100 | 100 | 1 | 17 | 739 | 8-Project Completed | Elamaran
4228-010 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-06-30 13:01 | 2017-11-09 17:00 | IOCL-EIL | 1 | 39.79 | 97 | 100 | 2 | 79.6 | 5040 | 8-Project Completed | Ethiraj
4228-010 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-07-20 07:41 | 2018-11-09 15:30 | IOCL-EIL | 1 | 39.79 | 97 | 100 | 2 | 79.6 | 5040 | 8-Project Completed | Ethiraj
4228-014 | Clearance By TPI | 2018-07-31 08:00 | 2018-07-02 09:52 | 2018-11-05 18:30 | IOCL-EIL | 1 | 11.57 | 100 | 100 | 2 | 23.1 | 1736 | 8-Project Completed | Ethiraj
4228-014 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-06-30 13:01 | 2018-11-05 17:00 | IOCL-EIL | 1 | 11.57 | 100 | 100 | 2 | 23.1 | 1736 | 8-Project Completed | Ethiraj
4228-102 | Shipping | 2018-07-31 08:00 | 2018-07-17 09:00 | 2018-11-10 17:00 | IOCL-EIL | 1 | 7.24 | 100 | 100 | 1 | 7.2 | 814 | 8-Project Completed | Ethiraj
4237-A | Despatch | 2018-09-08 08:00 | 2018-11-08 18:30 | 2019-01-30 10:50 | IOCL-EIL | 1 | 102.51 | 85 | 0 | 1 | 102.5 | 5670 | B-Production in Progress | Ethiraj
4237-B | Despatch | 2018-09-08 08:00 | 2018-08-09 19:02 | 2019-01-21 12:00 | IOCL-EIL | 1 | 63.87 | 88 | 0 | 1 | 63.9 | 3100 | B-Production in Progress | Ethiraj
4237-C | Despatch | 2018-09-08 08:00 | 2018-12-05 07:05 | 2019-01-21 21:24 | IOCL-EIL | 1 | 85.17 | 88 | 0 | 1 | 85.2 | 5070 | B-Production in Progress | Ethiraj
4237-D | Despatch | 2018-09-08 08:00 | 2018-08-08 18:30 | 2019-01-14 18:30 | IOCL-EIL | 4 | 48.45 | 85 | 0 | 1 | 48.5 | 2320 | B-Production in Progress | Ethiraj
4238-49 | Despatch-4238(A) | 2018-10-12 08:30 | 2018-09-24 17:30 | 2018-10-12 17:30 | HPCL | 1 | 57.65 | 100 | 100 | 1 | 57.7 | 5267 | 8-Project Completed | Elamaran
4238-7001 | Despatch-4238(B) | 2018-10-12 08:30 | 2018-09-18 13:31 | 2018-10-12 18:31 | HPCL | 2 | 20 | 100 | 100 | 2 | 20 | 1234 | 8-Project Completed | Elamaran
4256-1002 | Despatch 4256-A | 2019-03-12 08:00 | 2019-01-08 10:30 | 2019-03-09 18:30 | EIL-HPCL | 1 | 200.78 | 20 | 0 | 1 | 200.8 | 10920 | B-Production in Progress | Elamaran
4256-1007 | Despatch 4256-B | 2019-03-12 08:00 | 2018-12-29 21:30 | 2019-03-09 14:30 | EIL-HPCL | 1 | 84.72 | 17 | 0 | 1 | 84.7 | 4340 | B-Production in Progress | Elamaran
4256-1008 | Despatch 4256-C | 2019-03-12 08:00 | 2019-01-14 21:30 | 2019-03-11 13:30 | EIL-HPCL | 1 | 104.05 | 41 | 0 | 1 | 104.1 | 5450 | B-Production in Progress | Elamaran
4256-1009 | Despatch 4256 D | 2019-03-12 08:00 | 2019-01-31 19:30 | 2019-03-14 11:30 | EIL-HPCL | 1 | 267.21 | 28 | 0 | 1 | 267.2 | 14880 | B-Production in Progress | Elamaran
4256-1013 | Despatch 4256-N | 2019-03-12 08:00 | 2019-02-02 18:12 | 2019-03-07 09:30 | EIL-HPCL | 1 | 20.27 | 27 | 0 | 1 | 20.3 | 680 | B-Production in Progress | Elamaran
4256-102C | Despatch 4256-L | 2019-03-12 08:00 | 2019-01-31 07:30 | 2019-02-18 20:00 | EIL-HPCL | 1 | 58.96 | 26 | 0 | 1 | 59 | 2690 | B-Production in Progress | Elamaran
4256-2003 | Despatch 4256-E | 2019-03-12 08:00 | 2019-01-23 07:30 | 2019-03-16 19:30 | EIL-HPCL | 2 | 113.89 | 30 | 0 | 2 | 113.9 | 5240 | B-Production in Progress | Elamaran
4256-2004 | Despatch 4256-F | 2019-03-12 08:00 | 2019-02-01 07:30 | 2019-03-09 15:30 | EIL-HPCL | 2 | 96.31 | 19 | 0 | 2 | 96.3 | 4680 | B-Production in Progress | Elamaran
4256-2005 | Despatch 4256-G | 2019-03-12 08:00 | 2019-02-05 11:30 | 2019-03-11 13:42 | EIL-HPCL | 2 | 180.95 | 38 | 0 | 2 | 181 | 9140 | B-Production in Progress | Elamaran
4256-2009 | Despatch 4256-H | 2019-03-12 08:00 | 2019-02-05 11:30 | 2019-03-06 09:30 | EIL-HPCL | 2 | 110.79 | 14 | 0 | 2 | 110.8 | 5580 | B-Production in Progress | Elamaran
4256-2011 | Despatch 4256-I | 2019-03-12 08:00 | 2019-02-07 15:00 | 2019-02-27 12:00 | EIL-HPCL | 1 | 68.48 | 20 | 0 | 1 | 68.5 | 3420 | B-Production in Progress | Elamaran
4256-5001 | Despatch 4256-J | 2019-03-12 08:00 | 2019-02-12 11:30 | 2019-03-01 09:30 | EIL-HPCL | 2 | 88.68 | 41 | 0 | 2 | 88.7 | 4100 | B-Production in Progress | Elamaran
4256-6002 | Despatch 4256-K | 2019-03-12 08:00 | 2019-02-05 18:00 | 2019-02-16 18:00 | EIL-HPCL | 2 | 88.12 | 28 | 0 | 2 | 88.1 | 4000 | B-Production in Progress | Elamaran
4256-700-2003 | Despatch 4256-M | 2019-03-12 08:00 | 2019-01-19 08:30 | 2019-03-15 15:30 | EIL-HPCL | 2 | 95.4 | 22 | 0 | 2 | 95.4 | 4400 | B-Production in Progress | Elamaran
4266-72-E-51 | Despatch-4266C | 2019-02-24 08:30 | 2019-02-01 15:30 | 2019-03-14 17:30 | TECHNIP | 1 | 116.86 | 12 | 0 | 1 | 116.9 | 7160 | 2-Design Completed | Viswanathan
4266-74-E-04 | Despatch-4266E | 2019-02-24 08:30 | 2019-02-08 12:30 | 2019-03-16 17:30 | TECHNIP | 2 | 242.98 | 11 | 0 | 2 | 243 | 14425 | 2-Design Completed | Viswanathan
4266-74-E-106 | Despatch-4266F | 2019-02-24 08:30 | 2019-01-30 15:30 | 2019-02-18 17:30 | TECHNIP | 2 | 56.59 | 8 | 0 | 2 | 56.6 | 3000 | 2-Design Completed | Viswanathan
4266-74-E-51 | Despatch-4266D | 2019-02-24 08:30 | 2019-02-12 15:30 | 2019-02-20 17:30 | TECHNIP | 1 | 67.84 | 12 | 0 | 1 | 67.8 | 3950 | 2-Design Completed | Viswanathan
4266-75-E-12 | Despatch-4266G | 2019-02-24 08:30 | 2019-02-12 17:30 | 2019-03-20 06:30 | TECHNIP | 2 | 192.26 | 19 | 0 | 2 | 192.3 | 8113 | 2-Design Completed | Viswanathan
4266-75-E-56 A&B | Despatch-4266H | 2019-02-24 08:30 | 2019-04-02 11:30 | 2019-03-27 15:30 | TECHNIP | 2 | 110 | 5 | 0 | 2 | 110 | 6596 | 2-Design Completed | Viswanathan
4266-90-E-09 | Despatch-4266B | 2019-02-24 08:30 | 2019-02-19 10:30 | 2019-02-20 17:30 | TECHNIP | 2 | 157.71 | 18 | 0 | 2 | 157.7 | 10150 | 2-Design Completed | Viswanathan
4266-90-E-13C | Despatch-4266A | 2019-02-24 08:30 | 2019-02-16 14:30 | 2019-02-21 14:00 | TECHNIP | 1 | 199.89 | 14 | 0 | 1 | 199.9 | 10675 | 2-Design Completed | Viswanathan
4267-502-E-101 | Despatch-4267A | 2019-04-30 08:30 | 2019-03-02 12:30 | 2019-04-06 15:30 | TECHNIP-HPCL | 2 | 47.26 | 8 | 0 | 2 | 47.3 | 1850 | 2-Design Completed | Viswanathan
4267-502-E-104 | Despatch-4267B | 2019-04-30 08:30 | 2019-03-11 17:30 | 2019-03-13 12:30 | TECHNIP-HPCL | 2 | 35.88 | 2 | 0 | 2 | 35.9 | 1425 | 2-Design Completed | Viswanathan
4267-502-E-105 | Despatch-4267C | 2019-04-30 08:30 | 2019-02-28 15:30 | 2019-03-05 14:00 | TECHNIP-HPCL | 2 | 139.31 | 14 | 0 | 2 | 139.3 | 5375 | 2-Design Completed | Viswanathan
4267-502-E-108 | Despatch-4267D | 2019-04-30 08:30 | 2019-03-21 14:30 | 2019-03-19 12:30 | TECHNIP-HPCL | 2 | 33.99 | 7 | 0 | 2 | 34 | 1300 | 2-Design Completed | Viswanathan
4267-502-E-114 | Despatch-4267E | 2019-04-30 08:30 | 2019-03-07 17:30 | 2019-03-08 15:06 | TECHNIP-HPCL | 2 | 360.9 | 14 | 0 | 2 | 360.9 | 17860 | 2-Design Completed | Viswanathan
4267-502-E-119 | Despatch-4267F | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 35.28 | 4 | 0 | 2 | 35.3 | 1350 | 2-Design Completed | Viswanathan
4267-502-E-120 | Despatch-4267K | 2019-04-30 08:30 | 2019-03-21 17:30 | 2019-04-04 17:30 | TECHNIP-HPCL | 1 | 20 | 10 | 0 | 1 | 811.5 | 552 | 2-Design Completed | Viswanathan
4267-502-E-123 | Despatch-4267G | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 55.35 | 5 | 0 | 2 | 55.4 | 2570 | 2-Design Completed | Viswanathan
4267-502-E-123-1 | Despatch-4267G | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 55.35 | 5 | 0 | 2 | 55.4 | 2570 | 2-Design Completed | Viswanathan
4267-502-E-124 | Despatch-4267H | 2019-04-30 08:30 | 2019-03-08 11:42 | 2019-03-19 14:30 | TECHNIP-HPCL | 2 | 56.97 | 7 | 0 | 2 | 57 | 2710 | 2-Design Completed | Viswanathan
4267-502-E-129 | Despatch-4267I | 2019-04-30 08:30 | 2019-03-21 17:30 | 2019-03-20 09:30 | TECHNIP-HPCL | 2 | 26.95 | 9 | 0 | 2 | 27 | 1060 | 2-Design Completed | Viswanathan
4267-502-E-130 | Despatch-4267J | 2019-04-30 08:30 | 2019-04-04 17:30 | 2019-03-25 16:42 | TECHNIP-HPCL | 2 | 52.11 | 4 | 0 | 2 | 52.1 | 2300 | 2-Design Completed | Viswanathan
Site jobs | 4106 - Thermax site | 2018-04-18 08:30 |  | 2018-08-23 17:30 | All clients |  | 3.79 | 100 | 0 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4255 - MCCPTA site work | 2018-04-18 08:30 | 2018-05-02 12:30 | 2018-05-10 17:30 | All clients | 1 | 39.14 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4272 -RIL site work | 2018-04-18 08:30 |  | 2018-06-11 17:30 | All clients |  | 14.96 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4275 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-06-12 17:30 | All clients | 1 | 3.8 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4281 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-08-17 17:30 | All clients | 1 | 5.67 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4289 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-09-17 17:30 | All clients | 1 | 7.6 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4299 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-12-18 17:30 | All clients | 1 | 2.59 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4306 - MCCPTA site work | 2018-04-18 08:30 |  | 2018-12-18 17:30 | All clients | 1 | 3.16 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan

## Changes
Project | Despatch Name | CDD | BL FD | New FinishDate | ClientName | Des.Qty | Des.Val (Lakhs) | Pr.%WC | Task%WC | Pr.Qty | Pr.Val (Lakhs) | Project Budget (Hrs) | CompletionStatus | PM
4106 | Finished goods - Spares | 2018-09-01 08:00 | 0 | 2018-09-27 17:00 | Thermax | 1 | 5 | 11 | 0 | 1 | 5 | 0 | 8-Project Completed | Viswanathan
4161 | DESPATCH TO SITE | 2018-01-03 08:00 | 2017-10-09 12:00 | 2018-03-06 12:30 | BPCL | 3 | 39.16 | 100 | 100 | 3 | 41.2 | 2622 | 8-Project Completed | Anand
4166 | Despatch | 2018-03-31 08:00 | 0 | 2017-04-13 16:30 | Programme AD | 10 | 89 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4166 | Despatch | 2018-03-31 08:00 | 0 | 2017-04-13 16:30 | Programme AD | 20 | 178 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4166 | Despatch | 2018-03-31 08:00 | 0 | 2017-12-12 09:59 | Programme AD | 20 | 178 | 100 | 100 | 50 | 445 | 11925 | 8-Project Completed | Varun
4167 | DESPATCH TO SITE | 2017-10-07 08:00 | 2017-10-17 17:00 | 2017-12-22 17:00 | BORL | 1 | 67.21 | 100 | 100 | 1 | 67.2 | 2772 | 8-Project Completed | Anand
4169 | DESPATCH | 2017-12-20 08:00 | 2017-09-29 14:42 | 2017-09-29 14:44 | Essar | 1 | 15.29 | 100 | 100 | 2 | 214 | 8777 | 8-Project Completed | Varun
4169 | Despatch | 2017-12-20 08:00 | 2017-10-27 13:09 | 2018-03-16 14:00 | Essar | 1 | 198.71 | 100 | 100 | 2 | 214 | 8777 | 8-Project Completed | Varun
4170 | Depatch 4170F | 2018-01-01 06:00 | 2018-03-26 21:30 | 2018-03-26 21:30 | IOCL-EIL | 1 | 80.05 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170A1 | 2018-01-01 06:00 | 2018-02-16 20:30 | 2018-02-16 20:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170A2 | 2018-01-01 06:00 | 2018-02-16 20:30 | 2018-02-16 20:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170B1 | 2018-01-01 06:00 | 2018-01-30 20:30 | 2018-01-30 20:30 | IOCL-EIL | 1 | 62.03 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170B2 | 2018-01-01 06:00 | 2018-01-30 20:30 | 2018-01-30 20:30 | IOCL-EIL | 1 | 62.03 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170C1 | 2018-01-01 06:00 | 2018-02-16 21:30 | 2018-02-16 21:30 | IOCL-EIL | 1 | 19.76 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170C2 | 2018-01-01 06:00 | 2018-02-16 21:30 | 2018-02-16 21:30 | IOCL-EIL | 1 | 19.76 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170D1 | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 27.7 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170D2 | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 27.7 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170E | 2018-01-01 06:00 | 2018-03-16 21:30 | 2018-03-16 21:30 | IOCL-EIL | 1 | 30.92 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170G1 | 2018-01-01 06:00 | 2018-02-28 21:30 | 2018-02-28 21:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170G2 | 2018-01-01 06:00 | 2018-02-28 21:30 | 2018-02-28 21:30 | IOCL-EIL | 1 | 47.82 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170H | 2018-01-01 06:00 | 2018-03-28 20:30 | 2018-03-28 20:30 | IOCL-EIL | 1 | 118.32 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170I1 | 2018-01-01 06:00 | 2018-03-16 21:30 | 2018-03-16 21:30 | IOCL-EIL | 1 | 32.63 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170I2 | 2018-01-01 06:00 | 2018-03-13 20:30 | 2018-03-13 20:30 | IOCL-EIL | 1 | 32.63 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J1 | 2018-01-01 06:00 | 2018-02-23 21:30 | 2018-02-23 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J2A | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170J2B | 2018-01-01 06:00 | 2018-03-06 21:30 | 2018-03-06 21:30 | IOCL-EIL | 1 | 44.01 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170K1 | 2018-01-01 06:00 | 2018-03-24 20:30 | 2018-03-24 20:30 | IOCL-EIL | 1 | 13.4 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170K2 | 2018-01-01 06:00 | 2018-03-24 21:30 | 2018-03-24 21:30 | IOCL-EIL | 1 | 13.4 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4170 | Despatch 4170L | 2018-01-01 06:00 | 2018-03-14 20:30 | 2018-03-14 20:30 | IOCL-EIL | 1 | 32.72 | 100 | 100 | 21 | 910.6 | 90569 | 8-Project Completed | Elamaran
4174 | DESPATCH | 2017-12-14 08:00 | 2017-12-30 17:10 | 2018-02-05 17:00 | IOCL | 1 | 57.79 | 100 | 100 | 1 | 59.4 | 4688 | 8-Project Completed | Elamaran
4180 | Despatch | 2017-12-29 08:00 | 2018-01-22 21:30 | 2018-01-22 21:30 | NIOT | 1 | 43.08 | 100 | 100 | 2 | 86.2 | 1696 | 8-Project Completed | Varun
4180 | Despatch | 2017-12-29 08:00 | 2018-01-23 12:30 | 2018-01-23 12:30 | NIOT | 1 | 43.08 | 100 | 100 | 2 | 86.2 | 1696 | 8-Project Completed | Varun
4182 | DESPATCH | 2018-01-10 08:00 | 2017-09-05 12:21 | 2018-02-05 17:00 | UPL | 6 | 144 | 100 | 100 | 6 | 144 | 4812 | 8-Project Completed | Ethiraj
4183 | Despatch | 2018-01-04 08:00 | 2018-02-27 20:22 | 2018-03-31 10:00 | IOCL | 1 | 113.14 | 100 | 100 | 1 | 115.4 | 11102 | 8-Project Completed | Ethiraj
4197 | Despatch | 2018-01-06 08:00 | 2018-01-05 09:50 | 2018-02-03 08:36 | ASL | 8 | 92.1 | 100 | 100 | 8 | 92.1 | 13200 | 8-Project Completed | Anand
4211 | Despatch | 2018-07-17 08:00 | 2018-04-30 07:50 | 2018-04-30 14:47 | Advanced System Laboratory | 25 | 142.5 | 100 | 100 | 25 | 142.5 | 4450 | 8-Project Completed | Varun
4213 | Despatch | 2018-02-27 08:00 | 2018-01-30 16:00 | 2018-03-03 09:00 | SRF | 1 | 28.75 | 100 | 100 | 1 | 28.8 | 1220 | 8-Project Completed | Elamaran
4215 | Despatch | 2017-11-30 08:00 | 2018-01-19 15:30 | 2018-02-17 18:00 | SRF | 1 | 10.5 | 100 | 100 | 1 | 10.5 | 336 | 8-Project Completed | Varun
4216 | Product Transportation to Site | 2018-07-31 08:30 | 2018-06-16 17:30 | 2019-02-15 17:30 | BEML | 5 | 0.8 | 20 | 0 | 75 | 12 | 1800 | 9-On Hold | Varun
4218 | Despatch | 2018-08-11 08:00 | 2018-07-20 21:54 | 2018-08-30 14:00 | CPCL | 1 | 79.07 | 100 | 100 | 1 | 80.3 | 7383 | 8-Project Completed | Varun
4227 | Despatch | 2018-08-10 08:30 | 2018-03-17 14:30 | 2018-03-17 14:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 2018-05-19 11:30 | 2018-05-11 09:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 2018-05-19 11:30 | 2018-06-06 12:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4227 | Despatch - 20 Nos | 2018-08-10 08:30 | 0 | 2018-07-20 12:30 | BDL | 20 | 3.2 | 100 | 100 | 100 | 16 | 3000 | 8-Project Completed | Varun
4230 | Despatch | 2018-06-30 08:00 | 2018-03-31 18:30 | 2018-03-31 18:30 | ASL | 7 | 36.4 | 100 | 100 | 10 | 52 | 1600 | 8-Project Completed | Varun
4230 | Despatch | 2018-06-30 08:00 | 2018-04-26 18:00 | 2018-04-30 20:22 | ASL | 3 | 15.6 | 100 | 100 | 10 | 52 | 1600 | 8-Project Completed | Varun
4232 | Despatch | 2018-07-07 08:00 | 2018-06-16 10:30 | 2018-07-05 17:00 | IOCL-TECHNIP | 1 | 52.48 | 100 | 100 | 1 | 52.5 | 4245 | 8-Project Completed | Elamaran
4233 | Despatch | 2018-01-22 08:00 | 2017-12-30 17:30 | 2018-01-23 17:30 | KMML | 22 | 0.81 | 100 | 100 | 22 | 1 | 12 | 8-Project Completed | Varun
4239 | Invoice to Customer | 2018-02-03 08:30 | 2018-03-16 12:30 | 2018-03-17 12:30 | IGCAR | 1 | 9.47 | 100 | 100 | 1 | 9.5 | 260 | 8-Project Completed | 0
4240 | Despatch | 2018-07-20 08:30 | 2018-05-22 19:30 | 2019-03-26 19:30 | RCI | 2 | 19.4 | 18 | 0 | 2 | 19.4 | 840 | 9-On Hold | Varun
4240 | Final Inspection & Dispatch | 2018-07-20 08:30 | 2018-05-22 19:30 | 2019-03-26 19:30 | RCI | 0 | 0 | 18 | 0 | 2 | 19.4 | 840 | 9-On Hold | Varun
4241 | Despatch - 4241 | 2018-08-21 08:00 | 2018-08-10 09:30 | 2019-01-11 21:30 | IOCL-EIL | 1 | 5 | 63 | 0 | 1 | 5 | 2059 | B-Production in Progress | Elamaran
4242 | Despatched | 2018-03-10 08:00 | 2018-03-13 17:00 | 2018-03-13 17:00 | KMML | 1 | 2.52 | 100 | 100 | 1 | 2.5 | 50 | 8-Project Completed | PMO
4243 | despatch through courier | 2018-03-10 08:00 | 2018-03-05 17:30 | 2018-03-05 17:30 | Apid Engineer | 1 | 0.3 | 100 | 100 | 1 | 0.3 | 6 | 8-Project Completed | PMO
4245 | Finished good - Pump spares | 2018-03-31 08:30 | 2018-03-17 09:30 | 2018-08-27 17:30 | Grasim | 1 | 1.73 | 100 | 100 | 1 | 1.7 | 280 | 8-Project Completed | Viswanathan
4246 | Despatch-4246 | 2018-11-15 08:00 | 2018-11-13 16:41 | 2018-12-31 17:00 | SRF | 1 | 96 | 99 | 0 | 1 | 96 | 2955 | 6-QC Completed | Ethiraj
4247 | Despatch | 2018-06-30 08:00 | 0 | 2018-12-29 19:29 | SSIS | 0 | 0 | 99 | 0 | 2 | 20.9 | 2043 | 5-Production Completed | Varun
4247 | Payment followup and despatch | 2018-06-30 08:00 | 0 | 2018-12-29 19:29 | SSIS | 2 | 20.93 | 99 | 0 | 2 | 20.9 | 2043 | 5-Production Completed | Varun
4248 | Product Transportation to Site | 2018-06-18 08:30 | 2018-04-19 16:30 | 2018-06-27 15:30 | KMML | 3 | 1.32 | 100 | 100 | 3 | 1.3 | 70 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-07-02 14:30 | 2018-07-24 11:00 | SVCI | 2 | 21.76 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-06-22 20:30 | 2018-07-24 13:00 | SVCI | 2 | 21.76 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4249 | Despatch | 2018-07-05 08:30 | 2018-06-27 12:30 | 2018-07-27 12:30 | SVCI | 2 | 22.26 | 100 | 100 | 6 | 66.5 | 9780 | 8-Project Completed | Ethiraj
4250 | Finished good - Pump spares | 2018-03-31 08:30 | 2018-05-04 08:31 | 2018-08-21 17:30 | Grasim | 3 | 3.06 | 100 | 100 | 3 | 3.1 | 312 | 8-Project Completed | Viswanathan
4251 | Final Assembly & Machining | 2018-08-05 08:30 | 0 | 2018-11-28 16:30 | NPOL | 1 | 37.34 | 100 | 100 | 1 | 37.3 | 1330 | 8-Project Completed | Varun
4252 | Despatch | 2018-12-31 08:30 | 0 | 2019-01-02 19:30 | NPOL | 1 | 76 | 83 | 0 | 1 | 76 | 3130 | B-Production in Progress | Varun
4253 | Despatch | 2018-06-14 08:30 | 2018-06-13 09:30 | 2018-06-26 09:30 | KMML | 4 | 3.99 | 100 | 100 | 4 | 4 | 400 | 8-Project Completed | Elamaran
4254 | Despatch | 2018-10-21 08:30 | 2018-10-01 14:30 | 2018-10-23 18:30 | IOCL | 1 | 31.7 | 100 | 100 | 1 | 33 | 2957 | 8-Project Completed | Varun
4257 | Despatch | 2018-09-10 08:00 | 2018-08-21 09:30 | 2018-11-10 17:00 | Keltron | 1 | 43 | 100 | 100 | 1 | 43 | 2370 | 8-Project Completed | Elamaran
4258 | Despatch | 2018-10-13 08:00 | 2018-10-03 21:00 | 2018-09-29 19:30 | RRCAT | 5 | 13.5 | 100 | 100 | 5 | 13.5 | 530 | 8-Project Completed | Elamaran
4259 | Despatch | 2018-10-04 08:00 | 2018-09-17 12:30 | 2018-09-29 16:00 | Orient Paper Mills | 1 | 20.3 | 100 | 100 | 1 | 20.3 | 2720 | 8-Project Completed | Ethiraj
4260 | Despatch-4260-No1 No2 | 2018-10-04 08:00 | 2018-10-04 16:30 | 2019-01-03 08:00 | CCM CHEMICALS SDN BHD | 2 | 43.47 | 99 | 0 | 2 | 43.5 | 4780 | 6-QC Completed | Ethiraj
4261 | Finished good despatch | 2018-05-15 08:00 | 2018-03-05 17:30 | 2018-05-04 15:30 | DCW Limited | 1 | 9 | 41 | 0 | 1 | 9 | 400 | 8-Project Completed | Viswanathan
4262 | Despatch | 2018-09-15 08:00 | 2018-03-05 17:30 | 2018-09-01 17:00 | Tata Chemicals Ltd, Mithapur | 4 | 0.79 | 100 | 100 | 4 | 0.8 | 100 | 8-Project Completed | Ethiraj
4263 | Product Transportation to Site - 1st lot | 2018-10-17 08:00 | 2018-10-15 07:30 | 2018-09-27 08:00 | Kutch Chemical Industries Limited | 6 | 92.4 | 95 | 100 | 12 | 189.8 | 4320 | 7-Despatched | Ethiraj
4263 | Product Transportation to Site - 2nd lot | 2018-10-17 08:00 | 0 | 2018-10-26 16:00 | Kutch Chemical Industries Limited | 6 | 97.4 | 95 | 100 | 12 | 189.8 | 4320 | 7-Despatched | Ethiraj
4264 | Finished goods | 2018-07-15 08:00 | 2018-05-31 17:30 | 2018-05-31 17:30 | CAL, TEAM's Group company | 20 | 18.3 | 100 | 100 | 20 | 18.3 | 680 | 8-Project Completed | Viswanathan
4265 | Finished goods | 2018-10-14 08:00 | 0 | 2018-09-29 20:30 | The Kerala Minerals & Metals Ltd | 1 | 5.3 | 100 | 100 | 1 | 5.3 | 925 | 8-Project Completed | Elamaran
4268 | Despatch-4268 | 2018-12-24 08:30 | 2018-12-20 12:30 | 2019-01-15 09:30 | Technip Mumbai | 1 | 253.11 | 81 | 0 | 1 | 253.1 | 17360 | B-Production in Progress | Ethiraj
4269 | Despatch-4269 | 2018-12-25 08:30 | 2018-11-03 17:30 | 2018-12-31 14:30 | SPX FLOW | 2 | 69 | 96 | 0 | 2 | 69 | 1560 | B-Production in Progress | Ethiraj
4270 | Finished good - Anode | 2018-07-03 08:30 | 0 | 2018-05-02 17:30 | VXL Life sceinces, Mumbai | 1 | 0.8 | 0 | 0 | 2 | 1.6 | 300 | 8-Project Completed | Viswanathan
4270 | Finished good - Cathode | 2018-07-03 08:30 | 0 | 2018-06-11 17:30 | VXL Life sceinces, Mumbai | 1 | 0.9 | 0 | 0 | 2 | 1.6 | 300 | 8-Project Completed | Viswanathan
4271 | Finished goods | 2018-07-10 08:00 | 2018-07-05 17:30 | 2018-09-28 08:00 | KMML | 1 | 0.34 | 100 | 100 | 1 | 0.3 | 4 | 8-Project Completed | Elamaran
4273 | Despatch | 2018-09-27 08:00 | 2018-08-23 09:30 | 2018-09-25 09:30 | KMML, Kochi | 60 | 0.86 | 100 | 100 | 60 | 0.9 | 100 | 8-Project Completed | Varun
4274 | Despatch | 2019-03-30 08:00 | 0 | 2018-07-27 17:30 | NIOT | 4 | 0.46 | 100 | 100 | 10 | 1.2 | 100 | 5-Production Completed | Varun
4274 | Despatch | 2019-03-30 08:00 | 0 | 2018-08-24 17:30 | NIOT | 1 | 0.12 | 100 | 100 | 10 | 1.2 | 100 | 5-Production Completed | Varun
4276 | Finished good | 2018-06-30 08:00 | 0 | 2018-06-25 12:00 | Praxair | 1 | 0.89 | 20 | 0 | 1 | 0.9 | 0 | 8-Project Completed | Viswanathan
4279 | Finished goods | 2018-10-30 08:00 | 0 | 2018-10-29 17:00 | CCAL | 1 | 0.65 | 100 | 100 | 1 | 0.7 | 100 | 8-Project Completed | Hariprasath
4280 | Despatch | 2018-12-12 08:00 | 2018-10-03 09:30 | 2018-09-29 13:30 | NSTL, Vizag | 6 | 30 | 100 | 100 | 6 | 30 | 1650 | 8-Project Completed | Elamaran
4282 | Finished goods | 2018-10-30 08:00 | 0 | 2018-10-29 17:00 | CCAL | 1 | 0.32 | 100 | 100 | 1 | 0.3 | 3 | 8-Project Completed | Hariprasath
4283 | Finished goods - 1st Lot | 2018-07-15 08:00 | 2018-05-31 17:30 | 2018-07-30 14:30 | CAL, TEAM's Group company | 22 | 23.68 | 100 | 100 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 2nd Lot | 2018-07-15 08:00 | 0 | 2018-08-18 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 3rd Lot | 2018-07-15 08:00 | 0 | 2018-08-29 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 4th Lot | 2018-07-15 08:00 | 0 | 2018-09-26 14:30 | CAL, TEAM's Group company | 28 | 30.14 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4283 | Finished goods - 5th Lot | 2018-07-15 08:00 | 0 | 2018-10-23 14:30 | CAL, TEAM's Group company | 47 | 49.77 | 100 | 0 | 153 | 163.9 | 680 | 8-Project Completed | Viswanathan
4284 | Despatch-4284-2Nos | 2019-03-25 08:00 | 2019-03-15 13:30 | 2019-02-27 08:30 | Larsen & Toubro | 2 | 49.6 | 11 | 0 | 2 | 49.6 | 1640 | 4-Purchase Completed | Hariprasath
4285 | Finished goods | 2018-10-30 08:00 | 0 | 2018-10-29 17:00 | Tata Chemicals Limited | 1 | 0.3 | 100 | 100 | 1 | 0.3 | 0 | 8-Project Completed | Hariprasath
4286 | Despatch | 2019-02-15 08:30 | 2019-02-08 17:00 | 2019-02-08 17:00 | TVG SRAAC, Kurnool | 0 | 0 | 60 | 0 | 10 | 98.5 | 16300 | B-Production in Progress | Hariprasath
4286 | Despatch-4286-10Nos | 2019-02-15 08:30 | 2019-02-08 17:00 | 2019-02-08 17:00 | TVG SRAAC, Kurnool | 10 | 98.5 | 60 | 0 | 10 | 98.5 | 16300 | B-Production in Progress | Hariprasath
4287 | Inspection & dispatch | 2018-12-30 08:00 | 0 | 2018-10-26 17:00 | VEM Technologies, Hyd | 24 | 5.23 | 100 | 100 | 24 | 5.2 | 0 | 7-Despatched | Hariprasath
4288 | Finished goods | 2018-11-21 08:00 | 0 | 2018-10-23 17:00 | Lords Chloro Alkalies | 2 | 0.55 | 100 | 100 | 1 | 0.6 | 14 | 8-Project Completed | Hariprasath
4290 | Delivery - 10 nos | 2018-10-06 08:00 | 0 | 2018-09-17 17:30 | NIOT | 10 | 0.1 | 100 | 100 | 10 | 0.1 | 100 | 8-Project Completed | Hariprasath
4294 | Finished good | 2018-10-18 08:00 | 0 | 2018-10-18 17:00 | Kavinaya (Praxair) | 1 | 0.89 | 0 | 0 | 1 | 0.9 | 0 | 8-Project Completed | Hariprasath
4295 | Despatch-4295-2Nos | 2019-01-18 08:30 | 0 | 2019-01-15 17:30 | KMML | 2 | 10.68 | 82 | 0 | 2 | 10.7 | 860 | B-Production in Progress | Hariprasath
4296 | Despatch 4256-A | 2019-08-16 08:30 | 2019-01-08 10:30 | 2019-06-10 15:30 | Technimont | 1 | 200.78 | 3 | 0 | 20 | 1390 | 5282 | 2-Design Completed | Elamaran
4297 | Despatch-4297 | 2019-04-16 08:30 | 0 | 2019-03-29 17:30 | CCM | 4 | 16.66 | 45 | 0 | 4 | 16.7 | 700 | 2-Design Completed | Vinothkumar
4298 | Inspection & dispatch | 2018-12-30 08:00 | 0 | 2018-11-28 17:00 | BDL | 12 | 1.92 | 100 | 100 | 12 | 1.9 | 0 | 8-Project Completed | Hariprasath
4300 | Despatch-4300 | 2019-03-31 08:30 | 2019-03-28 17:30 | 2019-03-26 17:30 | YUSUF BIN AHMED KANOO W.L.L., | 64 | 15.67 | 22 | 0 | 64 | 15.7 | 448 | 3-PPC Completed | Vinothkumar
4301 | Despatch | 2019-04-03 08:30 | 0 | 2019-03-18 17:30 | MCCPTA | 1 | 2.53 | 14 | 0 | 1 | 2.5 | 8 | 3-PPC Completed | Hariprasath
4302 | Despatch-4302 | 2019-05-08 08:00 | 0 | 2019-05-04 09:30 | Sirpur Paper Mills | 1 | 10.07 | 39 | 0 | 1 | 10.1 | 1430 | 2-Design Completed | Vinothkumar
4303 | Inspection & dispatch | 2018-12-30 08:00 | 0 | 2018-11-15 17:00 | BDL | 1 | 0.05 | 0 | 0 | 1 | 0.1 | 0 | 8-Project Completed | Hariprasath
4305 | Despatch-4295-30Nos | 2019-01-03 08:30 | 2019-01-23 17:30 | 2019-01-25 12:30 | Modern Engineering & Plastics | 30 | 0.74 | 2 | 0 | 30 | 0.7 | 280 | 3-PPC Completed | Hariprasath
4309 | Despatch | 2019-03-23 08:00 | 2019-02-20 09:00 | 2019-02-20 09:00 | KMML | 40 | 0.51 | 8 | 0 | 40 | 0.5 | 8 | 3-PPC Completed | Hariprasath
4173-02 | DESPATCH | 2018-04-07 06:00 | 2018-01-09 06:04 | 2018-03-31 18:00 | IOCL-EIL | 2 | 111.72 | 100 | 100 | 2 | 111.7 | 9702 | 8-Project Completed | Ethiraj
4173-108 | Despatch | 2018-04-07 06:00 | 2018-03-31 13:30 | 2018-03-31 13:30 | IOCL-EIL | 1 | 65.62 | 100 | 100 | 1 | 65.6 | 5579 | 8-Project Completed | Ethiraj
4173-126 | DESPATCH | 2018-04-07 06:00 | 2018-03-30 08:40 | 2018-03-30 08:40 | IOCL-EIL | 2 | 43.75 | 100 | 100 | 2 | 43.8 | 4352 | 8-Project Completed | Ethiraj
4192-HC 150-1 | Despatch | 2019-01-07 08:00 | 2018-05-14 13:12 | 2018-09-05 17:00 | IGCAR | 1 | 66.77 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-2 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2018-12-27 09:30 | IGCAR | 1 | 66.77 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-2 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2018-12-27 09:30 | IGCAR | 0 | 0 | 100 | 100 | 1 | 66.8 | 16880 | 8-Project Completed | Varun
4192-HC 150-3 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-04-30 12:30 | IGCAR | 1 | 66.77 | 66 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-3 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-04-30 12:30 | IGCAR | 0 | 0 | 66 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-4 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-4 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 0 | 0 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-5 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-5 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 0 | 0 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-6 | Despatch | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 1 | 66.77 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-HC 150-6 | Testing | 2019-01-07 08:00 | 2018-08-07 21:30 | 2019-07-02 12:30 | IGCAR | 0 | 0 | 0 | 0 | 1 | 66.8 | 16880 | 9-On Hold | Varun
4192-VC-100 | Despatch | 2019-01-07 08:30 | 2018-10-09 08:30 | 2018-11-30 08:30 | IGCAR | 1 | 2.07 | 100 | 100 | 1 | 2.1 | 80 | 8-Project Completed | Varun
4192-VC-600 | Despatch | 2019-01-07 08:30 | 2018-10-09 08:30 | 2018-11-30 08:30 | IGCAR | 1 | 2.55 | 100 | 100 | 1 | 2.6 | 200 | 8-Project Completed | Varun
4201-0004 | Despatch | 2018-08-06 08:00 | 0 | 2018-09-29 14:00 | Dangote | 4 | 386.56 | 100 | 0 | 4 | 386.6 | 33620 | 6-QC Completed | Anand
4201-0005 | Despatch | 2018-08-31 08:00 | 0 | 2018-09-29 15:30 | Dangote | 4 | 301.44 | 100 | 0 | 4 | 301.4 | 26218 | 6-QC Completed | Anand
4203-AT 630-2 | Despatch | 2019-02-14 08:30 | 2018-07-27 22:00 | 2018-08-23 22:00 | IGCAR | 1 | 2.91 | 100 | 100 | 1 | 2.9 | 575 | 8-Project Completed | Varun
4203-AT 630-4,5,6 | Despatch | 2019-02-14 08:30 | 2018-07-27 22:00 | 2018-11-30 22:00 | IGCAR | 1 | 2.91 | 100 | 100 | 1 | 8.7 | 1725 | 8-Project Completed | Varun
4203-AT-400 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 22 | 50.6 | 0 | 0 | 22 | 50.6 | 8074 | 9-On Hold | Varun
4203-AT-400N | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 7 | 16.31 | 0 | 0 | 7 | 16.3 | 2628 | 9-On Hold | Varun
4203-AT-500 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 14 | 38.78 | 0 | 0 | 14 | 38.8 | 7393 | 9-On Hold | Varun
4203-AT-630 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 20 | 58.2 | 0 | 0 | 20 | 58.2 | 11523 | 9-On Hold | Varun
4203-AT-630-10 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-03 08:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 575 | B-Production in Progress | Varun
4203-AT-630-3 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-05 08:30 | IGCAR | 1 | 2.91 | 91 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-7 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2018-12-31 08:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-8 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2018-12-31 20:30 | IGCAR | 1 | 2.91 | 99 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630-9 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-01-03 08:30 | IGCAR | 1 | 2.91 | 98 | 0 | 1 | 2.9 | 576 | B-Production in Progress | Varun
4203-AT-630N | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 2 | 6.02 | 0 | 0 | 2 | 6 | 1155 | 9-On Hold | Varun
4203-AT-720 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 11 | 33.99 | 0 | 0 | 11 | 34 | 7070 | 9-On Hold | Varun
4203-RCAT-125 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 16 | 25.12 | 0 | 0 | 16 | 25.1 | 3057 | 9-On Hold | Varun
4203-RCAT-500 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 6 | 15.96 | 0 | 0 | 6 | 16 | 3528 | 9-On Hold | Varun
4203-RCAT-90 | Despatch | 2019-02-14 08:30 | 2018-11-14 16:30 | 2019-04-26 22:00 | IGCAR | 16 | 20.96 | 0 | 0 | 16 | 21 | 2165 | 9-On Hold | Varun
4203-RCVC-50-1 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 20:30 | IGCAR | 1 | 1.04 | 74 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-2 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 16:30 | IGCAR | 1 | 1.04 | 71 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-3 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 14:00 | IGCAR | 1 | 1.04 | 75 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4203-RCVC-50-4 | Despatch | 2019-02-14 08:30 | 2018-10-30 08:30 | 2019-01-08 14:00 | IGCAR | 1 | 1.04 | 75 | 0 | 1 | 1 | 43 | B-Production in Progress | Varun
4209-A&F | Despatch | 2018-10-01 06:00 | 0 | 2019-02-05 16:57 | Dangote | 2 | 88.35 | 51 | 0 | 2 | 88.4 | 9336 | B-Production in Progress | Anand
4209-B&G | Despatch | 2018-10-01 06:00 | 0 | 2018-11-20 17:30 | Dangote | 2 | 34.89 | 100 | 0 | 2 | 34.9 | 2086 | 6-QC Completed | Anand
4209-C&H | Despatch | 2018-10-01 06:00 | 0 | 2019-03-20 10:30 | Dangote | 2 | 221.48 | 46 | 0 | 2 | 221.5 | 22160 | B-Production in Progress | Anand
4209-D&I | Despatch | 2018-10-01 06:00 | 0 | 2018-12-28 11:00 | Dangote | 2 | 25.54 | 100 | 0 | 2 | 25.5 | 1450 | 6-QC Completed | Anand
4209-E&J | Despatch | 2018-10-01 06:00 | 0 | 2018-12-15 17:30 | Dangote | 2 | 10.37 | 99 | 0 | 2 | 10.4 | 570 | 6-QC Completed | Anand
4209-K&L | Despatch | 2018-10-01 06:00 | 0 | 2018-12-18 17:30 | Dangote | 4 | 21.82 | 100 | 0 | 4 | 21.8 | 1176 | 6-QC Completed | Anand
4209-M | Despatch | 2018-10-01 06:00 | 0 | 2019-01-08 12:03 | Dangote | 2 | 29.2 | 91 | 0 | 2 | 29.2 | 1560 | B-Production in Progress | Anand
4209-N | Despatch | 2018-10-01 06:00 | 0 | 2019-01-08 10:45 | Dangote | 1 | 17.01 | 91 | 0 | 1 | 17 | 1080 | B-Production in Progress | Anand
4209-O | Despatch | 2018-10-01 06:00 | 0 | 2018-12-14 17:30 | Dangote | 2 | 15.99 | 100 | 0 | 2 | 16 | 952 | 6-QC Completed | Anand
4209-P | Despatch | 2018-10-01 06:00 | 0 | 2019-01-08 14:02 | Dangote | 2 | 27.34 | 91 | 0 | 2 | 27.3 | 1502 | B-Production in Progress | Anand
4209-Q | Despatch | 2018-10-01 06:00 | 0 | 2018-12-15 12:30 | Dangote | 2 | 21.04 | 100 | 0 | 2 | 21 | 1142 | 6-QC Completed | Anand
4209-R&S | Despatch | 2018-10-01 06:00 | 0 | 2018-11-17 17:30 | Dangote | 2 | 11.79 | 100 | 0 | 2 | 11.8 | 518 | 6-QC Completed | Anand
4220-A1001 | Despatch 4220 A - AB | 2019-05-26 08:00 | 0 | 2019-01-18 17:30 | Dangote | 2 | 302.87 | 95 | 0 | 4 | 605.7 | 57103 | B-Production in Progress | Anand
4220-A1001 | Despatch 4220 A - CD | 2019-05-26 08:00 | 0 | 2019-02-11 17:30 | Dangote | 2 | 302.87 | 95 | 0 | 4 | 605.7 | 57103 | B-Production in Progress | Anand
4220-B1003 | Despatch | 2019-05-26 06:00 | 0 | 2019-12-31 17:30 | Dangote | 2 | 204.5 | 0 | 0 | 2 | 204.5 | 20354 | 2-Design Completed | Anand
4220-D1006 | Despatch | 2019-05-26 08:00 | 0 | 2020-01-27 08:44 | Dangote | 2 | 199.53 | 3 | 0 | 2 | 199.5 | 20080 | 4-Purchase Completed | Anand
4220-E1007 | Despatch | 2019-05-26 08:00 | 0 | 2019-03-28 17:30 | Dangote | 2 | 304.81 | 0 | 0 | 2 | 304.8 | 24348 | 4-Purchase Completed | Anand
4220-F1008 | Despatch | 2019-05-26 08:00 | 0 | 2019-06-29 17:30 | Dangote | 1 | 16.83 | 0 | 0 | 1 | 16.8 | 2053 | 4-Purchase Completed | Anand
4220-G1009-1 | Despatch | 2019-05-26 08:00 | 0 | 2019-07-17 17:30 | Dangote | 2 | 92.59 | 0 | 0 | 2 | 92.6 | 9310 | 4-Purchase Completed | Anand
4220-H1010 | Despatch | 2019-05-26 08:00 | 0 | 2019-03-27 17:30 | Dangote | 1 | 14.16 | 13 | 0 | 1 | 14.2 | 13494 | 4-Purchase Completed | Anand
4220-I1011 | Despatch | 2018-10-02 08:00 | 0 | 2019-05-28 15:00 | Dangote | 4 | 799.3 | 0 | 0 | 4 | 799.3 | 82197 | 4-Purchase Completed | Anand
4220-J1012 | Despatch | 2019-05-26 06:00 | 0 | 2019-07-12 17:00 | Dangote | 4 | 600.48 | 1 | 0 | 4 | 600.5 | 77331 | 4-Purchase Completed | Anand
4220-K1013 | Despatch | 2019-05-26 08:00 | 0 | 2019-08-23 11:00 | Dangote | 2 | 1057.37 | 0 | 0 | 2 | 1057.4 | 65261 | 4-Purchase Completed | Anand
4220-L1014 | Despatch | 2019-05-26 08:00 | 0 | 2019-07-18 10:28 | Dangote | 1 | 6.4 | 6 | 0 | 1 | 6.4 | 983 | 4-Purchase Completed | Anand
4220-N1011 | Despatch | 2019-05-26 08:00 | 0 | 2019-07-20 08:44 | Dangote | 1 | 38.85 | 0 | 0 | 1 | 38.9 | 7561 | 4-Purchase Completed | Anand
4220-O1011 | Despatch | 2019-05-26 08:00 | 0 | 2019-09-24 10:44 | Dangote | 1 | 38.26 | 0 | 0 | 1 | 38.3 | 13116 | 3-PPC Completed | Anand
4221-2403 | Despatch | 2018-09-01 08:00 | 0 | 2019-10-31 17:30 | Dangote | 1 | 10.66 | 3 | 0 | 1 | 10.7 | 517 | 2-Design Completed | Anand
4221-7001 | Despatch | 2018-09-01 08:00 | 0 | 2019-10-31 17:30 | Dangote | 1 | 31.08 | 29 | 0 | 1 | 31.1 | 872 | 2-Design Completed | Anand
4221-9101 | Despatch | 2018-09-01 08:00 | 2018-10-06 09:58 | 2019-11-05 17:58 | Dangote | 1 | 48.85 | 1 | 0 | 1 | 48.9 | 425 | 2-Design Completed | Anand
4224-103 | Despatch 4224-A | 2018-06-11 08:00 | 2018-05-31 20:30 | 2018-06-08 20:30 | IOCL-EIL | 1 | 33.03 | 100 | 100 | 1 | 35.5 | 3066 | 8-Project Completed | Elamaran
4224-309 | Despatch 4224-B | 2018-06-11 08:00 | 2018-06-06 17:40 | 2018-06-08 20:40 | IOCL-EIL | 1 | 16.98 | 100 | 100 | 1 | 17 | 739 | 8-Project Completed | Elamaran
4228-010 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-06-30 13:01 | 2017-11-09 17:00 | IOCL-EIL | 1 | 39.79 | 97 | 100 | 2 | 79.6 | 5040 | 8-Project Completed | Ethiraj
4228-010 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-07-20 07:41 | 2018-11-09 15:30 | IOCL-EIL | 1 | 39.79 | 97 | 100 | 2 | 79.6 | 5040 | 8-Project Completed | Ethiraj
4228-014 | Clearance By TPI | 2018-07-31 08:00 | 2018-07-02 09:52 | 2018-11-05 18:30 | IOCL-EIL | 1 | 11.57 | 100 | 100 | 2 | 23.1 | 1736 | 8-Project Completed | Ethiraj
4228-014 | Despatch Clearanceby TPI | 2018-07-31 08:00 | 2018-06-30 13:01 | 2018-11-05 17:00 | IOCL-EIL | 1 | 11.57 | 100 | 100 | 2 | 23.1 | 1736 | 8-Project Completed | Ethiraj
4228-102 | Shipping | 2018-07-31 08:00 | 2018-07-17 09:00 | 2018-11-10 17:00 | IOCL-EIL | 1 | 7.24 | 100 | 100 | 1 | 7.2 | 814 | 8-Project Completed | Ethiraj
4237-A | Despatch | 2018-09-08 08:00 | 2018-11-08 18:30 | 2019-01-30 10:50 | IOCL-EIL | 1 | 102.51 | 85 | 0 | 1 | 102.5 | 5670 | B-Production in Progress | Ethiraj
4237-B | Despatch | 2018-09-08 08:00 | 2018-08-09 19:02 | 2019-01-21 12:00 | IOCL-EIL | 1 | 63.87 | 88 | 0 | 1 | 63.9 | 3100 | B-Production in Progress | Ethiraj
4237-C | Despatch | 2018-09-08 08:00 | 2018-12-05 07:05 | 2019-01-21 21:24 | IOCL-EIL | 1 | 85.17 | 88 | 0 | 1 | 85.2 | 5070 | B-Production in Progress | Ethiraj
4237-D | Despatch | 2018-09-08 08:00 | 2018-08-08 18:30 | 2019-01-14 18:30 | IOCL-EIL | 4 | 48.45 | 85 | 0 | 1 | 48.5 | 2320 | B-Production in Progress | Ethiraj
4238-49 | Despatch-4238(A) | 2018-10-12 08:30 | 2018-09-24 17:30 | 2018-10-12 17:30 | HPCL | 1 | 57.65 | 100 | 100 | 1 | 57.7 | 5267 | 8-Project Completed | Elamaran
4238-7001 | Despatch-4238(B) | 2018-10-12 08:30 | 2018-09-18 13:31 | 2018-10-12 18:31 | HPCL | 2 | 20 | 100 | 100 | 2 | 20 | 1234 | 8-Project Completed | Elamaran
4256-1002 | Despatch 4256-A | 2019-03-12 08:00 | 2019-01-08 10:30 | 2019-03-09 18:30 | EIL-HPCL | 1 | 200.78 | 20 | 0 | 1 | 200.8 | 10920 | B-Production in Progress | Elamaran
4256-1007 | Despatch 4256-B | 2019-03-12 08:00 | 2018-12-29 21:30 | 2019-03-09 14:30 | EIL-HPCL | 1 | 84.72 | 17 | 0 | 1 | 84.7 | 4340 | B-Production in Progress | Elamaran
4256-1008 | Despatch 4256-C | 2019-03-12 08:00 | 2019-01-14 21:30 | 2019-03-11 13:30 | EIL-HPCL | 1 | 104.05 | 41 | 0 | 1 | 104.1 | 5450 | B-Production in Progress | Elamaran
4256-1009 | Despatch 4256 D | 2019-03-12 08:00 | 2019-01-31 19:30 | 2019-03-14 11:30 | EIL-HPCL | 1 | 267.21 | 28 | 0 | 1 | 267.2 | 14880 | B-Production in Progress | Elamaran
4256-1013 | Despatch 4256-N | 2019-03-12 08:00 | 2019-02-02 18:12 | 2019-03-07 09:30 | EIL-HPCL | 1 | 20.27 | 27 | 0 | 1 | 20.3 | 680 | B-Production in Progress | Elamaran
4256-102C | Despatch 4256-L | 2019-03-12 08:00 | 2019-01-31 07:30 | 2019-02-18 20:00 | EIL-HPCL | 1 | 58.96 | 26 | 0 | 1 | 59 | 2690 | B-Production in Progress | Elamaran
4256-2003 | Despatch 4256-E | 2019-03-12 08:00 | 2019-01-23 07:30 | 2019-03-16 19:30 | EIL-HPCL | 2 | 113.89 | 30 | 0 | 2 | 113.9 | 5240 | B-Production in Progress | Elamaran
4256-2004 | Despatch 4256-F | 2019-03-12 08:00 | 2019-02-01 07:30 | 2019-03-09 15:30 | EIL-HPCL | 2 | 96.31 | 19 | 0 | 2 | 96.3 | 4680 | B-Production in Progress | Elamaran
4256-2005 | Despatch 4256-G | 2019-03-12 08:00 | 2019-02-05 11:30 | 2019-03-11 13:42 | EIL-HPCL | 2 | 180.95 | 38 | 0 | 2 | 181 | 9140 | B-Production in Progress | Elamaran
4256-2009 | Despatch 4256-H | 2019-03-12 08:00 | 2019-02-05 11:30 | 2019-03-06 09:30 | EIL-HPCL | 2 | 110.79 | 14 | 0 | 2 | 110.8 | 5580 | B-Production in Progress | Elamaran
4256-2011 | Despatch 4256-I | 2019-03-12 08:00 | 2019-02-07 15:00 | 2019-02-27 12:00 | EIL-HPCL | 1 | 68.48 | 20 | 0 | 1 | 68.5 | 3420 | B-Production in Progress | Elamaran
4256-5001 | Despatch 4256-J | 2019-03-12 08:00 | 2019-02-12 11:30 | 2019-03-01 09:30 | EIL-HPCL | 2 | 88.68 | 41 | 0 | 2 | 88.7 | 4100 | B-Production in Progress | Elamaran
4256-6002 | Despatch 4256-K | 2019-03-12 08:00 | 2019-02-05 18:00 | 2019-02-16 18:00 | EIL-HPCL | 2 | 88.12 | 28 | 0 | 2 | 88.1 | 4000 | B-Production in Progress | Elamaran
4256-700-2003 | Despatch 4256-M | 2019-03-12 08:00 | 2019-01-19 08:30 | 2019-03-15 15:30 | EIL-HPCL | 2 | 95.4 | 22 | 0 | 2 | 95.4 | 4400 | B-Production in Progress | Elamaran
4266-72-E-51 | Despatch-4266C | 2019-02-24 08:30 | 2019-02-01 15:30 | 2019-03-14 17:30 | TECHNIP | 1 | 116.86 | 12 | 0 | 1 | 116.9 | 7160 | 2-Design Completed | Viswanathan
4266-74-E-04 | Despatch-4266E | 2019-02-24 08:30 | 2019-02-08 12:30 | 2019-03-16 17:30 | TECHNIP | 2 | 242.98 | 11 | 0 | 2 | 243 | 14425 | 2-Design Completed | Viswanathan
4266-74-E-106 | Despatch-4266F | 2019-02-24 08:30 | 2019-01-30 15:30 | 2019-02-18 17:30 | TECHNIP | 2 | 56.59 | 8 | 0 | 2 | 56.6 | 3000 | 2-Design Completed | Viswanathan
4266-74-E-51 | Despatch-4266D | 2019-02-24 08:30 | 2019-02-12 15:30 | 2019-02-20 17:30 | TECHNIP | 1 | 67.84 | 12 | 0 | 1 | 67.8 | 3950 | 2-Design Completed | Viswanathan
4266-75-E-12 | Despatch-4266G | 2019-02-24 08:30 | 2019-02-12 17:30 | 2019-03-20 06:30 | TECHNIP | 2 | 192.26 | 19 | 0 | 2 | 192.3 | 8113 | 2-Design Completed | Viswanathan
4266-75-E-56 A&B | Despatch-4266H | 2019-02-24 08:30 | 2019-04-02 11:30 | 2019-03-27 15:30 | TECHNIP | 2 | 110 | 5 | 0 | 2 | 110 | 6596 | 2-Design Completed | Viswanathan
4266-90-E-09 | Despatch-4266B | 2019-02-24 08:30 | 2019-02-19 10:30 | 2019-02-20 17:30 | TECHNIP | 2 | 157.71 | 18 | 0 | 2 | 157.7 | 10150 | 2-Design Completed | Viswanathan
4266-90-E-13C | Despatch-4266A | 2019-02-24 08:30 | 2019-02-16 14:30 | 2019-02-21 14:00 | TECHNIP | 1 | 199.89 | 14 | 0 | 1 | 199.9 | 10675 | 2-Design Completed | Viswanathan
4267-502-E-101 | Despatch-4267A | 2019-04-30 08:30 | 2019-03-02 12:30 | 2019-04-06 15:30 | TECHNIP-HPCL | 2 | 47.26 | 8 | 0 | 2 | 47.3 | 1850 | 2-Design Completed | Viswanathan
4267-502-E-104 | Despatch-4267B | 2019-04-30 08:30 | 2019-03-11 17:30 | 2019-03-13 12:30 | TECHNIP-HPCL | 2 | 35.88 | 2 | 0 | 2 | 35.9 | 1425 | 2-Design Completed | Viswanathan
4267-502-E-105 | Despatch-4267C | 2019-04-30 08:30 | 2019-02-28 15:30 | 2019-03-05 14:00 | TECHNIP-HPCL | 2 | 139.31 | 14 | 0 | 2 | 139.3 | 5375 | 2-Design Completed | Viswanathan
4267-502-E-108 | Despatch-4267D | 2019-04-30 08:30 | 2019-03-21 14:30 | 2019-03-19 12:30 | TECHNIP-HPCL | 2 | 33.99 | 7 | 0 | 2 | 34 | 1300 | 2-Design Completed | Viswanathan
4267-502-E-114 | Despatch-4267E | 2019-04-30 08:30 | 2019-03-07 17:30 | 2019-03-08 15:06 | TECHNIP-HPCL | 2 | 360.9 | 14 | 0 | 2 | 360.9 | 17860 | 2-Design Completed | Viswanathan
4267-502-E-119 | Despatch-4267F | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 35.28 | 4 | 0 | 2 | 35.3 | 1350 | 2-Design Completed | Viswanathan
4267-502-E-120 | Despatch-4267K | 2019-04-30 08:30 | 2019-03-21 17:30 | 2019-04-04 17:30 | TECHNIP-HPCL | 1 | 20 | 10 | 0 | 1 | 811.5 | 552 | 2-Design Completed | Viswanathan
4267-502-E-123 | Despatch-4267G | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 55.35 | 5 | 0 | 2 | 55.4 | 2570 | 2-Design Completed | Viswanathan
4267-502-E-123-1 | Despatch-4267G | 2019-04-30 08:30 | 2019-03-22 17:30 | 2019-03-20 15:30 | TECHNIP-HPCL | 2 | 55.35 | 5 | 0 | 2 | 55.4 | 2570 | 2-Design Completed | Viswanathan
4267-502-E-124 | Despatch-4267H | 2019-04-30 08:30 | 2019-03-08 11:42 | 2019-03-19 14:30 | TECHNIP-HPCL | 2 | 56.97 | 7 | 0 | 2 | 57 | 2710 | 2-Design Completed | Viswanathan
4267-502-E-129 | Despatch-4267I | 2019-04-30 08:30 | 2019-03-21 17:30 | 2019-03-20 09:30 | TECHNIP-HPCL | 2 | 26.95 | 9 | 0 | 2 | 27 | 1060 | 2-Design Completed | Viswanathan
4267-502-E-130 | Despatch-4267J | 2019-04-30 08:30 | 2019-04-04 17:30 | 2019-03-25 16:42 | TECHNIP-HPCL | 2 | 52.11 | 4 | 0 | 2 | 52.1 | 2300 | 2-Design Completed | Viswanathan
Site jobs | 4106 - Thermax site | 2018-04-18 08:30 | 0 | 2018-08-23 17:30 | All clients | 0 | 3.79 | 100 | 0 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4255 - MCCPTA site work | 2018-04-18 08:30 | 2018-05-02 12:30 | 2018-05-10 17:30 | All clients | 1 | 39.14 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4272 -RIL site work | 2018-04-18 08:30 | 0 | 2018-06-11 17:30 | All clients | 0 | 14.96 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4275 - MCCPTA site work | 2018-04-18 08:30 | 0 | 2018-06-12 17:30 | All clients | 1 | 3.8 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4281 - MCCPTA site work | 2018-04-18 08:30 | 0 | 2018-08-17 17:30 | All clients | 1 | 5.67 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4289 - MCCPTA site work | 2018-04-18 08:30 | 0 | 2018-09-17 17:30 | All clients | 1 | 7.6 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4299 - MCCPTA site work | 2018-04-18 08:30 | 0 | 2018-12-18 17:30 | All clients | 1 | 2.59 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan
Site jobs | 4306 - MCCPTA site work | 2018-04-18 08:30 | 0 | 2018-12-18 17:30 | All clients | 1 | 3.16 | 100 | 100 | 1 | 80.7 | 0 | 8-Project Completed | Viswanathan