## Audience
| First Meeting |  | First Meeting
| Date | 2019-05-04 | Date | 2019-05-05
| Time | 3 to 4 pm | Time | 4 to 5.30 pm
| Location | Conference Hall | Location | Conference Hall
| Moderator |  | Moderator
| Hari Thapliyal |  | Hari Thapliyal
Sno. | Participants | Attendance | Participants | Attendance
1 | KS | Present | KS | Present
2 | NV | Present | NV | Present
3 | GV | Present | GV | Present
4 | MKK | Present | MKK | Present
5 | AV | Present | AV | Absent
6 | MRL | Present | MRL | Present
7 | MS | Present | MS | Present
8 | BSR | Present | BSR | Present
9 | SRK | Present | SRK | Present

## ORANGE
| Me/My Department Expected from PMO (Orange) | [6 empty] | 179.4
| Card 27 |  |  |  | 1 to 5 (5 being Highest) |  | 179.4
Selected | Sno | Suggestions | Understandable | Address(Yes/No) | Priority | Complexity | Cumulative | Action Item
Yes | 6 | Perfect Planning For Each Activity | Yes |  | 43 | 2 | 43 | 1. Develop a checklist based on the best eng practices. - NV (max 15-May-19) 2. Follow the above checklist during CRM 3. Benchmark timing of activities. - Every HOD will give Benchmark to NV (Max 7-Jun-19)
Yes | 18 | Zero Ld | Yes |  | 40 | 5 | 83 | 1. Sales will interact with PMO and PPC for all tendor proposals and second stage of negotiation for other proposals. Define bidding process. - MS (max 31-May-19) 2. If time is constraint in bidding then consider LD amount in contract cost. 3. TOC implementation (1-Jun-19, NV) 4. Full kit data available (10-May-10, NV) 5. Full kit readyness (20-May-19, NV) 6. Measure the rework cost for 1 month (1-Jun-19) BSR 7. Use the rework cost input for planning purpose. (BSR)
Yes | 19 | Project Ownership | Yes |  | 40 | 3 | 123 | 1. Redefine Subcontracting process and involve PMO in decision making process. KS (31-May-19) 2. HoDs should attend DSUM (from 6-May-19, NV) 3. For all complex/critical project a PMT dotted line reporting to PM. (KS - 31-May-19)
Yes | 20 | Realistic Schedule & Resourcing | Yes | No | 39 | 2 | 162
Yes | 16 | Frequent (Monthly / Fortnightly) Report to All Customer About Status | Yes |  | 37 | 2 | 199 | 1. Stagewise project/product photograph should be available with PM. An SOP should be devloped.
No | 10 | Resources / Planning With Plan of Delivery | Yes |  | 36 | 3 | 235
No | 17 | Ensuing Documentation Is Completed in All Respect For Handing Over | Yes |  | 36 | 2 | 271
No | 9 | Detailed Project Milestone Plan / From PO Despatch | Yes |  | 35 | 2 | 306
No | 24 | Projectwise Progress Report Both in Terms of Amount And % at Any Point of Time (More Particularly Month Ends) | Yes |  | 33 | 1 | 339
No | 1 | More Experienced Project Engineers With A Decent Years of Experience in Fabrication (He & Pv) Field | Yes |  | 32 | 5 | 371
No | 7 | Follow Up With Clients For Approval | Yes |  | 32 | 2 | 403
No | 11 | Expediting of Required Inputs With Delivery/ Exploring Outsouring of project work | Yes |  | 31 | 3 | 434
No | 5 | Support From Others During Some Activity Fail | Yes |  | 29 | 3 | 463
No | 22 | Required Any Deviation, Issue then get It Approved From Customer Immediately | Yes |  | 28 | 1 | 491
No | 8 | Feed Back From Clients | Yes |  | 27 | 2 | 518
No | 13 | Understanding Organisation Capacity | Yes |  | 27 | 3 | 545
No | 14 | Able to Analyse the Root Cause of Failure And Success | Yes |  | 27 | 2 | 572
No | 12 | Able to Take Decision Since It Is Directive PMO | Yes |  | 26 | 4 | 598
No | 2 | 2Nd Level People As A Sustitute For Temporary / Permanent Handover | Yes | No |  | 5 | 598
No | 3 | Commercially Sound Projects With Adequate Commerical Freedom to Project Engineers | Yes | No |  | 5 | 598
No | 4 | Understanding of Reasonable Failure | Yes | No |  |  | 598
No | 15 | Proper Introduction to Customer About nominating Project Manager & Customer sign off | Yes | No |  | 1 | 598
No | 21 | Need Proper Planning From PMO | Yes | No |  | 2 | 598
No | 23 | If Any Problem Customer Interaction Is Required By PMO | Yes | No |  | 1 | 598
No | 25 | Reliable Delivery Schedule Dates | Yes | No |  | 2 | 598
No | 26 | Projected Possible LD Amounts | Yes | No |  | 1 | 598
No | 27 | Prompt Communication With Client | Yes | No |  | 1 | 598

## YELLOW
| I/My Department Could Have Given to PMO (Yellow) | [6 empty] | 135
| 26 Cards |  |  |  | 1 to 5 (5 being Highest) |  | 135
Selected | Sno | Suggestions | Understandable | Address(Yes/No) | Priority | Complexity | Cumulative | Action Item
Yes | 8 | On Time Delivery Without Compromising On Quality Requirements | Yes |  | 45 | 1 | 45 | Zero Ld
Yes | 7 | Getting Timely Update Especially Lessons Learnt From All Supporting Functions And Stakeholders | Yes |  | 39 | 1 | 84 | 1, A SOP should be written and implemented for capturing lessons for every depart. 2. Analyse the dailylog and create lessons learnt 3. Use the LL for daily planning, imporving checklist. 4. Use Lessons Log from TOC practice
Yes | 18 | Timely Indents | Yes |  | 38 | 2 | 122 | 1. Define & Automate the indenting process. SRK 5-Jun-19 2. Review the drawing to scale process and ASPEN process. Provide input to KS. 24-May-19, MRL 3. Develop other methods of bringing down the time for non-standard forging drawing. MRL. 24-May-19. 4. Explore possiblity of capturing BOM in Oracle. SRK. 24-May-19 5. Material naming convention across the department should be standardized. MRL. 24-May-19 6. Design department should use the standard materialcode during design work.
Yes | 22 | On Time Payment | Yes |  | 38 | 5 | 160 | 1. Bill receiving, approval, payment process should be refined. Discussion by GV with other stakeholders. (24-May-19)
Yes | 23 | On Time LC | Yes |  | 38 | 5 | 198 | 1. Procurement schedule should be provided to Finance in 15 days advance. So the procuerment process interface with Finance. (by AV 24-May)
No | 24 | On Time BG | Yes |  | 38 | 5 | 236
No | 10 | For Large Projects We Can involve Proejcts Before Finalising the Order | Yes |  | 31 | 2 | 267
No | 3 | Process to Be Outsourced to Meet the Date Planned | Yes |  | 26 | 3 | 293
No | 5 | Training | Yes |  | 26 | 3 | 319
No | 4 | Manpower | Yes |  | 25 | 3 | 344
No | 6 | Analysing the Data Available With us in Pmo System And Company Repository | Yes |  | 25 | 1 | 369
No | 12 | Provide For Initial Documents For Client Approval | Yes |  | 25 | 1 | 394
No | 9 | In Between Coordination Meeting May Be Necessary With Projects For Support On Either Side (Periodic Review) | Yes |  | 20 | 1 | 414
No | 16 | Technical Clarifications | Yes |  | 19 | 1 | 433
No | 17 | Bench Mark of Norms | Yes |  | 15 | 3 | 448
No | 13 | Share Some Better Idea For Improving System And Activity | Yes |  | 2 | 1 | 450
No | 19 | If Anything PMO Will Ask, We Will Provide For Example Delivery of Material (Or) The Same Thing in the Sub Contract Also We Will Share With Pmo | Yes |  | 0 | 1 | 450
No | 1 | Cycle Time of Activities And Manpower For the Plan - Taskwise | Yes | No |  |  | 450
No | 2 | Facilities / Process to Match the Process (Appropriate) For Schedule Preparation | Yes | No |  | 3 | 450
No | 11 | Give Final Documents For Payment Related Proejcts | Yes | No |  | 1 | 450
No | 14 | Design & Drawing | Yes | No |  | 1 | 450
No | 15 | Approved Documents | Yes | No |  | 1 | 450
No | 20 | [5 empty] | 450
No | 21 | [5 empty] | 450

## BLUE
| In Future I/My Department Expect this From PMO (Blue) | [6 empty] | 95.4
| 23 Cards |  |  |  | 1 to 5 (5 being Highest) |  | 95.4
Selected | Sno | Suggestions | Understandable | Address(Yes/No) | Priority | Complexity | Cumulative | Action Item
Yes | 14 | Every Day One One Channel Output From PMO Not Each Channels (Channels ==> Each Proejct Engr) (Prioritisation of the work on daily basis) | Yes |  | 38 | 1 | 38 | Work prioritation Across project should be done by PMO on weekly or daily basis based on the need.
Yes | 16 | Better Inter Departmental Coordination to Expedite Results | Yes |  | 37 | 1 | 75 | 1. HoDs should provide information about their inter department requirements to Project Managers on the need basis.
Yes | 20 | Closely Monitoring the Material Ordering Process Like PO Release, Advance Payment, ETA Dates Firmly | Yes |  | 35 | 1 | 110 | 1. Stock Material Inspection process should be followed. 2. Create a list of all the material available in the stock as per the system by 31-May-19
No | 5 | Resource & Schedule Accuracy | Yes |  | 34 | 2 | 144
No | 7 | Plan With Resources Planning With Other Projets Running in Parallel | Yes |  | 33 | 2 | 177
No | 11 | Total Control of Project From Initiation to Closure | Yes |  | 30 | 1 | 207
Yes | 3 | More Authority in Terms of Rewarding And Also Punishing to Have Better Control of Other Stakeholders And Their Delivery Commitments | Yes |  | 28 | 4 | 235 | 1. TEAM person of the Month selection process should be defined. KK for Production by 24-May-19. NV for non-Production by 24-May-19
No | 21 | Update the Progress Daily And Communicate in Real Time | Yes |  | 28 | 1 | 263
No | 8 | Materials Tracking With Plan And Its Acceptance Too to Issue For Production | Yes |  | 24 | 1 | 287
No | 22 | 1) Avoid Overloading And 2) Avoid Pessimistic Commitments 3) Do Not Try to Reduce the Process Timing Duration | Yes |  | 20 | 1 | 307
No | 17 | If Any Thing About the Materails These Should Tell us to Enable us to Block the Money | Yes |  | 11 | 1 | 318
No | 1 | Experienced & Seasoned Project Engineers From Similar Heat Exchangers / Pressure Vessel Fabrication Background From A Branded Organisation to Improve In-House Skill Sets (*Duplicate item) | Yes | No |  | 5 | 318
No | 2 | Project Engineers May Be Equippped With More Resources Like Laptop, Mobile, Allowances Etc | Yes | No |  | 5 | 318
No | 4 | Zero Ld (*Duplicate item) | Yes | No |  | 5 | 318
No | 6 | Project Complete Ownership (*Duplicate item) | Yes | No |  | 3 | 318
No | 9 | Outsourcing Activities And Its Receipt With Plan | Yes | No |  | 1 | 318
No | 10 | Communication With Customer Regularly | Yes | No |  | 1 | 318
No | 12 | Final Documentation Preparation Support (Like Mtc, Sub Contract, Report, Lab Report) | Yes | No |  | 1 | 318
No | 13 | Real Timing For My Activity With 10% Extra Cushion | Yes | No |  | 1 | 318
No | 15 | Continuous Follow Up With Clients Get Timely Approvals And Clarifications For Design & Drawings | Yes | No |  | 1 | 318
No | 18 | If Any Clarifications And …... From Pmo, Then Slow Down …....................... |  | No |  |  | 318
No | 19 | Pmo …............... |  | No |  |  | 318

## PINK
Me/My Department Got from PMO (Pink) | [6 empty] | 0
25 Cards |  |  |  | 1 to 5 (5 being Highest)
Sno | Suggestions | Understandable | Address(Yes/No) | Priority | Complexity | Cumulative | Action Item
1 | Good Support And Follow Up For Proudction Activity | Yes |  |  |  | 0
2 | Quality Compromising Pressure to Achieve Delivery |  | No |  |  | 0
3 | Different PMO Project Will Not Give Priority Wise Scheduling |  | No |  |  | 0
4 | Weekly Meeting With Some Note On Risk And Issues On Current Jobs | Yes |  |  |  | 0
5 | Activities & Schedule Without Considering the Resources (i.e. Plan Not in Line With Available Resources, Either Not Indicating Requirement Also). |  | No |  |  | 0
6 | Documents Upload in Client Server | Yes |  |  |  | 0
7 | Followup For Approvals | Yes |  |  |  | 0
8 | Inter Departmental Coordination | Yes |  |  |  | 0
9 | One Point Source for Project Updation | Yes |  |  |  | 0
10 | Process For Identifying Obstacles & Constraints | Yes |  |  |  | 0
11 | Ease of Facing Clients | Yes |  |  |  | 0
12 | Customer / Client Meeting / Visit to Shop Support / Deviations /Acceptance From Client | Yes |  |  |  | 0
13 | Despatch Coordination | Yes |  |  |  | 0
14 | Status of Project - Progress - % Growth | Yes |  |  |  | 0
15 | Project Manager Is in Drivers Seat Instead of Production Department | Yes |  |  |  | 0
16 | Status of All Projects Is Open & Visible to Everyone Transparently | Yes |  |  |  | 0
17 | Organisation Type Has Been Changed From Weak Matrix to Strong Matrix Type. Hence we are more System Driven | Yes |  |  |  | 0
18 | PMO Initiative Is Ok, But Things Are Not Done Properly |  | No |  |  | 0
19 | Pmo Will Have to Take All the Inputs From Other Department And …................... Something Its Ok |  | No |  |  | 0
20 | There Is Continuous Review of Each Project | Yes |  |  |  | 0
21 | Point of Contact Available For Project to Know the Status | Yes |  |  |  | 0
22 | Project Status to Some Extent | Yes |  |  |  | 0
23 | LD Projections | Yes |  |  |  | 0
24 | Critical Requirements Which Will Delay Project If Not Complied | Yes |  |  |  | 0