## Organization
# | Practice Name | Status | Comment
1 | Type of Projects: Fixed Price & Resource Based. | Discussed
2 | Presales Estimation Process for Different Kind of Project | Discussed | Not in place.
3 | Engagement Plan for Different kind of Projects | Discussed | Not in place.
4 | Resource Management Across Different Project | Discussed | Not in place.
5 | Any compliance requirements from govt, customer or org? | Discussed | Internal process audit for fixed price project in place. Not for resource based projects.
6 | Practices to Evaluate resource project for a project | Discussed | Not in place.
7 | Team level reward and recognization system | Discussed | Not in place. At individual level it exists.
8 | Processes to Build OPA | Discussed | Not in place.
9 | Resource-Skill mapping and skill improvement policy in place? | Discussed | Not in place.
10 | What key challenges you see and their reasons within the organization? Did you do this exercise ever at org level? | Discussed | Never done
11 | What KPIs you use to measure the performance of team, project, organization? Any system to track these? | Discussed | At project level within cost and time. Timesheet data is available.
| What practices are in place to share cross project learning and skill transfer? | Discussed | Not in place
T&M not exists.

## Project1
General Details of Project
Project Type: Resource Based Product Development Project.
Resources are supplied to the customer to develop customer's product.
Introduction to project, technology, customer and team
Restaurant Discovery/Registration Platform
Project Start: Nov'21 - Apr'22,
Number of Sprint: 5
Technology: MEAN Stack Technology - Angular/Node, MySQL, Flutter,
Technology Leader within Project
Angular - Romy / Vinay
NodeJS: Ashwini/ Pankaj/ Harshit
MySQL - Ashwini / Pankaj
Customer
Customer: Tom, Australia.
Customer POCs: Tom (Sponsor), Niti (PM), Lara(Sr. PM).
Signity Team
Dev Team: Romy / Vinay / Ashwini/ Pankaj/Harshit/
Project Manager: None
Account Manager: ??
Two more people added Anjali/Dharmendra (Angular) towards the end of project.
Area of Practice | Practices with Project | Implementation Status | Observations within Area of Practice
Agile Values & Principles | Agile Values and Principles of the Team | 0% | No Agile Value System in Place
No agreed Agile Principles in Place
Product Backlog | Product Backlog Development | <25% | Not created, maintained and used properly.
| Product Backlog Grooming | 0% | No user story estimation
| Value Based Prioritization of User Stories | 0% | Only high level features. No user stories created.
Concept of Epic, Features, User story not understood properly.
User Story Detailing | INVEST Model of User Story | 0% | User story explanation was happening during execution but no idea of user story during Sprint planning.
Concept of INVEST is missing for user stories.
Sprint planning | Sprint Planning | <25% | Sprint Plan is there but not followed.
Product backlog informally
No user stories
Sprint Plan not created in right way. Customer did it unilaterally.
Task splitting was not done by team
Task estimation was not done.
Task self assignment practice is missing.
Sprint duration is not fixed
Team was forced to complete given number of user stories in a given sprint.
No place for Tech spike, research
Level of Planning | Release Planning | 0% | No Release Plan
| Level of Planning | <25% | Question: Different levels of planning done, frequency, responsibilities?
No clarity around release planning, sprint planning, project plan
Question: What are practices for estimation, how it happens, who is responsible?
No clarity.
Daily Scrum | Daily Standup Meeting | <50% | Daily scrum not done properly.
Doing demo during Daily standup.
Quality | DoD for User Story | <0% | Question: What is DoD at different level like User story, features, sprint, release?
| DoD for Sprint | <0% | No clarity.
Question: Are you doing retrospective?
No.
Question: How product quality is ensured?
No unit testing, no functional test cases, no UAT test cases.
TDD is missing
Test Automation is missing
Project Governance | Project Tracking by Team | 0% | Unknown team velocity
| Project Dashboard/Metrics | 0% | No metrics in place
Communication | Close Communication | 0% | No way to document what was discussed during technical discussion.
No way to track the decision.
No way to build knowledge system from the discussions happened
No communication between team members
No communication with SM
Risk Management | Risk Identification | <25% | Risk Register is available for the name sake.
| Risk Tracking | 0% | Risk Register is not updated.
No risk tracking, ownership etc.
No risk assessment.
Issue Management | Issue Management | 0% | No impediment/issue register.
| Daily Impediment Management | 0% | No self assignment
No tracking of impediments
Product Demo | Product Demo | <25% | Practice not used properly. Team is doing it daily. For example.
Demo should be between PO and end-user
Dev Team should be involved during this.
Defects should be entered into product backlog
Demo shouldn't have any functional error.
Scrum master was taking product Demo. It is incorrect practice.
Requirement | Adapting the Change | <50% | Customer didn't change requirement during sprint but user stories of sprint itself was not properly defined.
Team was taking time to develop multiple solutions and customer was happy in making decision about any solution. But this whole approach was considered typical development and not R&D.
Built | CI, CD | <0% | No continuous built
Auto Built is missing
Full manual testing after each built.
Team Reward System | Promoting Team Spirit | 0% | None
Human Resource Management in Project | Resource Integration in Team, Team Building, Feedback system | 0% | Customer interview process exists for resource empanelment into the project.
But customer not happy with those resources, want to change them
Interview and "Human Resource Assignment" process is not matured.
Feedback system is not matured
Team is not willing to work with customer and on the project due to low motivation, feedback system, evaluation system, attitude of Product Owner.
Roles & Responsibilities | SM Role | <25% | Scrum Master (SM)
Scrum Master role played by PM.
Scrum Master R&R not defined.
SM not doing as she/he is suppose to do in any Agile Project.
| PO Role | <25% | Product Owner (PO)
Product Owner role played by Tom.
PO R&R not defined.
PO not doing as she/he is suppose to do in any Agile Project.
| Management Role | <25% | Management Team
Lara's R&R not clearly defined in project. SM roles is diluted.
| Development Team (DT) | <25% | Development Team
R&R of DT not defined.
DT is not self organizing, self motivated, empowered.
Doesn't have say in sprint planning and commitment. Practice wrongly used.
Miscellaneous | Stable Team | <25% | Added resources during sprint. It is not a good practice.

## Project2
General Details of Project
Project Type: Fixed Price Product Development Project.
We are responsible to finish the project within predefined fixed cost.
Introduction to project, technology, customer and team
GoAutoPoint
Number of Sprint: 7
Current Spirint: 3
Mobile App : Native, Android, Java, Kotlin, Swift5
Admin Panel : Angular / NodeJS
Service Provider Panel: Angular / NodeJS
Technology Leader within Project
Android: Ramesh
Java: Ramesh
Kotlin : Ramesh
Swift5: Gulam Ali
Angular: Dharmendra
NodeJS: Rahul Jha
Customer
Customer: ALZ Enterprise Solutaiton., Saudi Arabia.
Customer POCs: Badr (PO)
Signity Team
Dev Team: Ramesh, Gualm Ali, Dharmendra, Rahul Jha
Project Manager + SM: Ravindra
Account Manager: Ashish Tripati
Area of Practice | Practice | Implementation Status | Observation
Agile Values & Principles | Agile Values and Principles of the Team | 0% | No Agile Value System in Place
No agreed Agile Principles in Place
Product Backlog | Product Backlog Development | 80% | As per disucssion Product backlog is created
| Product Backlog Grooming |  | User story estimation using Fibinnoci complexity tech.
| Value Based Prioritization of User Stories |  | Concept of Epic, Features, User story not implimented.
User Story Detailing | INVEST Model of User Story | 0% | User story explanation was happening during execution but no idea of user story during Sprint planning.
Concept of INVEST is missing for user stories.
Sprint planning | Sprint Planning | >75% | Sprint duration 2 week. 2 hrs to estimate a sprint.
Sprint duration is not fixed.
Tech spike/ R&D planning done correctly.
Task splitting is done by team
Task estimation is done by team
Planning poker for task & user story estimation.
Level of Planning | Release Planning | 0% | No clarity around release planning, project plan
| Level of Planning | <25% | Question: Different levels of planning done, frequency, responsibilities?
No concept of level of planning
Question: What are the practices for estimation, how it happens, who is responsible?
Daily Scrum | Daily Standup Meeting | 75% | As per discussion daily standup is done properly. But, can make more engaging.
Challenges and dependency identified.
5 People participate in daily scrum. PO does not participate in Daily standup.
Involve PO in daily standup.
Quality | DoD for User Story | <50% | Question: What is DoD at different level like User story, features, sprint, release?
| DoD for Sprint | <50% | Partial Implementation
Question: Are you doing retrospective?
Partial Implementation
Question: How product quality is ensured?
No unit testing, no functional test cases, no UAT test cases.
TDD is missing
Test Automation is missing
Project Governance | Project Tracking by Team | 0% | Unknown team velocity
| Project Dashboard/Metrics |  | No risk register, tracking, ownership etc.
Communication | Close Communication | 100% | As per discussion communications are happening the way it need in any virutal agile team.
People regularly share updates in status update meeting and daily standup.
Email, slack channel is used for communcation
Risk Management | Risk Identification | <25% | Risk Register is available for the name sake.
| Risk Tracking | 0% | Risk Register is not updated.
No tracking of risk.
No risk assessment.
Issue Management | Issue Management | >50% | No impediment/issue register.
| Daily Impediment Management | >50% | No self assignment
No tracking of impediments
Product Demo | Product Demo | <25% | As per the discussion they are
Requirement | Adapting the Change | 100% | As per discussion requirement management are done the way it should happen in any agile project.
Have concept of impact severity in place and allow to change even sprint user story if impact is least servere.
Built | CI, CD | <0% | No continuous built
Auto Built is missing
Full manual testing after each built.
Team Reward System | Promoting Team Spirit | <50% | At emotional level/ recognition it looks fine. Weekly apprication post.
Other reward like opportunit to learn, earn, grow it can be integrated further.
Human Resource Management in Project | Resource Integration in Team, Team Building, Feedback system | 100% | As per discussion team work the way any agile team should work.
Roles & Responsibilities | SM Role | 100% | As per discussion SM is doing what he is suppose to do.
| PO Role | 100% | As per discussion SM is doing what he is suppose to do.
| Dev Team | 100% | As per discussion SM is doing what he is suppose to do.
Miscellaneous | Stable Team | 100% | Team is stable
Challenges Mentioned |  |  | Schedule not on track.
Optimization of UI on certain devices.
30% built is not good because of development and built processes.
70% due to UAT issues.

## Recommendations
Note
1 | All the findings are recorded from the word of mouth of people participated in discussions. Physical documentation, process verification is not done. As this is quite lengthy process.
2 | Our recommendtions for the organization is based on what participants stated during the interview.
3 | Organization level practices are not discussed, as focussed was only 2 projects.
| Recommendations | Priority
1 | Conduct training for your all project team and let all people sync in terms of dos and don'ts of agile project management. (I can help in this) | 1
2 | Depending upon different types of project (fix price, time and material, resource based) provide a set of practices to customer. Creating an agreement with customer that they understood the practices and share responsbility. Tracking those practices. (I can help in this) | 2
3 | Develop some practices which encourage Agile Team spirit and not heroism (I can help in this) | 3
4 | Develop some practices to share resources between maintenance and dev work of the same or different projects. (I can help in this) | 4
5 | Make CI, CD, TDD part of your development process, without this it is extremely difficult to ensure good quality product in Agile. | 5
6 | Engaging agile coach at the start of project can help in following.
A. Basic training, right agile practices are in place from the start of a project.
B. To convince customer what will work and what will create pain down the line.
C. To convince customer that we are serious about project success, either you engage agile coach from your side or we engage from our side, but that person should be common for the entire project team. S/he can be available for both side for intially 2 to 3 sprints.