## Sheet1
http://project-management.com/top-10-main-causes-of-project-failure/ | Root Causes
Poor planning and/or inadequate process | Process-Planning
Inefficient way to document and track progress | M&C
Poor leadership at any level | HR
Failure to set expectations and manage them | HR
Inadequately-trained project managers | HR
Inaccurate cost estimation | Process-Planning
Lack of communication at any level | Communication
Culture or ethical misalignment | HR
Competing priorities | Org-Integration
Disregard of project warning signs | Org-Integration
http://www.project-skills.com/top-7-reasons-for-project-management-failure.html
Lack of Senior Management Involvement | HR
Poor Requirements | Scope
Unrealistic Expectations | Stakeholder
Scope Creep | Scope
Lack of User Involvement | Stakeholder
Inexperienced Project Managers | HR
Lack of Resources | HR
http://www.projectsmart.co.uk/reasons-why-projects-fail.php
Poorly managed | M&C
Lack of a solid project plan | Process-Planning
Centralised proactive management initiatives to combat project risk | HR
Poorly defined roles and responsibilities | HR
Team weaknesses | HR
Poor communication | Communication
Overruns of schedule and cost | Process-Planning
Scope creep | Scope
Ignoring project warning signs | Risk
Undefined objectives and goals | Org-Integration
Lack of user input | Stakeholder
Enterprise management of budget resources | Cost
Inadequate or vague requirements | Scope
Unrealistic timeframes and tasks | Time
Insufficient resources (funding and personnel) | HR
Estimates for cost and schedule are erroneous | Process-Planning
No change control process | M&C
Inadequate testing processes | Quality
Lack of management commitment | Org-Integration
Lack of organisational support | Org-Integration
Provides universal templates and documentation | Org-Integration
Stakeholder conflict | Stakeholder
Competing priorities | Org-Integration
Business politics | Org-Integration
Lack of prioritisation and project portfolio management | Org-Integration
Meeting end user expectations | Scope
Bad decisions | Org-Integration
http://www.mindtools.com/pages/article/newPPM_58.htm
Definition of Project Failure | Org-Integration
The wrong business requirements have been addressed | Scope
It's not possible to deliver the business case | Scope
Governance is poor | M&C
Implementation is poor | M&C
People lose focus on the project's benefits | Org-Integration
The environment changes | Org-Integration
Challenge #1 - Lack of Visibility of all Projects | Org-Integration
Challenge #2 - Unclear Project Objectives | Org-Integration
Challenge #3 - No Visibility into Resource Workload | Org-Integration
Challenge #4 - Gaps in Communication | Communication
http://2020projectmanagement.com/2013/02/top-10-reasons-for-project-failure/
1. Mismatch between the project and organisation’s strategic priorities. | Org-Integration
2. No pre-agreed measures of project success. | Org-Integration
3. Ill-defined senior management ownership and leadership. | Stakeholder
4. Ineffective engagement with stakeholders. | Stakeholder
5. Poor project management technical skills. | HR
6. Non-standard approach to project management and risk management. | Org-Integration
7. Inability to differentiate stages of project development and implementation. | Org-Integration
8. Proposal evaluation focused on price rather than long-term value for money and achievement of business benefits. | Org-Integration
9. Lack of contact with senior management levels in the organisation. | Stakeholder
10. Poor project team integration between clients, the supplier team and supply chain. | Stakeholder
http://blog.entry.com/top-reasons-projects-fail
1. Poor requirements. | Scope
2. Inadequate communication. | Communication
3. Insufficient planning. | Process-Planning
4. Lack of customer engagement. | Stakeholder
http://kellyprojectsolutions.com/top-5-reasons-projects-fail/
Project Manager Skill & Leadership | HR
Unclear Goals & Business Alignment | Org-Integration
Scope Changes & Change Management | Scope
Staffing & Inappropriate Skills | HR
Executive Support | Stakeholder
http://www.hks.harvard.edu/m-rcbg/ethiopia/Publications/Top%2010%20Reasons%20Why%20Systems%20Projects%20Fail.pdf
Top 10 Reasons Why Systems Projects Fail
1. Don’t use a specific methodology because coding is all that is really important. | Org-Integration
2. Create the project plan by working backwards from a drop-dead system completion date. | Time
3. Don’t bother with a data model. Just build whatever tables you need. | Scope
4. Use a Technical Lead that has never built a similar system. Hiring such talent is too expensive. | Cost
5. Hire forty developers to make the coding go faster. | HR
6. Build the system in Java, even though most of the development team still thinks that Java is coffee and you have no intention of ever deploying to the Web. | Scope
7. Three months before the system goes live, assign one junior developer to handle the data migration. | Process-Planning
8. Skip the testing phase because the project is way behind schedule. | Quality
9. Change the system to support critical new requirements discovered during final development. | M&C
10. Buy a commercial, off-the-shelf package and customize it … a lot. | Process-Planning
http://www.zdnet.com/blog/projectfailures/cio-analysis-why-37-percent-of-projects-fail/12565
The study identifies five top causes of troubled projects:
1. Requirements: Unclear, lack of agreement, lack of priority, contradictory, ambiguous, imprecise. | Scope
2. Resources: Lack of resources, resource conflicts, turnover of key resources, poor planning. | HR
3. Schedules: Too tight, unrealistic, overly optimistic. | Time
4. Planning: Based on insufficient data, missing items, insufficient details, poor estimates. | Process-Planning
5. Risks: Unidentified or assumed, not managed. | Risk

## Sheet2
# | Causes | Root Causes
2 | Poor planning and/or inadequate process | Process-Planning
3 | Inefficient way to document and track progress | M&C
4 | Poor leadership at any level | 06-HR
5 | Failure to set expectations and manage them | 06-HR
6 | Inadequately-trained project managers | 06-HR
7 | Inaccurate cost estimation | Process-Planning
8 | Lack of communication at any level | 07-Communication
9 | Culture or ethical misalignment | 06-HR
10 | Competing priorities | 01-Integration
11 | Disregard of project warning signs | 01-Integration
14 | Lack of Senior Management Involvement | 06-HR
15 | Poor Requirements | 02-Scope
16 | Unrealistic Expectations | 10-Stakeholder
17 | Scope Creep | 02-Scope
18 | Lack of User Involvement | 10-Stakeholder
19 | Inexperienced Project Managers | 06-HR
20 | Lack of Resources | 06-HR
23 | Poorly managed | M&C
24 | Lack of a solid project plan | Process-Planning
25 | Centralised proactive management initiatives to combat project risk | 06-HR
26 | Poorly defined roles and responsibilities | 06-HR
27 | Team weaknesses | 06-HR
28 | Poor communication | 07-Communication
29 | Overruns of schedule and cost | Process-Planning
30 | Scope creep | 02-Scope
31 | Ignoring project warning signs | 08-Risk
32 | Undefined objectives and goals | 01-Integration
33 | Lack of user input | 10-Stakeholder
34 | Enterprise management of budget resources | 04-Cost
35 | Inadequate or vague requirements | 02-Scope
36 | Unrealistic timeframes and tasks | 03-Time
37 | Insufficient resources (funding and personnel) | 06-HR
38 | Estimates for cost and schedule are erroneous | Process-Planning
39 | No change control process | M&C
40 | Inadequate testing processes | 05-Quality
41 | Lack of management commitment | 01-Integration
42 | Lack of organisational support | 01-Integration
43 | Provides universal templates and documentation | 01-Integration
44 | Stakeholder conflict | 10-Stakeholder
45 | Competing priorities | 01-Integration
46 | Business politics | 01-Integration
47 | Lack of prioritisation and project portfolio management | 01-Integration
48 | Meeting end user expectations | 02-Scope
49 | Bad decisions | 01-Integration
52 | Definition of Project Failure | 01-Integration
53 | The wrong business requirements have been addressed | 02-Scope
54 | It's not possible to deliver the business case | 02-Scope
55 | Governance is poor | M&C
56 | Implementation is poor | M&C
57 | People lose focus on the project's benefits | 01-Integration
58 | The environment changes | 01-Integration
61 | Challenge #1 - Lack of Visibility of all Projects | 01-Integration
62 | Challenge #2 - Unclear Project Objectives | 01-Integration
63 | Challenge #3 - No Visibility into Resource Workload | 01-Integration
64 | Challenge #4 - Gaps in Communication | 07-Communication
67 | Mismatch between the project and organisation’s strategic priorities. | 01-Integration
68 | No pre-agreed measures of project success. | 01-Integration
69 | Ill-defined senior management ownership and leadership. | 10-Stakeholder
70 | Ineffective engagement with stakeholders. | 10-Stakeholder
71 | Poor project management technical skills. | 06-HR
72 | Non-standard approach to project management and risk management. | 01-Integration
73 | Inability to differentiate stages of project development and implementation. | 01-Integration
74 | Proposal evaluation focused on price rather than long-term value for money and achievement of business benefits. | 01-Integration
75 | Lack of contact with senior management levels in the organisation. | 10-Stakeholder
76 | Poor project team integration between clients, the supplier team and supply chain. | 10-Stakeholder
79 | Poor requirements. | 02-Scope
80 | Inadequate communication. | 07-Communication
81 | Insufficient planning. | Process-Planning
82 | Lack of customer engagement. | 10-Stakeholder
85 | Project Manager Skill & Leadership | 06-HR
86 | Unclear Goals & Business Alignment | 01-Integration
87 | Scope Changes & Change Management | 02-Scope
88 | Staffing & Inappropriate Skills | 06-HR
89 | Executive Support | 10-Stakeholder
93 | Don’t use a specific methodology because coding is all that is really important. | 01-Integration
94 | Create the project plan by working backwards from a drop-dead system completion date. | 03-Time
95 | Don’t bother with a data model. Just build whatever tables you need. | 02-Scope
96 | Use a Technical Lead that has never built a similar system. Hiring such talent is too expensive. | 04-Cost
97 | Hire forty developers to make the coding go faster. | 06-HR
98 | Build the system in Java, even though most of the development team still thinks that Java is coffee and you have no intention of ever deploying to the Web. | 02-Scope
99 | Three months before the system goes live, assign one junior developer to handle the data migration. | Process-Planning
100 | Skip the testing phase because the project is way behind schedule. | 05-Quality
101 | Change the system to support critical new requirements discovered during final development. | M&C
102 | Buy a commercial, off-the-shelf package and customize it … a lot. | Process-Planning
106 | Requirements: Unclear, lack of agreement, lack of priority, contradictory, ambiguous, imprecise. | 02-Scope
107 | Resources: Lack of resources, resource conflicts, turnover of key resources, poor planning. | 06-HR
108 | Schedules: Too tight, unrealistic, overly optimistic. | 03-Time
109 | Planning: Based on insufficient data, missing items, insufficient details, poor estimates. | Process-Planning
110 | Risks: Unidentified or assumed, not managed. | 08-Risk

## Sheet6
Row Labels
01-Integration
02-Scope
03-Time
04-Cost
05-Quality
06-HR
07-Communication
08-Risk
10-Stakeholder
M&C
Process-Planning
Grand Total