## Slide 1: Project Management Workshop
Trainer :Hari Prasad Thapliyal
    MBA, MCA, PGDOM, PGDFM, CIC, MCITP, MCTS, CSM, PMP, PMI-ACP, PRINCE2, Agile
    Project Management Mentor, Trainer & Coach
[PMI-ACP : #318050]
[PMP : #1563385]
Content related queries please write to hari.prasad@vedavit-ps.com
This content is legal only for participants of VGL Jaipur May’16 Training
'PMI-ACP', 'PMI', and 'ACP' are a registered marks of the Project Management Institute, Inc.

## Slide 2: Trainer Introduction
MCA, MBA (Operations), PGDFM, PMP, MCITP, PMI-ACP, Prince2 Practitioner and CSM
2 decades of experience in IT Delivery, Training, Consulting, Agile/Scrum. 16+ years in various IT delivery positions, 6 years as Project Management Trainer/Coach/Mentor.
Trained 3000+ leaders in India and internationally
190+ corporate / open-house trainings on PMP®, Agile Project Management, PMI-ACP®, PRINCE2, PMI-RM®, PMI-SM®, CAPM®, Microsoft Project® 2007 & 2010, Enterprise Microsoft Project Server® 2007 & 2010, AgileEVM, Earn Value Management, Function Point Estimation (FPA)
Delivered many trainings at international location for the citizen of Philippines, Singapore, Indonesia, Malaysia, Thailand, Japan
Class room training experience of around 5500+ hours
FPA counting experience of more than 30000 FP of 15+ proposals/projects
CMMI (1.1, 1.2), ISO9001:2000 initiative rollout
Ex-Vice President- Volunteer Development with PMI Chennai Chapter
Ex-Vice President- Volunteer Development with PMI Mumbai Chapter
Ex-Chair of Ethics Committee of PMI Mumbai Chapter
Member of PMI Mumbai Chapter & PMI Chennai Chapter
Member of PMI (Project Management Institute) USA

## Slide 3: Working Agreements
Working Time
Break Time
Electronics
Corner Talk
Group Exercises
Participation
Our Values (for this project)
  Focus
  Communication
  Respect
  Openness
  Courage
  Share
Everybody
Notes: Project Management Concepts
06/28/13
Version 3.1, 4/01 © 2003 by AstroWix
3

## Slide 4: Workshop Agenda Project Planning & Management
Project Planning
Stakeholder Identification
WBS (Work breakdown Structure)
Risk Identification and Planning
Communication Planning & Management
Software Estimation techniques
Scheduling and Controlling (Waterfall/Iterative /Agile)
Resource planning & Management

## Slide 5: Workshop Agenda Requirement/ Design/ Test
Project Management
  Importance of requirements for project success
  Project Management Methodology / Lifecycle Selection
  Effective requirement gathering techniques
  Business Requirements v/s Software Requirements
  Verifying and Validating Requirements
  Managing Scope
Requirements phase in different development models (Waterfall/Iterative/Agile)
  Requirement Elicitation techniques
  Change Management
  Stakeholder Management
Design
  Analysis vs Design in IT Projects
  Design Methodologies
Test Management
  Test strategy and planning
  Test design
  Test case preparation
  Test Execution
  Defect tracking and reporting
  Requirements Traceability Matrix
  UAT

## Slide 6: Workshop Agenda ITIL Processes
Production Support and Issue Management
Release Management

## Slide 7: Project Management

## Slide 8: Project Planning
10 Dimension of Planning
Component of Planning
  How to Execute
    What
    Who
    When
    How to do
  How to Monitor & Control (M&C)
    What to monitor
    How to measure
    Who will measure
    How to control
    How to report

## Slide 9: Choose Right Methodology
Waterfal
Iterative
Agile

## Slide 10: Waterfall

## Slide 11: Spiral

## Slide 12: Agile vs Traditional

## Slide 13: Value, Risk, Productivity in Agile vs Traditional

## Slide 14: Core of Agile

## Slide 15: Scrum in a Glance

## Slide 16: Stakeholder Identification & Management
Who are stakeholders?
Prepare Stakeholder Register for Every Critical Project
Perform stakeholder interest and influence analysis
Development stakeholder management approach for every key stakeholders
Apply the approach
Keep your stakeholder register updated
Keep evaluating your approach and aligning it to the need

## Slide 17: WBS (Work Breakdown Structure)
What is WBS?
Why WBS is Important?
How many ways of creating WBS?

## Slide 18: Risk Identification and Planning
What is Risk?
Prepare Risk Register for every critical project
Analyse impact, probability, exposure of every risk
Prioritize risk based on the exposure
Understand risk tolerance of stakeholders
Based on the exposure and tolerance make decision which risk must have response plan
Prepare risk response plan for every high priority risk
Every risk must have a risk owner
Keep risk register updated
Periodically keep evaluating your risk response plan

## Slide 19: Communication Planning & Management
Every critical project should know what information need to be communicated, to whom, at what frequency, via what channel and when
Keep your various approved reporting format ready during the project planning or modify it based on the need
Keep communication as per the plan
Track adhoc communication
Evaluate your communication effectiveness on periodic basis and alter it based on the need.
Track your communication efforts at some place

## Slide 20: Software Estimation Techniques
Judgement, Experience
  Analogous Estimation
  3 Point Estimation
  Parametric Estimation
  Story Points
Scientific Techniques
  Function Point
  Use Case

## Slide 21: Estimation: Important Points
No estimation is without assumptions. So document the assumptions.
Estimation is never absolute number. So communicate estimation with range
Estimation must be done of every important aspect of the project like size, duration, cost, efforts
10 Persons for 4 month = 40 person months <> 4 Person 10 Months 
Mind the difference between calendar days, duration, efforts, ideal engineering efforts
Even if you have to backward planning (from project end date) in a short duration project. Estimation and negotiation is must.
That estimation is of no use which has not been communicated, agreed and basedlined for tracking purpose. So communicate and get approval.
Estimate buffer (efforts, time, cost) separately and track it separately.

## Slide 22: Scheduling and Controlling
Every project manager must know the critical path and critical activities of his project.
Critical activities are those where float / slack is zero.
Float is not same as buffer
Every schedule must be baselined before PM start tracking activities
Perform plan vs actual analysis on regular basis
Whenever deviation is beyond the threshold limit corrective and preventive action need to taken and this must be communicated to relevant stakeholders.
Track your buffer your separetely

## Slide 23: Resource Planning & Management
Every activity cannot be fastracked.
Every activity cannot be crashed
Resources should not be overloaded then their availability
Productivity is never 100%
Thinks will go wrong so plan resources accordingly so that you do not fail on your committed baselines.
Manager buffer resources and buffer time/cost of resources carefully

## Slide 24: Requirements, Design & Test

## Slide 25: Requirements, Design & Test
Document and track every functional and non-functional requirement through a central system
Functional Requirement and Specification documents should have analysed requirements and system. Customer should know functional architecture of the system.
Use difference level of abstraction diagram to visualize the functional system.
Use difference type of architecture to visualize the solution
Document how will you test and prove that the functional and non-functional requirements of system are completely built or partially built.
Involve testers throughout project lifecycle. Tester and developers should not understand requirements from each other but from business analyst and customer.
In an agile built solution and deliver value in increments

## Slide 26: Importance of Requirements for Project Success
Test case for every functionality is must. This is success criteria of delivery of functionality
Test product against the non-functional requirements
Change management system should be agreed with stakeholders and it must be in place for fixed price project.

## Slide 27: Effective Requirement Gathering Techniques
Observation & Conversation
Interviews
Surveys & Questionnaires
Prototyping
Focus Groups
* Do not make any absolute commitment to customer about the requirement implementation till the time requirement are not analyzed and architecture solution has not committed by technical.

## Slide 28: Requirements Types
Business Requirements
Stakeholder Requirements
System Requirements ( functional and non-functional)
Transition Requirements

## Slide 29: Business Requirements
Business Requirements describe why the organization is undertaking the project. Project charter, business case, or in a project vision and scope statement. You can’t build software from such high-level information. It help get the project owner, stakeholders and project team on the same song sheet.
Problem Statement
Project Vision
Project Constraints (Budget, Schedule, and Resource)
Business Objectives
Project Scope Statements (Features)
Business Process Analysis
Stakeholder Analysis
IT Service Impact Analysis
Ex: "We need to establish an online customer portal.” “The portal should list our products under various categories."

## Slide 30: Stakeholder Requirements (Software Req.)
Stakeholder Requirements, user needs, user requirements, describe what users do with the system, such as the activities that users must be able to perform. These are generally documented using narrative text, use cases, scenarios, user stories, or event-response tables. Generally documented in a User Requirements Document (URD). Signed off by user community.
Ex: Use Case for Login
  1. Go to website
  2. Click on login
  3. Enter username and password
  4. You are redirected to the start page.

## Slide 31: Solution Requirements (Software Req.)
Solution (System) Requirements are what the developers use to build the system. These are the traditional “shall” statements that describe what the system “shall do.” System requirements are classified as either functional or nonfunctional requirements.
A functional requirement specifies something that the developer needs to build to deliver the solution.
Ex: "The system shall be able to register a product using the following fields: Name (20 characters long), Details (2000 characters long), Price (currency), Category (pick list).“
Ex: "The system shall support that up to 5 pictures can be listed per product.“

## Slide 32: Non-Functional Requirements
Nonfunctional requirements specify all the remaining requirements not covered by functional requirements.
Ex: “System should be able to support 50 concurrent users” “Interest and due calculation report should be ready with 3 seconds” “Application should work on all latest browsers”
Business continuity, Compliance, Interoperability, Maintainability, Performance
Interface: Integration with other system
Operations: Installation, system management
Reliability: Failure rates, availability, recoverability
Usability: Different ability people, navigation, help, documentation, difference experience level people
Legal, packaging, hardware

## Slide 33: Transition Requirements (Software Req.)
Transition Requirements describe capabilities that the solution must have in order to facilitate transition from the current state of the enterprise to a desired future state, but that will not be needed once that transition is complete. They are differentiated from other requirements types because they are always temporary in nature and because they cannot be developed until both an existing and new solution are defined. They typically cover data conversion from existing systems, skill gaps that must be addressed, and other related changes to reach the desired future state. They are developed and defined through solution assessment and validation.”

## Slide 34: Transition Requirements (Software Req.)
Data Conversion and Migration Data conversions Temporary interfaces User Access and Security Rights Security privileges User access User Acceptance Testing Test case development Test facility Production Turnover and Transition User support and help desk Operations Application support User Preparation and Transition Skill enhancements Training delivery One-on-one support Super user programs Customer and Supplier Preparation and Transition Communications and notifications Data interchange | Pilot Testing Model office Pilot test Organizational Changes Temporary staffing for backfill New hires Transfers Outplacements Infrastructure Transition Servers Storage Network Personal computing devices Changes to Policies, Procedures and Forms Policies Procedures Workflow Forms Business Continuity BC contracts DR Testing
No matter how good the code, with out attention to transition requirements, stakeholder won’t be satisfied with the result.

## Slide 35: Verifying and Validating Requirements
Verification is the process of confirming that the designed and built product fully addresses documented requirements. Verification consists of performing various inspections, tests, and analyses throughout the product lifecycle to ensure that the design, iterations, and the finished product fully addresses the requirements.
Validation is the process of confirming the completeness and correctness of requirements. Validation also ensures that the requirements: 1) achieve stated business objectives, 2) meet the needs of stakeholders, and 3) are clear and understood by the developers. Validation is essential to identification of missing requirements and to ensure that the requirements meet certain quality characteristics.

## Slide 36: Managing Scope & Change Management
Define change control board and their threshold limits.
Define process of managing changes and make sure team follow that
Understand the meaning of scope creep and manage it
Have project boundary defined in terms of within scope and out of scope in business requirement document.

## Slide 37: Requirements Phase in Different Development Models
Waterfall : The first phase of project lifecycle
Iterative : At the start of every iteration. Output of iteration may be architecture, non-working prototype, POC
Agile : Requirements are elaborated during product backlog grooming in every sprint for the future sprint work.

## Slide 38: Requirement Elicitation Techniques
Reference document, product
Para-phrasing
Throwaway prototype (paper, board, electronic)
Speak user’s language

## Slide 39: Analysis vs Design in IT Projects
Analysis
  Business Rule
  Workflow
  Duplicity
  Priority
  Usecase
  Consistency

## Slide 40: Why are Requirements so Important

## Slide 41: Integration & Integration Testing
No last-minute change request.
Defect is not change request.
Ensure defect fix do not break other part of the system (automation)
Automate as much as possible to guarantee high quality
Involve customer

## Slide 42: Agile Methods / Practices
Agile Unified Process
DRY
XP
DSDM (Dynamic Systems Development Method)
Agile Software Development
KISS
RUP (Rational Unified Process)
Scrum
TDD
Unified Process
YAGNI
Waterfall
Spiral

## Slide 43: Release Management
Release calendar
Release plan (hardware/software, responsibilities, activities, validation, plan B)
Migration Strategy
Minimal Downtime
Configuration Control
Release Documents
Committed Team
Defect Prioritization

## Slide 44: Design Methodologies
Hierarchy Architecture / Structured Analysis and Design Technique: This approach utilizes a diagram to describe the hierarchy of a system's functions.
Data Structured Systems Development: Data structure determines the system structure in this methodology.
Object Oriented Design: This methodology is based on a system of interacting objects.
Agile Design
Heterogeneous Architecture
SOA Architecture
Interaction Oriented Software Architecture
Master/Slaves Software Architecture
Data Flow Architecture
Top Down Design or Stepwise Refinement: This starts from the end solution and works backwards, refining each step along the way.
Bottom Up Design: This methodology starts with a foundation and works up towards a solution.
Structured Design: This is an industry standard. The technique starts by identifying inputs and desired outputs to create a graphical representation.

## Slide 45: Test Design /Test Strategy and Planning
Based on the complexity of application make what different level of testing will be performed.
Make a plan to ensure each type of testing. (Infrastructure, Responsibilities, Activities, Schedule, Cost, Test Case, Reporting, Defect Fixing)
Is any third party certification required after testing

## Slide 46: Processes for Testing & reporting
Test case preparation
Test case review
Test case execution
Reporting Test Results
Defect Logging

## Slide 47: Defect Tracking and Reporting
Defect Logging
Defect Prioritization
Defect Assignment to Dev
Defect fix confirmation (update test case pass/fail)

## Slide 48: Requirements Traceability Matrix
Use RTM to track the progress of each functionality
RTM is excel sheet kind of column structure
RTM contains: Req Id, BC Ref, Design Ref, TC Ref, Dev Ref, Delivery Status, Rel. #, Owner
Update RTM during and verification and validation
Use RTM for preparing delivery status report

## Slide 49: UAT
Help customer in writing User Acceptance Testcases in advance
Encourage customer to test the product using UA Testcases
Define UAT environment and validate before UAT start
Train customer about how/where to log UAT defects
Dedicated team to fix the UAT defects on priority and made decision
Do not work on any new requirements while fixing any UAT defect

## Slide 50: ITIL Processes

## Slide 51: IT Systems Includes
Firewalls
Various type of local, intranet and cloud Storage
Directory Services
Various Types of Database Servers
Various Types of OS
Various Types of Web Client
DHCP Services
Application Servers
Various type of Network devices and protocols

## Slide 52: Challenges
Change in business happening every moment and this sends out it ripples
Challenges is how to ensure high security, performance, availability with distributed and heterogeneous system and manage all this with lesser cost and outsourced team!

## Slide 53: So..
How they manage the complex challenges
  Banks,
  Insurance
  FMCG
  Transporters
  Airlines
  Financial Security
  Defence
  Oil & Gas
  Universities

## Slide 54: Learn from others…
Processes
Functions
Roles
That how they manage services and service lifecycle

## Slide 55: What is service?
The best way to think about a service is to think terms of customer. Why should they pay for it? Business is the customer of IT.
If services are not available then it's not a service. So availability management is the key.
All the service support and service delivery disciplines work together to deliver agreed levels of service availability to our customers.

## Slide 56: Functions and Roles
4 Functions
  The Service Desk
  Technical Management,
  Application Management,
  IT Operations Management
Roles & RACI
  Process owner
  Service owner
Technology and Architecture for Service Management & Service Automation

## Slide 57: The ITIL V3 Service Lifecycle
ITIL Core
ITIL Web
ITIL Complimentary Guidance

## Slide 58: ITL Core Processes

## Slide 62: ITIL Levels

## Slide 63: ITIL Levels

## Slide 64: Processes
IT Service Strategy | IT Service Design | IT Service Transition | IT Service Operation | IT Continual Service Improvement
Portfolio Management Financial Management Demand Management | Service Catalogue Management Service Level Management Capacity Management Availability Management Continuity Management Information Security Management Supplier Management | Support & Transition Management Change Management Asset & Configuration Management Release & Deploy Management Validation Management Evaluation Management Knowledge Management | Event Management Incident Management Problem Management Fulfillment Management Access Management Service Desk Function Management Service Operations Function Management Technical Operations Function Management Application Operations Function Management | IT Governance Management (using COBIT best practices) IT Resource Management IT Quality Management (using Six Sigma methods) IT Security Management (using ISO standards) Service Measurement Service Reporting Service Improvement

## Slide 65: Products (Tools)
IT Service Strategy | IT Service Design | IT Service Transition | IT Service Operation | IT Continual Service Improvement
Service Request & Planning Tools Service Knowledge & Configuration Management Tools (SK-CMS) | Service Catalogue Tools Service Level Management Tools Capacity Planning Tools Service Modeling Tools SK-CMS | Asset Management Tool Service provision Tool Run Book Task Automation Tools SK-CMS | Service Desk with Incident Management Tool Problem Management Tool Event Management Tool Run Book Technology Troubleshooting Tool Run Book Application Troubleshooting Tool SK-CMS | Compliance Management & Measurement Tools SK-CMS

## Slide 66: People
IT Service Strategy | IT Service Design | IT Service Transition | IT Service Operation | IT Continual Service Improvement
Service Definition Manager Service Research Manager Financial Analysis Manager Service Marketing Manager Service Forecast Manager | Engineering Manager for Security Desktop Network Systems, Servers & Storage Applications | Assets Manager for Security Desktop Network Systems, Servers & Storage Applications | Operation Manager for Security Desktop Network Systems, Servers & Storage Applications | Service Measurement Manager Quality Measurement Manager Compliance Measurement Manager Security Measurement Manager Resource Measurement Manager