## Day 1 Flow
First Time Managers Program
Module: Operational Excellence & Business Acumen
Day 1 Detailed Flow of Topics
| Start - End Time | Duration | Overview | Title | Methodology
| 8.30 - 9.00 am | 30m | Session Opening | Ice-breaker session | With the help of a Co-facilitator from L&TTS & Context Setting
Slot 1 | 9.00 - 11.00 am | 2h | Introduction to Operational Excellence with respect to Projects, Businss Value of a Project & Project Success Criteria | Introduction to Operational Excellence, Expectation Setting with Audience, Workshop Ground Rules Introduce the casestudy project and establish the importance of this to do all the exercises of this workshop Define Project Understand difference between scope, requirement, wants, business value of the need and project boundary Meaning of the Project Success for your stakeholders. Define Project Success Criteria. | Facilitator Led Session + Group Exercise
Tea Break - 15 mins
Slot 2 | 11.15 am - 1.00 pm | 1h 45m | Stakeholder Identification & Mapping, Project Acceptace Criteria & Test Cases, Opportunities for operational improvement, Linking Measurement with Project Success | Relationship between product signoff and acceptance criteria. How to establish acceptance criteria? Relationship between project acceptance criteria & test cases. How to establish acceptance test cases? Relationship between measurement and project success. What to measure? How to measure? When to measure? Who are stakeholders? How to identify them? How to map them to requirments | Facilitator Led Session + Group Exercise
Break for Lunch - 1 hr
Slot 3 | 2.00 - 3.30 pm | 1h 30m | Requirement Tracibility Matrix, Prject Planning with MS Project Software | Project Planning: Understand & Prepare Requirement Traciblity Matrix for tracking progress of the project deliverables Planning with Microsoft Project: Understand WBS, WBS type, Control Accounts and which type of WBS is suitable for my project. | Facilitator Led Session + Group Exercise + MS Project Software
Tea Break - 15 mins
Slot 4 | 3.45 - 5.30 pm | 1h 45m | Project Estimation, Cost Estimation, Resource Estimation, Baselining, Negotiating baseline with relevant stakeholders | Project Scheduling: Create a WBS Process of creating a project schedule Guidelines for sequencing project activities Estimation: Importance of Estimation Guidelines & Processes Estimate resources, duration, cost. What is a baseline? What does it comprised of? Establish importance of baseline. Best practices for project baselining Negotiating baseline with relevant stakeholders. Baseline Complete Project | Facilitator Led Session + Group Exercise + Best Practices Sharing

## Day 2 Flow
First Time Managers Program
Module: Operational Excellence & Business Acumen
Day 2 Detailed Flow of Topics
| Start - End Time | Duration | Overview | Title | Methodology
| 8.30 - 9.00 am | 30m | Review Session | Review of Learning from Day-1 | Facilitator Led Session
Slot 1 | 9.00 - 11.00 am | 2h | Linking operational activities with organization's success, Project Tracking & Measurement, Types of Analysis Techniques, Buffer Management, Change Management | Buffer Management Difference between slack & buffer. How to estimate buffer? What should be part of buffer? Relationship between buffers and risk Pro-Active Project Tracking What to track? When to track? Who should track what? How to track? Tracking, measuring & analysing Various types of analysis techniques Project Governance Structures & What to review with whom How to accommodate change in PLC In fixed bid project, how to manage expectation when there is deviation for the plan | Facilitator Led Session + Group Exercise + Cases
Tea Break - 15 mins
Slot 2 | 11.15 am - 1.00 pm | 1h 45m | Pro-Active Project Communication & reporting, Status Reports, Progress report, Forecast report, Management By Exception | Pro-active Communication & Reporting How to establish the purpose of every communication. What to communicate? Decision making process, speed of decision making and technology of communication What should be part of a status report? What should be part of a progress report? What should be part of a forecast report? Interpersonal Skills & perception management Management by Exception for minimal escalation, effective management. | Facilitator Led Session + Group Exercise + Cases
Break for Lunch - 45 mins
Slot 3 | 1.45 - 3.45 pm | 2h | Risk Management, Opportunities for operational improvement, Failure Management & Operational Failures, How to bring your Project back On-Track? | Risk Management What is the meaning of risk? How to identify risk? Relationship between risk, assumption, dependency, constraints, risk impact Prepare a risk register Risk assessment Strategies to manage threats (negative risks) Strategies to manage opportunites (positive risks) How to establish contingency buffer to manager risks Risk tracking & reporting. Timing, Responsoblites, Format Failure Management How to bring almost failed project on track Case Studies of failure management | Facilitator Led Session + Group Exercise + Case Studies
Tea Break - 15 mins
Slot 4 | 4.00 - 6.00 pm | 2h | Understanding how your projects contribute to the bottom line?, Business Acumen, Financial Ratios, B/S, P&L A/C, Invoicing & Billing | Business Acumen Type of cost. Cost of ownership. License & Software Costs etc. Financial Ratios: Contribution Margin, Gross Margin, pyramid ratio. Read one L&T monthly report and understand Reading Balance Sheet Reading Profit & Loss A/c Invoicing Cycle & Billing Analysis | Facilitator Led Session + Group Exercise
Slot 5 | 6.00 - 6.30 pm | 0.5 h | Closing | Session Closure: Action Planning

## InfoNeeded
Info Needed for Designing Course Content
Name of Key information/documents flow between various department involved in any project
Sample documents of above
Case study of a project involving all the department
List of Existing Project Management Processes
List of Financial Ratio more often used by mangement
List of typical resons due to which project get challenged or failed within L&T TS

## Misc Notes
7-Point Theme for the Workshop
1 | Proactiveness
2 | Plan the work and work the plan
3 | Report the progress
4 | Report with solution and seek advice
5 | Remain Motivated
6 | Measurement is the key to improve
7 | Communication
Case Studies
Cases will be based on live ongoing projects so that participant can relate to them. For this, will require project specific information from L&TTS.

## Detailed hour-by-hour coverage
|  | Total (Min) | 940 | 15.6667
Day | Topics | Methodology | Time (Min) | Mapping
Day - 1 | Introduction, Expectation Setting with Audience, Workshop Ground Rule | Coach-led interactions | 45
| Speak about the casestudy project and establish the importance of this to do all the exercises of this workshop | Coach-led interactions | 15
| Define Project |  |  | 10. Requirement development / management
| Understand difference between scope, requirement, wants, business value of the need and project boundary | Concept Capsule & Exercise | 25
| Meaning of the Project Success for your stakeholders. Define Project Success Criteria. | Concept Capsule & Exercise | 25
| Relationship between product signoff and acceptance criteria. How to establish acceptance criteria? | Concept Capsule & Exercise | 25
| Relationship between project signoff and success criteria. How to establish success criteria? | Concept Capsule & Exercise | 25
| Relationship between project acceptance criteria & test cases. How to establish acceptance test cases? | Concept Capsule & Exercise | 25
| Relationship between measurement and project success. What to measure? How to measure? When to measure? | Concept Capsule & Exercise | 25 | 9. Possible Metrixes to measure project progress
| Who are stakeholders? How to identify them? How to map them to requirments | Concept Capsule | 10
| Understand & Prepare Requirement Traciblity Matrix for tracking progress of the project deliverables | Concept Capsule & Exercise | 15
| Planning with Microsoft Project |  |  | 1. MS Project – Project Planning and Tracking, Value Chain method, Critical Path Analysis
| Understand WBS, WBS type, Control Accounts and which type of WBS is suitable for my project. | Concept Capsule | 20
| Create a WBS | Group Exercise | 20
| Process of creating a project schedule | Concept Capsule | 20
| Guidelines for sequencing project activities | Concept Capsule | 20
| Importance of Estimation Guidelines & Process | Concept Capsule | 20
| Estimate resources, duration, cost. | Group Exercise | 30
| What is a baseline? What does it comprised of? Establish importance of baseline. Best practices for project baselining. Negotiating baseline with relevant stakeholders. | Concept Capsule | 20
| Baseline Complete Project | Group Exercise | 15 | 2. Tips and Techniques to ensure adherence to Project deadlines
Day - 2
| Buffer Management |  |  | 4. Buffer generation / Anticipating associated risk in case of non-adherence
| Difference between slack & buffer. How to estimate buffer? What should be part of buffer? | Concept Capsule | 15
| Relationship between buffers and risk | Concept Capsule | 15
| Project Tracking |  |  | 6. Proactive tracking and reporting
| What to track? When to track? Who should track what? How to track? | Concept Capsule & Exercise | 30
| Tracking, measuring & analysing | Concept Capsule | 30 | 9. Possible Metrixes to measure project progress
| Various types of analysis techniques | Concept Capsule | 15
| Project Governance Structures & What to review with whom | Concept Capsule | 15 | 7. Project Lifecycle / reviews / Risks at milestone / Solutions out of it
Communication & Reporting
| How to establish the purpose of every communication. What to communicate? | Concept Capsule | 15
| Decision making process, speed of decision making and technology of communication | Concept Capsule | 15
| What should be part of a status report? | Concept Capsule & Exercise | 15
| What should be part of a progress report? | Concept Capsule & Exercise | 15
| What should be part of a forecast report? | Concept Capsule & Exercise | 15
| Interpersonal Skills & perception management | Case study | 30 | 12. Perception Management
| Management by Exception for minimal escalation, effective management. | Concept Capsule | 15 | 3. Escalation Reduction
| Risk Management |  |  | 5. Risk Planning / Assessment / Management and Mitigation
| What is the meaning of risk? How to identify risk? Relationship between risk, assumption, dependency, constraints, risk impact | Concept Capsule | 30
| Prepare a risk register | Concept Capsule & Exercise | 20
| Risk assessment | Concept Capsule & Exercise | 15
| Strategies to manage threats (negative risks) | Concept Capsule & Exercise | 15
| Strategies to manage opportunites (positive risks) | Concept Capsule & Exercise | 15
| How to establish contingency buffer to manager risks | Concept Capsule & Exercise | 15
| Risk tracking & reporting. Timing, Responsoblites, Format | Concept Capsule & Exercise | 15
How to bring almost failed project on track
| Case Studies of failure management | Case study | 30 | 8. Case Studies of failure management
Business Acumen
| Type of cost. Cost of ownership. License & Software Costs etc. | Concept Capsule | 15
| Financial Ratios: Contribution Margin, Gross Margin, pyramid ratio. | Concept Capsule & Case Study | 15 | 11. Basics of Contribution margin, Gross Margin, Estimation awareness etc.
| Read one L&T monthly report and understand | Exerise & Discussion | 15
| Reading Balance Sheet | Concept Capsule & Case Study | 20
| Reading Profit & Loss A/c | Concept Capsule & Case Study | 20
| Invoicing Cycle & Billing Analysis | Concept Capsule & Case Study | 20
| L&T Processes and Tools: Forecast, Pulse, Timesheet, Control Tower etc. | Concept Capsule | 20
| Session Closure: Action Planning | Concept Capsule | 20
Inputs received in the conference call on 5-Nov-16
Keeping R&R of the trainees in mind emphasise on the concepts/exercises so that they understand their work better.
Prepare some pre workshop material so that participant can read/work/understand it before they come for worshop. It will save time in class, deep the learning, asking more relevant questions
One slide for links for the further study.
How to accodate change in PLC
In fixed bid project, how to manage expectation when there is deviation for the plan
Special emphasis on perception management and expectation management
How to map communication need to stakeholders type. Tools like VNGC
Input Required from L&T TS
A small case study of a project connecting all the deparments.
R&R of participants
L&T Monthly report
Waiting for input from Arun on Microsoft Project.