## Day 1 Flow
`1
Module: Operational Excellence & Business Acumen
Day 1
| Start - End Time | Duration | Title | Methodology
| 8.30 - 9.00 am | 30m | Ice-breaker session | With the help of a Co-facilitator from L&TTS & Context Setting
Slot 1 | 9.00 - 11.00 am | 2h | • Setup a project, Define project scope, project charter & project boundary | Facilitator Led Session + Group Exercise
Tea Break - 15 mins
Slot 2 | 11.15 am - 1.00 pm | 1h 45m | • Choose a project management method and define project life-cycle • Prepare RTM for tracking progress of project deliverables (requirement management, requirement ellicitation, development process, Value Chain analysis) | Facilitator Led Session + Group Exercise
Break for Lunch - 1 hr
Slot 3 | 2.00 - 3.30 pm | 1h 30m | • Define project success criteria • Define acceptance criteria • Define acceptance test cases • Define project metrics | Facilitator Led Session + Group Exercise
Tea Break - 15 mins
Slot 4 | 3.45 - 5.30 pm | 1h 45m | • Estimation of Resources, Duration, Cost (Buffer generation) • Prepare project funding requirements • Prepare project cash flow [All this using tool Microsoft Project] | Facilitator Led Session + Group Exercise

## Day 2 Flow
First Time Managers Program
Module: Operational Excellence & Business Acumen
Day 1
| Start - End Time | Duration | Title | Methodology
| 8.30 - 9.00 am | 30m | Review of Learning from Day-1 | Facilitator Led Session
Slot 1 | 9.00 - 11.00 am | 2h | • Task identification for Work Breakdown Structure • How to Prepare and negotiate a project schedule (critical path analysis, guidelines to prepare project schedule, lead/lag analysis, Tips and Techniques to ensure adherence to Project deadlines etc)? [All this using tool Microsoft Project] | Facilitator Led Session + Group Exercise
Tea Break - 15 mins
Slot 2 | 11.15 am - 1.00 pm | 1h 45m | • Management by exception & review • How to Prepare a progress report? • How to Prepare a status report? • Project Forecasting - How to Prepare a forecast report? • Earned Value Management & Proactive Status tracking | Facilitator Led Session + Group Exercise
Break for Lunch - 1 hr
Slot 3 | 2.00 - 3.30 pm | 1h 30m | • How to reduce Escalation? • Risk Indentification & Assessment - Prepare a risk register • Risk Management - Prepare risk response strategies (Management and Mitigation) • Case Studies of failure management • Perception Management, expectation management, engagement management | Facilitator Led Session + Group Exercise
Tea Break - 15 mins
Slot 4 | 3.45 - 5.30 pm | 1h 45m | • Reading Balance Sheet & Profit & Loss A/C • Financial Ratios: Contribution Margin, Gross Margin, pyramid ratio, estimation, License & Software Costs etc. • Invoicing Cycle & Billing Analysis • L&T Processes and Tools: Forecast, Pulse, Timesheet, Control Tower etc. • Session Closure: Action Planning | Facilitator Led Session + Group Exercise + Co-facilitator for L&T Processes & Tools

## InfoNeeded
Info Needed for Designing Course Content
Name of Key information/documents flow between various department involved in any project
Sample documents of above
Case study of a project involving all the department
List of Existing Project Management Processes
List of Financial Ratio more often used by mangement
List of typical resons due to which project get challenged or failed within L&T TS

## Misc Notes
7-Point Theme for the Workshop
1 | Proactiveness
2 | Plan the work and work the plan
3 | Report the progress
4 | Report with solution and seek advice
5 | Remain Motivated
6 | Measurement is the key to improve
7 | Communication
Case Studies
Cases will be based on live ongoing projects so that participant can relate to them. For this, will require project specific information from L&TTS.