## Sheet1
4-Feb is Awareness Campaign | Deliverables |  | Who | Due Date
Awareness Campaign
| Trainer Profile |  | Hari | 2016-12-27
Create and Provide Content for 1 Page Broucher Creation
Ok | PMP |  | Hari | 2016-12-27
| PMI-ACP |  | Hari | 2016-12-27
| Scrum Agile |  | Hari | 2016-12-27
| Function Point estimation |  | Hari | 2016-12-27
| Project Risk Management |  | Hari | 2016-12-27
Ok | CAPM |  | Hari | 2016-12-27
| Project Schedule Professional |  | Hari | 2016-12-27
| Microsoft Project |  | Hari | 2016-12-27
Ok | PRINCE2 Foundation |  | Hari | 2016-12-27
Ok | PRINCE2 Practitioner |  | Hari | 2016-12-27
| 20+ Customized Training |  | Hari | 2016-12-27
| Email format for PMP |  | Hari | 2016-12-27
| Email format for Summary Training |  | Hari | 2016-12-27
| Summary 1 Page Broucher for each course |  | Nidhi | 2017-01-06
| PMP |  | Nidhi | 2017-01-06
| PMI-ACP |  | Nidhi | 2017-01-06
| Scrum Agile |  | Nidhi | 2017-01-06
| Function Point estimation |  | Nidhi | 2017-01-06
| Project Risk Management |  | Nidhi | 2017-01-06
| CAPM |  | Nidhi | 2017-01-06
| Project Schedule Professional |  | Nidhi | 2017-01-06
| Microsoft Project |  | Nidhi | 2017-01-06
| PRINCE2 Foundation |  | Nidhi | 2017-01-06
| PRINCE2 Practitioner |  | Nidhi | 2017-01-06
| 20+ Customized Training |  | Nidhi | 2017-01-06
| Email format for PMP |  | Hari | 2016-12-27
| Email format for Summary Training |  | Hari | 2016-12-27
Compaign Work
| Morning: Trainer Profile |  | Nidhi | 2017-01-01
| After Noon: Offerings |  | Nidhi
| Evening: About 4-Feb Workshop (About Agile) |  | Nidhi
One Day wokshop for Awarenss
Attractive & Prospective. Growing, Caree Opportunties & Effective Mgr, Trends & Tools
| Agenda for 4-Feb Workshop |  | Hari | 2017-01-20
1 hr: Trainer Intro
1 hr: Training Offerings
1 hr: Current Challenges & Trends
Method: Agile: 3 / Tools Coming program
1 hr: Q/A
Audience: Potential PM, Upgrading their skills, learn new trends.
Duration: 7 Hours
Post Awareness Campiagn
Apr Workshop
Pre Apr Workshop
Apr Workshop
Post Apr Workshop
May/Sep/Oct/Nov Workshop | Hari need to give dates for May |  | Hari | 2016-12-27
4-8 Apr (PMP), 10-12 Apr (PMI-ACP)
9-13 May (PMP), 15-18-May (PMI-ACP)
5-9 Sep (PMP), 11-13-Sep (PMI-ACP)
3-7 Oct (PMP), 9-11-Oct (PMI-ACP)
7-11 Nov (PMP), 13-15-Nov (PMI-ACP)

## Sheet3
| PIC | About | Why | Outline | Audience | Del Method | Deliverables | SEO | Prerequisite
FPA | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
PMI-RMP | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
MSP | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
PMP | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
PRINCE2 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
PMI-SP
PMI-ACP | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
PMI-CAPM
Agile-Scrum
EPM
20+ Customized Trainings
SMC | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
SPOC |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes

## Broucher Outline
Broucher Outline
| About Course | Hari | 2016-12-27
| Why this Course | Hari | 2016-12-27
| Course Outline | Hari | 2016-12-27
| Course Audience | Hari | 2016-12-27
| Course Takeaway | Hari | 2016-12-27
| Prerequisite of this course | Hari | 2016-12-27
| Course Teaser | Nidhi | 2016-12-28