## Sheet1
Review group | Assessment criterion |  | Question | Option A | Option B | Option C | Option D | Comments (please enter you comments)
6 | 1.1d Recall what makes a project a PRINCE2 project | 1 | What makes a project a PRINCE2 project? | It has processes that satisfy the objectives of PRINCE2 processes | It has a permanent project organization to deliver a long-term result | It has an established technology to improve business-as-usual | It has detailed designs for product delivery that are approved by the project board
6 | 2.1b Explain the PRINCE2 principle: learn from experience | 2 | What is an advantage of applying the principle 'learn from experience'? | The project team can repeat successes from previous projects | The project team can develop a business case for the project | The project can be to divided into management stages | The project team can use tolerances to delegate authority
6 | 2.1d Explain the PRINCE2 principle: manage by stages | 3 | How does the project plan help to support the 'manage by stages' principle? | By identifying the customer's quality expectations | By defining products to ensure they are fit for purpose | By identifying the major control points and milestones | By estimating the timescales and costs of the project
6 | 2.1g Explain the PRINCE2 principle: tailor to suit the project | 4 | What is likely to be reduced by applying the 'tailor to suit the project' principle? | Management effort | Project risks | Training time | Procurement procedures
6 | 3.2.2 Describe what PRINCE 2 requires, as a minimum, for managing organization | 5 | By the end of which process must the frequency of communications to stakeholders be defined? | 'Starting up a project' | 'Directing a project' | 'Initiating a project' | 'Managing product delivery'
6 | 3.2.3b Describe the roles and responsibilities of: Executive | 6 | Which role is responsible for ensuring the project is justified in terms of cost? | Project manager | Executive | Senior user | Senior supplier
6 | 3.2.3j Explain which roles can be combined | 7 | Which roles should NOT be combined? | Project board and change authority | Project manager and team manager | Executive and project manager | Project manager and project support
6 | 3.4.2 Describe what PRINCE 2 requires, as a minimum, for managing plans | 8 | Which approach must be used when producing project and stage plans, as a minimum requirement for managing plans? | Activity-based planning approach | Product-based planning approach | Agile approach | Risk management approach
6 | 3.4.3c Recall the factors to consider when structuring the project into management stages | 9 | Which statement describes a valid reason for planning a shorter management stage? | The work to deliver the project is well defined and understood | The project is similar to previous projects that were delivered successfully | The stage is the first delivery stage of a project within a complex programme | The project manager and project board are confident the timescales will be met
6 | 3.6.2 Describe what PRINCE2 requires, as a minimum, for managing change | 10 | Which is a minimum requirement for controlling change? | To record issues in an issue register | To have the project board decide on off-specifications | To have the change authority decide on requests for change | To record informal issues in the daily log
6 | 4.3c Explain the context of the PRINCE2 process: Initiating a project | 11 | Which risk would materialize if a project moved directly from the 'starting up a project' to the 'controlling a stage' process? | A lack of clarity over how to achieve the project's objectives may waste money | A supplier's business case may become different from the customer's business case | The project board appointments and responsibilities may not be established correctly | Unsound assumptions about the project's scope and timescale may affect the work started
Review feedback is given below corresponding to the rows above.
|  | 1 | Ok | "It" has two meaning "PRINCE2" or "The Project" So be specific like "The Project has…" | Same as Option A | Same as Option A | Same as Option A
|  | 2 | What is an advantage of applying the principle 'learn from experience' in project lifecycle? | Ok | Ok | To know the number of management stages the project can be devided into | To know/determine the amount of tolerances required to delegate authority
|  | 3 | Ok | Ok | By defining specialist products to ensure they are fit for the purpose | Ok | ok
|  | 4 | Ok | Management efforts | Ok | Ok | Ok
|  | 5 | Ok | Ok | Ok | Ok | Ok
|  | 6 | Ok | Ok | Ok | Ok | Ok
|  | 7 | OK | Ok | Ok | Ok | Ok
|  | 8 | Duirng stage/project planning, which approach must be used as a minimum? | Ok | Ok | Ok | Ok
|  | 9 | Ok | Ok | Ok | Based on the intent you can put better option. This is confusing text. | Ok
|  | 10 | What is a minimum requirement for controlling change in a project? | Ok | Ok | ok | Ok
|  | 11 | Ok | Ok | Ok | Ok | Ok
Note on D15: Hari Thapliyal: Rational Putting this word "in project lifecycle" helps candidate in knowing that question is not related to specific phase of the project but entire project. Therefore select those options which are related to all phases.
Note on G15: Hari Thapliyal: Rational Option C is confusing
Note on H15: Hari Thapliyal: Option D can be written more precisely for quick interpretation by non-enlish community
Note on F16: Hari Thapliyal: Rational Do you want to help candidate think too broadly or he should think to the point and select the option?
Note on D21: Hari Thapliyal: Rational Long question! with too much text understanding the question is taking time, in this case.
Note on D23: Hari Thapliyal: Rational I think "what" is better word in place of "which". To fully qualify the question I think adding "in a project" is better for understanding.