## Project Charter
GOALS |  | STAKEHOLDERS | CORE TEAM MEMBERS
Spreading the ideas of Shri. Rajiv Malhotra using the small video Clips |  | - Anyone who would like to learn about the Topics being covered by Shri. Rajiv Malhotra.A12 - Infinity Foundation | - Hari Thapliyal - Ashish Dhar - Gururaj Deshpande - Tejal Desai - Ritesh Kumar
OPPORTUNITY |  | SUMMARY PROJECT STATUS | MILESTONES
Currently , the ideas of Rajiv Jee has been scattered across various videos. The videos are long, therefore it requires to be watched it for longer time to understand his perspective and the ideas on various topics. In today's world peoples attention span has reduced , and therefore it is quite possible that someone with interest in his ideas, but can't watch it. Therefore there is an opportunity to serve the market by offering the smaller videos clips of lecture given by "Shri. Rajiv Malhotra" at various venues and would be specific to certain topics. |  | Project Start Date : 10th Nov,2014 Project End Date : 28th Feb,2015 | Please refer to the Tab: MILESTONES
OBJECTIVES |  | SPONSORS | Project Manager/Project Coordinator
1. Categorization and Sub Categorization of all the topics being covered by Shri. Rajiv Malhotra as part of inculcation. 2. Create the small video clips from the Larger video (lecture given by Shri. Rajiv Malhotra at various venues). 3. Create questions specific to category and sub category. 4. Ensure the video clips are of professional quality.i.e. it should have proper start and end, have decent sound/video quality. |  | Shri Rajiv Malhotra | Ritesh Kumar
IN SCOPE | BUSINESS CASE
The video clips which we have received from Shri. Rajiv Malhotra. - Total Number of Venues Covered : 32 (Approx) - Total Number of Clips : 275 (Approx) | For now, no intentions of revenue generations or any business interests.
CONSTRAINTS | ASSUMPTIONS
- Limited to available/On-hands video clips and the questions - Could only address few Category/Subcategory .i.e. Topics/Subtopics covered by Shri Rajiv Malhotra | The quality of videos clips received are good, are well prepared, and should be able to cover most of the topics if not fully but partially for sure.
DELIVERABLES
1. Template Creation 2. POC (work with small number of video clips to see the feasibility) 3. Create Category and Sub Category 4. Define the quality of video/audio etc by working on the assigned clips and filling the template. 5. Work on the video clips, using the Template as an input (feedback). Ensure the quality of work is consistent.

## CoreTeam Members-Contact Detail
Name | Cell/Phone # | Email Address | Skype ID | Remarks
Hari Thapliyal | +91-953-599-9336 | hari.thapliyal@gmail.com | hari.thapliyal
Ashish Dhar | +91-991-150-4610 | ashish@greatwideopen.in | ashish-dhar
Gururaj Deshpande | +1-484-560-8767 | gurudesh@yahoo.com | gururajd@hotmail.com
Tejal Desai | +1-734-330-7988 | tejal.desai@ymail.com
Ritesh Kumar | +1-817-714-6172 | riteshkrsingh@gmail.com | riteshkrsingh
Note on A4: 3217 W CEDAR ST ALLENTOWN, PA 18104 United States

## MILESTONES
MILESTONES | STATUS | DUE DATE | COMPLETION DATE | Comments | Legends
Team Setup | GREEN | 2014-12-07 | 2014-12-07 |  | GREEN | On Track
Infrastructure and Tools established | GREEN | 12/0/2014 | 2014-12-08 |  | RED | Lagging/Running Behind
Feasibility Study | GREEN | 2014-12-14 | 2014-12-10 |  | BLUE | Work in Process
Assignment of Work to each team Member | GREEN | 2014-12-14 | 2014-12-14 |  | YELLOW | Yet to start
Template Work Completion | YELLOW | 2014-12-24
Video Editting completion | YELLOW | 2014-02-10
Upload of the video clips to targetted Website | YELLOW | 2014-02-18
Spreading the News | YELLOW | 2014-02-22
Note on A6: All the fields of tempates should be filled. This should have no ambiguity at all, what so ever.

## DELIVERABLES-
MILESTONES | DELIVERABLES | STATUS | DUE DATE | COMPLETION DATE | Comments | Legends
Team Setup | Introduction of Team Members to each other | GREEN | 2014-12-07 | 2014-12-07 |  | GREEN | On Track
| Communication Channel Established | GREEN | 2014-12-09 | 2014-12-08 | CoreTeam Members-Contact Detail | RED | Lagging/Running Behind
Infrastructure and Tools established | Knowledge Repository Established | GREEN | 2014-12-14 | 2014-12-10 | https://drive.google.com/folderview?id=0BzrlmTtOnvUAU0tSRnFRZXJydm8&usp=sharing | BLUE | Work in Process
Feasibility Study | Create an initial template to capture the quality of videos |  | 2014-12-06 | 2014-12-06
| Assigning small sample of work to each team member to work on template | GREEN | 2014-12-12 | 2014-12-12 | Feasibility Study
| Finalization of Template (based on feedback from various team members) | GREEN | 2014-12-14 | 2014-12-14
Assignment of Work to each team Member | Creation of Category and Sub-Category (In totality) | RED | 2014-12-12 |  | https://drive.google.com/file/d/0BzrlmTtOnvUAbktPSjNTQVJSMVk/view?usp=sharing | YELLOW | Yet to start
| Assigning work to each team member a group of templates | GREEN | 2014-12-14 | 2014-12-14 | Assignment
Template Work Completion | Cross Verification of work from each team members |  | 2014-12-23
| Assigning the Category and Sub-Category to each Video Clips |  | 2014-01-12
Video Editting completion | Edit the vido Clips (based on the template input) |  | 2014-01-20
Upload of the video clips to targetted Website | Uploading the vido to the targetted Website |  | 2014-02-10
Spreading the News | Spreading the news |  | 2014-02-20
Note on B4: https://drive.google.com/folderview?id=0BzrlmTtOnvUAU0tSRnFRZXJydm8&usp=sharing
Note on B9: Tejal.
Note on A10: All the fields of tempates should be filled. This should have no ambiguity at all, what so ever.
Note on B12: Cross Verification: Verify each others work to make sure, everybody is on the same page.

## Feasibility Study Plan
Category | URL | Assigned To | Status
Vidya Bharti Foundation | https://www.flickr.com/gp/127527788@N03/F2en48/ | Ritesh | Completed
University of Toronto | https://www.flickr.com/gp/127527788@N03/RCc9X0/ | Tejal | Completed
UMass | https://www.flickr.com/gp/127527788@N03/58p650/ | Gururaj | Completed
SIES,Commerce College | https://www.flickr.com/gp/127527788@N03/s0Xqc8/ | Hari | Completed
Toronto Public Discussion | https://www.flickr.com/gp/127527788@N03/6p908h/ | Ashish | Completed
NOTE: | Everybody needs to take 5 Video and fill the template and provide feedback to improve template

## ASSIGNED TASK
Venue of Speech | Assigned To | Google Drive | flicker location
Asian Chamber of Commerce | Gururaj Deshpande | Video Repository (Google Drive) | https://www.flickr.com/gp/127527788@N03/28P501/
Atlanta | Ashish Dhar |  | https://www.flickr.com/gp/127527788@N03/AS680a/
Aurovile | Hari Thapliyal |  | https://www.flickr.com/gp/127527788@N03/QZ5x5J/
BABA Ramdev | Hari Thapliyal |  | https://www.flickr.com/gp/127527788@N03/LoZ70q/
Bay Area | Ashish Dhar |  | https://www.flickr.com/gp/127527788@N03/XX13Bb/
Bhabha Atomic Center | Ritesh Kumar |  | https://www.flickr.com/gp/127527788@N03/D2a1x9/
Chicago | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/2p2Vd8/
Chicago-2 | Gururaj Deshpande |  | https://www.flickr.com/gp/127527788@N03/cwZ1y0/
Chinmay Mission | Hari Thapliyal |  | https://www.flickr.com/gp/127527788@N03/GW3R24/
Google Hangout | Ritesh Kumar |  | https://www.flickr.com/gp/127527788@N03/6u5PNa/
Houston | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/xU64TG/
IISc | Hari Thapliyal |  | https://www.flickr.com/gp/127527788@N03/t0M3V9/
IIT Alumni | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/M4c281/
IIT Kharagpur, Indian Mind Science... | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/Ga5Zuw/
IIT Madras | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/ZjK689/
IIT Mumbai, Are Indian Buying back Their Ideas | Ritesh Kumar |  | https://www.flickr.com/gp/127527788@N03/7FBe43/
Indus, Indra's Net Grand Narrative | Ashish Dhar |  | https://www.flickr.com/gp/127527788@N03/ph8iHG/
Irvine | Hari Thapliyal |  | https://www.flickr.com/gp/127527788@N03/0Y9F8M/
JNU | Ritesh Kumar |  | https://www.flickr.com/gp/127527788@N03/x0dx2F/
Lakshminarayan Mandir- Toronto | Ashish Dhar |  | https://www.flickr.com/gp/127527788@N03/7N6956/
Pondi | Gururaj Deshpande |  | https://www.flickr.com/gp/127527788@N03/120035/
Princeton-Breaking India | Gururaj Deshpande |  | https://www.flickr.com/gp/127527788@N03/Qir07Q/
Ramakrishna Mission | Gururaj Deshpande |  | https://www.flickr.com/gp/127527788@N03/50eZ03/
SIES,Commerce College | Hari Thapliyal |  | https://www.flickr.com/gp/127527788@N03/s0Xqc8/
SIES,Relevance of Indian knowledge system | Gururaj Deshpande |  | https://www.flickr.com/gp/127527788@N03/99pguj/
Somaiya | Ritesh Kumar |  | https://www.flickr.com/gp/127527788@N03/554kC7/
Toronto Civic | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/d8585G/
Toronto Public Discussion | Ashish Dhar |  | https://www.flickr.com/gp/127527788@N03/6p908h/
UMass | Gururaj Deshpande |  | https://www.flickr.com/gp/127527788@N03/58p650/
University of Toronto | Tejal Desai |  | https://www.flickr.com/gp/127527788@N03/RCc9X0/
Vidya Bharti Foundation | Ritesh Kumar |  | https://www.flickr.com/gp/127527788@N03/F2en48/
Atlanta |  | ASHISH
Bay Area
Chicago
Indus, Indra's Net Grand Narrative
Lakshminarayan Mandir- Toronto
IISc
Toronto Public Discussion
Bhabha Atomic Center |  | RITESH
Google Hangout
IIT Mumbai, Are Indian Buying back Their Ideas
JNU
Somaiya
Vidya Bharti Foundation
Aurovile |  | HARI
Chinmay Mission
IISc
Irvine
SIES,Commerce College
BABA Ramdev
Pondi |  | GURURAJ
Princeton-Breaking India
Ramakrishna Mission
SIES,Relevance of Indian knowledge system
UMass
Chicago-2
Asian Chamber of Commerce
Toronto Civic |  | TEJAL
University of Toronto
IIT Alumni
IIT Madras
Houston
IIT Kharagpur, Indian Mind Science...
Chicago