## YFS - Strategic Priorities
Strategic Priorities for Youth for Seva
Sl No | Strategic Focus Areas | Goals | Targets - Year 1 | Targets - Year 5 | Year 1 2017-18 | Year 2 2018-19 | Year 3 2019-20 | Year 4 2020-21 | Year 5 2021-22
1 | Build Community Ownership | 1. Build deep and engaging community volunteers to build self sustaining communities 2. Design and perfect the 'School model'. Pilot it, incorporate changes and scale the model 3. Build self sustaining community model through volunteering for apartment complexes and Yuva Mundles. Scale both the models after incorporating learnings from the pilot | Overall Vounteers Engagement - 50,000 (including all programs) 10 Schools as Pilot | Overall Volunteer Engagement - 2,00,000 across all programs Cover 3 Taluks in 3 States | 1) Create and design a 'School model' with focus on deep, committed, engaged volunteers from the community 2) Identify 10 government schools where the school model can be piloted in Telengana and Karnataka 3) Create systems and processes to attract volunteers, identify change makers, build their capacity and share responsibility to develop the school | 1) Ensure volunteers to become part of the School Development and Monitoring Committee (SDMC) for the 10 pilot schools 2) Perfect the 'School Model' and scale it to one taluk in each of the states - Telengana and Karnataka. 3) Pilot the model in Tier 2 cities and villages in the two states | 1) Scale the 'School Model' across schools in 2 taluks in two states - Telangana/ Karnataka, enter a new state with and one new state with focus on taluk (40 -80 schools - urbal; rural schools) 2) Build in at least 2 new initiatives in the School Model - School Alumnai program; replicatable model for groups to implement it on their own using a framework | 1) Evaluate pilot schools on their ability to be self-sufficient with the support of community volunteers 2) Create an exit plan for the 10 schools and hand over responsibility to key members of the volunteering group for the school 5) Expand 'School Model' to schools in 2 taluks in 3 states | 1) Monitor and evaluate progress of the schools that have exited the 'School Model' 2) Evaluate and identify more schools to exit after 3 years of intervention through the School Model program 3) Create exit plans and hand over responsibilities to volunteers and school administration 4) Expand 'School Model' to schools in 3 taluks in 3 states
|  |  | Study on self sufficient communities | 100 communities in Karnataka, Telangana and Gurgaon | 1) Initiate research and data gathering phase for the 'Community model'. Identified clusters/ taluk the program will be piloted | 1) Create and design a 'Community Model' with focus on deep, committed, engaged volunteers from the community working for the betterment of the community 2) Community Model augmented to suit two communities - apartment complexes and Yuva Mundles 3) Pilot the Community Model (apartments and yuva mundles) in 5 cities with a total of 15 communities. Focus on metros and tier 2 cities | 1) Perfect the 'Community Model' and scale it to 30 communities across Karnataka, Telengana and Gurgaon 2) Pilot this model in villages with partner (like Gram Panchayat or Hindu Seva Pratistana) where the school model is implemented 3) Create systems and processes to attract community volunteers, identify change agents, build their capacity and share responsibility to develop the community | 1) Scale the 'Community Model' across 65 communities across Karnataka, Telengana and Gurgaon 2) Expand the model in villages along with partners (gram panchayat; hindu seva pratistana) | 1) Evaluate pilot communities on their ability to be self suffient with the support of volunteers 2) Create exit plans for the 15 communities and hand over responsibilities to the community 3) Commission a study on the assessment of program; assess different frameworks that have been implemented and their impact 4) Expand 'Community Model' to new communities 100 across Karnataka, Telengana and Gurgaon
2 | Create Change Makers | 1. Create a study on 'What makes a Change Maker' and identify qualities, support required to be a great change maker 2. Design and pilot a change maker program that will build capacity of volunteers who can transition into change makers 3. Incubate change makers and ideas through partnership with social incubator organizations | 50 Change Makers - with the existing initatives and programs Change Manager Program Design | 1000 Change makers 20 Social Incubators | 1) Commission a research project on 'What makes volunteers, change makers?' - Identify key people within the system and conduct the study to understand their profile, background, motivators, accelerators, aspirations, what support they got, what else do they want to become change makers - Identify key attributes that contribute towards becoming of change makers 2) Design a 'Change Maker Program' that will address the following - Early identification of change maker ability in volunteers - Level 1 program - build awareness on the development landscape in India; what does it take to build sustainable communities and responsible citizens contributing to the development of the country - Level 2 program - build capacity among change makers to take ownership and commit to bringing in social change - Level 3 program - Allocate mentors from YFS or the social sector to build skills among change makers to create a pipeline for YFS or any other organization | 1) Pilot the 'Change Maker program' upto 3 levels and incorporate feedback into the program 2) Initiate partnerships with social incubator organizations and agree on broad terms of engagement 3) Identify at least 12 ideas/ change makers who can be incubated to bring about social change (Yuva Chetana and our volunteers) | 1) Incubate at least 10 ideas/ change makers in partnership with other social incubator organizations; 2) Tie up with 3 corporates to run the level 1 (and/or level 2) of the change maker program 3) Tie up with University to offer it as one of the subjects/ courses for existing students | 1) Facilitate level 1 and 2 of the program for at least 10 corporates (a few in smaller cities) 2) Tie up with more universities/ institutes to offer this course (a few in smaller cities 3) Create an open house program where individuals can nominate themselves and attend Level 1 program 4) Incubate at least 15 social incubation ideas/ change makers | 1) Strengthen the Change maker program including all the changes from the last few years 2) Continue offering the program in Universities, Corporates or Open house programs 2) Incubate at least 20 ideas/change makers
3 | Be a Thought Leader in the volunteering space | 1) Create opportunities and events to bring together the volunteering community and learn from each other 2) Become the 'go-to' organization for volunteering in India 3) Consult with the Government ministries on youth development policies and CSR Law 4) Educate corporates to build strong volunteering engagement and create awareness about the development space | 2 Publications 1 YouTube Channel | R&D Hub Reseach papers and presentations in 5 forums | 1) Facilitate a 'Volunteering Conclave' to celebrate 10 years of YFS - Participation from the corporates, government, volunteering organizations and individual volunteers - Ensure white papers or articles/ 1 publication are published to capture the philosophy of development/ need for volunteering - Ensure appropriate coverage and branding in media and social media - Launch the YouTube Channels - Launch of monthly/ quarterly newsletter from YFS in the conclave | 1) Brand YFS as the 'go-to' organization for volunteering in India - Create online knowledge repository - Share best practices and case studies to increase awareness around volunteering - Tools and tips to start volunteering in the community - Models of volunteering - Framework and approach of volunteering - Toolkit for set up of volunteering process in organizations - Concept of self sustaining communities through deep, engaging and committed volunteering 2) Be in a position to educating corporates and CSR teams to build strong volunteering engagement; deeper understanding of the development space; and their approach towards using the CSR money more efficiently | 1) Be in a position to consultant the Government with youth development policies as well as changes to the CSR Law | 1) Ensure YFS's volunteering model, deep engagement volunteering model becomes a case study written by Indian and International Universities (Harvard etc.) | 1) Invite organizations from neighbouring countries to study the volunteering models and concept of development in India
4 | Build Government and Strategic partnership | 1) Create partnership with the government to be implementation partners for NMMS across 4 states in India 2) Be implementation partners for at least 10 government programs implemented at the state level 3) Enter into strategic partnerships with key players in the education, health and sustainable lifestyle domain to bring in sustainable change | 2 strategic partnerships NMMS in 600 schools | Official partner for 10 programs across states 5 strategic partnerships | 1) Partner with the State Government of Telangana to implement the NMMS program in 600 schools in Hyderabad urban region 2) Partner with one large NGO to support their existing program in Karnataka | 1) Expand implementation of NMMS to 4 states based on scheme utilization 2) Scale the NGO program to 2 states 3) Identify 2 more strategic partners to implement programs in health, education or sustainable lifestyle domains | 1) Scale NMMS implementation to more states based on scheme utilization 2) Identify and become implementation partners for 6 other government programs 3) Get into 1 more (total of 3) strategic partnerships with organizations | 1) Become implementation partners for at least 8 government programs led at the state level 2) Scale the existing programs like NMMS to more states 3) Have at least 4 strategic partnerships with organizations across 3 domains that are focus areas for YFS | 1) Become implementation partner for at least 10 government programs led at the state level 2) Have at least 5 strategic partnership with organizations in the health, education and sustainable lifestyle domain

## 1 year Operational Plan
Activities | Q1 Milestones Apr 2017 to June 2017 | Q2 Milestones Jul 2017 to Sep 2017 | Q3 Milestones Oct 2017 to Dec 2017 | Q4 Milestones Jan 2018 to Mar 2018
Program Design and Roll Out
New Programs
School Model program - Design and Pilot | 1) Identify team that will work on the School Model program 2) Allocation of funds for the program 3) Define program objectives and name of the program 4) Put together a team of specialist (External and Internal) to brainstorm and come up with a broad design of the School Model program (Program framework, Objectives and outcomes, Exit Strategy, Communication and Branding Plan, Funding plan, Community volunteer mobilization and training, Alumni connect, monitoring and evaluation framework (during and post exit of schools); a replicatable model for groups to implement it on their own using a framework) 5) Internal team to finalize the program design and get it reviewed by a review team (internal and external) 6) Identify 10 schools to implement the School model program and sensitize volunteers and school administration program | 1) Sign an MoU with the 10 schools for implementation of School Model program - for this year and next 2) Identify what aspects of the program will be implemented as a part of the pilot along with these schools | 1) Implement the program as per the project plan/ implementation plan | 1) Implement the program as per project plan 2) Review and evaluate progress over the last 5-6 months 3) Communicate with key stakeholders in schools (funders, government etc.) about the progress of the program 4) Make changes to the School Model based on feedback from the schools
Community Model program - Research and Data gathering |  |  | 1) Research on community based volunteering and what does it take to build a sustainable and self-sufficient community 2) Design thinking discussion/ workshop to understand broad area of research to be conducted | 1) Research on areas/ geographies that will be most receptive to adopting this model. Identify pilot locations for the launch next year 2) Define program objectives and name of the program
Change Maker program - Design | 1) Identify consultant who can work on conducting the study on 'what makes volunteers into change makers' 2) Identify existing change makers within YFS network and initiate the study. Also identify change makers with other volunteering organizations like iVolunteer; Bhoomi etc. to expand the scope of the study | 1) Use the findings of the study to write a white paper that can be published as a study conducted by YFS 2) Conduct a secondary research on what programs are available and if partnerships can be explored 3) Use the results from the study to define program objectives and name for the Change Maker program | 1) Identify a design partner who can work on co-designing this program (university/ institute/ organization). Sign an MoU with the design partner 2) Design the 'Change Maker program for 3 levels and an evaluation process to identify change makers early on. Include program objectives and outcomes, team required to run the program (internal, external, volunteers); branding and communication plan; review and monitoring framework; funding etc. | 1) (Continued) Design the 'Change Maker program for 3 levels and an evaluation process to identify change makers early on. Include program objectives and outcomes, team required to run the program (internal, external, volunteers); branding and communication plan; review and monitoring framework; funding etc. 2) Get the Program reviewed by experts and incorporate feedback 3) Identify a pilot group/ organization to go through the Change Maker program
Implementation of National Means cum Merit Scheme program | 1) Identify a team that will work on the NMMS program 2) Study the NMMS scheme and identify all the possible ways that YFS can add value 3) Put together a proposal on partnership with the Telangana government for Hyderabad region (600 schools) 4) Based on inputs/ approval from the Telangana government - design the implementation of the program 5) Sign an MoU with the Telangana government to implement the scheme | 1) Launch the program and implement it as per the project plan | 1) Review progress of implementation towards end of the quarter 2) Send regular update reports to DSERT/ Ministry | Plan for the next year's implementation
Strategic partnership with one large NGO for program implementation |  | 1) Establish connect with key peoplewithin the NGO to explore partnership for existing program 2) Review the existing program and identify areas where YFS and the NGO can partner 2) Sign a MoU with NGO to impletement the program together | 1) Define the program objectives and implementation plan 2) Identify schools where the program can be launched 3) Work with DSERT/ Government for joint permission to implement the program (if permissions are not there already) | 1) Implement the program in ____ schools across ___ districts in Karnataka 2) Identify other programs within the NGO that YFS can partner with
Existing Programs
Phase out - Teacher training; handwriting workshop; School kits; Scholarships; Tuition centres | 1) Identify the current situation and commitments to various stakeholders for the existing programs 2) Communicate to the internal team about the change in focus areas for YFS | 1) Put together a phase out plan for the existing programs 2) Communicate to the key stakeholders (funders, schools, volunteers etc.) 3) Implement the phase out plan 4) Decision on Vidya Chetana and therefore integrating the tuition centre and scholarship program (VC+) | 1) Implement the phase out plan | 1) Completely phase out the existing programs by the end of the year
Phase out existing programs like - lake restoration; milk bank or any other enviroment, infrastructure projects | 1) Identify the current situation and commitments to various stakeholders for the existing programs 2) Communicate to the internal team about the change in focus areas for YFS | 1) Put together a phase out plan for the existing programs 2) Communicate to the key stakeholders (funders, schools, volunteers etc.) 3) Implement the phase out plan | 1) Implement the phase out plan | 1) Completely phase out the existing programs by the end of the year
YFS Internship; Project Intership; College program etc. | 1) Assess the current situation and commitments to various stakeholders for the existing progams 2) Review posibility of incorporating into other programs or phasing it out | 1) Put together a phase out or integration plan for the existing programs 2) Communicate to the key stakeholders (funders, schools, volunteers etc.) 3) Implement the phase out plan | 1) Implement the phase out or integration plan | 1) Implement the phase out or integration plan
School Infrastructure Program | 1) Identify the current program and objectives defined 2) Redefine the objectives of the program to cover the following - School building reconstruction - School Kits - Toilets - Science labs - Library - Garden and eco-friendly environment | 1) Relook at the program design and modify it to suit the changed objectives and aspects of the program 2) Put together a program/ project plan to implement the program (end to end) in pilot schools | 1) Implement the plan for the pilot schools - monitor and review process of the program 2) Plan and implement the program in other schools identified 3) Identify PAN India or state wise contractors; service providers who can help with scaling the program | 1) Review progress of implementation of School Infrastructure program 2) Identify options for maintenance of the school/ equipment and sign off with the school authorities 3) Implement the exit plan for the pilot schools
Spoken English; Maths; Reading Mother tongue; Chiguru Events | 1) Identify current program objectives and commitments made to existing schools, funders and stakeholders 2) Honour existing commitments | 1) Review possibilities of integrating these programs in the 'School Model' program 2) Integrate and pilot it as a holistic school development model
Human Resources
Organization Structure + Recruitment | 1) Finalize on the organization structure along with levels and designations 2) Put together a communication plan to communicate internally -especially to affected people (role change, designation change etc.) 3) Put together request to hire critical positions to start the new programs | 1) Bring on board new employees, orient them to YFS vision, values, ways of working and so on 2) Implement the hiring plan based on the new programs and implementation | 1) Implement the hiring plan based on the new programs and implementation | 1) Implement the hiring plan based on the new programs and implementation
Tracking, monitoring and reporting
Program review and tracking |  | 1) Put together weekly milestones in the project plan - with qualitative and quantitative outcomes 2) Review progress on a monthly basis for all new and existing programs 3) Review performance of the program team and share feedback | 1) Put together weekly milestones in the project plan - with qualitative and quantitative outcomes 2) Review progress on a monthly basis for all new and existing programs 3) Review performance of the program team and share feedback | 1) Put together weekly milestones in the project plan - with qualitative and quantitative outcomes 2) Review progress on a monthly basis for all new and existing programs 3) Review performance of the program team and share feedback
Stakeholder Management and reporting |  | 1) Put together format for reporting to key stakeholders (Government; Corporates; Partners etc.) for different programs 2) Publish quarterly reports on progress of the program to the relevant stakeholders | 1) Publish quarterly reports on progress of the program to the relevant stakeholders 2) Review meeting with strategic partners to review progress of the program | 1) Publish quarterly reports on progress of the program to the relevant stakeholders 2) Review meeting with strategic partners to review progress of the program
Review and Evaluation
Assessments and Evaluation |  | 1) Baseline assessment for School Model 2) Based on the design look at the evalation framework for other new programs 3) Impact assessment for Doctors for seva - existing program
Marketing, Branding, Communication and PR
Seminars and Conclaves | 1) Put together a plan for the 10th year celebration for YFS 2) Identify a team that will work on planning the seminar/ conclave | 1) Implement the plan with focus on design of the conclave, agenda, speakers, guest list, showcase success stories, networking event, venue, pre and post conclave engagement etc. 2) Bring on board sponsors and partners for the conclave 3) Raise funds for the conclave | 1) Conduct the conclave as per project plan | 1) Conduct post conference follow up with the corporates, NGO partners and the Government 2) Put together an implementation plan based on outcomes of the conclave
Social Media |  | 1) Put together a social media campaign to create awareness around all the new programs and bring in more volunteer registration and conversion 2) Crowd source ideas, thoughts, articles to create excitement and increase awareness | 1) Implement the social media campaign on Facebook, twitter, LinkedIn and Instagram | 1) Implement the social media campaign on Facebook, twitter, LinkedIn and Instagram
Website |  | 1) Review the existing website and create content that will share the vision, focus areas clearly 2) Identify website design partners/ volunteers to make changes to the website | 1) Ensure all changes on the website are made and reflects the changes explicitly 2) Identify partners who can work on maintenance of the website | 1) Maintenance of website; add new profiles of people as they join the team
Branding and Visibility |  | 1) Brand the sttory telling Mega event of 12k volunteers across India 2) Create a newsletter format and launch it to key stakeholders. Issue the newsletter every quarter | 1) Create a short video on stories from the field and use it to create visibility
Public Relations |  | 1) Plan for 2 publications to be released in Y1. Identify what will be areas of focus; who will work on it; when it will be published 2) Identify high worth individuals to be speakers and associated with the new programs | 1) Plan for the YouTube channel launch. Identify what will be areas of focus; who will work on it; when it will be launched; how will it be sustained etc. 2) Launch the YouTube Channel 3) Release the publications | 1) Post conclave follow up and publications
Fund Raising
Funding Proposals & Raising funds | 1) Put together a plan for fund raising and allocate responsibilities | 1) Write out funding proposals for - School Model, NMMS implementation and NGO large organization | 1) Raise funds with Corporates for the programs | 1) Write out proposal for Change Maker program