## Slide 1: CSR Projects
Samarpaka Seva Foundations
No. 4259, I Floor
2nd Main, Girinagar I Phase,
Bangalore- 560085
Rajanna S, Managing Trustee, hosura@yahoo.com |+91-9845378434
Ramanath Pai, Director Operations, Ramanath.pai@gmail.com |+91-9900951007

## Slide 2: Who are we?
Samarpaka Seva Foundation (SSF) is a non profit social platform that connects Corporate CSR initiatives and the NGO projects and ensure high effectiveness and impact for the Corporate CSR Objective.
SSF is a team of 9 humanitarians with 200 years of combined experience in corporate and social sectors. We have deep expertise and network in conceptualizing, incubating and implementing social sector projects across India.
Our platform maximizes the value of investment for all stakeholders – Beneficiaries, NGOs, Donors, Government and Society by and large.

## Slide 3: Our Mission & Vision
Vision
To create a platform which enables the social and service organizations, to meet their several resource requirements and thus become a benchmarked organization in social sector.
(I think this very loose statement)
Mission
???

## Slide 4: Our Values
Service
Equality
Integrity
Competency
Sampark Seva
Foundation

## Slide 5: Proposed Projects Under Our Programs
Year 2017-18

## Slide 6: Health & Wellness Health Camps
Objective
This program aims to provide quality, affordable, accessible healthcare to children from government, corporation and government aided schools through team of doctors and non-medical staff.

## Slide 7: Health & Wellness Health Camps
October 2017
September 2018
13 States 19 Location
50
10,000
70
16
Health & Wellness Health Camps
INR 285 Cost/Child
INR 31 L Project Cost

## Slide 8: Sanitation Toilet Constructions
Objective
To construct eco friendly toilets and make the area free of open defecation
Standard ready to install toilet. Plumbing & small civil work at location.
(I feel objective need to be refined)

## Slide 9: Sanitation Toilet Constructions
On Demand
Tribal belt in Karnataka & Tamilnadu - 150
Tribal villages - 10
Varanasi -30
Tribal belt – 4
Villages around Bangalore - 26
Bidar - 30
In and around Bangalore rural – 90
INR 40 K
is cost of each Toilet
150 Toilet Constructions
INR 60 L Project Cost

## Slide 10: Water Drinking Water Facility at Rural Schools
Objective
Clean drinking water to rural children of government & aided schools
(I think objective need to be defined)

## Slide 11: Water Drinking Water Facility at Rural Schools
Rama Lakshmamma Vidhya Samsthe, Munganahalli, Adinaranaiah, Chintamani Taluk
Need: Bore well & Rainwater harvesting
Water filter & Hand wash basin
For 10 Schools
INR 10L Project Cost
INR 5L Project Cost
Tumkur village
Put complete address of school and Picture if possible

## Slide 12: Capex Shelter for Destitute children - Nele
Objective
?????
Define objective of this project.
There are 8 Nele where 260 students who are studying from 1st Standard to Master are living. In Nele a child’s holistic development - Education, Health, Food, Cultural, Sports, Counseling, is taken care by us.

## Slide 13: Capex Shelter for Destitute children - Nele
INR 6L Project Cost
Requirements | Quantity
Laptops | 2
Washing Machines | 3
Wet Grinders | 2
Computers | 6
DVD Players | 6
Carom board, Cricket set | 2
Badminton Court construction | 2

## Slide 14: Our Presence

## Slide 15: Benefits of SSF Program

## Slide 16: How we work..

## Slide 17: Health & Wellness Health Camps with Vistaar Finance

## Slide 18: Project Scope
Define project or program scope clearly ??????

## Slide 19: Project Phases
Phase1: Identification of locations and schools
Phase 2: Initial screening of ~10,000 school children across 13 different states of Vistaar Finance’s presence
Phase 3: Take-up few critical cases for next level of treatment and referrals
Out of Scope: Dental consultation / treatment not included. Surgeries not included.
October 2017
September 2018
13 States 19 Location
Health & Wellness Health Camps
INR 31 L Project Cost

## Slide 20: High Level Project Schedule
Preparation phase
Identification of Government schools (along with VISTARA)
Permissions/approvals from concerned Government departments
Hiring/training of coordinators for the project
Sign-off with partners for Dental/Eye screening/treatment
Identification of doctors for the program
Screening
Health screening of all children
Initiate Eye-prescreening / screening activities
Documenting the data
Treatment for needy children at school
Documentation & Reporting
Referrals
Referrals thru specialists after parental consent.
Eye screening / treatments
Dental screening & follow-ups.
 | Schedule 2017 |  |  |  | Schedule 2018 |  |  | 
Execution Plan | 15-Sep-17 | 31-Oct-17 | 30-Nov-17 | 31-Dec-17 | 31-Jan-18 | 28-Feb-18 | 31-Mar-18 | 30-Apr-18
Preparation phase |  |  |  |  |  |  |  | 
Pre-screening activity |  |  |  |  |  |  |  | 
Screening by doctors |  |  |  |  |  |  |  | 
Eye screening / treatment |  |  |  |  |  |  |  | 
Referrals follow-up / treatment |  |  |  |  |  |  |  | 
Reporting |  |  |  |  |  |  |  | 
Impact assessment |  |  |  | Data collection & Impact reporting |  |  |  | 

## Slide 21: Project Estimates & Budget
Account Head | Cost
Direct Cost per camp - first level | 97,000
Print and media | 5,000
Direct Cost per school - follow-up level | 41,000
Admin and Organisation expenses | 17,000
Total budget per location (4 schools/location) | 160,000
Total budget for 19 locations (Approx Project Cost) | 3,100,000
INR 285 Cost/Child

## Slide 22: Project Estimates- Headwise
Cost Head | Units | Unit Cost | Cost
Direct Cost per camp - first level |  |  | 
Doctor's honorarium | 3 | 2000 | 6,000
Medicines at the premises | 150 | 100 | 15,000
Volunteers / Area executives | 3 | 6000 | 18,000
Project Coordinator | 1 | 12000 | 12,000
Documentation and reporting | 1 | 5000 | 5,000
Transportation and food | 1 | 13000 | 13,000
Snack for children and teachers | 600 | 20 | 12,000
Coordination cost from the office | 1 | 7200 | 7,200
First aid kit for school | 1 | 1000 | 1,000
Logistics of food, stationary and other items | 1 | 2000 | 2,000
Stationary and others | 1 | 1500 | 1,500
Other direct cost |  |  | 4,535
 |  | Sub-Total | 97,235
Print and media | 1 | 5000 | 5,000
 |  | Sub-Total | 5,000
Direct Cost per school - follow-up level |  |  | 
Spectacles | 40 | 400 | 16,000
Dental follow-up treatment | 0 | 500 | -
Logistics of students and parents | 25 | 800 | 25,000
 |  | Sub-Total | 41,000
Indirect cost during follow-ups |  |  | 
Permissions and laisoning requirements |  |  | 
Special medical testing /doctor's expences |  | Not covered | 
Hospital and other operating charges |  |  | 
 |  | Sub-Total | -
Admin and Organisation expenses | 1 |  | 16,948
 |  | Sub-Total | 16948
Total budget per location (4 schools/location) |  | Grand-Total | 171,000
Total budget for 19 locations |  |  | 3,043,477

## Slide 23: Project Governance
Initial Health Assessment would be conducted and children data captured
Reports of treatments completed, pending cases and overall status
Referrals for each child tracked to closure
Ongoing Treatments recorded
Internal monthly review meetings will be held to review Project Status
  If required support (manpower/guidance/re-planning) will be provided to bring project on track
  Corrective Actions will be taken as required
Reports will be generated at the end of month. The format will include, but not limited to
  Status of the activities for the month
  Current status - Data and charts from all schools on number screened, treated & pending under each type of ailment
  Plan for next month
Reviews with VISTARA
  October 2017 (Preparation and Planning Milestone)
  Dec’18 (Milestone review, Execution Phase)
  Fe(Milestone review, Execution Phase)
  Feb’18 (end of program)
  Any other time as it may be appropriate (initiated by VISTARA or SST)

## Slide 24
Next Step?